4





**15TH OCTto3RD NOV,2022**

**KEYFEATURES**

• DeputyCommissionerstoleadtheinitiative

• RuraldevelopmentDepartmenttobethenodaldepartment

• PlanningDevelopment&MonitoringdepartmentandITtobethesupport departments

**ACTIONSANDTIMELINES**

|  |  |  |  |
| --- | --- | --- | --- |
| **ACTION** | **RESPONSIBILITY** | **LATESTBY** | **REMARKS** |
| **Janabhiyan** | Alldepartments | Oct15-26th | Goingon |
| **DeputationofSecttstaff/ HoDs** | GAD | Oct14 | Done |
| **DeploymentofStaffto Panchayatsandservingof ordersondeployedofficers** | DCs | Oct25 | DCswilldeployseniorlevelstaff fromthedistricts.Strictactionto betakenagainstabstentions.No exemptionstobegiven |
| **Trainingofdistricttrainors onB2V4** | RDD | Oct26 |  |
| **Trainingofvisitingofficers** | DCs | Oct27 |  |
| **FieldVisitstobecompleted by** | VisitingOfficers | Nov3 | DCstosuperviseandensurethat eachPanchayatisvisitedwithin theperiodspecified |
| **DataofB2V4tobe uploadedby** | VisitingOfficers | Nov10 | DCstosuperviseandensurethat dataofallPanchayatsisupload- edbythevisitingofficerwithin theperiodspecified |

**INSTRUCTIONSFORTHEVISITINGOFFICER(DAYWISE)**

|  |  |  |
| --- | --- | --- |
| **DATE** | **INSTRUCTIONS** | **ACTIONPOINTS** |
| **Day0** | Meetingwithdeputy commissionerandhis/her team | a. TakeprintoutsoffilledbookletsofB2V1,B2V2andB2V3from [www.jkpanchayat.in](http://www.jkpanchayat.in)  b.Alsotakeprintoutsofthesummarizedexcelsheetsofthe previousphasesfrom[www.jkpanchayat.in](http://www.jkpanchayat.in)  c. CollectATRsonissuesraisedduringprevious3phasesfromthe officeofDeputyCommissioner(Planningdeptt)  d.Takeprintsofblank 2bookletsofB2V4from[www.jkpanchayat.in](http://www.jkpanchayat.in)e.Takeplansfor2previousyearsandATRsfromtheplanningdeptt f. CompletetrainingsondifferentcomponentsofB2V4being  organizedbyrespectiveDeputyCommissioners  g.CollectListofnewworksstarted/ongoing/completedduringthe previousandcurrentFinancialyearunderthefollowingheads:  • PRIgrants  • DistrictPlan  • UTplan  • MGNREGA  • Otherschemesofotherdepartments  • Anyotherwork  h. Plans/beneficiarylists:  • MGNREGAdraftplandocumentfortheyear2022-23.  • ListofAwaas+beneficiariesalongwithIHHL Convergence  • Listofpensionbeneficiaries.  • ListofSHGs  • Listofagricultureschemebeneficiaries  i. Listsofbeneficiariesfor:  • Variouscertificates/benefitstobedistributedbythe visitingofficer.  • Anyotheractivitiesidentifiedbydifferentdepartments |

|  |  |  |  |
| --- | --- | --- | --- |
| **Day1** | Reachthevillage | 1. | Ensurethatallfrontlineworkersofdifferentdepttsarepresent. |
|  |  | 2. | Ensureexhibitionbydifferentdepts.aboutindividualbeneficiary schemes |
|  |  | 3. | InspectJKB/PSBcounters/outlets |
|  |  | 4. | Participate/ensureorganizationofsportsactivityinplayfield,talent hunt/culturalevent/youthactivity |
|  |  | 5. | GandhiKatha(suggesteddetailsuploadedonjkpanchayat.in) |
|  |  | 6. | Visitatleast2amritsarovarsandgetitsgeotaggedphotos |
|  |  | 7. | InspectKhidmat(CSC)CentresandcreateGenerateawarenesson  225schemesparticularlyG2CschemeslikeBEAMS,Janbhagidari, AapkiZaminAapkiNigrani,DigitalJ&K |
|  |  | 8. | Visitingofficershallalsoplanandconductpanchayatlevelconver- gencemeetingofalldepartments |
|  |  | 9. | CheckeffectivenessofCentrallysponsoredschemes |
|  |  | 10. | VisitandinspectallgovernmentestablishmentsincludingPHE, AWC,FPS,schools,etc |
|  |  | 11. | Attemptsaturationofdeliverableso JanAbhiyanandwherever deficienciesfound,leadadrivetoachievealldeliverables |
|  |  | 12. | Assesseffectivenessofsanitationcampaigninthepanchayat |
|  |  | 13. | Ensureselfemploymentactivitiesfor15youthperpanchayat |
|  |  | 14. | Identify20potentialcandidatesperpanchayatforHIMAYATtraining alongwiththetradeonwhichtheywanttraining |
|  |  | 15. | Whereverpossible,distributeemploymentlettersforpeopleselect- edundervariousgovernmentemployments |
|  |  | 16. | Intheevening,holdnormalmeetingwith seniorcitizens,govtem- ployeesincludingretiredemployees,exservicemen,youthclub,and any citizens ofthevillagewhoareenrolledincollege/university |
|  |  | 17. | OpendiscussiononNashaMuktAbhiyan |

Day2 Haveameetingwithall stakeholders-depttofficials andpanchayatmembers

1. Discussionontheandassesstheprogressofdifferentschemesrelating tothelocalizedSDGsprioritizedforthatvillageaspertheresolution passedby thatGramPanchayaton21st April22,onNationalPanchayti RajDay.

2. Sensitizevillage residentsaboutmyScheme”portal(myscheme.in) whichincludesinformationaboutalltheschemesbeingrunbyCen- tral/State/UTgovtacrossthecountry

3. Hold meeting of theBiodiversityManagementCommitteestodeliber- ateonissuespertaining toconservation of biodiversityandsustaina- bleutilizationof biologicalresources.

4. PrepareVillagedevelopmentplan,inconsultancywithGrampanchayat, discussitingramsabhaandgetitapproved.

5. Ensure saturationofsoilhealthcardandgoldenhealthcardunderGold- enHealthCardunderAyushmanBharat,

6. Ensuresaturation of OldAge PensionScheme

7. EnsureDomicileSaturation.

8. EnsureKCCSaturation

9. Ensure saturationoflandpassbooks

10. Ensureregistrationofvillagevendorsneededforanyscheme,onGEM

portal

11. Ensurepanchayatcontractors registration

12. EncouragePanchayatmembers forimportanceofplantationdrivein

PanchayatunderHarGaonHariyali

13. Ensure paintingondigitalJ&Kinpanchayatghars

14. Ensure paintingonpanchayatactivitesandCSSinpanchayatghars

15. Thevisiting officeshallchecknoof kindergarten andplayfields present inthepanchayat for kidsandstudents,iftheinfrastructure present inthesearegoodenough.

16. Holdmeeting withpanchayatmembers todiscussaboutcorruption menaceandstepsrequiredtomakeJ&Kcorruptionfree

17. Obtaina candidassessmentaboutperformanceofvariousdeptts in- cludingfairfeedbackaboutdiscrepanciesinfunctioning

18. Check thestatusof NashaMuktAbhiyanandreporting of drugad- dictstoDeputyCommissioner.

19. IdentifyTouristDestinations,Circuits,ThemeTreks,IdentifyHomestays, providesupportfortourismactivities throughVillageCooperative

20. OrganizeTalentHuntatPanchayatLevel

21. Conductsocialauditofatleast5worksunderfollowingschemes:

a. MGNREGA

b.PMAY

c. IHHLtoiletsandpayments d.CSCs

e.AMRITSAROVARS

22. Holda mahilasabha anda balsabhaandrecordproceedingsinthefor- matgiven

23. InauguratevillagehaatunderJKSRLM

24. Checkifyouthclubsareformedinthepanchayatandwhatactivities theyareengagedin

25. Organizea villagelevelculturaleventtoengagepanchayatmembers

26. SensitizeGPaboutE-kitabkoshaninitiativeofJ&KGovtforempowering youthsthrough onlinedigitalliteracy

**GENERALINSTRUCTIONS**

1. Thevisitingofficershallrefrainhimself/herselfgivingorofferinganycommitmentonbehalfofthe governmentandshalladoptanunbiasedattitudeinreportingissues.As faraspossible,his/her observation shouldbebasedona fairandanalytical viewemergingfromhis/herinteractioninthe village.

2. Heisgoingtothevillageasplanningofficer,notforsanctioninganyworksorformakinganycom- mitments.

3. Whilepreparingvillagedevelopmentplan,hehastoensurethat,demandsareprioritizedandre- flectedunderavailableschemes,wherevernecessarythelargerworksaretobereferredtoadminis- trativedepttunderCSS/UTplansunderintimationtoDCsandrestoftheworkstoDCsforreflecting itunderdistrict/CSS plans

4. His workshallbehardcoreplanningandauditandisnota PRexercise.

5. EveryDeputyCommissionerhastoensurethatatleastoneRDDofficial(ideallyPanchayatSecre- tary)ispresent ineverypanchayatwithrelevantpanchayatrecords,toensureconductofallactivi- tiesasplanned.Panchayatwiseorderneedstobeissuedinadvance.

6. Visitingofficershouldideallycarryhis/herlaptoptocompletethereportsatthepanchayatlevel itselfanduploadthefinalreport,duly signedbothbythesarpanchandbythevisitingofficeron [www.jkpanchayat.in](http://www.jkpanchayat.in)portal,beforetheyleavepanchayat.

7. Focus ofvisitareyouth,skills,self-employment,nashamukt,bhrashtracharmukt,Rozgaryukt J&K, besidestocarryforwardtheactivities duringJanAbhiyanandsaturatethem.

8. Inadditionattentionmaybegiventothefollowingareas a. MakefulluseofCentrallySponsoredSchemes

b.Saturationofindividualbeneficiaryschemes c. Self-employmentschemes

d.Banklinkedschemes-includingdepartmentalsubsidyschemes e.Empowermentandtransparencythrough digitalinitiatives

f. Effectivenessofgrassrootsmachinery–

i. Patwari,VLWpresent andavailable

ii. AvailablefundsutilizedinpublicinterestandasperGramSabharesolutions iii. Fairness ingovernance

iv. CSS/Individual beneficiaryschemesetc v. BrashtacharMuktJ&K

vi. BhaiMuktJ&K

vii. NashaMuktJ&K

9. ThePRImembers (Sarpanchs,Panchs,BDCChairperson)shallbeattheforefrontofallactivities and givendueimportanceandtheapproach shouldbetostrengthenthemandmakethemfeelem- powered.He/sheshallensurethattheBDCchairpersonandSarpanch/Panch arepresent atthetime ofinaugurationandceremonies.

10. Visitingofficershallnotleavethedistrictwithoutuploadingthereport,duly signedonthe**www. jkpanchayat.in**portal.EveryDeputyCommissionerhastoensurethat.

**A) DetailsofReportingOfficer:**

Name: GURMUKH SINGH

Designation: JOINT TRANSPORT COMMISSIONER, J&K

Department/placeof posting: M.V.D, TRANSPORT DEPTT.

MobileNo: 9419114670

EmailID: gurmukh210@gmail.com

HomeDistrict: JAMMU

Datesof visit: 31/10/2022-01/11/2022

**B) LocationaldetailsofPanchayat:(tobepre-filled,informationtobetakenfromtheprevious phasesbooklets/summarizedexcelsheetuploadedonjkpanchayat.in/b2v4.php)(tobevali- datedbythevisitingofficerandmissingdetailstobefilled)**

NameofthePanchayat: DHANDAL WEST

LocalGovernmentDirectory(LGD)codeof thePanchayat: 005072

Nameof CDBlock: JAGANOO

NameofTehsil: RAMNAGAR

Nameof District: UDHAMPUR

**C) PanchayatProfile:**

No.ofrevenuevillagesinthePanchayat: 01

No.ofhamletsinthePanchayat: WARDS 7

No.ofhouseholdsinthePanchayat: 320

Population(approx)of thePanchayat: 2700

**Part-II:**

(TobefilledupbytheVisitingOfficerduringhis/hertwodayvisittothePanchayat.AllFieldshavetobe

filledbytheVisitingOfficerbeforethebookletishandedovertotheDC

**FrontlineOfficers/OfficialswhowereassignedtothePanchayatfortheprogramme:**

|  |  |  |
| --- | --- | --- |
| Department | Name | Designation |
| AGRICULTURE | VIKAS GUPTA | A.E.A OFFICER |
| EDUCATION | YASH PAL, KEWAL RAJ | TEACHER |
| RDD | SANJEEV KUMAR | B.D.O |
| ICDS | AMRIT PRABHA | SUPERVISOR |
| HEALTH | DR. CHARU KHAJURIA | DOCTOR |
| ANIMAL HUSBANDRY DEPTT | MOHD. AMIN | SUPERVISOR |
| SHEEP HUSBANDRY | IMTIYAZ AHMED | STOCK ASSISTANT |
| REVENUE DEPTT | RAM KUMAR | NAIB TEHSILDAR |
| BANK | RAMAN GUPTA | BRANCH HEAD |
| FOREST | PANKAJ KUMAR | FOREST GUARD |
| YOUTH & SPORTS | PARKASH SINGH JAMWAL | R.E.K TEACHER |
| PDD | MOHAN LAL | METER READER |
| I&FC | KASHMIRI LAL | WORK SUPERVISOR |
| TRANSPORT | YOUGAL KISHORE SHAMRA | A.R.T.O |

**Detailsofabsentemployeesvis-à-vislistfurnishedbytheDCoffice:**

|  |  |  |
| --- | --- | --- |
| Department | Name | Designation |
| P.H.E |  |  |
| HORTICULTURE |  |  |
| P.W.D |  |  |
| P.M.G.S.Y |  |  |
| EMPLOYMENT |  |  |
| C.A.P.D |  |  |
| FLORICULTURE |  |  |
| POLICE |  |  |
|  |  |  |
|  |  |  |
|  |  |  |
|  |  |  |
|  |  |  |
|  |  |  |
|  |  |  |

**DAY1-ACTIVITIES**

**AGENDA1:PANCHAYATASSETREGISTER**

**Infrastructure:**

1. PanchayatGharInfrastructure **N** a. Govtbuilding/private **PYT.GHAR NOTAVAILABLE**

b. New/needingrepairs

2. Furniture(Y/N) **N**

3. Computer/printer(Y/N) **Y**

4. Internet(Y/N) **N**

5. Telephone(Y/N) **N**

6. Toilet(CSC/partofpanchayatghar)(Y/N) **N**

7. Water(Y/N) **N**

8. Electricity(Y/N) **N**

9. Bankbranch(Y/N) **N**

10. CSC(Y/N) **N**

11. Patwarkhana(Y/N) **N**

12. Villagehaat(Y/N) **Y**

13. Playground(Y/N) **Y**

14. School-

a. Kindergarten(Y/N) **N**

b.Primary(Y/N) **Y**

c. Secondary(Y/N) **N**

d. College (Y/N) **N**

e.University(Y/N) **N**

15. AnganwadiCentre(Y/N) **Y**

a. (govt/private) **PRIVATE**

b.Totalchildrenenrolled **133**

15. AmritSarovars–details,location,condition **NOT AVAILABLE**

16. Governmentoffices-details,whetherfunctionalornot **NO GOVT OFFICE IN PYT. ONLY 4 GOVT. SCHOOLS**

17. Rationshop(Y/N) **N**

18. Placesoftourismimportance–names,littledetailsonhistorical/culturalimportance **PAROLA(FOREST AREA)**

19. Villageheritagesites/treks-names,littledetailson historical/culturalimportance **DONU, KERIYA(FOREST AREA WITH PINE TREES)**

20. VLWOffice (Y/N) **N**

21. PrimaryHealthcareCentre(Y/N), **N**

22. ListofIncompleteBuildings-names,yearofconstruction **GMS NAKKI(DHANDAL), STARTED 2008-09, NOT COMPLETED TILL DATE.**

23. ListofUnderutilizedBuildings-names **N**

**DAY1-ACTIVITIES**

**AGENDA2:**

**DIFFERENTINSTITUTIONS/INFRASTRUCTUREPROJECTSTOBEVISITED**

|  |  |  |
| --- | --- | --- |
| **AMRITSAROVARS** | **Visit,verify** | **COMMENTS** |
| KhidmatCentres | Create/Generateawarenesson225schemes particularlyG2CschemsAapkiZaminAapkiNigrani, Beams,Janbhagidari,DigitalJ&K | NOT AVAILABLE |
| JKB/PSBcounters/outlets | a)Statusofcounter b)Numberofvisitors | NIL |
| Incompletebuildings/pro- jects | Verify whetheridentificationandredistribution done | G.M.S NAKKI (DHANDAL) |
| PDS | Visit,evaluate,onlinestatus | NIL |
| PHC | Visit-evaluate,statusofstaff,equipmentand quality | NIL |
| Youthclubs | Meet,interact,seeksuggestions | YES, INTERACTED AND WANT BIG GROUND STADIUM |
| SHG | Meet,identifyproblems,seeksuggestions | YES, NO MARKETING AVANUES FOR PRODUCTS |
| PMAY | Inspect,Inaugurate | INSPECTED AND INAUGRATED 2 HOUSES |
| Myschool,mypride progress;schools-water, toilets,staff | Visit,checkforwater,electricity,sanitation,meet studentsandstaff | WATER ISSUE, BOUNDARY WALL NEEDED FOR 4 SCHOOLS& SOME REPAIR WORK |
| SwachhSBM | Evaluate | TOILETS AVAILABLE BUT SCARCITY OF WATER |
| Panchayatplayground, Sportskitsdistribution Villagegames | Ensure,verify.Participateinatleastonegamein theplayground | PARTICIPATED IN TUG OF WAR, SPORTS ACTIVITIES AND DISTRIBUTED SPORTS KITS |
| HarGaonHariyali, Planta- tiondrive | Evaluatestatus,feedback | PLANTATION BEING DONE AND PLANTED 3 PLANTS IN VISIT |
| Villageculturalevent  Dangal/Haat/Mela | Participatein;ensurethatitisheld | CULTURAL EVENTS IN THE FORM OF DANCE, SONG ETC. |
| Exhibitionofschemes | Ensurethateverydepartmentparticipatesand thatitcontinuesfortheentiredurationofB2V | EXHIBITION DONE BY DIFFERENT DEPTTS. |
| JalJeewanMission verifica- tion- WSS/JSD  Electricitysupply | Verify | NO OFFICER REPORTED |

**DAY1-ACTIVITIES**

**AGENDA3:SATURATEJANBHIYAN**

**DELIVERABLESANDRECORDDEFICIENCIESIFANY(INSERTDELIVERABLESLISTHEREASPERGADFORMAT**

**DAY1-ACTIVITIES**

**AGENDA4:**

**SELFEMPLOYMENTACTIVITIES**

EnsureSelf-employmentactivities foryouth,distributeemploymentlettersforpeopleselectedunder varioussocialschemes(15ISTHETARGETPERPANCHAYAT) **SELF EMPLOYMENT UNDER SHG’S & 20 IDENTIFIED UNDER HIMAYAT**

**Numberofcasesindifferentcategoriessanctioned: Detailsofthebanksanctioningit:**

**Totalamountinvolved:**

**DAY1ACTIVITIES**

**AGENDA5**

Intheevening,holdinformalmeetings withseniorcitizens,govtemployees,retdemployees,youthclub andothercitizenswhoareenrolledoncollege/universityandhavediscussiononGandhiKatha,Nasha MuktAbhiyan,corruptionfreegovernance,doublingfarmersincomeandrecordtheproceedings

**DAY2**

a. NoofIndividualCompostPitsconstructed**8** b.NoofIndividualSoakPitsconstructed **18**

V. No.ofBiodiversitymanagementcommitteemeetingsheld: **YES**

VI. IsthenameofSarpanchdisplayedoncitizeninformationboardsofallRD&PRschemes:Yes/No **YES**

VII. AreSarpanchsbeinginvolvedinstart/inaugurationofactivities:Yes/No **YES**

VIII. WhethersubjectshavebeenassignedbytheSarpanchtothePanchs:Yes/No **YES**

IX. Whethergrievancesredressalboxisinstalled:Yes/No **YES**

X. NoofgrievancesreceivedpertainingtoPanchayatlevel **N** XI. NoofgrievancesdisposedofatPanchayatlevel: **NIL**

XII. WhethertheSarpanch/PanchayatSecretaryhavedigitalsignatures:**YES**

XIII. WhetherallMGNREGA/14thFCpayments arebeingmadebySarpanchthrough DigitalSignature

Certificate(DSC):**YES**

**HUMAN RESOURCEAVAILABLEATTHEPANCHAYAT LEVEL:**

|  |  |  |  |  |
| --- | --- | --- | --- | --- |
| **SRNO.** | **DEPARTMENTWISESTAFF** | **NUMBERS** | | **NAMES** |
|  |  | SANCTIONED | ACTUAL |  |
|  | Ruraldevelopmentdepartment: BDO  JE GRS TA | 1  1  1  1 | 1  0  0  1 | KULDEEP SHARMA  SANDEEP PADYAL |
|  | SCHOOLEDUCATION: TEACHER  HEADMASTER ANYOTHER | TOTAL 21  2 | 19  1 |  |
|  | JAL JEEVAN: | 2 | 2 |  |
|  | PDD: LINEMAN JE  ANYOTHER | 2 | 2 |  |
|  | FOOD&CIVILSUPPLIES | NIL | NIL |  |
|  | AGRICULTURE&ANIMALHUS- BANDARY | AEO-1  AN-0 | 1  0 |  |
|  | SOCIALWELFARE | NIL | NIL |  |
|  | HEALTH: ASHA ANM  AYUSHDOCTOR ALLOPATHICDOCTOR | 2  0  0  0 | 2  0  0  0 |  |
|  | ANYOTHERDEPARTMENT |  |  |  |

**DAY2-ACTIVITIES**

**AGENDANO.1**

DiscussionontheandassesstheprogressofdifferentschemesrelatingtothelocalizedSDGsprior-itizedforthatvillageaspertheresolutionpassedbythatGramPanchayaton21stApril22,onNational PanchayatiRajDay(Copyoftheresolutiontobetakenfrom[www.jkpanchayat.in](http://www.jkpanchayat.in)portalunderthelinkof GramSwarajMonth)

1. SDGs AGREED FORTHATVILLAGE,TOBEIMPLEMENTED BYMARCH2024: YES

2. STATUSOFWORKSUNDERTHEFOLLOWINGSCHEMES:

**1 Cleanandgreenvillage**

i.InitiativestakenbythePanchayatformanagingSolidandLiquidWaste **CONST. OF SOAK PITS, COMPOST PITS& MAGIC PITS**

ii. InitiativestakenbythePanchayatforusinggreensourcesoffuellikesolar,biogas

**NIL**

iii. Hasmappingoflanduse,waterbodies,forest,slopes,wetlands,degradedforestwithintheGram

Panchayatbeendone?Yes/No.IfNo,reason,thereof **YES**

iv. HastheClimateResiliencePlanbeendevelopedfortheGP?Yes/No **NO**

v. StepstakenbytheGramSabhaabouttheclimatechangemitigationfactorslikereducingenergy consumption,usageoffossilfuels,plastics,non-renewablebuildingmaterialsandalsotopromote measureslikeplantingoftrees,conservingforests,usageofgoodagriculturalpracticeslikedrip irrigation,waterconservationmeasuresandconservationofwetlands. **PLANTATION DONE BY FOREST DEPTT.**

vi. Whetherschoolshavestartedsegregatingwaste **YES**

vii. Whetherschoolshavetheirowncompost/soakagepitsforsolid/liquidwastemanagement -

**2 Healthyvillage**

i) Aremeetings relatedtoVillageHealthandSanitationCommitteebeingheldregularly? **YES**

ii) DoalltheeligibleindividualsbeenprovidedtheGoldenCard? **YES 90%**

iii) ArealltheChildrenbeingimmunizedaspertheSchedulerecommendedbyGovt.ofIndia? **YES**

iv) ArealltheeligibleindividualsbeenvaccinatedagainstCOVID-19? **YES**

v) DoesGramPanchayatensurethatallpregnantwomenaregettingnecessaryprenatalcheckups? **YES**

vi) WhetherallthedeliverieswereInstitutionalizedorconductedbytrainedMidwives? **YES(IN HOSPITALS)**

**3 Watersufficientvillage**

i) DoalltheIHHsintheGramPanchayathavewaterpipelineconnections?**NO**

ii) WhetherGramPanchayathastakenstepsforgreywatermanagement.IfYespleasespecify **YES COMPOST&SOAK PITS**

iii) DoalltheIHHsintheGramPanchayathavetoilets? **YES**

iv) ArealltheIHHstoiletsfunctionalornot? **NOT ALL ARE FUNCTIONAL**

v) DoalltheSchools/Anganwadicentershavea toiletfacilityornot? **YES**

vi) Areallthetoiletsintheschools/Aaganwadifunctionalornot? **NOT FUNCTIONAL IN SCHOOLS DUE TO SCARCITY OF WATER**

vii) WhetherGramPachachayatBhawanhasseparate toiletsforwomenornot?

**4 ChildFriendlyvillage**

i) Doallthechildrenundertheageof0-6yearsbeenenrolledintheAnganwadicentersforpre- schooling?Yes/NO **YES**

ii) HowmanyBalSabha’swereorganizedintheGramPanchayat **ONCE MONTHLY**

iii) WhethertheissuesraisedbyBalSabhaareaddressedduringtheGramSabha. Yes/NO **YES**

iv) WhetherGramPanchayatistrackingthedatarelatedtodropoutchildrenandchildrenwithirregular attendance?Yes/NO. **YES**

v) DoalltheschoolsundertheGramPanchayathaveseparate toiletsforgirlsandboys?Yes/No **YES**

**5 Villagewithgoodgovernance**

i) IsCSClocatedintheGramPanchayatBhawanornot? **NO**

ii) IsthelistofbeneficiariesrelatedtotheSchemes/ProgramsdisplayedontheGrampanchayatwallor not?

**NO PYT. GHAR NOT AVAILABLE**

iii) DoestheGramPanchayathasitsbuildingornot? **NO**

iv) IstheGramPanchayatofficefunctionalornot? **NO, MEETING HELD IN DHANDAL PANCHAYAT**

v) Aretheactivities approved undertheHalqaPanchayatDevelopmentPlandisplayedontheGram

Panchayatwallornot?

**PYT. GHAR NOT AVAILALE**

vi) IsSocialAuditofearlierSchemes/Programscarriedoutornot? **YES**

**6 Povertyfreeandenhancedlivelihoodvillage**

1. HasGramPanchayatdevelopedanycriteria fortheidentificationofthepoor?Yes/Noifyesspecify NO
2. ii) HavealltheeligiblehouseholdsregisteredinPDSornot? YES

iii) HasGramPanchayatprovidedspaceforSelf-helpGroupsinPanchyatGharforholdingmeetingsor not? YES

iv) HavealltheeligiblehouseholdsbeenregisteredforPensionornot? NO

v) HasGramPanchayatfacilitatedYouthforSkillEnhancementCoursesandPlacement? YES

vi) HasJobCardsbeendistributedtoalltheeligibleindividualsunderMGNREGA? YES

vii) HasGramPanchayatfacilitatedSHGsforBankAccountLinkages?YES

**7 Sociallysecuredvillage**

i) WhetherGramPanchayatismaintainingdatarelatedtoDifferentlyAbledPeople?

ii) IsGramPanchayatOffice DisabledFriendlyornot? NO

iii) Areprovisionsfora separate BudgetundertheResourceEnvelopeforWomenandChildrenmadeor not? NO

iv) DoalltheSchools intheGramPanchayathavefacilitiesforDifferentlyAbledChildrenliketoilets, barrier-freeaccess,etc.,ornot? YES

v) Arealltheeligibleindividualsaregettingpensions,likeoldagepension,widowpension,etc? SATURATION NOT DONE YET DUE TO DOMICILE CERTIFCATE

vi) ArealltheeligiblehouseholdsgettingbenefitsfromIAYornot? YES

**8 EngenderedDevelopmentinVillage**

i) HowmanyMahilaSabha’swereorganizedintheGramPanchayat ONCE IN A MONTH

ii) WhetherSHGsfederationshavebeenprovidedspaceformeetings inthePanchayatBhawan(Yes/ No) PYT. GHAR NOT AVAILABLE

iii) WhetherGPshavetakenstepsforincreasingwomen’sparticipationinGramSabha(Yes/No) YES

iv) NumberofwomenbeneficiariesheadedhouseholdscoveredunderPDS

system 25

v) Numberofbeneficiaries(outoftotaleligiblepopulation)receivingsocialprotectionbenefitsunder

PradhanMantriMatritvaVandanaYojana………………….

9 Self-sufficientinfrastructureinthevillage

1. WhetherGPhasa CommunityHallwithaccesstoelectricity,furniture,watersupply,

toilet NOT AVAILABLE

1. WhethertheDisastermanagementplanisavailableattheGPLevel(Yes/No) NO
2. Whetherchild-friendlyparkwithrequiredfacilitiesisavailableinGP(Yes/No) NO
3. WhethertheGPhaseasyaccesstoGodownforstorage(Yes/No) NO

v. Whetherstreetlightsareprovidedinpublicplacesforensuringsafety(Yes/No) YES

**DAY2ACTIVITIES**

**AGENDANO.2**

SensitizevillageresidentsaboutmyScheme”portal(myscheme.in)whichincludesinformationaboutall theschemesbeingrunbyCentral/State/UT govtacrossthecountry YES DONE

*(SchemeMaterialavailablefromhttps://jkpanchayat.in/b2v4.php)*

**DAY2ACTIVITIES**

**AGENDANO.3**

HoldmeetingoftheBiodiversityManagementCommitteestodeliberateonissues pertainingtoconserva- tionofbiodiversityandsustainableutilizationofbiologicalresources.HeshouldcheckPeopleBiodiversity register(PBR)ofthatpanchayatandreviewifBiodiversityManagementCommittee constitutedforthat panchayatis holdingminimum4meetings inayearandmeeting onceinevery3months *(RoleofBMC availableathttps://jkpanchayat.in/b2v4.php)*

COMMITTEEMEMBERS**7**PRESENT 4

BIODIVERSITYREGISTERPHOTOS NO

PAST 4MEETINGDETAILS-DATES,MINUTESPHOTOS NO

**DAY2ACTIVITIES**

**AGENDA4**

Visitingofficershallalsoplanandconductpanchayatlevelconvergencemeeting ofalldepartmentsand prepareVillagedevelopmentplanforvillage,inconsultancywithGrampanchayat,discussitingram sabhaandgetitapproved. **YES DONE**

(GPDPformatavailableonhttps://jkpanchayat.in/b2v4.php)

**InadditionGPDPplanshallalsoinclude:**

 Touristplaceswhichneedtobedeveloped PAROLA, KODI FORT

 Specificproductwhichneedstobedeveloped

 Tourism-homestays

 20candidatesfortrainingunderHimayatschemealongwithtradeinwhich trainingistobegiven YES PROVIDED

**DAY2ACTIVITIES**

**AGENDA5**

Ensuresaturationoffollowingschemesandgivestatus:

|  |  |  |  |
| --- | --- | --- | --- |
| **NAMEOFTHESCHEME** | **TOTALELIGIBLE BENEFICIARIESIN THE VILLAGE** | **TOTALBENEFICIARIESWHO AVAILEDTHEBENEFITSOFTHESCHEME** | **REASONSFOR PENDENCY** |
| GoldenHealthCardunder  AyushmanBharat | 2700 | 2430 | UNDER PROCESS |
| Jananisurakshayojana | 32 | 32 |  |
| OLDAGEpension | 50 | 45 | NOT APPLIED |
| Widowpension | 14 | 06 | DOCUMENTS NOT AVAILABLE |
| Disabilitypension | 16 | 16 |  |
| Domicilecertificate | 2700 | 1890 | DISTANCE B/W TEHSIL OFFICE, CSC CENTRE NOT AVAILABLE. |
| Kisancreditcard | 203 | 203 |  |
| PMkisansammannidhi | 223 | 223 |  |

|  |  |  |  |
| --- | --- | --- | --- |
| Landpassbook | 600 | 60 ISSUED | REST DOWNLOADED BUT PRINT OUT NOT TAKEN |
| Registrationofvillageven- dorsonGEMportal | NIL | NIL |  |
| Registrationofvillagecon- tractorsonjktendersportal | 7 | 7 |  |
| Registrationofvillagecon- tractorsonPWDportal | 7 | 7 |  |
| Incompletebuildings/pro- jects | G.M.S DHANDAL |  |  |

**DAY2ACTIVITIES**

**AGENDA6**

**NASHAMUKTABHIYAN**

1. Whethergramsabharesolutionpassed **YES**

2. Detailsofactivities conducted **AWARENESS AMONG YOUTH REGARDING VARIOUS SCHEMES, CORRUPTION FREE, NASHA MUKT ETC.**

3. Whetherallactivities andGSresolutionuploadedonjkpanchayats.inportal YES

4. Howmanydrugaddictsinthevillage NIL

5. WhetherreportedtotheDeputyCommissioner -

6. Howmanyregisteredforrehabilitationundergovernmentprogramme-

**DAY2ACTIVITIES**

**AGENDA7**

**SOCIALAUDIT**

Conductsocialauditofatleast5workseachunderfollowingschemes:

|  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- |
| NAMEOFTHE SCHEME | DETAILSOFTHE WORKS | YEAROFWORK APPROVAL | AMOUNT APPROVED  FORTHEWORK | WHETHER  WORKEXECUTED SATISFACTORILY | GEO- TAGGED PHOTOS | ANY GRIEVANCE RECORDED RELATINGTOTHAT WORK |
| MGNREGA | LAND DEVELOPMENT | 2021-22 | 2.95 LACS | YES | YES | NO |
| PMAY | REKHA DEVI  KULBIR SINGH | 2020-21  2021-22 | 1.30 LACS/HOUSE | YES | YES | NO |
| IHHL  UNDERSBM-G | SURAJ SINGH | 2018-19 | 12000 | YES | YES | NO |
| CSCUNDER SBMG | NIL |  |  |  |  |  |
| AMRIT SAROVARS | NIL |  |  |  |  |  |

**DAY2ACTIVITIES**

**AGENDA8**

**MAHILASABHA**

Totalwomeninthevillageabovetheageof18 850

Totalattended 55

Proceedings:

*(Plinsertpointerstobediscussedthere–referpalliproceedings)*

**DAY2ACTIVITIES**

**AGENDA9**

**BALSABHA**

Holda balsabhaandrecordproceedings

Totalchildreninthevillageabovetheageof….. Totalattended 57

Proceedings:

*(Plinsertpointerstobediscussedthere–referpalliproceedings)*

**DAY2ACTIVITIES**

**AGENDA10**

**INAUGURATIONS**

|  |  |  |  |
| --- | --- | --- | --- |
| **SR NO.** | **ASSETS/ACTIVITIES INAUGRATED** | **STATUSOFTHEASSET/AC- TIVITIES(NUMBER,OTHER DETAILS)** | **GEO-TAGGED PHOTOS** |
|  | VILLAGEHAATunderJKSRLM (SUN- DAYMARKET) | HANDLOOM, SWEETS, DECORATION ITEMS, VEGETABLES, KALARI, MILK PRODUCTS |  |
|  | PMAYhousesifanyreadyforinaugra- tion | YES, 2 INAUGRATED |  |
|  | Swachhgramprojects-segregation shedsetc | NA |  |
|  | Amritsarovars | NA |  |
|  | Sportskits | DISTRIBUTED |  |
|  | Villageculturalevents | ORGANISED IN SCHOOLS |  |
|  | JJMassets/projects | DATA NOT AVAILABLE AS NOBODY REPRESENTED LINE DEPTT. |  |
|  | Anyothertobeidentifiedatdistrict level |  |  |

**FOLLOWUPOF(B2V1,B2V2&B2V3):**

*(Prefilledexcelsheet tobetakenfromdistrictlevel/andalsotobedownloaded*

*from*[*www.jkpanchayat.in)*](http://www.jkpanchayat.in)

|  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- |
| S.NO. | Particulars | | | | Actiontaken | Remarks# |
| I. UrgentPublicRequirements/Demands-B2V1 | | | | | | |
| 1 WATER SUPPLY SCARCITY | |  | | | TAKEN IN JJM |  |
| 2 POOR ROAD CONNECTIVITY | |  | | | SOME WORK DONE |  |
| 3 AMBULANCE SERVICE | |  | | | TAKEN WITH HEALTH DEPTT. | AS REPORT SUBMITTED BY CONCERNED DEPTT. |
| 4 POOR ELECTRICITY SERVICE | |  | | |  |  |
| 5 EDUCATION(DEFICIENCY OF STAFF) | |  | | | TAKEN WITH EDUCATION DEPTT. |  |
| 6 NO AVAILABILITY OF SHEEP AND ANIMAL HUSBANDRY CENTRE | |  | | |  |  |
| 7 NO AVAILABILITY OF PYT. GHAR | |  | | |  |  |
| II. UrgentPublicRequirements/Demands-B2V2 | | | | | | |
| 1 SCARCITY OF WATER & ELECTRICITY | | |  | | UNDER JJM |  |
| 2 POOR ROAD INFRASTRUCTURE | | |  | | SOME IMPROVEMENT |  |
| 3 HEALTH SERVICE(SUB CENTRE) | | |  | | TAKEN WITH HEALTH DEPTT. |  |
| 4 VETERINARY DISPENSARY (CENTRE) | | |  | | NO ACTION TAKEN |  |
| 5 UPGRADATION OF GMS TO GHS | | |  | | NO ACTION TAKEN |  |
| 6 PYT. GHAR CONSTRUCTION | | |  | | NO ACTION TAKEN |  |
| 7 PROMOTION OF TOURISM | | |  | | NO ACTION TAKEN |  |
| S.NO. | | | Particulars | | Actiontaken | Remarks# |
| III. MajorProblems–B2V1 | | | | | | |
| 1 WATER SCARCITY | | | |  | UNDER JJM |  |
| 2 POOR ROAD CONNECTIVITY | | | |  | TAKEN UP WITH PMGSY |  |
| 3 NO AVAILABILITY OF PYT. GHAR | | | |  | FORWARD FOR IDENTIFICATION OF LAND TO REVENUE DEPTT. |  |

|  |  |  |  |
| --- | --- | --- | --- |
| 4 YPGRADATION OF GMS TO GHS |  | FORWARD TO EDUCATION DEPTT. |  |
| 5 |  |  |  |
| IV. MajorProblems-B2V2 | | | |
| 1 POOR WATER SUPPLY |  | JJM |  |
| 2 POOR ROAD INFRASTRUCUTRE |  | TAKEN UP WITH PMGSY |  |
| 3 POOR ELECTRICITY SUPPLY |  | TAKEN UP WITH PDD |  |
| 4 NON AVAILABILITY OF PYT. GHAR |  | TAKEN UP WITH REVENUE DEPTT. |  |
| 5 UPGRADATION OF GMS TO GHS |  | TAKEN UP WITH EDUCATION DEPTT. |  |
| V. MajorProblems-B2V3 | | | |
| 1 POOR ROAD CONNECTIVITY |  | TAKEN UP WITH PMGSY DEPTT. |  |
| 2 NON PAYMENT OF LAND COMPENSATION |  | NO ACTION TAKEN |  |
| 3 POOR ELECTRICITY INFRASTRUCTURE |  | TAKEN UP WITH PDD DEPTT. |  |
| 4 |  |  |  |
| 5 |  |  |  |
| VI. MajorComplaints-B2V1 | | | |
| 1 WATER SCARCITY |  | JJM |  |
| 2 POOR ROAD & ELECTRICITY |  | TAKEN UP WITH CONCERNED DEPTT. |  |
| 3 NON AVAILABILITY OF PYT. GHAR |  | TAKEN UP WITH REVENUE DEPTT. FOR LAND IDENTIFICATION |  |
| VII. MajorComplaints-B2V2 | | | |
| 1 WATER SCARCITY |  | JJM |  |
| 2 POOR ROAD & ELECTRICITY |  | TAKEN UP WITH CONCERNED DEPTT. |  |
| 3 |  |  |  |
| VIII. MajorComplaints-B2V3 | | | |
| 1 POOR ROAD CONNECTIVITY |  | TAKEN UP WITH PMGSY DEPTT. |  |
| 2 NON PAYMENT OF LAND COMPENSATION |  | NO ACTION TAKEN |  |
| 3 POOR ELECTRICITY INFRASTRUCTURE |  | TAKEN UP WITH PDD DEPTT. |  |

**OVERALLPERCEPTIONOFFUCNTIONING OF GOVERNMENTDEPARTMENTS**

1. **BESTDEPARTMENT: AGRICULTURE**

**2. LEASTRESPONSIVEDEPARTMENT: PHE**

**GENERALASSESSMENTOFTHEVISTINGOFFICER**

|  |  |
| --- | --- |
| I | AnymajorcomplaintbroughttothenoticeoftheVisitingOfficer: SCARCITY OF DRINKING WATER, ELECTRICITY POLES, MAINTAINANCE OF PMGSY ROAD, BOUNDARY WALL OF SCHOOLS |
| II | Major/urgentpublicdemandsthatwas/werereflectedearlierbuthavenotbeenaddressedsofar: WATER SUPPLY SCHEME, PANCHAYAT GHAR NOT AVAILABLE, VETERINARY & HEALTH SUB CENTRE, BANK & KHIDMAT CENTRE |
| III | Overallassessmentofthevisitandsuggestions:  (Thevisitingofficertoensurethattheoverallassessmentisrecordedindetailsalongwithconcretesugges- tions) |
| IV | OverallRatingofgovtfunctioningas givenbythePanchayat(Scaleof0to10) 7 |
| V | CertificatefromSarpanchthatthevisitingofficerhasstayedinthepanchayatfor2days |

BIG BOULDER OVER PIPAL TO TRILLA PMGSY ROAD WHICH CAN CAUSE EXTENSIVE DAMAGE TO PEOPLE AND THE ROAD VERY DANGEROUS TO BE ADDRESSED IMMEDIATELY.

**SignatureofSarpanch SignatureoftheVisitingOfficer**

**Name JAGRITI RAJPUT NameGURMUKH SINGH(JKAS)**

**JOINT TRANSPORT COMMISIONER J&K**

THE PANCHAYAT DHANDAL WEST WAS CREATED FROM DHANDAL PANCHAYAT IN YEAR 2018.

1. THERE IS NO PANCHAYAT GHAR
2. THERE IS NO CSC CENTRE IN PYT.
3. THERE ARE MEAGRE GOVT. BUILDINGD ONLY SCHOOLS ARE AVAILABLE IN PANCHAYAT.
4. THERE IS ACUTE SCARCITY OF DRINKING WATER IN PYT.
5. THERE IS URGENT REQUIREMENT OF POLES FROM PDD AND SOME NEW TRANSFORMERS ARE ALSO REQUIRED.
6. THE PMGSY ROAD WHICH WAS BLACKTOPPED IN YEAR 2021NEEDS REPAIR AT SOME PLACES AND THE DRAINS/NALLAHS ALONG THE ROADS NEEDS TO BE CLEANED.
7. THERE IS NO HEALTH SUB CENTRE/ VETERINARY SUB CENTRE IN PYT.
8. THERE IS NO BANK IN PYT.
9. UDHAMPUR, GORDI VIA DHANDAL BUS SERVICE IS THE DEMAND OF PYT.
10. THE IRRIGATION CHANNEL TO BE REPAIRED FROM DERI NALLAH TO KADWAHI LEHAR

THESE ALL ISSUES TO BE BROUGHT TO THE NOTICE OF CONCERNED DEPTT SO THAT MEASURES CAN BE TAKEN TO RESOLVE THE PROBLEMS FACED BY PYT.



**DepartmentofRuralDevelompentandPanchayatiRaj**

**GovernmentofJammu &Kashmir**