4





**15TH OCTto3RD NOV,2022**

**KEYFEATURES**

• DeputyCommissionerstoleadtheinitiative

• RuraldevelopmentDepartmenttobethenodaldepartment

• PlanningDevelopment&MonitoringdepartmentandITtobethesupport departments

**ACTIONSANDTIMELINES**

|  |  |  |  |
| --- | --- | --- | --- |
| **ACTION** | **RESPONSIBILITY** | **LATESTBY** | **REMARKS** |
| **Janabhiyan** | Alldepartments | Oct15-26th | Goingon |
| **DeputationofSecttstaff/ HoDs** | GAD | Oct14 | Done |
| **DeploymentofStaffto Panchayatsandservingof ordersondeployedofficers** | DCs | Oct25 | DCswilldeployseniorlevelstaff fromthedistricts.Strictactionto betakenagainstabstentions.No exemptionstobegiven |
| **Trainingofdistricttrainors onB2V4** | RDD | Oct26 |  |
| **Trainingofvisitingofficers** | DCs | Oct27 |  |
| **FieldVisitstobecompleted by** | VisitingOfficers | Nov3 | DCstosuperviseandensurethat eachPanchayatisvisitedwithin theperiodspecified |
| **DataofB2V4tobe uploadedby** | VisitingOfficers | Nov10 | DCstosuperviseandensurethat dataofallPanchayatsisupload- edbythevisitingofficerwithin theperiodspecified |

**INSTRUCTIONSFORTHEVISITINGOFFICER(DAYWISE)**

|  |  |  |
| --- | --- | --- |
| **DATE** | **INSTRUCTIONS** | **ACTIONPOINTS** |
| **Day0** | Meetingwithdeputy commissionerandhis/her team | a. TakeprintoutsoffilledbookletsofB2V1,B2V2andB2V3from [www.jkpanchayat.in](http://www.jkpanchayat.in)b.Alsotakeprintoutsofthesummarizedexcelsheetsofthe previousphasesfrom[www.jkpanchayat.in](http://www.jkpanchayat.in)c. CollectATRsonissuesraisedduringprevious3phasesfromthe officeofDeputyCommissioner(Planningdeptt)d.Takeprintsofblank 2bookletsofB2V4from[www.jkpanchayat.in](http://www.jkpanchayat.in)e.Takeplansfor2previousyearsandATRsfromtheplanningdeptt f. CompletetrainingsondifferentcomponentsofB2V4beingorganizedbyrespectiveDeputyCommissionersg.CollectListofnewworksstarted/ongoing/completedduringthe previousandcurrentFinancialyearunderthefollowingheads:• PRIgrants• DistrictPlan• UTplan• MGNREGA• Otherschemesofotherdepartments• Anyotherworkh. Plans/beneficiarylists:• MGNREGAdraftplandocumentfortheyear2022-23.• ListofAwaas+beneficiariesalongwithIHHL Convergence• Listofpensionbeneficiaries.• ListofSHGs• Listofagricultureschemebeneficiariesi. Listsofbeneficiariesfor:• Variouscertificates/benefitstobedistributedbythe visitingofficer.• Anyotheractivitiesidentifiedbydifferentdepartments |

|  |  |  |  |
| --- | --- | --- | --- |
| **Day1** | Reachthevillage | 1. | Ensurethatallfrontlineworkersofdifferentdepttsarepresent. |
|  |  | 2. | Ensureexhibitionbydifferentdepts.aboutindividualbeneficiary schemes |
|  |  | 3. | InspectJKB/PSBcounters/outlets |
|  |  | 4. | Participate/ensureorganizationofsportsactivityinplayfield,talent hunt/culturalevent/youthactivity |
|  |  | 5. | GandhiKatha(suggesteddetailsuploadedonjkpanchayat.in) |
|  |  | 6. | Visitatleast2amritsarovarsandgetitsgeotaggedphotos |
|  |  | 7. | InspectKhidmat(CSC)CentresandcreateGenerateawarenesson225schemesparticularlyG2CschemeslikeBEAMS,Janbhagidari, AapkiZaminAapkiNigrani,DigitalJ&K |
|  |  | 8. | Visitingofficershallalsoplanandconductpanchayatlevelconver- gencemeetingofalldepartments |
|  |  | 9. | CheckeffectivenessofCentrallysponsoredschemes |
|  |  | 10. | VisitandinspectallgovernmentestablishmentsincludingPHE, AWC,FPS,schools,etc |
|  |  | 11. | Attemptsaturationofdeliverableso JanAbhiyanandwherever deficienciesfound,leadadrivetoachievealldeliverables |
|  |  | 12. | Assesseffectivenessofsanitationcampaigninthepanchayat |
|  |  | 13. | Ensureselfemploymentactivitiesfor15youthperpanchayat |
|  |  | 14. | Identify20potentialcandidatesperpanchayatforHIMAYATtraining alongwiththetradeonwhichtheywanttraining |
|  |  | 15. | Whereverpossible,distributeemploymentlettersforpeopleselect- edundervariousgovernmentemployments |
|  |  | 16. | Intheevening,holdnormalmeetingwith seniorcitizens,govtem- ployeesincludingretiredemployees,exservicemen,youthclub,and any citizens ofthevillagewhoareenrolledincollege/university |
|  |  | 17. | OpendiscussiononNashaMuktAbhiyan |

Day2 Haveameetingwithall stakeholders-depttofficials andpanchayatmembers

1. Discussionontheandassesstheprogressofdifferentschemesrelating tothelocalizedSDGsprioritizedforthatvillageaspertheresolution passedby thatGramPanchayaton21st April22,onNationalPanchayti RajDay.

2. Sensitizevillage residentsaboutmyScheme”portal(myscheme.in) whichincludesinformationaboutalltheschemesbeingrunbyCen- tral/State/UTgovtacrossthecountry

3. Hold meeting of theBiodiversityManagementCommitteestodeliber- ateonissuespertaining toconservation of biodiversityandsustaina- bleutilizationof biologicalresources.

4. PrepareVillagedevelopmentplan,inconsultancywithGrampanchayat, discussitingramsabhaandgetitapproved.

5. Ensure saturationofsoilhealthcardandgoldenhealthcardunderGold- enHealthCardunderAyushmanBharat,

6. Ensuresaturation of OldAge PensionScheme

7. EnsureDomicileSaturation.

8. EnsureKCCSaturation

9. Ensure saturationoflandpassbooks

10. Ensureregistrationofvillagevendorsneededforanyscheme,onGEM

portal

11. Ensurepanchayatcontractors registration

12. EncouragePanchayatmembers forimportanceofplantationdrivein

PanchayatunderHarGaonHariyali

13. Ensure paintingondigitalJ&Kinpanchayatghars

14. Ensure paintingonpanchayatactivitesandCSSinpanchayatghars

15. Thevisiting officeshallchecknoof kindergarten andplayfields present inthepanchayat for kidsandstudents,iftheinfrastructure present inthesearegoodenough.

16. Holdmeeting withpanchayatmembers todiscussaboutcorruption menaceandstepsrequiredtomakeJ&Kcorruptionfree

17. Obtaina candidassessmentaboutperformanceofvariousdeptts in- cludingfairfeedbackaboutdiscrepanciesinfunctioning

18. Check thestatusof NashaMuktAbhiyanandreporting of drugad- dictstoDeputyCommissioner.

19. IdentifyTouristDestinations,Circuits,ThemeTreks,IdentifyHomestays, providesupportfortourismactivities throughVillageCooperative

20. OrganizeTalentHuntatPanchayatLevel

21. Conductsocialauditofatleast5worksunderfollowingschemes:

a. MGNREGA

b.PMAY

c. IHHLtoiletsandpayments d.CSCs

e.AMRITSAROVARS

22. Holda mahilasabha anda balsabhaandrecordproceedingsinthefor- matgiven

23. InauguratevillagehaatunderJKSRLM

24. Checkifyouthclubsareformedinthepanchayatandwhatactivities theyareengagedin

25. Organizea villagelevelculturaleventtoengagepanchayatmembers

26. SensitizeGPaboutE-kitabkoshaninitiativeofJ&KGovtforempowering youthsthrough onlinedigitalliteracy

**GENERALINSTRUCTIONS**

1. Thevisitingofficershallrefrainhimself/herselfgivingorofferinganycommitmentonbehalfofthe governmentandshalladoptanunbiasedattitudeinreportingissues.As faraspossible,his/her observation shouldbebasedona fairandanalytical viewemergingfromhis/herinteractioninthe village.

2. Heisgoingtothevillageasplanningofficer,notforsanctioninganyworksorformakinganycom- mitments.

3. Whilepreparingvillagedevelopmentplan,hehastoensurethat,demandsareprioritizedandre- flectedunderavailableschemes,wherevernecessarythelargerworksaretobereferredtoadminis- trativedepttunderCSS/UTplansunderintimationtoDCsandrestoftheworkstoDCsforreflecting itunderdistrict/CSS plans

4. His workshallbehardcoreplanningandauditandisnota PRexercise.

5. EveryDeputyCommissionerhastoensurethatatleastoneRDDofficial(ideallyPanchayatSecre- tary)ispresent ineverypanchayatwithrelevantpanchayatrecords,toensureconductofallactivi- tiesasplanned.Panchayatwiseorderneedstobeissuedinadvance.

6. Visitingofficershouldideallycarryhis/herlaptoptocompletethereportsatthepanchayatlevel itselfanduploadthefinalreport,duly signedbothbythesarpanchandbythevisitingofficeron [www.jkpanchayat.in](http://www.jkpanchayat.in)portal,beforetheyleavepanchayat.

7. Focus ofvisitareyouth,skills,self-employment,nashamukt,bhrashtracharmukt,Rozgaryukt J&K, besidestocarryforwardtheactivities duringJanAbhiyanandsaturatethem.

8. Inadditionattentionmaybegiventothefollowingareas a. MakefulluseofCentrallySponsoredSchemes

b.Saturationofindividualbeneficiaryschemes c. Self-employmentschemes

d.Banklinkedschemes-includingdepartmentalsubsidyschemes e.Empowermentandtransparencythrough digitalinitiatives

f. Effectivenessofgrassrootsmachinery–

i. Patwari,VLWpresent andavailable

ii. AvailablefundsutilizedinpublicinterestandasperGramSabharesolutions iii. Fairness ingovernance

iv. CSS/Individual beneficiaryschemesetc v. BrashtacharMuktJ&K

vi. BhaiMuktJ&K

vii. NashaMuktJ&K

9. ThePRImembers (Sarpanchs,Panchs,BDCChairperson)shallbeattheforefrontofallactivities and givendueimportanceandtheapproach shouldbetostrengthenthemandmakethemfeelem- powered.He/sheshallensurethattheBDCchairpersonandSarpanch/Panch arepresent atthetime ofinaugurationandceremonies.

10. Visitingofficershallnotleavethedistrictwithoutuploadingthereport,duly signedonthe**www. jkpanchayat.in**portal.EveryDeputyCommissionerhastoensurethat.

**A) DetailsofReportingOfficer:**

Name: Safeer Ahmed

Designation:Poultry Development officer

Department/placeof posting: Animal Husbandry deptt.Rajouri PDD

MobileNo: 7006280255

EmailID: safeetak@gmail.com

HomeDistrict:Doda

Datesof visit 1&2nd Nov.2022

**B) LocationaldetailsofPanchayat:(tobepre-filled,informationtobetakenfromtheprevious phasesbooklets/summarizedexcelsheetuploadedonjkpanchayat.in/b2v4.php)(tobevali- datedbythevisitingofficerandmissingdetailstobefilled)**

NameofthePanchayat :saj 2

LocalGovernmentDirectory(LGD)codeof thePanchayat: 240200

Nameof CDBlock: plangarh

NameofTehsil: Thannamandi

Nameof District: Rajouri

**C) PanchayatProfile:**

No.ofrevenuevillagesinthePanchayat:df 01

No.ofhamletsinthePanchayat: 20

No.ofhouseholdsinthePanchayat: 450

Population(approx)of thePanchayat: 2573

**Part-II:**

(TobefilledupbytheVisitingOfficerduringhis/hertwodayvisittothePanchayat.AllFieldshavetobe

filledbytheVisitingOfficerbeforethebookletishandedovertotheDC

**FrontlineOfficers/OfficialswhowereassignedtothePanchayatfortheprogramme:**

|  |  |  |
| --- | --- | --- |
| Department | Name | Designation |
| Rdd | Mohd Razaq  | Inspector Panchayat  |
| Jel Shakti  | Shabir Ahmed  | Line Man  |
| CADP | Mohd Amin  | Dealer  |
| Pdd | Faiz Ul Rasool  | Line Man  |
| Sheep Husbandry  | Zakir Hussain  | AsM |
| Social Forester | Ghulam Rasool  | G A |
| Health  | Zahida Fatima  | Asha  |
| Icds | Gulshan Aro | FMPHW |
| Health  | Zahida Parveen  | AWW |
| IcDS | Shenaz Akther  | ICDS  |
|  |  |  |
|  |  |  |
|  |  |  |

**Detailsofabsent employeesvis-à-vislistfurnishedbytheDCoffice:**

|  |  |  |
| --- | --- | --- |
| Department | Name | Designation |
| PHE  | Mohd Shabir  | Line Man |
| Irrigation  | Mohd Razaq  | WSW  |
| Social welfare  | Mohd Farooq  | Craft Assistant  |
| Fisheries  | Mohd Nasir  | Inspector  |
| Agr. | Satinder Paul  | AEA |
| Hot.  | Hayat Mir  | Tech. |
| Sheep Husb. | Aurangzeb  | Flock. |
| Phy Edu.Youth Services  | Mohd Farooq  | Phy Education  |
| PMGSY | Safiq Ahmed  | AE |
|  |  |  |
|  |  |  |
|  |  |  |
|  |  |  |
|  |  |  |
|  |  |  |

**DAY1-ACTIVITIES**

**AGENDA1:PANCHAYATASSETREGISTER**

**Infrastructure:**

1. PanchayatGharInfrastructure a. Govtbuilding/private

b. New/needingrepairs

2. Furniture(Y/N) Y

3. Computer/printer(Y/N) N

4. Internet(Y/N) N

5. Telephone(Y/N) N

6. Toilet(CSC/partofpanchayatghar)(Y/N) N

7. Water(Y/N) N

8. Electricity(Y/N) N

9. Bankbranch(Y/N) N

10. CSC(Y/N) Y

11. Patwarkhana(Y/N) N

12. Villagehaat(Y/N) N

13. Playground(Y/N) N

14. School-

a. Kindergarten(Y/N) N

b.Primary(Y/N) Y

c. Secondary(Y/N) N

d. College (Y/N) N

e.University(Y/N) N

15. AnganwadiCentre(Y/N)

a. (govt/private) private

b.Totalchildrenenrolled 141

15. AmritSarovars–details,location,condition NO

16. Governmentoffices-details,whetherfunctionalornot Not Tehsildar Saj

17. Rationshop(Y/N) Y

18. Placesoftourismimportance–names,littledetailsonhistorical/culturalimportance Kopra Cammri

19. Villageheritagesites/treks-names,littledetailson historical/culturalimportance N

20. VLWOffice (Y/N) N

21. PrimaryHealthcareCentre(Y/N), Y

22. ListofIncompleteBuildings-names,yearofconstruction Community Hall 2021

23. ListofUnderutilizedBuildings-names Anganwadi centre w 6

**DAY1-ACTIVITIES**

**AGENDA2:**

**DIFFERENTINSTITUTIONS/INFRASTRUCTUREPROJECTSTOBEVISITED**

|  |  |  |
| --- | --- | --- |
| **AMRITSAROVARS** | **Visit,verify** | **COMMENTS** |
| KhidmatCentres | Create/Generateawarenesson225schemes particularlyG2CschemsAapkiZaminAapkiNigrani, Beams,Janbhagidari,DigitalJ&K | One khadmat centre present  |
| JKB/PSBcounters/outlets | a)Statusofcounter b)Numberofvisitors |  |
| Incompletebuildings/pro- jects | Verify whetheridentificationandredistribution done | Community Centre  |
| PDS | Visit,evaluate,onlinestatus |  Functioning property  |
| PHC | Visit-evaluate,statusofstaff,equipmentand quality | Meets Public Demands  |
| Youthclubs | Meet,interact,seeksuggestions |  |
| SHG | Meet,identifyproblems,seeksuggestions | Centre is quite out far away from population  |
| PMAY | Inspect,Inaugurate | 145 unit 100 completed hand over  |
| Myschool,mypride progress;schools-water, toilets,staff | Visit,checkforwater,electricity,sanitation,meet studentsandstaff | Water supply not proper electricity  |
| SwachhSBM | Evaluate | 60-70 % toilet Completed 30-40 % stell awacted  |
| Panchayatplayground, Sportskitsdistribution Villagegames | Ensure,verify.Participateinatleastonegamein theplayground |  |
| HarGaonHariyali, Planta- tiondrive | Evaluatestatus,feedback | No Such drive conducted  |
| VillageculturaleventDangal/Haat/Mela | Participatein;ensurethatitisheld |  |
| Exhibitionofschemes | Ensurethateverydepartmentparticipatesand thatitcontinuesfortheentiredurationofB2V |  |
| JalJeewanMission verifica- tion- WSS/JSDElectricitysupply | Verify | Left irrigation scheme Mehrajpura to kopra tenders still awaited  |

**DAY1-ACTIVITIES**

**AGENDA3:SATURATEJANBHIYAN**

**DELIVERABLESANDRECORDDEFICIENCIESIFANY(INSERTDELIVERABLESLISTHEREASPERGADFORMAT**

**DAY1-ACTIVITIES**

**AGENDA4:**

**SELFEMPLOYMENTACTIVITIES**

EnsureSelf-employmentactivities foryouth,distributeemploymentlettersforpeopleselectedunder varioussocialschemes(15ISTHETARGETPERPANCHAYAT)

**Numberofcasesindifferentcategoriessanctioned: Detailsofthebanksanctioningit:**

**Totalamountinvolved:**

**DAY1ACTIVITIES**

**AGENDA5**

Intheevening,holdinformalmeetings withseniorcitizens,govtemployees,retdemployees,youthclub andothercitizenswhoareenrolledoncollege/universityandhavediscussiononGandhiKatha,Nasha MuktAbhiyan,corruptionfreegovernance,doublingfarmersincomeandrecordtheproceedings

**DAY2**

a. NoofIndividualCompostPitsconstructed N b.NoofIndividualSoakPitsconstructed 30

V. No.ofBiodiversitymanagementcommitteemeetingsheld:1

VI. IsthenameofSarpanchdisplayedoncitizeninformationboardsofallRD&PRschemes:Yes/No Y

VII. AreSarpanchsbeinginvolvedinstart/inaugurationofactivities:Yes/No Y

VIII. WhethersubjectshavebeenassignedbytheSarpanchtothePanchs:Yes/No

IX. Whethergrievancesredressalboxisinstalled:Yes/No Y

X. NoofgrievancesreceivedpertainingtoPanchayatlevel: XI. NoofgrievancesdisposedofatPanchayatlevel:

XII. WhethertheSarpanch/PanchayatSecretaryhavedigitalsignatures:Yes/No Y

XIII. WhetherallMGNREGA/14thFCpayments arebeingmadebySarpanchthrough DigitalSignature

 Certificate(DSC):Yes/NoY

**HUMAN RESOURCEAVAILABLEATTHEPANCHAYAT LEVEL:**

|  |  |  |  |
| --- | --- | --- | --- |
| **SRNO.** | **DEPARTMENTWISESTAFF** | **NUMBERS** | **NAMES** |
|  |  | SANCTIONED | ACTUAL |  |
|  | Ruraldevelopmentdepartment: BDOJE GRS TA | 1374 | 1133 |  |
|  | SCHOOLEDUCATION: TEACHERHEADMASTER ANYOTHER | 63 | 63 |  |
|  | JAL JEEVAN: | 4 | 2 |  |
|  | PDD: LINEMAN JEANYOTHER | 211 | 4 |  |
|  | FOOD&CIVILSUPPLIES | 2 | 2 |  |
|  | AGRICULTURE&ANIMALHUS- BANDARY | 0 | 0 |  |
|  | SOCIALWELFARE | 0 | 0 |  |
|  | HEALTH: ASHA ANMAYUSHDOCTOR ALLOPATHICDOCTOR | 3000 | 3 |  |
|  | ANYOTHERDEPARTMENT |  |  |  |

**DAY2-ACTIVITIES**

**AGENDANO.1**

DiscussionontheandassesstheprogressofdifferentschemesrelatingtothelocalizedSDGsprior-itizedforthatvillageaspertheresolutionpassedbythatGramPanchayaton21stApril22,onNational PanchayatiRajDay(Copyoftheresolutiontobetakenfrom[www.jkpanchayat.in](http://www.jkpanchayat.in)portalunderthelinkof GramSwarajMonth)

1. SDGs AGREED FORTHATVILLAGE,TOBEIMPLEMENTED BYMARCH2024:

2. STATUSOFWORKSUNDERTHEFOLLOWINGSCHEMES:

**1 Cleanandgreenvillage**

i.InitiativestakenbythePanchayatformanagingSolidandLiquidWaste voluntarily measures take by pyt it self

ii. InitiativestakenbythePanchayatforusinggreensourcesoffuellikesolar,biogas

 nil

iii. Hasmappingoflanduse,waterbodies,forest,slopes,wetlands,degradedforestwithintheGram

Panchayatbeendone?Yes/No.IfNo,reason,thereof lock of awareness

iv. HastheClimateResiliencePlanbeendevelopedfortheGP?Yes/No yes

v. StepstakenbytheGramSabhaabouttheclimatechangemitigationfactorslikereducingenergy consumption,usageoffossilfuels,plastics,non-renewablebuildingmaterialsandalsotopromote measureslikeplantingoftrees,conservingforests,usageofgoodagriculturalpracticeslikedrip irrigation,waterconservationmeasuresandconservationofwetlands.

vi. Whetherschoolshavestartedsegregatingwaste no

vii. Whetherschoolshavetheirowncompost/soakagepitsforsolid/liquidwastemanagement no

**2 Healthyvillage**

i) Aremeetings relatedtoVillageHealthandSanitationCommitteebeingheldregularly?yes

ii) DoalltheeligibleindividualsbeenprovidedtheGoldenCard? Yes

iii) ArealltheChildrenbeingimmunizedaspertheSchedulerecommendedbyGovt.ofIndia? yes

iv) ArealltheeligibleindividualsbeenvaccinatedagainstCOVID-19? Yes

v) DoesGramPanchayatensurethatallpregnantwomenaregettingnecessaryprenatalcheckups?yes

vi) WhetherallthedeliverieswereInstitutionalizedorconductedbytrainedMidwives?yes

**3 Watersufficientvillage**

i) DoalltheIHHsintheGramPanchayathavewaterpipelineconnections? No

ii) WhetherGramPanchayathastakenstepsforgreywatermanagement.IfYespleasespecify yes

 iii) DoalltheIHHsintheGramPanchayathavetoilets? Yes

iv) ArealltheIHHstoiletsfunctionalornot? Yes

v) DoalltheSchools/Anganwadicentershavea toiletfacilityornot?all school have toilets

vi) Areallthetoiletsintheschools/Aaganwadifunctionalornot? yes

vii) WhetherGramPachachayatBhawanhasseparate toiletsforwomenornot? no

**4 ChildFriendlyvillage**

i) Doallthechildrenundertheageof0-6yearsbeenenrolledintheAnganwadicentersforpre- schooling?Yes/NO yes

ii) HowmanyBalSabha’swereorganizedintheGramPanchayat 10

iii) WhethertheissuesraisedbyBalSabhaareaddressedduringtheGramSabha. Yes/NO yes

iv) WhetherGramPanchayatistrackingthedatarelatedtodropoutchildrenandchildrenwithirregular attendance?Yes/NO. no

v) DoalltheschoolsundertheGramPanchayathaveseparate toiletsforgirlsandboys?Yes/No yes

**5 Villagewithgoodgovernance**

i) IsCSClocatedintheGramPanchayatBhawanornot? No

ii) IsthelistofbeneficiariesrelatedtotheSchemes/ProgramsdisplayedontheGrampanchayatwallor not?yes

iii) DoestheGramPanchayathasitsbuildingornot? No

iv) IstheGramPanchayatofficefunctionalornot? Functional from sented building

v) Aretheactivities approved undertheHalqaPanchayatDevelopmentPlandisplayedontheGram

Panchayatwallornot? Y

vi) IsSocialAuditofearlierSchemes/Programscarriedoutornot? Yes

**6 Povertyfreeandenhancedlivelihoodvillage**

i) HasGramPanchayatdevelopedanycriteria fortheidentificationofthepoor?Yes/Noifyesspecify land holding

 ii) HavealltheeligiblehouseholdsregisteredinPDSornot? Yes

iii) HasGramPanchayatprovidedspaceforSelf-helpGroupsinPanchyatGharforholdingmeetings or not? No

iv) HavealltheeligiblehouseholdsbeenregisteredforPensionornot? Yes

v) HasGramPanchayatfacilitatedYouthforSkillEnhancementCoursesandPlacement? No

vi) HasJobCardsbeendistributedtoalltheeligibleindividualsunderMGNREGA? Yes

vii) HasGramPanchayatfacilitatedSHGsforBankAccountLinkages? No

**7 Sociallysecuredvillage**

i) WhetherGramPanchayatismaintainingdatarelatedtoDifferentlyAbledPeople? No

ii) IsGramPanchayatOffice DisabledFriendlyornot? No

iii) Areprovisionsfora separate BudgetundertheResourceEnvelopeforWomenandChildrenmadeor not? Not

iv) DoalltheSchools intheGramPanchayathavefacilitiesforDifferentlyAbledChildrenliketoilets, barrier-freeaccess,etc.,ornot? Not

v) Arealltheeligibleindividualsaregettingpensions,likeoldagepension,widowpension,etc? yes

vi) ArealltheeligiblehouseholdsgettingbenefitsfromIAYornot?

Yes

**8 EngenderedDevelopmentinVillage**

i) HowmanyMahilaSabha’swereorganizedintheGramPanchayat 2

ii) WhetherSHGsfederationshavebeenprovidedspaceformeetings inthePanchayatBhawan(Yes/ No) no

iii) WhetherGPshavetakenstepsforincreasingwomen’sparticipationinGramSabha(Yes/No) yes

iv) NumberofwomenbeneficiariesheadedhouseholdscoveredunderPDS

system 05

v) Numberofbeneficiaries(outoftotaleligiblepopulation)receivingsocialprotectionbenefitsunder

PradhanMantriMatritvaVandanaYojana 25

9 Self-sufficientinfrastructureinthevillage

i. WhetherGPhasa CommunityHallwithaccesstoelectricity,furniture,watersupply, toilet under construction

ii. WhethertheDisastermanagementplanisavailableattheGPLevel(Yes/No) no

 iii. Whetherchild-friendlyparkwithrequiredfacilitiesisavailableinGP(Yes/No) no

 iv. WhethertheGPhaseasyaccesstoGodownforstorage(Yes/No) no

v. Whetherstreetlightsareprovidedinpublicplacesforensuringsafety(Yes/No) no

**DAY2ACTIVITIES**

**AGENDANO.2**

SensitizevillageresidentsaboutmyScheme”portal(myscheme.in)whichincludesinformationaboutall theschemesbeingrunbyCentral/State/UT govtacrossthecountry

*(SchemeMaterialavailablefromhttps://jkpanchayat.in/b2v4.php)*

**DAY2ACTIVITIES**

**AGENDANO.3**

HoldmeetingoftheBiodiversityManagementCommitteestodeliberateonissues pertainingtoconserva- tionofbiodiversityandsustainableutilizationofbiologicalresources.HeshouldcheckPeopleBiodiversity register(PBR)ofthatpanchayatandreviewifBiodiversityManagementCommittee constitutedforthat panchayatis holdingminimum4meetings inayearandmeeting onceinevery3months *(RoleofBMC availableathttps://jkpanchayat.in/b2v4.php)*

COMMITTEEMEMBERS PRESENT

BIODIVERSITYREGISTERPHOTOS

PAST 4MEETINGDETAILS-DATES,MINUTESPHOTOS

**DAY2ACTIVITIES**

**AGENDA4**

Visitingofficershallalsoplanandconductpanchayatlevelconvergencemeeting ofalldepartmentsand prepareVillagedevelopmentplanforvillage,inconsultancywithGrampanchayat,discussitingram sabhaandgetitapproved.

(GPDPformatavailableonhttps://jkpanchayat.in/b2v4.php)

**InadditionGPDPplanshallalsoinclude:**

 Touristplaceswhichneedtobedeveloped 1 saj kopra top

 Specificproductwhichneedstobedeveloped

 Tourism-homestays nil

 20candidatesfortrainingunderHimayatschemealongwithtradeinwhich trainingistobegiven nil

**DAY2ACTIVITIES**

**AGENDA5**

Ensuresaturationoffollowingschemesandgivestatus:

|  |  |  |  |
| --- | --- | --- | --- |
| **NAMEOFTHESCHEME** | **TOTALELIGIBLE BENEFICIARIESIN THE VILLAGE** | **TOTALBENEFICIARIESWHO AVAILEDTHEBENEFITSOFTHESCHEME** | **REASONSFOR PENDENCY** |
| GoldenHealthCardunderAyushmanBharat | 95% competed  | 20% | Shall avail the benefit if contingency arises  |
| Jananisurakshayojana | 50 | 23 | At the compeletion of pregmency  |
| OLDAGEpension | 144 | 144 | Nil  |
| Widowpension | 18 | 18 | nil |
| Disabilitypension | 90 | 90 | nil |
| Domicilecertificate | 500 | 200 | Pendency due to lack awareness  |
| Kisancreditcard | 302 | 302 | Overage  |
| PMkisansammannidhi | 300 | 50 | Pendency due to lack of awareness  |

|  |  |  |  |
| --- | --- | --- | --- |
| Landpassbook | 300 | 50 | Pendency due to lack of awareness |
| Registrationofvillageven- dorsonGEMportal | Nil  | Nil  | Pendency due to lack of awareness |
| Registrationofvillagecon- tractorsonjktendersportal | 4 | 4 | Not interested  |
| Registrationofvillagecon- tractorsonPWDportal | Nil  |  Nil  | NA |
| Incompletebuildings/pro- jects | 1 | 1 | In progress  |

**DAY2ACTIVITIES**

**AGENDA6**

**NASHAMUKTABHIYAN**

1. Whethergramsabharesolutionpassed yes

2. Detailsofactivities conducted awareness camp

3. Whetherallactivities andGSresolutionuploadedonjkpanchayats.inportal 30%

4. Howmanydrugaddictsinthevillage no record available

5. WhetherreportedtotheDeputyCommissioner no

6. Howmanyregisteredforrehabilitationundergovernmentprogramme

 Nil

**DAY2ACTIVITIES**

**AGENDA7**

**SOCIALAUDIT**

Conductsocialauditofatleast5workseachunderfollowingschemes:

|  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- |
| NAMEOFTHE SCHEME | DETAILSOFTHE WORKS | YEAROFWORK APPROVAL | AMOUNT APPROVEDFORTHEWORK | WHETHERWORKEXECUTED SATISFACTORILY | GEO- TAGGED PHOTOS | ANY GRIEVANCE RECORDED RELATINGTOTHAT WORK |
| MGNREGA | P wall 3 | 2021-22 | 5 Lak  |  Satisfactory  |  Upload  |  Work completed  |
| PMAY | House Construction  | 2021-22 | 9.60 |  |  |  |
| IHHLUNDERSBM-G | IHHL Unit 6 | 2021-22 | 72 thousand  |  |  |  |
| CSCUNDER SBMG | Sanitary 2 | 2021-22 | 3.60 lakh  |  |  |  |
| AMRIT SAROVARS | Nil | 2021-22 | Nil  |  |  |  |

**DAY2ACTIVITIES**

**AGENDA8**

**MAHILASABHA**

Totalwomeninthevillageabovetheageof18

Totalattended 20

Proceedings: Mahila sabah

*(Plinsertpointerstobediscussedthere–referpalliproceedings)*

**DAY2ACTIVITIES**

**AGENDA9**

**BALSABHA**

Holda balsabhaandrecordproceedings

Totalchildreninthevillageabovetheageof 12 Totalattended 30

Proceedings:

*(Plinsertpointerstobediscussedthere–referpalliproceedings)*

**DAY2ACTIVITIES**

**AGENDA10**

**INAUGURATIONS**

|  |  |  |  |
| --- | --- | --- | --- |
| **SR NO.** | **ASSETS/ACTIVITIES INAUGRATED** | **STATUSOFTHEASSET/AC- TIVITIES(NUMBER,OTHER DETAILS)** | **GEO-TAGGED PHOTOS** |
|  | VILLAGEHAATunderJKSRLM (SUN- DAYMARKET) | Nil  | Nil  |
|  | PMAYhousesifanyreadyforinaugra- tion | All beneficiaries have shifted in their house  | Nil  |
|  | Swachhgramprojects-segregation shedsetc | Nil  | Nil  |
|  | Amritsarovars | Nil  | Nil  |
|  | Sportskits | Nil  | Nil  |
|  | Villageculturalevents | Nil | Nil  |
|  | JJMassets/projects | Hand pump water points 8 | Photos upload with geotags  |
|  | Anyothertobeidentifiedatdistrict level |  |  |

**FOLLOWUPOF(B2V1,B2V2&B2V3):**

*(Prefilledexcelsheet tobetakenfromdistrictlevel/andalsotobedownloaded*

*from*[*www.jkpanchayat.in)*](http://www.jkpanchayat.in)

|  |  |  |  |
| --- | --- | --- | --- |
| S.NO. | Particulars | Actiontaken | Remarks# |
| I. UrgentPublicRequirements/Demands-B2V1 |
| 1 |  |  |  |
| 2 |  |  |  |
| 3 |  |  |  |
| 4 |  |  |  |
| 5 |  |  |  |
| 6 |  |  |  |
| 7 |  |  |  |
| II. UrgentPublicRequirements/Demands-B2V2 |
| 1 |  |  |  |
| 2 |  |  |  |
| 3 |  |  |  |
| 4 |  |  |  |
| 5 |  |  |  |
| 6 |  |  |  |
| 7 |  |  |  |
| S.NO. | Particulars | Actiontaken | Remarks# |
| III. MajorProblems–B2V1 |
| 1 |  |  |  |
| 2 |  |  |  |
| 3 |  |  |  |

|  |  |  |  |
| --- | --- | --- | --- |
| 4 |  |  |  |
| 5 |  |  |  |
| IV. MajorProblems-B2V2 |
| 1 |  |  |  |
| 2 |  |  |  |
| 3 |  |  |  |
| 4 |  |  |  |
| 5 |  |  |  |
| V. MajorProblems-B2V3 |
| 1 | Nara to comiri  |  |  |
| 2 | Nara to Hakla Mohalla  |  |  |
| 3 | Main Road to Khokhar Mohalla  |  |  |
| 4 |  |  |  |
| 5 |  |  |  |
| VI. MajorComplaints-B2V1 |
| 1 | Not Completed  |  |  |
| 2 |  |  |  |
| 3 |  |  |  |
| VII. MajorComplaints-B2V2 |
| 1 |  |  |  |
| 2 |  |  |  |
| 3 |  |  |  |
| VIII. MajorComplaints-B2V3 |
| 1 |  |  |  |
| 2 |  |  |  |
| 3 |  |  |  |

**OVERALLPERCEPTIONOFFUCNTIONING OF GOVERNMENTDEPARTMENTS**

1. **BESTDEPARTMENT:**

**2. LEASTRESPONSIVEDEPARTMENT:**

**GENERALASSESSMENTOFTHEVISTINGOFFICER**

|  |  |
| --- | --- |
| I | AnymajorcomplaintbroughttothenoticeoftheVisitingOfficer: funds requirement for different Rural Development Scheme |
| II | Major/urgentpublicdemandsthatwas/werereflectedearlierbuthavenotbeenaddressedsofar: Electricity poles road and dispensary  |
| III | Overallassessmentofthevisitandsuggestions:(Thevisitingofficertoensurethattheoverallassessmentisrecordedindetailsalongwithconcretesugges- tions) |
| IV | OverallRatingofgovtfunctioningas givenbythePanchayat(Scaleof0to10) 4  |
| V | CertificatefromSarpanchthatthevisitingofficerhasstayedinthepanchayatfor2days yes  |

**SignatureofSarpanch SignatureoftheVisitingOfficer**

**Name……………………… Name………………………**



**DepartmentofRuralDevelompentandPanchayatiRaj**

**GovernmentofJammu &Kashmir**