4

15TH OCTto3RD NOV,2022

# KEYFEATURES

- DeputyCommissionerstoleadtheinitiative

- RuraldevelopmentDepartmenttobethenodaldepartment

- PlanningDevelopment&MonitoringdepartmentandITtobethesupport departments

# ACTIONSANDTIMELINES

| ACTION | RESPONSIBILITY | LATESTBY | REMARKS |
| --- | --- | --- | --- |
| Janabhiyan | Alldepartments | Oct15-26th | Goingon |
| DeputationofSecttstaff/ HoDs | GAD | Oct14 | Done |
| DeploymentofStaffto Panchayatsandservingof ordersondeployedofficers | DCs | Oct25 | DCswilldeployseniorlevelstaff fromthedistricts.Strictactionto betakenagainstabstentions.No exemptionstobegiven |
| Trainingofdistricttrainors onB2V4 | RDD | Oct26 |  |
| Trainingofvisitingofficers | DCs | Oct27 |  |
| FieldVisitstobecompleted by | VisitingOfficers | Nov3 | DCstosuperviseandensurethat eachPanchayatisvisitedwithin theperiodspecified |
| DataofB2V4tobe uploadedby | VisitingOfficers | Nov10 | DCstosuperviseandensurethat dataofallPanchayatsisupload- edbythevisitingofficerwithin theperiodspecified |

INSTRUCTIONSFORTHEVISITINGOFFICER(DAYWISE)

| DATE | INSTRUCTIONS | ACTIONPOINTS |
| --- | --- | --- |
| Day0 | Meetingwithdeputy commissionerandhis/her team | - TakeprintoutsoffilledbookletsofB2V1,B2V2andB2V3from www.jkpanchayat.in - Alsotakeprintoutsofthesummarizedexcelsheetsofthe previousphasesfromwww.jkpanchayat.in - CollectATRsonissuesraisedduringprevious3phasesfromthe officeofDeputyCommissioner(Planningdeptt) - Takeprintsofblank 2bookletsofB2V4fromwww.jkpanchayat.ine.Takeplansfor2previousyear sandATRsfromtheplanningdeptt f. CompletetrainingsondifferentcomponentsofB2V4being organizedbyrespectiveDeputyCommissioners g.CollectListofnewworksstarted/ongoing/completedduringthe previousandcurrentFinancialyearunderthefollowingheads: - PRIgrants - DistrictPlan - UTplan - MGNREGA - Otherschemesofotherdepartments - Anyotherwork - Plans/beneficiarylists: - MGNREGAdraftplandocumentfortheyear2022-23. - ListofAwaas+beneficiariesalongwithIHHL Convergence - Listofpensionbeneficiaries. - ListofSHGs - Listofagricultureschemebeneficiaries - Listsofbeneficiariesfor: - Variouscertificates/benefitstobedistributedbythe visitingofficer. - Anyotheractivitiesidentifiedbydifferentdepartments |

| Day1 | Reachthevillage | 1. | Ensurethatallfrontlineworkersofdifferentdepttsarepresent. |
| --- | --- | --- | --- |
|  |  | 2. | Ensureexhibitionbydifferentdepts.aboutindividualbeneficiary schemes |
|  |  | 3. | InspectJKB/PSBcounters/outlets |
|  |  | 4. | Participate/ensureorganizationofsportsactivityinplayfield,talent hunt/culturalevent/youthactivity |
|  |  | 5. | GandhiKatha(suggesteddetailsuploadedonjkpanchayat.in) |
|  |  | 6. | Visitatleast2amritsarovarsandgetitsgeotaggedphotos |
|  |  | 7. | InspectKhidmat(CSC)CentresandcreateGenerateawarenesson 225schemesparticularlyG2CschemeslikeBEAMS,Janbhagidari, AapkiZaminAapkiNigrani,DigitalJ&K |
|  |  | 8. | Visitingofficershallalsoplanandconductpanchayatlevelconver- gencemeetingofalldepartments |
|  |  | 9. | CheckeffectivenessofCentrallysponsoredschemes |
|  |  | 10. | VisitandinspectallgovernmentestablishmentsincludingPHE, AWC,FPS,schools,etc |
|  |  | 11. | Attemptsaturationofdeliverableso JanAbhiyanandwherever deficienciesfound,leadadrivetoachievealldeliverables |
|  |  | 12. | Assesseffectivenessofsanitationcampaigninthepanchayat |
|  |  | 13. | Ensureselfemploymentactivitiesfor15youthperpanchayat |
|  |  | 14. | Identify20potentialcandidatesperpanchayatforHIMAYATtraining alongwiththetradeonwhichtheywanttraining |
|  |  | 15. | Whereverpossible,distributeemploymentlettersforpeopleselect- edundervariousgovernmentemployments |
|  |  | 16. | Intheevening,holdnormalmeetingwith seniorcitizens,govtem- ployeesincludingretiredemployees,exservicemen,youthclub,and any citizens ofthevillagewhoareenrolledincollege/university |
|  |  | 17. | OpendiscussiononNashaMuktAbhiyan |

| Day2 | Haveameetingwithall stakeholders-depttofficials andpanchayatmembers | - Discussionontheandassesstheprogressofdifferentschemesrelating tothelocalizedSDGsprioritizedforthatvillageaspertheresolution passedby thatGramPanchayaton21st April22,onNationalPanchayti RajDay. - Sensitizevillage residentsaboutmyScheme”portal(myscheme.in) whichincludesinformationaboutalltheschemesbeingrunbyCen- tral/State/UTgovtacrossthecountry - Hold meeting of theBiodiversityManagementCommitteestodeliber- ateonissuespertaining toconservation of biodiversityandsustaina- bleutilizationof biologicalresources. - PrepareVillagedevelopmentplan,inconsultancywithGrampanchayat, discussitingramsabhaandgetitapproved. - Ensure saturationofsoilhealthcardandgoldenhealthcardunderGold- enHealthCardunderAyushmanBharat, - Ensuresaturation of OldAge PensionScheme - EnsureDomicileSaturation. - EnsureKCCSaturation - Ensure saturationoflandpassbooks - Ensureregistrationofvillagevendorsneededforanyscheme,onGEM portal - Ensurepanchayatcontractors registration - EncouragePanchayatmembers forimportanceofplantationdrivein PanchayatunderHarGaonHariyali - Ensure paintingondigitalJ&Kinpanchayatghars - Ensure paintingonpanchayatactivitesandCSSinpanchayatghars - Thevisiting officeshallchecknoof kindergarten andplayfields present inthepanchayat for kidsandstudents,iftheinfrastructure present inthesearegoodenough. - Holdmeeting withpanchayatmembers todiscussaboutcorruption menaceandstepsrequiredtomakeJ&Kcorruptionfree - Obtaina candidassessmentaboutperformanceofvariousdeptts in- cludingfairfeedbackaboutdiscrepanciesinfunctioning - Check thestatusof NashaMuktAbhiyanandreporting of drugad- dictstoDeputyCommissioner. - IdentifyTouristDestinations,Circuits,ThemeTreks,IdentifyHomestays, providesupportfortourismactivities throughVillageCooperative - OrganizeTalentHuntatPanchayatLevel - Conductsocialauditofatleast5worksunderfollowingschemes: - MGNREGA b.PMAY c. IHHLtoiletsandpayments d.CSCs e.AMRITSAROVARS - Holda mahilasabha anda balsabhaandrecordproceedingsinthefor- matgiven - InauguratevillagehaatunderJKSRLM - Checkifyouthclubsareformedinthepanchayatandwhatactivities theyareengagedin - Organizea villagelevelculturaleventtoengagepanchayatmembers - SensitizeGPaboutE-kitabkoshaninitiativeofJ&KGovtforempowering youthsthrough onlinedigitalliteracy |
| --- | --- | --- |

# GENERALINSTRUCTIONS

- Thevisitingofficershallrefrainhimself/herselfgivingorofferinganycommitmentonbehalfofthe governmentandshalladoptanunbiasedattitudeinreportingissues.As faraspossible,his/her observation shouldbebasedona fairandanalytical viewemergingfromhis/herinteractioninthe village.

- Heisgoingtothevillageasplanningofficer,notforsanctioninganyworksorformakinganycom- mitments.

- Whilepreparingvillagedevelopmentplan,hehastoensurethat,demandsareprioritizedandre- flectedunderavailableschemes,wherevernecessarythelargerworksaretobereferredtoadminis- trativedepttunderCSS/UTplansunderintimationtoDCsandrestoftheworkstoDCsforreflecting itunderdistrict/CSS plans

- His workshallbehardcoreplanningandauditandisnota PRexercise.

- EveryDeputyCommissionerhastoensurethatatleastoneRDDofficial(ideallyPanchayatSecre- tary)ispresent ineverypanchayatwithrelevantpanchayatrecords,toensureconductofallactivi- tiesasplanned.Panchayatwiseorderneedstobeissuedinadvance.

- Visitingofficershouldideallycarryhis/herlaptoptocompletethereportsatthepanchayatlevel itselfanduploadthefinalreport,duly	signedbothbythesarpanchandbythevisitingofficeron www.jkpanchayat.inportal,beforetheyleavepanchayat.

- Focus ofvisitareyouth,skills,self-employment,nashamukt,bhrashtracharmukt,Rozgaryukt J&K, besidestocarryforwardtheactivities duringJanAbhiyanandsaturatethem.

- Inadditionattentionmaybegiventothefollowingareas a. MakefulluseofCentrallySponsoredSchemes b.Saturationofindividualbeneficiaryschemes c.

Self-employmentschemes

d.Banklinkedschemes-includingdepartmentalsubsidyschemes e.Empowermentandtransparencythrough digitalinitiatives

- Effectivenessofgrassrootsmachinery–

  - Patwari,VLWpresent andavailable

  - AvailablefundsutilizedinpublicinterestandasperGramSabharesolutions iii.

Fairness ingovernance

iv.	CSS/Individual beneficiaryschemesetc v.

BrashtacharMuktJ&K

- BhaiMuktJ&K

- NashaMuktJ&K

- ThePRImembers (Sarpanchs,Panchs,BDCChairperson)shallbeattheforefrontofallactivities and givendueimportanceandtheapproach shouldbetostrengthenthemandmakethemfeelem- powered.He/sheshallensurethattheBDCchairpersonandSarpanch/Panch arepresent atthetime ofinaugurationandceremonies.

- Visitingofficershallnotleavethedistrictwithoutuploadingthereport,duly signedonthewww. jkpanchayat.inportal.EveryDeputyCommissionerhastoensurethat.

## DetailsofReportingOfficer:

Name: Ranbir Singh Bali

Designation:Director Finance, Forest, Ecology & Environment Department

Department/placeof posting:Civil Secretariate, J&K

MobileNo:8492023172

EmailID:rsbali6@gmail.com

HomeDistrict:Baramulla

Datesof visit:1st& 2nd November 2022

## LocationaldetailsofPanchayat:(tobepre-filled,informationtobetakenfromtheprevious phasesbooklets/summarizedexcelsheetuploadedonjkpanchayat.in/b2v4.php)(tobevali- datedbythevisitingofficerandmissingdetailstobefilled)

NameofthePanchayat:CHANDOOSA-A

LocalGovernmentDirectory(LGD)codeof  thePanchayat:242435

Nameof CDBlock:Baramulla

NameofTehsil:Wagoora

Nameof	District:Baramulla

## PanchayatProfile:

No.ofrevenuevillagesinthePanchayat:1Chandoosa

No.ofhamletsinthePanchayat:2

No.ofhouseholdsinthePanchayat:620

Population(approx)of thePanchayat:3884

# Part-II:

(TobefilledupbytheVisitingOfficerduringhis/hertwodayvisittothePanchayat.AllFieldshavetobe filledbytheVisitingOfficerbeforethebookletishandedovertotheDC

## FrontlineOfficers/OfficialswhowereassignedtothePanchayatfortheprogramme:

| Department | Name | Designation |
| --- | --- | --- |
| Rural Development & REW | N.P Singh & Sajad Ahmad | AE & VLW |
| Agriculture | Muzamil Fayaz | JAED |
| Animal Husbandry | Surinder Singh | Sr. Veterinary Assistant |
| Finance | Mohammad Akbar | Treasury Officer |
| Geology & Mining | Ghulam Mohammad Magray | Class IV |
| Social Forestry | Arshad Ahmad Lala | DFO |
| Fisheries | Javid Ahmad Bhat | Fisheries Guard |
| Sheep Husbandry | Ghulam Hassan Dar | Block Supervisor |
| J&K Bank | Ishtiyaq Ahmad Malla | Incharge Advance |
| Forest Development Corporation | Sonaullah | Forester |
| PHE | Imtiyaz Ahmad | JE |
| PDD | Anzar Altamash | JE |
| R&B | Imtiyaz Ahmad | JE |
| ICDS | Suriya | Supervisor |
| Social Welfare | Majib U Nisa | Field Social Worker |
| Health | Dr. Zahoor | Medical Officer |
| Youth Supports &Services | Naseer Ahmad Bhat | PET |
| Horticulture | Tariq Ahmad Khan | I/C HDO |
| Revenue | Riyaz Ahmad Bhat | Patwari |
| Handicrafts | Rifat Ara | SCI |
| Education | Harmeet Kour | ZEO |
| Forest Territorial | Pervaiz Ahmad | DFO |
| Soil & Water Conservation | Arshad Ali Qadri | District Soil & water Conservation Officer |
| Wild Life | Mohammad Ayoub | Forester |
| Khidmat Centre (CSC) | Bilal Ahmad Wani | VLE |

Detailsofabsentemployeesvis-à-vislistfurnishedbytheDCoffice:

| Department | Name | Designation |
| --- | --- | --- |
| Seri Culture | Mohammad Sadiq |  |
| Co-Operative | Shoib Ahmad |  |
| PMGSY |  |  |
| FCS&CA | Saif Ud Din |  |
| Handloom | Mohamamd Ismail |  |
| NRLM |  |  |
| Fire & Emergency |  |  |

# DAY1-ACTIVITIES

## AGENDA1:PANCHAYATASSETREGISTER

Infrastructure:

  - PanchayatGharInfrastructure

    - Govtbuilding/private	Govt  Building

    - New/needingrepairs	Need Repairing

  - Furniture(Y/N)	Y

  - Computer/printer(Y/N)	Y

  - Internet(Y/N)	N

  - Telephone(Y/N)	N

  - Toilet(CSC/partofpanchayatghar)(Y/N)	N/ Needs in the shape of mini secretariate

  - Water(Y/N)	Y

  - Electricity(Y/N)	N

  - Bankbranch(Y/N)	Y

  - CSC(Y/N)	Y

  - Patwarkhana(Y/N)	Y

  - Villagehaat(Y/N)	N

  - Playground(Y/N)	N

  - School-

    - Kindergarten(Y/N)	N b.Primary/Middle(Y/N)		Y (2 No’s/4 Nos)

c.	Secondary(Y/N)	Y (1 No)

d. College (Y/N)		N e.University(Y/N)	N

  - AnganwadiCentre(Y/N)	Y (11 Nos)

    - (govt/private)	Private b.Totalchildrenenrolled		251

- AmritSarovars–details,location,condition	Nill

- Governmentoffices-details,whetherfunctionalornot	8 All functional

- Rationshop(Y/N)	Y

- Placesoftourismimportance–names,littledetailsonhistorical/culturalimportance	Nill

- Villageheritagesites/treks-names,littledetailson historical/culturalimportance	Nill

- VLWOffice (Y/N)	Y

- PrimaryHealthcareCentre(Y/N),	Y (SDH)

- ListofIncompleteBuildings-names,yearofconstruction	Hr Sec School Chandoosa Year 2005, Govt Girls Middle School Year 2002, Boys Middle School Faqirbagh Year 2003

- ListofUnderutilizedBuildings-names NILL

# DAY1-ACTIVITIES

AGENDA2: DIFFERENTINSTITUTIONS/INFRASTRUCTUREPROJECTSTOBEVISITED

| AMRITSAROVARS | Visit,verify | COMMENTS |
| --- | --- | --- |
| KhidmatCentres | Create/Generateawarenesson225schemes particularlyG2CschemsAapkiZaminAapkiNigrani, Beams,Janbhagidari,DigitalJ&K | Visited Khidmat Centre & working on the schemes mentioned therein further I recomand for Creation of AADHAR Centre at Khidmat Centre to be authorized for updating & prepration of Fresh AADHAR Cards to facilitate round about population of 10000 |
| JKB/PSBcounters/outlets | a)Statusofcounter b)Numberofvisitors | JKB Counter Good visiters aprox 900 per day |
| Incompletebuildings/pro- jects | Verify whetheridentificationandredistribution done | Visited & Verified |
| PDS | Visit,evaluate,onlinestatus | Visited/Yes |
| PHC | Visit-evaluate,statusofstaff,equipmentand quality | Visits Very poor quality of equipments |
| Youthclubs | Meet,interact,seeksuggestions | Yes/Need of Playground & Indoor Stadium, however boys & girls have gifted the state with gold siliver &bronz Medal |
| SHG | Meet,identifyproblems,seeksuggestions | Not reported |
| PMAY | Inspect,Inaugurate | Visited/Under Construction total 12 Nos |
| Myschool,mypride progress;schools-water, toilets,staff | Visit,checkforwater,electricity,sanitation,meet studentsandstaff | Visited/Poor facilities of water electricity and sanitization |
| SwachhSBM | Evaluate | 95% |
| Panchayatplayground, Sportskitsdistribution Villagegames | Ensure,verify.Participateinatleastonegamein theplayground | No playground is available however participated in one game Vollyball, also uploaded snap on DCGAD group/ Sports kits also distributed/SQAYT Martial Art (Creation of Kashmir |

| 4 |  |  |
| --- | --- | --- |
| HarGaonHariyali, Planta- tiondrive | Evaluatestatus,feedback | Yes & 97% progress |
| Villageculturalevent Dangal/Haat/Mela | Participatein;ensurethatitisheld | Yes |
| Exhibitionofschemes | Ensurethateverydepartmentparticipatesand thatitcontinuesfortheentiredurationofB2V | Yes Agriculture & Horticulture |
| JalJeewanMission verifica- tion- WSS/JSD Electricitysupply | Verify | 60% |

# DAY1-ACTIVITIES

AGENDA3:SATURATEJANBHIYAN DELIVERABLESANDRECORDDEFICIENCIESIFANY(INSERTDELI VERABLESLISTHEREASPERGADFORMAT

4

DAY1-ACTIVITIES

## AGENDA4:

SELFEMPLOYMENTACTIVITIES

EnsureSelf-employmentactivities foryouth,distributeemploymentlettersforpeopleselectedunder varioussocialschemes(15ISTHETARGETPERPANCHAYAT)

Numberofcasesindifferentcategoriessanctioned: 2 Detailsofthebanksanctioningit:		J&K Bank Chandoosa Totalamountinvolved:	10.00 Lakhs

# DAY1ACTIVITIES

## AGENDA5

Intheevening,holdinformalmeetings withseniorcitizens,govtemployees,retdemployees,youthclub andothercitizenswhoareenrolledoncollege/universityandhavediscussiononGandhiKatha,Nasha MuktAbhiyan,corruptionfreegovernance,doublingfarmersincomeandrecordtheproceedings

## DAY2

a.	NoofIndividualCompostPitsconstructed		NILL b.NoofIndividualSoakPitsconstructed	98

- No.ofBiodiversitymanagementcommitteemeetingsheld:	4

- IsthenameofSarpanchdisplayedoncitizeninformationboardsofallRD&PRschemes:Yes/No	Yes

- AreSarpanchsbeinginvolvedinstart/inaugurationofactivities:Yes/No	Yes

- WhethersubjectshavebeenassignedbytheSarpanchtothePanchs:Yes/No	Yes

- Whethergrievancesredressalboxisinstalled:Yes/No	No

- NoofgrievancesreceivedpertainingtoPanchayatlevel:	NILL

- NoofgrievancesdisposedofatPanchayatlevel:	NILL

- WhethertheSarpanch/PanchayatSecretaryhavedigitalsignatures:Yes/No	Yes

- WhetherallMGNREGA/14thFCpayments arebeingmadebySarpanchthrough DigitalSignature Certificate(DSC):Yes/No	Yes

# HUMAN RESOURCEAVAILABLEATTHEPANCHAYAT LEVEL:

| SRNO. | DEPARTMENTWISESTAFF | NUMBERS |  | NAMES |
| --- | --- | --- | --- | --- |
|  |  | SANCTIONED | ACTUAL | Fayaz Ahmad Showkat Ahmad Sajads Ahmad Showkat Ahmad Irfan Ahmad |
|  | Ruraldevelopmentdepartment: | 1 1 1 1 1 | 1 1 1 1 1 |  |
|  | BDO |  |  |  |
|  | JE |  |  |  |
|  | VLW |  |  |  |
|  | GRS |  |  |  |
|  | TA |  |  |  |
|  | SCHOOLEDUCATION: |  |  |  |
|  | TEACHER | Hr Sec 31, | Hr Sec 31, |  |
|  |  | Middle & | Middle & |  |
|  |  | Primary 23 | Primary 23 |  |
|  | HEADMASTER/Principal ANYOTHER | NILL/1 9 | NILL/1 9 |  |
|  | JAL JEEVAN: | 6 | 6 |  |
|  | PDD: LINEMAN JE ANYOTHER | 2 1 1 | 2 1 1 |  |
|  | FOOD&CIVILSUPPLIES | 2 | 2 |  |
|  | AGRICULTURE&ANIMALHUS- | 3 | 3 |  |
|  | BANDARY |  |  |  |

| 4 |  |  |  |  |
| --- | --- | --- | --- | --- |
|  | SOCIALWELFARE ICDS workers/Helpers | NILL 11/11 | NILL 11/11 |  |
|  | HEALTH: ASHA ANM AYUSHDOCTOR ALLOPATHICDOCTOR | 7 4 0 15 | 7 4 0 15 |  |
|  | ANYOTHERDEPARTMENT Forest Department Revenue | 8+8 1+1 | 8+8 1+1 |  |

DAY2-ACTIVITIES

## AGENDANO.1

DiscussionontheandassesstheprogressofdifferentschemesrelatingtothelocalizedSDGsprior- itizedforthatvillageaspertheresolutionpassedbythatGramPanchayaton21stApril22,onNational PanchayatiRajDay(Copyoftheresolutiontobetakenfromwww.jkpanchayat.inportalunderthelinkof GramSwarajMonth)

  - SDGs AGREED FORTHATVILLAGE,TOBEIMPLEMENTED BYMARCH2024: Yes

  - STATUSOFWORKSUNDERTHEFOLLOWINGSCHEMES:	Plan Submitted

## Cleanandgreenvillage

- InitiativestakenbythePanchayatformanagingSolidandLiquidWastePlan Submitted

- InitiativestakenbythePanchayatforusinggreensourcesoffuellikesolar,biogasPlan Submitted

- Hasmappingoflanduse,waterbodies,forest,slopes,wetlands,degradedforestwithintheGram Panchayatbeendone?Yes/No.IfNo,reason,thereofYes

- HastheClimateResiliencePlanbeendevelopedfortheGP?Yes/No	Yes

- StepstakenbytheGramSabhaabouttheclimatechangemitigationfactorslikereducingenergy consumption,usageoffossilfuels,plastics,non-renewablebuildingmaterialsandalsotopromote measureslikeplantingoftrees,conservingforests,usageofgoodagriculturalpracticeslikedrip irrigation,waterconservationmeasuresandconservationofwetlands.	Forest Department has taken innitative

- Whetherschoolshavestartedsegregatingwaste No

- Whetherschoolshavetheirowncompost/soakagepitsforsolid/liquidwastemanagement Yes only at Hr Sec School Chandoosa

## Healthyvillage

- Aremeetings relatedtoVillageHealthandSanitationCommitteebeingheldregularly? Yes at the time of COVID

- DoalltheeligibleindividualsbeenprovidedtheGoldenCard?	80%

- ArealltheChildrenbeingimmunizedaspertheSchedulerecommendedbyGovt.ofIndia?	YES

- ArealltheeligibleindividualsbeenvaccinatedagainstCOVID-19?	YES

- DoesGramPanchayatensurethatallpregnantwomenaregettingnecessaryprenatalcheckups?	YES

- WhetherallthedeliverieswereInstitutionalizedorconductedbytrainedMidwives?	YES

## Watersufficientvillage

- DoalltheIHHsintheGramPanchayathavewaterpipelineconnections?	60%

- WhetherGramPanchayathastakenstepsforgreywatermanagement.IfYespleasespecif.	Innitated Process

- DoalltheIHHsintheGramPanchayathavetoilets?	YES

- ArealltheIHHstoiletsfunctionalornot?	YES

- DoalltheSchools/Anganwadicentershavea toiletfacilityornot?	YES

- Areallthetoiletsintheschools/Aaganwadifunctionalornot?	YES

- WhetherGramPachachayatBhawanhasseparate toiletsforwomenornot? NO

## ChildFriendlyvillage

- Doallthechildrenundertheageof0-6yearsbeenenrolledintheAnganwadicentersforpre- schooling?Yes/NO	YES

- HowmanyBalSabha’swereorganizedintheGramPanchayat 1

- WhethertheissuesraisedbyBalSabhaareaddressedduringtheGramSabha. Yes/NO Indoor Play ground and saperate toilet facilities for males & females recomanded

- WhetherGramPanchayatistrackingthedatarelatedtodropoutchildrenandchildrenwithirregular attendance?Yes/NO.	YES

- DoalltheschoolsundertheGramPanchayathaveseparate toiletsforgirlsandboys?Yes/No NO

## Villagewithgoodgovernance

- IsCSClocatedintheGramPanchayatBhawanornot?	NO

- IsthelistofbeneficiariesrelatedtotheSchemes/ProgramsdisplayedontheGrampanchayatwallor not? YES

- DoestheGramPanchayathasitsbuildingornot?	YES

- IstheGramPanchayatofficefunctionalornot?	YES

- Aretheactivities approved undertheHalqaPanchayatDevelopmentPlandisplayedontheGram Panchayatwallornot?

YES

- IsSocialAuditofearlierSchemes/Programscarriedoutornot?	YES

## Povertyfreeandenhancedlivelihoodvillage

- HasGramPanchayatdevelopedanycriteria fortheidentificationofthepoor?Yes/Noifyesspecify YES

- ii)   HavealltheeligiblehouseholdsregisteredinPDSornot?	YES

- HasGramPanchayatprovidedspaceforSelf-helpGroupsinPanchyatGharforholdingmeetings or not? NO

- HavealltheeligiblehouseholdsbeenregisteredforPensionornot?	NO

- HasGramPanchayatfacilitatedYouthforSkillEnhancementCoursesandPlacement?	NO

- HasJobCardsbeendistributedtoalltheeligibleindividualsunderMGNREGA?	YES

- HasGramPanchayatfacilitatedSHGsforBankAccountLinkages?	YES

## Sociallysecuredvillage

- WhetherGramPanchayatismaintainingdatarelatedtoDifferentlyAbledPeople?	YES

- IsGramPanchayatOffice DisabledFriendlyornot?	NO

- Areprovisionsfora separate BudgetundertheResourceEnvelopeforWomenandChildrenmadeor not? NO

- DoalltheSchools intheGramPanchayathavefacilitiesforDifferentlyAbledChildrenliketoilets, barrier- freeaccess,etc.,ornot?	NO

- Arealltheeligibleindividualsaregettingpensions,likeoldagepension,widowpension,etc? 45%

- ArealltheeligiblehouseholdsgettingbenefitsfromIAYornot? YES

## EngenderedDevelopmentinVillage

- HowmanyMahilaSabha’swereorganizedintheGramPanchayat 1

- WhetherSHGsfederationshavebeenprovidedspaceformeetings inthePanchayatBhawan(Yes/ No) No

- WhetherGPshavetakenstepsforincreasingwomen’sparticipationinGramSabha(Yes/No)  YES

- NumberofwomenbeneficiariesheadedhouseholdscoveredunderPDS system 6%

- Numberofbeneficiaries(outoftotaleligiblepopulation)receivingsocialprotectionbenefitsunder PradhanMantriMatritvaVandanaYojana NILL

- Self-sufficientinfrastructureinthevillage

- WhetherGPhasa CommunityHallwithaccesstoelectricity,furniture,watersupply, toilet No

- WhethertheDisastermanagementplanisavailableattheGPLevel(Yes/No)  NO

- Whetherchild-friendlyparkwithrequiredfacilitiesisavailableinGP(Yes/No) No

- WhethertheGPhaseasyaccesstoGodownforstorage(Yes/No) Yes

- Whetherstreetlightsareprovidedinpublicplacesforensuringsafety(Yes/No) No

# DAY2ACTIVITIES

## AGENDANO.2

SensitizevillageresidentsaboutmyScheme”portal(myscheme.in)whichincludesinformationaboutall theschemesbeingrunbyCentral/State/UT govtacrossthecountry (SchemeMaterialavailablefromhttps://jkpanchayat.in/b2v4.php)

Yes Acknowleged

# DAY2ACTIVITIES

## AGENDANO.3

HoldmeetingoftheBiodiversityManagementCommitteestodeliberateonissues	pertainingtoconserva- tionofbiodiversityandsustainableutilizationofbiologicalresources.HeshouldcheckPeopleBiodiversity register(PBR)ofthatpanchayatandreviewifBiodiversityManagementCommittee		constitutedforthat panchayatis	holdingminimum4meetings	inayearandmeeting	onceinevery3months	(RoleofBMC availableathttps://jkpanchayat.in/b2v4.php)

COMMITTEEMEMBERS	13

PRESENT	6

BIODIVERSITYREGISTERPHOTOS	Yes

PAST  4MEETINGDETAILS-DATES,MINUTESPHOTOS

# DAY2ACTIVITIES

## AGENDA4

Visitingofficershallalsoplanandconductpanchayatlevelconvergencemeeting ofalldepartmentsand prepareVillagedevelopmentplanforvillage,inconsultancywithGrampanchayat,discussitingram sabhaandgetitapproved.

(GPDPformatavailableonhttps://jkpanchayat.in/b2v4.php)

InadditionGPDPplanshallalsoinclude: Touristplaceswhichneedtobedeveloped Specificproductwhichneedstobedeveloped Tourism-homestays

20candidatesfortrainingunderHimayatschemealongwithtradeinwhich trainingistobegiven

# DAY2ACTIVITIES

## AGENDA5

Ensuresaturationoffollowingschemesandgivestatus:

| NAMEOFTHESCHEME | TOTALELIGIBLE BENEFICIARIESIN THE VILLAGE | TOTALBENEFICIARIESWHO AVAILEDTHEBENEFITSOFT HESCHEME | REASONSFOR PENDENCY |
| --- | --- | --- | --- |
| GoldenHealthCardunder AyushmanBharat | 3884 | 2330 | Number of beneficiaries have not been registered with AADHAR & Ration cards as well |
| Jananisurakshayojana |  |  |  |
| OLDAGEpension | 301 | 301 |  |
| Widowpension | 63 | 63 |  |
| Disabilitypension | 84 | 84 |  |
| Domicilecertificate | 3884 | 1942 | Citizen not applied |
| Kisancreditcard | 620 | 286 | AADHAR not UPDATED |
| PMkisanSammannidhi | 620 | 286 | AADHAR not UPDATED |

| Landpassbook | 620 | 293 | Server/Portal Problem |
| --- | --- | --- | --- |
| Registrationofvillageven- dorsonGEMportal | N/A | N/A | During B2V4 they have been acknowledged |
|  | 2 | 2 |  |
| Registrationofvillagecon- tractorsonjktendersportal |  |  |  |
|  | 2 | 2 |  |
| Registrationofvillagecon- tractorsonPWDportal |  |  |  |
| Incompletebuildings/pro- jects | 3 | 3 | Funds not provided |

# DAY2ACTIVITIES

## AGENDA6 NASHAMUKTABHIYAN

  - Whethergramsabharesolutionpassed	YES

  - Detailsofactivities conducted	Awareness Camps

  - Whetherallactivities andGSresolutionuploadedonjkpanchayats.inportal YES

  - Howmanydrugaddictsinthevillage	NIL

  - WhetherreportedtotheDeputyCommissioner	NIL

  - Howmanyregisteredforrehabilitationundergovernmentprogramme NILL

# DAY2ACTIVITIES

## AGENDA7 SOCIALAUDIT

Conductsocialauditofatleast5workseachunderfollowingschemes:

| NAMEOFTHE SCHEME | DETAILSOFTHE WORKS | YEAROFWORK APPROVAL | AMOUNT APPROVED FORTHEWORK | WHETHER WORKEXECUTED SATISFACTORILY | GEO- TAGGED PHOTOS | ANY GRIEVANCE RECORDED RELATINGTOTHAT WORK |
| --- | --- | --- | --- | --- | --- | --- |
| MGNREGA | 5 | 2021-22 | 4.00 Lakhs | Yes | Yes | No |
| PMAY | 5 | 2021-22 | 7.90 Lakhs | Yes | Yes | No |
| IHHL UNDERSBM-G | 5 | 2021-22 | 0.60 Lakhs | Yes | Yes | No |
| CSCUNDER SBMG | NIL | NIL | NIL | NIL | NIL | NIL |
| AMRIT SAROVARS | NIL | NIL | NIL | NIL | NIL | NIL |

# DAY2ACTIVITIES

## AGENDA8 MAHILASABHA

Totalwomeninthevillageabovetheageof18	850

Totalattended	30

Proceedings: Discussed regarding health issues awareness of schemes with respect to education self employment generation

(Plinsertpointerstobediscussedthere–referpalliproceedings)

# DAY2ACTIVITIES

## AGENDA9 BALSABHA

Holda balsabhaandrecordproceedings

Totalchildreninthevillageabovetheageof 680Totalattended	300

Proceedings: Discussed about the games, environment, SBM, etc

(Plinsertpointerstobediscussedthere–referpalliproceedings)

# DAY2ACTIVITIES

AGENDA10 INAUGURATIONS

| SR NO. | ASSETS/ACTIVITIES INAUGRATED | STATUSOFTHEASSET/AC- TIVITIES(NUMBER,OTHER DETAILS) | GEO-TAGGED PHOTOS |
| --- | --- | --- | --- |
|  | VILLAGEHAATunderJKSRLM (SUN- DAYMARKET) | NIL | NIL |
|  | PMAYhousesifanyreadyforinaugra- tion | NIL | NIL |
|  | Swachhgramprojects-segregation shedsetc | NIL | NIL |
|  | Amritsarovars | NIL | NIL |
|  | Sportskits | Volleyball Set, Cricket Set | YES |
|  | Villageculturalevents | SQAYT Martial Art | YES |
|  | JJMassets/projects | NIL | NIL |
|  | Anyothertobeidentifiedatdistrict level | NIL | NIL |

# FOLLOWUPOF(B2V1,B2V2&B2V3):

(Prefilledexcelsheet tobetakenfromdistrictlevel/andalsotobedownloaded fromwww.jkpanchayat.in)

| S.NO. | Particulars | Actiontaken | Remarks# |
| --- | --- | --- | --- |
| I. UrgentPublicRequirements/Demands-B2V1 |  |  |  |
| 1 | Drinking Water | NIL | Known to concerned department |
| 2 | PMAY/Land acquition | NIL | Known to concerned department |
| 3 | Degree College for Panchayat | NIL | Known to concerned department |
| 4 | Black Top of Road | Work Done | Work Done |
| 5 | Tata Sumo Stand Registration | NIL | NIL |
| 6 | Ambulance for CHC Chandoosa | Provided | Provided |
| 7 | ICDS Nutrition | Improved | Improved |
| II. UrgentPublicRequirements/Demands-B2V2 |  |  |  |
| 1 | Upgradation of Filtration Plant & Reservoir | Under Progress |  |
| 2 | BSNL Exchange | NIL |  |
| 3 | Land Aquistion for hospital | NIL |  |
| 4 | Widenning of Baramulla Punch Road | Completed |  |
| 5 | ECG X Ray Plant | Yes |  |
| 6 | Creation of Block | NIL |  |
| 7 | /Creation of Tehsil | NIL |  |
| S.NO. | Particulars | Actiontaken | Remarks# |
| III. MajorProblems–B2V1 |  |  |  |
| 1 | Forest & Estate Land Encroachment | NIL | Known to Department |
| 2 BACKTOVILLAGEPHASE- | Land Sliding IV (15THOCTTO3RDNOV) | Some Areas have been protection walls and cratings ¦ 25 |  |

4

3

Shortage of Electricity

NIL

Known to Department

| 4 | Material Payment pending under MG NEREGA | Pending 2016-17 | Ratio problem |
| --- | --- | --- | --- |
| 5 | Drinking Water Shortage | NIL | Known to Department |
| IV. MajorProblems-B2V2 |  |  |  |
| 1 | Upgradation of Receiving Station PDD | Partially upgraded |  |
| 2 | Hospital Problem | Not addressed yet | Known to Department |
| 3 | Drinking Water Problem | Not addressed yet | Known to Department |
| 4 |  |  |  |
| 5 |  |  |  |
| V. MajorProblems-B2V3 |  |  |  |
| 1 | Drinking Water upgradation | Not addressed yet | Known to Department |
| 2 | Drainage/graveyard & Shamshan Ghat | Not addressed yet | Known to Department |
| 3 | PR Bunds/Retaining Walls | Action Taken |  |
| 4 | Upgradation of Receiving Station | Partiallay upgraded |  |
| 5 | Health Sanitation/Transport Facility | Not addressed yet | Known to Department |
| VI. MajorComplaints-B2V1 |  |  |  |
| 1 | State/Forest Land encroachment | Not addressed yet | Known to Department |
| 2 | Health Shortage of Staff/ Sanitation/ | Not addressed yet | Known to Department |
| 3 | Drinking Water & Electricity Problem | Not addressed yet | Known to Department |
| VII. MajorComplaints-B2V2 |  |  |  |
| 1 | Non Execution problems under B2V1 in general | Not addressed yet | Known to Department |
| 2 | No covering of leakage of pipes | Not addressed yet | Known to Department |
| 3 | Land compensation to concerned | Not addressed yet | Known to Department |
| VIII. MajorComplaints-B2V3 |  |  |  |
| 1 24 ¦ | Health department sanitation/Staff/Equipment Problem | Not addressed yet BACKTOVILLAGEPHASE- | Known to Department IV (15THOCTTO3RDNOV) |

| 4 2 | Road Connectivity | Addressed |  |
| --- | --- | --- | --- |
| 3 | Transport facility SRTC | Not addressed yet | Known to Department |
|  | Upgradation of receiving station | Partially Upgraded |  |

BACKTOVILLAGEPHASE-IV (15THOCTTO3RDNOV)

| 25