4





**15TH OCTto3RD NOV,2022**

**KEYFEATURES**

• DeputyCommissionerstoleadtheinitiative

• RuraldevelopmentDepartmenttobethenodaldepartment

• PlanningDevelopment&MonitoringdepartmentandITtobethesupport departments

**ACTIONSANDTIMELINES**

|  |  |  |  |
| --- | --- | --- | --- |
| **ACTION** | **RESPONSIBILITY** | **LATESTBY** | **REMARKS** |
| **Janabhiyan** | Alldepartments | Oct15-26th | Goingon |
| **DeputationofSecttstaff/ HoDs** | GAD | Oct14 | Done |
| **DeploymentofStaffto Panchayatsandservingof ordersondeployedofficers** | DCs | Oct25 | DCswilldeployseniorlevelstaff fromthedistricts.Strictactionto betakenagainstabstentions.No exemptionstobegiven |
| **Trainingofdistricttrainors onB2V4** | RDD | Oct26 |  |
| **Trainingofvisitingofficers** | DCs | Oct27 |  |
| **FieldVisitstobecompleted by** | VisitingOfficers | Nov3 | DCstosuperviseandensurethat eachPanchayatisvisitedwithin theperiodspecified |
| **DataofB2V4tobe uploadedby** | VisitingOfficers | Nov10 | DCstosuperviseandensurethat dataofallPanchayatsisupload- edbythevisitingofficerwithin theperiodspecified |

**INSTRUCTIONSFORTHEVISITINGOFFICER(DAYWISE)**

|  |  |  |
| --- | --- | --- |
| **DATE** | **INSTRUCTIONS** | **ACTIONPOINTS** |
| **Day0** | Meetingwithdeputy commissionerandhis/her team | a. TakeprintoutsoffilledbookletsofB2V1,B2V2andB2V3from [www.jkpanchayat.in](http://www.jkpanchayat.in)  b.Alsotakeprintoutsofthesummarizedexcelsheetsofthe previousphasesfrom[www.jkpanchayat.in](http://www.jkpanchayat.in)  c. CollectATRsonissuesraisedduringprevious3phasesfromthe officeofDeputyCommissioner(Planningdeptt)  d.Takeprintsofblank 2bookletsofB2V4from[www.jkpanchayat.in](http://www.jkpanchayat.in)e.Takeplansfor2previousyearsandATRsfromtheplanningdeptt f. CompletetrainingsondifferentcomponentsofB2V4being  organizedbyrespectiveDeputyCommissioners  g.CollectListofnewworksstarted/ongoing/completedduringthe previousandcurrentFinancialyearunderthefollowingheads:  • PRIgrants  • DistrictPlan  • UTplan  • MGNREGA  • Otherschemesofotherdepartments  • Anyotherwork  h. Plans/beneficiarylists:  • MGNREGAdraftplandocumentfortheyear2022-23.  • ListofAwaas+beneficiariesalongwithIHHL Convergence  • Listofpensionbeneficiaries.  • ListofSHGs  • Listofagricultureschemebeneficiaries  i. Listsofbeneficiariesfor:  • Variouscertificates/benefitstobedistributedbythe visitingofficer.  • Anyotheractivitiesidentifiedbydifferentdepartments |

|  |  |  |  |
| --- | --- | --- | --- |
| **Day1** | Reachthevillage | 1. | Ensurethatallfrontlineworkersofdifferentdepttsarepresent. |
|  |  | 2. | Ensureexhibitionbydifferentdepts.aboutindividualbeneficiary schemes |
|  |  | 3. | InspectJKB/PSBcounters/outlets |
|  |  | 4. | Participate/ensureorganizationofsportsactivityinplayfield,talent hunt/culturalevent/youthactivity |
|  |  | 5. | GandhiKatha(suggesteddetailsuploadedonjkpanchayat.in) |
|  |  | 6. | Visitatleast2amritsarovarsandgetitsgeotaggedphotos |
|  |  | 7. | InspectKhidmat(CSC)CentresandcreateGenerateawarenesson  225schemesparticularlyG2CschemeslikeBEAMS,Janbhagidari, AapkiZaminAapkiNigrani,DigitalJ&K |
|  |  | 8. | Visitingofficershallalsoplanandconductpanchayatlevelconver- gencemeetingofalldepartments |
|  |  | 9. | CheckeffectivenessofCentrallysponsoredschemes |
|  |  | 10. | VisitandinspectallgovernmentestablishmentsincludingPHE, AWC,FPS,schools,etc |
|  |  | 11. | Attemptsaturationofdeliverableso JanAbhiyanandwherever deficienciesfound,leadadrivetoachievealldeliverables |
|  |  | 12. | Assesseffectivenessofsanitationcampaigninthepanchayat |
|  |  | 13. | Ensureselfemploymentactivitiesfor15youthperpanchayat |
|  |  | 14. | Identify20potentialcandidatesperpanchayatforHIMAYATtraining alongwiththetradeonwhichtheywanttraining |
|  |  | 15. | Whereverpossible,distributeemploymentlettersforpeopleselect- edundervariousgovernmentemployments |
|  |  | 16. | Intheevening,holdnormalmeetingwith seniorcitizens,govtem- ployeesincludingretiredemployees,exservicemen,youthclub,and any citizens ofthevillagewhoareenrolledincollege/university |
|  |  | 17. | OpendiscussiononNashaMuktAbhiyan |

Day2 Haveameetingwithall stakeholders-depttofficials andpanchayatmembers

1. Discussionontheandassesstheprogressofdifferentschemesrelating tothelocalizedSDGsprioritizedforthatvillageaspertheresolution passedby thatGramPanchayaton21st April22,onNationalPanchayti RajDay.

2. Sensitizevillage residentsaboutmyScheme”portal(myscheme.in) whichincludesinformationaboutalltheschemesbeingrunbyCen- tral/State/UTgovtacrossthecountry

3. Hold meeting of theBiodiversityManagementCommitteestodeliber- ateonissuespertaining toconservation of biodiversityandsustaina- bleutilizationof biologicalresources.

4. PrepareVillagedevelopmentplan,inconsultancywithGrampanchayat, discussitingramsabhaandgetitapproved.

5. Ensure saturationofsoilhealthcardandgoldenhealthcardunderGold- enHealthCardunderAyushmanBharat,

6. Ensuresaturation of OldAge PensionScheme

7. EnsureDomicileSaturation.

8. EnsureKCCSaturation

9. Ensure saturationoflandpassbooks

10. Ensureregistrationofvillagevendorsneededforanyscheme,onGEM

portal

11. Ensurepanchayatcontractors registration

12. EncouragePanchayatmembers forimportanceofplantationdrivein

PanchayatunderHarGaonHariyali

13. Ensure paintingondigitalJ&Kinpanchayatghars

14. Ensure paintingonpanchayatactivitesandCSSinpanchayatghars

15. Thevisiting officeshallchecknoof kindergarten andplayfields present inthepanchayat for kidsandstudents,iftheinfrastructure present inthesearegoodenough.

16. Holdmeeting withpanchayatmembers todiscussaboutcorruption menaceandstepsrequiredtomakeJ&Kcorruptionfree

17. Obtaina candidassessmentaboutperformanceofvariousdeptts in- cludingfairfeedbackaboutdiscrepanciesinfunctioning

18. Check thestatusof NashaMuktAbhiyanandreporting of drugad- dictstoDeputyCommissioner.

19. IdentifyTouristDestinations,Circuits,ThemeTreks,IdentifyHomestays, providesupportfortourismactivities throughVillageCooperative

20. OrganizeTalentHuntatPanchayatLevel

21. Conductsocialauditofatleast5worksunderfollowingschemes:

a. MGNREGA

b.PMAY

c. IHHLtoiletsandpayments d.CSCs

e.AMRITSAROVARS

22. Holda mahilasabha anda balsabhaandrecordproceedingsinthefor- matgiven

23. InauguratevillagehaatunderJKSRLM

24. Checkifyouthclubsareformedinthepanchayatandwhatactivities theyareengagedin

25. Organizea villagelevelculturaleventtoengagepanchayatmembers

26. SensitizeGPaboutE-kitabkoshaninitiativeofJ&KGovtforempowering youthsthrough onlinedigitalliteracy

**GENERALINSTRUCTIONS**

1. Thevisitingofficershallrefrainhimself/herselfgivingorofferinganycommitmentonbehalfofthe governmentandshalladoptanunbiasedattitudeinreportingissues.As faraspossible,his/her observation shouldbebasedona fairandanalytical viewemergingfromhis/herinteractioninthe village.

2. Heisgoingtothevillageasplanningofficer,notforsanctioninganyworksorformakinganycom- mitments.

3. Whilepreparingvillagedevelopmentplan,hehastoensurethat,demandsareprioritizedandre- flectedunderavailableschemes,wherevernecessarythelargerworksaretobereferredtoadminis- trativedepttunderCSS/UTplansunderintimationtoDCsandrestoftheworkstoDCsforreflecting itunderdistrict/CSS plans

4. His workshallbehardcoreplanningandauditandisnota PRexercise.

5. EveryDeputyCommissionerhastoensurethatatleastoneRDDofficial(ideallyPanchayatSecre- tary)ispresent ineverypanchayatwithrelevantpanchayatrecords,toensureconductofallactivi- tiesasplanned.Panchayatwiseorderneedstobeissuedinadvance.

6. Visitingofficershouldideallycarryhis/herlaptoptocompletethereportsatthepanchayatlevel itselfanduploadthefinalreport,duly signedbothbythesarpanchandbythevisitingofficeron [www.jkpanchayat.in](http://www.jkpanchayat.in)portal,beforetheyleavepanchayat.

7. Focus ofvisitareyouth,skills,self-employment,nashamukt,bhrashtracharmukt,Rozgaryukt J&K, besidestocarryforwardtheactivities duringJanAbhiyanandsaturatethem.

8. Inadditionattentionmaybegiventothefollowingareas a. MakefulluseofCentrallySponsoredSchemes

b.Saturationofindividualbeneficiaryschemes c. Self-employmentschemes

d.Banklinkedschemes-includingdepartmentalsubsidyschemes e.Empowermentandtransparencythrough digitalinitiatives

f. Effectivenessofgrassrootsmachinery–

i. Patwari,VLWpresent andavailable

ii. AvailablefundsutilizedinpublicinterestandasperGramSabharesolutions iii. Fairness ingovernance

iv. CSS/Individual beneficiaryschemesetc v. BrashtacharMuktJ&K

vi. BhaiMuktJ&K

vii. NashaMuktJ&K

9. ThePRImembers (Sarpanchs,Panchs,BDCChairperson)shallbeattheforefrontofallactivities and givendueimportanceandtheapproach shouldbetostrengthenthemandmakethemfeelem- powered.He/sheshallensurethattheBDCchairpersonandSarpanch/Panch arepresent atthetime ofinaugurationandceremonies.

10. Visitingofficershallnotleavethedistrictwithoutuploadingthereport,duly signedonthe**www. jkpanchayat.in**portal.EveryDeputyCommissionerhastoensurethat.

**A) DetailsofReportingOfficer:**

Name: zafar iqbal naik

Designation:principal

Department/placeof posting:govt high secondary fateh pur

MobileNo:7889346610 ,9858024166

EmailID:iqbalnaik94898gmail.com

HomeDistrict:RAJOURI

Datesof visit:01-11-2022

**B) LocationaldetailsofPanchayat:(tobepre-filled,informationtobetakenfromtheprevious phasesbooklets/summarizedexcelsheetuploadedonjkpanchayat.in/b2v4.php)(tobevali- datedbythevisitingofficerandmissingdetailstobefilled)**

NameofthePanchayat:SASALKOTE

LocalGovernmentDirectory(LGD)codeof thePanchayat:

Nameof CDBlock:DOONGI

NameofTehsil:RAJOURI

Nameof District:RAJOURI

**C) PanchayatProfile:**

No.ofrevenuevillagesinthePanchayat:df 02

No.ofhamletsinthePanchayat: 08

No.ofhouseholdsinthePanchayat: APPROX 700

Population(approx)of thePanchayat: 1872

**Part-II:**

(TobefilledupbytheVisitingOfficerduringhis/hertwodayvisittothePanchayat.AllFieldshavetobe

filledbytheVisitingOfficerbeforethebookletishandedovertotheDC

**FrontlineOfficers/OfficialswhowereassignedtothePanchayatfortheprogramme:**

|  |  |  |
| --- | --- | --- |
| Department | Name | Designation |
| RDD | SANJEET SHARMA | SECTARY PANCHAYAT |
| RDD | MOHD IQBAL | GRS |
| SOCIAL FOREST | SATISH , SUBASH | J.R MALI |
| ICDS | BHOLI DEVI | AWW |
| CSE VLE | KARAN KUMAR | VLE |
| PWD | RAKESH KUMAR | JE |
| EDUCATION | ROSHAN LAL | ZEO |
| PDD | SANJAY KUMAR | LINE MAN |
| ICDS | SONU SHARMA | AWW |
| REVENUE | IMRAN MALIK | PATWARI |
| CAPD | RAJESH KUMAR | SALES MAN |
| FOREST | MOHD ISAQ | FOREST GUARD |
| RDD | SANJAY CHIB | ACCOUNT ASSISTANT |

**Detailsofabsentemployeesvis-à-vislistfurnishedbytheDCoffice:**

|  |  |  |
| --- | --- | --- |
| Department | Name | Designation |
| PHE | VIJAY KUMAR | SUPERVISOR |
|  |  |  |
|  |  |  |
|  |  |  |
|  |  |  |
|  |  |  |
|  |  |  |
|  |  |  |
|  |  |  |
|  |  |  |
|  |  |  |
|  |  |  |
|  |  |  |
|  |  |  |
|  |  |  |

**DAY1-ACTIVITIES**

**AGENDA1:PANCHAYATASSETREGISTER**

**Infrastructure:**

1. PanchayatGharInfrastructure a. Govtbuilding/private GOVT BUILDING

b. New/needingrepairs NEED REPAIR

2. Furniture(Y/N) YES

3. Computer/printer(Y/N) YES

4. Internet(Y/N) NO

5. Telephone(Y/N) NO

6. Toilet(CSC/partofpanchayatghar)(Y/N) YES

7. Water(Y/N) NO

8. Electricity(Y/N) YES

9. Bankbranch(Y/N) NO

10. CSC(Y/N) YES

11. Patwarkhana(Y /N) YES

12. Villagehaat(Y/N) YES

13. Playground(Y/N) YES

14. School-

a. Kindergarten(Y/N) NO

b.Primary(Y/N) YES

c. Secondary(Y/N) YES

d. College (Y/N) YES

e.University(Y/N) NO

15. AnganwadiCentre(Y/N) YES

a. (govt/private) GOVT

b.Totalchildrenenrolled 95

15. AmritSarovars–details,location,condition NO

16. Governmentoffices-details,whetherfunctionalornot FUNCTIONAL

17. Rationshop(Y/N) YES

18. Placesoftourismimportance–names,littledetailsonhistorical/culturalimportance MEHARI W.NO 5

19. Villageheritagesites/treks-names,littledetailson historical/culturalimportance KALIKA MATA MANDIR,RAVI DASS MANDIR

20. VLWOffice (Y/N) YES

21. PrimaryHealthcareCentre(Y/N), NO

22. ListofIncompleteBuildings-names,yearofconstruction DAKBANGLOW DOONGI SINCE 2012

23. ListofUnderutilizedBuildings-names

30000 GALLON WATER TANK AT SASALKOTE MIDDLE SCHOOL

**DAY1-ACTIVITIES**

**AGENDA2:**

**DIFFERENTINSTITUTIONS/INFRASTRUCTUREPROJECTSTOBEVISITED**

|  |  |  |
| --- | --- | --- |
| **AMRITSAROVARS** | **Visit,verify** | **COMMENTS** |
| KhidmatCentres | Create/Generateawarenesson225schemes particularlyG2CschemsAapkiZaminAapkiNigrani, Beams,Janbhagidari,DigitalJ&K | VISITED AND VERIFIED |
| JKB/PSBcounters/outlets | a)Statusofcounter b)Numberofvisitors | THERE IS NO BRANCH |
| Incompletebuildings/pro- jects | Verify whetheridentificationandredistribution done | DAKBANGLOW SASALKOTE |
| PDS | Visit,evaluate,onlinestatus | VISITED AND FOUND FUNCTIONAL |
| PHC | Visit-evaluate,statusofstaff,equipmentand quality |  |
| Youthclubs | Meet,interact,seeksuggestions | ---- |
| SHG | Meet,identifyproblems,seeksuggestions | NOT CREATED YET |
| PMAY | Inspect,Inaugurate | YES INSPECTED W.NO 7 |
| Myschool,mypride progress;schools-water, toilets,staff | Visit,checkforwater,electricity,sanitation,meet studentsandstaff | YES VISITED MIDDLE SCHOOL SASALKOTE |
| SwachhSBM | Evaluate | YES |
| Panchayatplayground, Sportskitsdistribution Villagegames | Ensure,verify.Participateinatleastonegamein theplayground | NOT SUPPLIED YET, WATCHED VOLLYBALL MATCH |
| HarGaonHariyali, Planta- tiondrive | Evaluatestatus,feedback | YES BUT NOT SATISFACTORY |
| Villageculturalevent  Dangal/Haat/Mela | Participatein;ensurethatitisheld | YES |
| Exhibitionofschemes | Ensurethateverydepartmentparticipatesand thatitcontinuesfortheentiredurationofB2V | YES MOST DEPARTMENT COORPORATED |
| JalJeewanMission verifica- tion- WSS/JSD  Electricitysupply | Verify | JAL JEVAN MISSION PROGRESS IS NOT SATISFACTORYAND PDD AS PER SAROPANCH STATEMENT |

**DAY1-ACTIVITIES**

**AGENDA3:SATURATEJANBHIYAN**

**DELIVERABLESANDRECORDDEFICIENCIESIFANY(INSERTDELIVERABLESLISTHEREASPERGADFORMAT**

**DAY1-ACTIVITIES**

**AGENDA4:**

**SELFEMPLOYMENTACTIVITIES**

EnsureSelf-employmentactivities foryouth,distributeemploymentlettersforpeopleselectedunder varioussocialschemes(15ISTHETARGETPERPANCHAYAT)

**Numberofcasesindifferentcategoriessanctioned: Detailsofthebanksanctioningit:**

**Totalamountinvolved:**

**DAY1ACTIVITIES**

**AGENDA5**

Intheevening,holdinformalmeetings withseniorcitizens,govtemployees,retdemployees,youthclub andothercitizenswhoareenrolledoncollege/universityandhavediscussiononGandhiKatha,Nasha MuktAbhiyan,corruptionfreegovernance,doublingfarmersincomeandrecordtheproceedings

**DAY2**

a. NoofIndividualCompostPitsconstructed 05b.NoofIndividualSoakPitsconstructed 150

V. No.ofBiodiversitymanagementcommitteemeetingsheld:03

VI. IsthenameofSarpanchdisplayedoncitizeninformationboardsofallRD&PRschemes:Yes/No YES

VII. AreSarpanchsbeinginvolvedinstart/inaugurationofactivities:Yes/No YES

VIII. WhethersubjectshavebeenassignedbytheSarpanchtothePanchs:Yes/No YES

IX. Whethergrievancesredressalboxisinstalled:Yes/No NO

X. NoofgrievancesreceivedpertainingtoPanchayatlevel: 20XI. NoofgrievancesdisposedofatPanchayatlevel:20

XII. WhethertheSarpanch/PanchayatSecretaryhavedigitalsignatures:Yes/No YES

XIII. WhetherallMGNREGA/14thFCpayments arebeingmadebySarpanchthrough DigitalSignature

Certificate(DSC):Yes/No

YES

**HUMAN RESOURCEAVAILABLEATTHEPANCHAYAT LEVEL:**

|  |  |  |  |  |
| --- | --- | --- | --- | --- |
| **SRNO.** | **DEPARTMENTWISESTAFF** | **NUMBERS** | | **NAMES** |
|  |  | SANCTIONED | ACTUAL |  |
|  | Ruraldevelopmentdepartment: BDO  JE GRS TA | 01 | 01 | MOHD IQBAL |
|  | SCHOOLEDUCATION: TEACHER  HEADMASTER ANYOTHER | -  09  - | -  08  - |  |
|  | JAL JEEVAN: | ----- | 04 ON NEED BASSIS |  |
|  | PDD: LINEMAN JE  ANYOTHER | 01 | 01 | SANJAY KUMAR |
|  | FOOD&CIVILSUPPLIES | 01 | 01 | RAJESH KUMAR |
|  | AGRICULTURE&ANIMALHUS- BANDARY |  |  | ROMESH CHANDER |
|  | SOCIALWELFARE |  |  |  |
|  | HEALTH: ASHA ANM  AYUSHDOCTOR ALLOPATHICDOCTOR |  |  |  |
|  | ANYOTHERDEPARTMENT |  |  |  |

**DAY2-ACTIVITIES**

**AGENDANO.1**

DiscussionontheandassesstheprogressofdifferentschemesrelatingtothelocalizedSDGsprior-itizedforthatvillageaspertheresolutionpassedbythatGramPanchayaton21stApril22,onNational PanchayatiRajDay(Copyoftheresolutiontobetakenfrom[www.jkpanchayat.in](http://www.jkpanchayat.in)portalunderthelinkof GramSwarajMonth)

1. SDGs AGREED FORTHATVILLAGE,TOBEIMPLEMENTED BYMARCH2024:

2. STATUSOFWORKSUNDERTHEFOLLOWINGSCHEMES:

**1 Cleanandgreenvillage**

i.InitiativestakenbythePanchayatformanagingSolidandLiquidWaste YES COMMITTEE FORMED

ii. InitiativestakenbythePanchayatforusinggreensourcesoffuellikesolar,biogas IN PROCESS

IN PROCESS

iii. Hasmappingoflanduse,waterbodies,forest,slopes,wetlands,degradedforestwithintheGram

Panchayatbeendone?Yes/No.IfNo,reason,thereof YES

iv. HastheClimateResiliencePlanbeendevelopedfortheGP?Yes/No YES

v. StepstakenbytheGramSabhaabouttheclimatechangemitigationfactorslikereducingenergy consumption,usageoffossilfuels,plastics,non-renewablebuildingmaterialsandalsotopromote measureslikeplantingoftrees,conservingforests,usageofgoodagriculturalpracticeslikedrip irrigation,waterconservationmeasuresandconservationofwetlands. YES

vi. Whetherschoolshavestartedsegregatingwaste YES

vii. Whetherschoolshavetheirowncompost/soakagepitsforsolid/liquidwastemanagement YES

**2 Healthyvillage**

i) Aremeetings relatedtoVillageHealthandSanitationCommitteebeingheldregularly? YES

ii) DoalltheeligibleindividualsbeenprovidedtheGoldenCard? 95 PERCENT

iii) ArealltheChildrenbeingimmunizedaspertheSchedulerecommendedbyGovt.ofIndia?YES

iv) ArealltheeligibleindividualsbeenvaccinatedagainstCOVID-19?YES

v) DoesGramPanchayatensurethatallpregnantwomenaregettingnecessaryprenatalcheckups?

vi) WhetherallthedeliverieswereInstitutionalizedorconductedbytrainedMidwives?YES

**3 Watersufficientvillage**

i) DoalltheIHHsintheGramPanchayathavewaterpipelineconnections?NO

ii) WhetherGramPanchayathastakenstepsforgreywatermanagement.IfYespleasespecifyYES CONST OF SOAK PIT

iii) DoalltheIHHsintheGramPanchayathavetoilets?YES

iv) ArealltheIHHstoiletsfunctionalornot?FUNCTIONAL

v) DoalltheSchools/Anganwadicentershavea toiletfacilityornot?YES

vi) Areallthetoiletsintheschools/Aaganwadifunctionalornot?FUNCTIONAL

vii) WhetherGramPachachayatBhawanhasseparate toiletsforwomenornot?YES

**4 ChildFriendlyvillage**

i) Doallthechildrenundertheageof0-6yearsbeenenrolledintheAnganwadicentersforpre- schooling?Yes/NO YES

ii) HowmanyBalSabha’swereorganizedintheGramPanchayat-----------07--------

iii) WhethertheissuesraisedbyBalSabhaareaddressedduringtheGramSabha. Yes/NO YES

iv) WhetherGramPanchayatistrackingthedatarelatedtodropoutchildrenandchildrenwithirregular attendance?Yes/NO. YES

v) DoalltheschoolsundertheGramPanchayathaveseparate toiletsforgirlsandboys?Yes/No YES

**5 Villagewithgoodgovernance**

i) IsCSClocatedintheGramPanchayatBhawanornot? YES

ii) IsthelistofbeneficiariesrelatedtotheSchemes/ProgramsdisplayedontheGrampanchayatwallor not? YES

iii) DoestheGramPanchayathasitsbuildingornot? YES

iv) IstheGramPanchayatofficefunctionalornot? FUNCTIONAL

v) Aretheactivities approved undertheHalqaPanchayatDevelopmentPlandisplayedontheGram

Panchayatwallornot? YES

vi) IsSocialAuditofearlierSchemes/Programscarriedoutornot? YES

**6 Povertyfreeandenhancedlivelihoodvillage**

1. HasGramPanchayatdevelopedanycriteria fortheidentificationofthepoor?Yes/Noifyesspecify YES
2. ii) HavealltheeligiblehouseholdsregisteredinPDSornot?YES

iii) HasGramPanchayatprovidedspaceforSelf-helpGroupsinPanchyatGharforholdingmeetings or not? YES

iv) HavealltheeligiblehouseholdsbeenregisteredforPensionornot?YES

v) HasGramPanchayatfacilitatedYouthforSkillEnhancementCoursesandPlacement?NO

vi) HasJobCardsbeendistributedtoalltheeligibleindividualsunderMGNREGA? YES

vii) HasGramPanchayatfacilitatedSHGsforBankAccountLinkages? NO

**7 Sociallysecuredvillage**

i) WhetherGramPanchayatismaintainingdatarelatedtoDifferentlyAbledPeople? YES

ii) IsGramPanchayatOffice DisabledFriendlyornot? FRIENDLY

iii) Areprovisionsfora separate BudgetundertheResourceEnvelopeforWomenandChildrenmadeor not? NO

iv) DoalltheSchools intheGramPanchayathavefacilitiesforDifferentlyAbledChildrenliketoilets, barrier-freeaccess,etc.,ornot? YES

v) Arealltheeligibleindividualsaregettingpensions,likeoldagepension,widowpension,etc?

vi) ArealltheeligiblehouseholdsgettingbenefitsfromIAYornot?

YES

**8 EngenderedDevelopmentinVillage**

i) HowmanyMahilaSabha’swereorganizedintheGramPanchayat-----------------09--

ii) WhetherSHGsfederationshavebeenprovidedspaceformeetings inthePanchayatBhawan(Yes/ No) NO

iii) WhetherGPshavetakenstepsforincreasingwomen’sparticipationinGramSabha(Yes/No) YES

iv) NumberofwomenbeneficiariesheadedhouseholdscoveredunderPDS

system……………12…………

v) Numberofbeneficiaries(outoftotaleligiblepopulation)receivingsocialprotectionbenefitsunder

PradhanMantriMatritvaVandanaYojana……………NO…….

9 Self-sufficientinfrastructureinthevillage YES

i. WhetherGPhasa CommunityHallwithaccesstoelectricity,furniture,watersupply, toilet…………YES…………….

ii. WhethertheDisastermanagementplanisavailableattheGPLevel(Yes/No) YES

iii. Whetherchild-friendlyparkwithrequiredfacilitiesisavailableinGP(Yes/No) NO

iv. WhethertheGPhaseasyaccesstoGodownforstorage(Yes/No) NO

v. Whetherstreetlightsareprovidedinpublicplacesforensuringsafety(Yes/No) NOT SATISFIED

**DAY2ACTIVITIES**

**AGENDANO.2**

SensitizevillageresidentsaboutmyScheme”portal(myscheme.in)whichincludesinformationaboutall theschemesbeingrunbyCentral/State/UT govtacrossthecountry

*(SchemeMaterialavailablefromhttps://jkpanchayat.in/b2v4.php)*

**DAY2ACTIVITIES**

**AGENDANO.3**

HoldmeetingoftheBiodiversityManagementCommitteestodeliberateonissues pertainingtoconserva- tionofbiodiversityandsustainableutilizationofbiologicalresources.HeshouldcheckPeopleBiodiversity register(PBR)ofthatpanchayatandreviewifBiodiversityManagementCommittee constitutedforthat panchayatis holdingminimum4meetings inayearandmeeting onceinevery3months *(RoleofBMC availableathttps://jkpanchayat.in/b2v4.php)*

COMMITTEEMEMBERS PRESENT

BIODIVERSITYREGISTERPHOTOS

PAST 4MEETINGDETAILS-DATES,MINUTESPHOTOS

**DAY2ACTIVITIES**

**AGENDA4**

Visitingofficershallalsoplanandconductpanchayatlevelconvergencemeeting ofalldepartmentsand prepareVillagedevelopmentplanforvillage,inconsultancywithGrampanchayat,discussitingram sabhaandgetitapproved.

(GPDPformatavailableonhttps://jkpanchayat.in/b2v4.php)

**InadditionGPDPplanshallalsoinclude:**

 Touristplaceswhichneedtobedeveloped

 Specificproductwhichneedstobedeveloped PEANUT ORNAMENT FLOWERS

 Tourism-homestays

 20candidatesfortrainingunderHimayatschemealongwithtradeinwhich trainingistobegiven

**DAY2ACTIVITIES**

**AGENDA5**

Ensuresaturationoffollowingschemesandgivestatus:

|  |  |  |  |
| --- | --- | --- | --- |
| **NAMEOFTHESCHEME** | **TOTALELIGIBLE BENEFICIARIESIN THE VILLAGE** | **TOTALBENEFICIARIESWHO AVAILEDTHEBENEFITSOFTHESCHEME** | **REASONSFOR PENDENCY** |
| GoldenHealthCardunder  AyushmanBharat | 1872 | 1700 | UNDER PROCESS |
| Jananisurakshayojana | 05 | 05 | ------- |
| OLDAGEpension | 86 | 73 | UNDER PROCESS |
| Widowpension | 30 | 24 | ---DO---- |
| Disabilitypension | 34 | 31 | ---DO--- |
| Domicilecertificate | 1872 | 1750 | UNDER PROCESS |
| Kisancreditcard | 240 | 240 | ------- |
| PMkisansammannidhi | 297 | 297 | ----------- |

|  |  |  |  |
| --- | --- | --- | --- |
| Landpassbook | 40 | 50 | IN PROGRESS |
| Registrationofvillageven- dorsonGEMportal | NIL | NIL | --- |
| Registrationofvillagecon- tractorsonjktendersportal | 05 | ---- | ---- |
| Registrationofvillagecon- tractorsonPWDportal | 03 | ----- | ------ |
| Incompletebuildings/pro- jects | PWD DAK BANGLOW | ----- | NO FUND AVAILABLE |

**DAY2ACTIVITIES**

**AGENDA6**

**NASHAMUKTABHIYAN**

1. Whethergramsabharesolutionpassed YES

2. Detailsofactivities conducted AWARENESS CAMP IS ORGANISED

3. Whetherallactivities andGSresolutionuploadedonjkpanchayats.inportal YES

4. Howmanydrugaddictsinthevillage NIL

5. WhetherreportedtotheDeputyCommissioner --------------

6. Howmanyregisteredforrehabilitationundergovernmentprogramme

NIL

**DAY2ACTIVITIES**

**AGENDA7**

**SOCIALAUDIT**

Conductsocialauditofatleast5workseachunderfollowingschemes:

|  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- |
| NAMEOFTHE SCHEME | DETAILSOFTHE WORKS | YEAROFWORK APPROVAL | AMOUNT APPROVED  FORTHEWORK | WHETHER  WORKEXECUTED SATISFACTORILY | GEO- TAGGED PHOTOS | ANY GRIEVANCE RECORDED RELATINGTOTHAT WORK |
| MGNREGA | BAL WORKOF CULVERT | 2021-22 | 3.00 | YES | YES | NOT |
| PMAY | RATTAN KUMAR | 2020-21 | 1.30 | YES | YES | NOT |
| IHHL  UNDERSBM-G | SHAM LAL | 2020-21 | 0.12 | YES | YES | NOT |
| CSCUNDER SBMG | SHAM LAL | 2020-21 | 1.80 | YES | YES | NOT |
| AMRIT SAROVARS | ----- | ------ | ----- | --- | ----- | ------- |

**DAY2ACTIVITIES**

**AGENDA8**

**MAHILASABHA**

Totalwomeninthevillageabovetheageof18 700

Totalattended 70

Proceedings: ALL THE CENTRAL SPONSERED SCHEMED ARE DISCUSSED

*(Plinsertpointerstobediscussedthere–referpalliproceedings)*

**DAY2ACTIVITIES**

**AGENDA9**

**BALSABHA**

Holda balsabhaandrecordproceedings -----

Totalchildreninthevillageabovetheageof…..

171 Totalattended 44

Proceedings: CUOLTURAL ACTIVITIES PERFORMED

*(Plinsertpointerstobediscussedthere–referpalliproceedings)*

**DAY2ACTIVITIES**

**AGENDA10**

**INAUGURATIONS**

|  |  |  |  |
| --- | --- | --- | --- |
| **SR NO.** | **ASSETS/ACTIVITIES INAUGRATED** | **STATUSOFTHEASSET/AC- TIVITIES(NUMBER,OTHER DETAILS)** | **GEO-TAGGED PHOTOS** |
|  | VILLAGEHAATunderJKSRLM (SUN- DAYMARKET) | ---------- | ----------------- |
|  | PMAYhousesifanyreadyforinaugra- tion | YES | YES |
|  | Swachhgramprojects-segregation shedsetc | YES | ------ |
|  | Amritsarovars | ------------ | ------------------ |
|  | Sportskits | --------------- | ---------------- |
|  | Villageculturalevents | YES | YES |
|  | JJMassets/projects | UNDER PROCESS |  |
|  | Anyothertobeidentifiedatdistrict level | ----- | ------------------ |

**FOLLOWUPOF(B2V1,B2V2&B2V3):**

*(Prefilledexcelsheet tobetakenfromdistrictlevel/andalsotobedownloaded*

*from*[*www.jkpanchayat.in)*](http://www.jkpanchayat.in)

|  |  |  |  |
| --- | --- | --- | --- |
| S.NO. | Particulars | Actiontaken | Remarks# |
| I. UrgentPublicRequirements/Demands-B2V1 | | | |
| 1 ELECTRIC TRANSFORMER |  | NONE |  |
| 2 PHE CONNECTION |  | NONE |  |
| 3BORE WELL |  | NONE |  |
| 4 |  |  |  |
| 5 |  |  |  |
| 6 |  |  |  |
| 7 |  |  |  |
| II. UrgentPublicRequirements/Demands-B2V2 | | | |
| 1 SHORTAGE OF HAND PUMP |  | PARTIALY |  |
| 2COMMUNITY HALL |  | NONE |  |
| 3PHC |  | NONE |  |
| 4 |  |  |  |
| 5 |  |  |  |
| 6 |  |  |  |
| 7 |  |  |  |
| S.NO. | Particulars | Actiontaken | Remarks# |
| III. MajorProblems–B2V1 | | | |
| 1 |  |  |  |
| 2 |  |  |  |
| 3 |  |  |  |

|  |  |  |  |
| --- | --- | --- | --- |
| 4 |  |  |  |
| 5 |  |  |  |
| IV. MajorProblems-B2V2 | | | |
| 1 |  |  |  |
| 2 |  |  |  |
| 3 |  |  |  |
| 4 |  |  |  |
| 5 |  |  |  |
| V. MajorProblems-B2V3 | | | |
| 1 |  |  |  |
| 2 |  |  |  |
| 3 |  |  |  |
| 4 |  |  |  |
| 5 |  |  |  |
| VI. MajorComplaints-B2V1 | | | |
| 1PHE DEPT NOT WORKINGPROPERLY |  |  |  |
| 2PDD DEPT NOT WORKING PROPERLY |  |  |  |
| 3 |  |  |  |
| VII. MajorComplaints-B2V2 | | | |
| 1 |  |  |  |
| 2 |  |  |  |
| 3 |  |  |  |
| VIII. MajorComplaints-B2V3 | | | |
| 1PHE DEPT NOT WORKINGPROPERLY |  | NONE |  |
| 2PDD DEPT NOT WORKING PROPERLY |  | NONE |  |
| 3 |  |  |  |

**OVERALLPERCEPTIONOFFUCNTIONING OF GOVERNMENTDEPARTMENTS**

1. **BESTDEPARTMENT: RDD ,SOCIAL WELFARE,AGRICULTURE**

**2. LEASTRESPONSIVEDEPARTMENT: PHE PDD**

**GENERALASSESSMENTOFTHEVISTINGOFFICER**

|  |  |
| --- | --- |
| I | AnymajorcomplaintbroughttothenoticeoftheVisitingOfficer: PHE PDD |
| II | Major/urgentpublicdemandsthatwas/werereflectedearlierbuthavenotbeenaddressedsofar: |
| III | Overallassessmentofthevisitandsuggestions:  (Thevisitingofficertoensurethattheoverallassessmentisrecordedindetailsalongwithconcretesugges- tions) EXTRA PAGES ATTACHED |
| IV | OverallRatingofgovtfunctioningas givenbythePanchayat(Scaleof0to10) 07 |
| V | CertificatefromSarpanchthatthevisitingofficerhasstayedinthepanchayatfor2days |

**SignatureofSarpanch SignatureoftheVisitingOfficer**

**Name SH JAGDISH RAJ Name ZAFAR IQBAL**



**DepartmentofRuralDevelompentandPanchayatiRaj**

**GovernmentofJammu &Kashmir**





