4

15TH OCTto3RD NOV,2022

KEYFEATURES

•     DeputyCommissionerstoleadtheinitiative

•    RuraldevelopmentDepartmenttobethenodaldepartment

•	PlanningDevelopment&MonitoringdepartmentandITtobethesupport departments

ACTIONSANDTIMELINES

| ACTION | RESPONSIBILITY | LATESTBY | REMARKS |
| --- | --- | --- | --- |
| Janabhiyan | Alldepartments | Oct15-26th | Goingon |
| DeputationofSecttstaff/ HoDs | GAD | Oct14 | Done |
| DeploymentofStaffto Panchayatsandservingof ordersondeployedofficers | DCs | Oct25 | DCswilldeployseniorlevelstaff fromthedistricts.Strictactionto betakenagainstabstentions.No exemptionstobegiven |
| Trainingofdistricttrainors onB2V4 | RDD | Oct26 |  |
| Trainingofvisitingofficers | DCs | Oct27 |  |
| FieldVisitstobecompleted by | VisitingOfficers | Nov3 | DCstosuperviseandensurethat eachPanchayatisvisitedwithin theperiodspecified |
| DataofB2V4tobe uploadedby | VisitingOfficers | Nov10 | DCstosuperviseandensurethat dataofallPanchayatsisupload- edbythevisitingofficerwithin theperiodspecified |

INSTRUCTIONSFORTHEVISITINGOFFICER(DAYWISE)

| DATE | INSTRUCTIONS | ACTIONPOINTS |
| --- | --- | --- |
| Day0 | Meetingwithdeputy commissionerandhis/her team | a. TakeprintoutsoffilledbookletsofB2V1,B2V2andB2V3from www.jkpanchayat.in b.Alsotakeprintoutsofthesummarizedexcelsheetsofthe previousphasesfromwww.jkpanchayat.in c. CollectATRsonissuesraisedduringprevious3phasesfromthe officeofDeputyCommissioner(Planningdeptt) d.Takeprintsofblank 2bookletsofB2V4fromwww.jkpanchayat.ine.Takeplansfor2previousyearsandATRsfromtheplanningdeptt f. CompletetrainingsondifferentcomponentsofB2V4being organizedbyrespectiveDeputyCommissioners g.CollectListofnewworksstarted/ongoing/completedduringthe previousandcurrentFinancialyearunderthefollowingheads: • PRIgrants • DistrictPlan • UTplan • MGNREGA • Otherschemesofotherdepartments • Anyotherwork h. Plans/beneficiarylists: • MGNREGAdraftplandocumentfortheyear2022-23. • ListofAwaas+beneficiariesalongwithIHHL Convergence • Listofpensionbeneficiaries. • ListofSHGs • Listofagricultureschemebeneficiaries i. Listsofbeneficiariesfor: • Variouscertificates/benefitstobedistributedbythe visitingofficer. • Anyotheractivitiesidentifiedbydifferentdepartments |

| Day1 | Reachthevillage | 1. | Ensurethatallfrontlineworkersofdifferentdepttsarepresent. |
| --- | --- | --- | --- |
|  |  | 2. | Ensureexhibitionbydifferentdepts.aboutindividualbeneficiary schemes |
|  |  | 3. | InspectJKB/PSBcounters/outlets |
|  |  | 4. | Participate/ensureorganizationofsportsactivityinplayfield,talent hunt/culturalevent/youthactivity |
|  |  | 5. | GandhiKatha(suggesteddetailsuploadedonjkpanchayat.in) |
|  |  | 6. | Visitatleast2amritsarovarsandgetitsgeotaggedphotos |
|  |  | 7. | InspectKhidmat(CSC)CentresandcreateGenerateawarenesson 225schemesparticularlyG2CschemeslikeBEAMS,Janbhagidari, AapkiZaminAapkiNigrani,DigitalJ&K |
|  |  | 8. | Visitingofficershallalsoplanandconductpanchayatlevelconver- gencemeetingofalldepartments |
|  |  | 9. | CheckeffectivenessofCentrallysponsoredschemes |
|  |  | 10. | VisitandinspectallgovernmentestablishmentsincludingPHE, AWC,FPS,schools,etc |
|  |  | 11. | Attemptsaturationofdeliverableso JanAbhiyanandwherever deficienciesfound,leadadrivetoachievealldeliverables |
|  |  | 12. | Assesseffectivenessofsanitationcampaigninthepanchayat |
|  |  | 13. | Ensureselfemploymentactivitiesfor15youthperpanchayat |
|  |  | 14. | Identify20potentialcandidatesperpanchayatforHIMAYATtraining alongwiththetradeonwhichtheywanttraining |
|  |  | 15. | Whereverpossible,distributeemploymentlettersforpeopleselect- edundervariousgovernmentemployments |
|  |  | 16. | Intheevening,holdnormalmeetingwith seniorcitizens,govtem- ployeesincludingretiredemployees,exservicemen,youthclub,and any citizens ofthevillagewhoareenrolledincollege/university |
|  |  | 17. | OpendiscussiononNashaMuktAbhiyan |

Day2            Haveameetingwithall stakeholders-depttofficials andpanchayatmembers

1.       Discussionontheandassesstheprogressofdifferentschemesrelating tothelocalizedSDGsprioritizedforthatvillageaspertheresolution passedby thatGramPanchayaton21st April22,onNationalPanchayti RajDay.

2.	Sensitizevillage residentsaboutmyScheme”portal(myscheme.in) whichincludesinformationaboutalltheschemesbeingrunbyCen- tral/State/UTgovtacrossthecountry

3.	Hold meeting of theBiodiversityManagementCommitteestodeliber- ateonissuespertaining toconservation of biodiversityandsustaina- bleutilizationof biologicalresources.

4.       PrepareVillagedevelopmentplan,inconsultancywithGrampanchayat, discussitingramsabhaandgetitapproved.

5.       Ensure saturationofsoilhealthcardandgoldenhealthcardunderGold- enHealthCardunderAyushmanBharat,

6.       Ensuresaturation  of OldAge PensionScheme

7.       EnsureDomicileSaturation.

8.       EnsureKCCSaturation

9.       Ensure saturationoflandpassbooks

10.     Ensureregistrationofvillagevendorsneededforanyscheme,onGEM

portal

11.     Ensurepanchayatcontractors registration

12.     EncouragePanchayatmembers forimportanceofplantationdrivein

PanchayatunderHarGaonHariyali

13.     Ensure paintingondigitalJ&Kinpanchayatghars

14.     Ensure paintingonpanchayatactivitesandCSSinpanchayatghars

15.	Thevisiting officeshallchecknoof kindergarten andplayfields present inthepanchayat for kidsandstudents,iftheinfrastructure present inthesearegoodenough.

16.     Holdmeeting withpanchayatmembers todiscussaboutcorruption menaceandstepsrequiredtomakeJ&Kcorruptionfree

17.     Obtaina candidassessmentaboutperformanceofvariousdeptts in- cludingfairfeedbackaboutdiscrepanciesinfunctioning

18.	Check thestatusof NashaMuktAbhiyanandreporting of drugad- dictstoDeputyCommissioner.

19.     IdentifyTouristDestinations,Circuits,ThemeTreks,IdentifyHomestays, providesupportfortourismactivities throughVillageCooperative

20.     OrganizeTalentHuntatPanchayatLevel

21.     Conductsocialauditofatleast5worksunderfollowingschemes:

a.       MGNREGA

b.PMAY

c.        IHHLtoiletsandpayments d.CSCs

e.AMRITSAROVARS

22.     Holda mahilasabha anda balsabhaandrecordproceedingsinthefor- matgiven

23.     InauguratevillagehaatunderJKSRLM

24.     Checkifyouthclubsareformedinthepanchayatandwhatactivities theyareengagedin

25.     Organizea villagelevelculturaleventtoengagepanchayatmembers

26.     SensitizeGPaboutE-kitabkoshaninitiativeofJ&KGovtforempowering youthsthrough onlinedigitalliteracy

GENERALINSTRUCTIONS

1.	Thevisitingofficershallrefrainhimself/herselfgivingorofferinganycommitmentonbehalfofthe governmentandshalladoptanunbiasedattitudeinreportingissues.As faraspossible,his/her observation shouldbebasedona fairandanalytical viewemergingfromhis/herinteractioninthe village.

2.	Heisgoingtothevillageasplanningofficer,notforsanctioninganyworksorformakinganycom- mitments.

3.	Whilepreparingvillagedevelopmentplan,hehastoensurethat,demandsareprioritizedandre- flectedunderavailableschemes,wherevernecessarythelargerworksaretobereferredtoadminis- trativedepttunderCSS/UTplansunderintimationtoDCsandrestoftheworkstoDCsforreflecting itunderdistrict/CSS plans

4.    His workshallbehardcoreplanningandauditandisnota PRexercise.

5.	EveryDeputyCommissionerhastoensurethatatleastoneRDDofficial(ideallyPanchayatSecre- tary)ispresent  ineverypanchayatwithrelevantpanchayatrecords,toensureconductofallactivi- tiesasplanned.Panchayatwiseorderneedstobeissuedinadvance.

6.	Visitingofficershouldideallycarryhis/herlaptoptocompletethereportsatthepanchayatlevel itselfanduploadthefinalreport,duly signedbothbythesarpanchandbythevisitingofficeron www.jkpanchayat.inportal,beforetheyleavepanchayat.

7.	Focus ofvisitareyouth,skills,self-employment,nashamukt,bhrashtracharmukt,Rozgaryukt J&K, besidestocarryforwardtheactivities duringJanAbhiyanandsaturatethem.

8.    Inadditionattentionmaybegiventothefollowingareas a.     MakefulluseofCentrallySponsoredSchemes

b.Saturationofindividualbeneficiaryschemes c.     Self-employmentschemes

d.Banklinkedschemes-includingdepartmentalsubsidyschemes e.Empowermentandtransparencythrough digitalinitiatives

f.       Effectivenessofgrassrootsmachinery–

i.       Patwari,VLWpresent  andavailable

ii.      AvailablefundsutilizedinpublicinterestandasperGramSabharesolutions iii.   Fairness ingovernance

iv.    CSS/Individual beneficiaryschemesetc v.      BrashtacharMuktJ&K

vi.   BhaiMuktJ&K

vii.  NashaMuktJ&K

9.	ThePRImembers (Sarpanchs,Panchs,BDCChairperson)shallbeattheforefrontofallactivities and givendueimportanceandtheapproach shouldbetostrengthenthemandmakethemfeelem- powered.He/sheshallensurethattheBDCchairpersonandSarpanch/Panch arepresent  atthetime ofinaugurationandceremonies.

10.	Visitingofficershallnotleavethedistrictwithoutuploadingthereport,duly signedonthewww. jkpanchayat.inportal.EveryDeputyCommissionerhastoensurethat.

A)   DetailsofReportingOfficer:

Name:             Dr SURESH AGSTAM

Designation:	VETERNARY ASSISTANT SURGEON

Department/placeof  posting: VAS OFFICE, RAMNAGAR

MobileNo:   7006892108

EmailID:   	sagstam@gmail.com

HomeDistrict:                                    UDHAMPUR

Datesof  visit:         01-11-2022 & 02-11-2022

B)	LocationaldetailsofPanchayat:(tobepre-filled,informationtobetakenfromtheprevious phasesbooklets/summarizedexcelsheetuploadedonjkpanchayat.in/b2v4.php)(tobevali- datedbythevisitingofficerandmissingdetailstobefilled)

NameofthePanchayat:                     DHAMMA

LocalGovernmentDirectory(LGD)codeof  thePanchayat:	    240338

Nameof  CDBlock:         MAJALTA

NameofTehsil:               MAJALTA

Nameof    District:                                            UDHAMPUR

C)     PanchayatProfile:

No.ofrevenuevillagesinthePanchayat:df             03

No.ofhamletsinthePanchayat:	                                07

No.ofhouseholdsinthePanchayat:                    481

Population(approx)of  thePanchayat:               2019 (APPROX)

Part-II:

(TobefilledupbytheVisitingOfficerduringhis/hertwodayvisittothePanchayat.AllFieldshavetobe

filledbytheVisitingOfficerbeforethebookletishandedovertotheDC

FrontlineOfficers/OfficialswhowereassignedtothePanchayatfortheprogramme:

| S.NO. | Department | Name | Designation |
| --- | --- | --- | --- |
| 1 | SOCIAL WELFARE | ALL | SUPERVISOR,AWW,AWH |
| 2 | ANIMAL HUSBANDRY | SUDERSHAN KUMAR | VETERNARY PHARMACIST |
| 3 | AGRICULTURE | SANJEEVAN SINGH | JAEO |
| 4 | HEALTH | RANU KOTWAL | COMMUNITY HEALTH OFFICER |
| 5 | AYURVEDIC DEPTT | DR RAKESH PANDITA | MEDICAL OFFICER |
| 6 | PMGSY | AMIT ABROL | AEE |
| 7 | PDD | ALL | LINEMAN, METER READER |
| 8 | HORTICULTURE | PARVEEN KUMAR | HTG-IV |
| 9 | RDD | RAKESH SHARMA , RAJESH SINGH SANJEEV SINGH | ACCTT.ASSTT. & 2 GRS |
| 10 | POSHAN (ICDS) | ALL | SUPERVISOR,AWW,AWH |
| 11 | REVENUE | RAJ SINGH | PATWARI |
| 12 | FOREST | MOHD AFZAL JEET | FOREST GUARD |
| 13 | JK BANK | SAMRITUI, PARTEEK KUMAR | ASSISTANT MANAGER,INSURER |

Detailsofabsentemployeesvis-à-vislistfurnishedbytheDCoffice:

| Department | Name | Designation |
| --- | --- | --- |

DAY1-ACTIVITIES

AGENDA1:PANCHAYATASSETREGISTER

Infrastructure:

1.		PanchayatGharInfrastructure

a.  Govtbuilding/private                                         GOVT

b.  New/needingrepairs                                   NEW

2.       Furniture(Y/N)                                                     YES

3.       Computer/printer(Y/N)                                       YES

4.       Internet(Y/N)                                                        NO

5.       Telephone(Y/N)                                                    NO

6.       Toilet(CSC/partofpanchayatghar)(Y/N)               YES

7.       Water(Y/N)                                                            YES

8.       Electricity(Y/N)                                                      YES

9.       Bankbranch(Y/N)                                                   NO

10.     CSC(Y/N)                                                                NO

11.     Patwarkhana(Y/N)                                                 NO

12.     Villagehaat(Y/N)                                                     YES

13.     Playground(Y/N)                                                     YES

14.     School-

a.        Kindergarten(Y/N)                                      NO

b.Primary(Y/N)                                                     YES

c. Secondary(Y/N)                                                 YES

d. College (Y/N)                                                     NO

e.University(Y/N)                                                  NO

15.     AnganwadiCentre(Y/N)                                           YES

a.        (govt/private)                                                PRIVATE

b.Totalchildrenenrolled                                         208

15.     AmritSarovars–details,location,condition              NIL

16.     Governmentoffices-details,whetherfunctionalornot FUNCTIONAL

17.     Rationshop(Y/N)                                                                NO

18.      Placesoftourismimportance–names,littledetailsonhistorical/culturalimportance Baba Baloor TEMPLE

19.      Villageheritagesites/treks-names,littledetailson historical/culturalimportance Baba Baloor TEMPLE

20.     VLWOffice (Y/N)                                              YES

21.     PrimaryHealthcareCentre(Y/N),                     NO

22.     ListofIncompleteBuildings-names,yearofconstruction NIL

23.     ListofUnderutilizedBuildings-names                               NIL

DAY1-ACTIVITIES

AGENDA2:

DIFFERENTINSTITUTIONS/INFRASTRUCTUREPROJECTSTOBEVISITED

| AMRITSAROVARS | Visit,verify | COMMENTS |
| --- | --- | --- |
| KhidmatCentres | Create/Generateawarenesson225schemes particularlyG2CschemsAapkiZaminAapkiNigrani, Beams,Janbhagidari,DigitalJ&K | NA(NOT Available due to which local people faces lot of hardship) |
| JKB/PSBcounters/outlets | a)Statusofcounter b)Numberofvisitors | No counter of any bank available in branch |
| Incompletebuildings/pro- jects | Verify whetheridentificationandredistribution done | N/A |
| PDS | Visit,evaluate,onlinestatus | N/A |
| PHC | Visit-evaluate,statusofstaff,equipmentand quality | N/A |
| Youthclubs | Meet,interact,seeksuggestions | N/A |
| SHG | Meet,identifyproblems,seeksuggestions | N/A |
| PMAY | Inspect,Inaugurate | YES,8 |
| Myschool,mypride progress;schools-water, toilets,staff | Visit,checkforwater,electricity,sanitation,meet studentsandstaff | YES |
| SwachhSBM | Evaluate | YES |
| Panchayatplayground, Sportskitsdistribution Villagegames | Ensure,verify.Participateinatleastonegamein theplayground | YES |
| HarGaonHariyali, Planta- tiondrive | Evaluatestatus,feedback | YES |
| Villageculturalevent Dangal/Haat/Mela | Participatein;ensurethatitisheld | YES |
| Exhibitionofschemes | Ensurethateverydepartmentparticipatesand thatitcontinuesfortheentiredurationofB2V | YES |
| JalJeewanMission verifica- tion- WSS/JSD Electricitysupply | Verify | WATER SUPPLY IN ALTERNATE DAYS |

DAY1-ACTIVITIES

AGENDA3:SATURATEJANBHIYAN

DELIVERABLESANDRECORDDEFICIENCIESIFANY(INSERTDELIVERABLESLISTHEREASPERGADFORMAT

DELIVERABLES

SATURATION OF AYUSHMAN GOLDEN CARD =97.02% SATURATION OF JANANI SURAKSHA YOJANA= 54.16% SATURATION OF OLD AGE PENSION SCHEME= 100% SATURATION OF WIDOW PENSION= 100% SATURATION OF DISABILITYY PENSION=100% SATURATION OF DOMICILE CERTIFICATE=90.22% SATURATION OF KISAN CREDIT CARD= 66.21% SATURATION OF LAND PASSBOOK= OUT OF 1292 ELIGIBLE BENEFICIRIES, 5 LANDPASSBOOKS PREPARES AND 1 ISSUED DURING B2V4 REGISTRATION OF VILLAGE VENDORS ON GEM PORTAL= NIL REGISTRATION OF VILLAGE CONTRACTORS ON PWD PORTAL , JK TENDERS PORTAL=100% PERSON IDENTIFIED UNDER HIMAYAT SCHEME=20

DAY1-ACTIVITIES

AGENDA4:

SELFEMPLOYMENTACTIVITIES

EnsureSelf-employmentactivities foryouth,distributeemploymentlettersforpeopleselectedunder varioussocialschemes(15ISTHETARGETPERPANCHAYAT)

___

Numberofcasesindifferentcategoriessanctioned NIL

Detailsofthebanksanctioningit: NIL

Totalamountinvolved:   NIL

DAY1ACTIVITIES

AGENDA5

Intheevening,holdinformalmeetings  withseniorcitizens,govtemployees,retdemployees,youthclub andothercitizenswhoareenrolledoncollege/universityandhavediscussiononGandhiKatha,Nasha MuktAbhiyan,corruptionfreegovernance,doublingfarmersincomeandrecordtheproceedings

DAY2

a.       NoofIndividualCompostPitsconstructed 10

b.NoofIndividualSoakPitsconstructed 45

V.          No.ofBiodiversitymanagementcommitteemeetingsheld: YES

VI.         IsthenameofSarpanchdisplayedoncitizeninformationboardsofallRD&PRschemes:Yes/No   YES

VII.       AreSarpanchsbeinginvolvedinstart/inaugurationofactivities:Yes/No              YES

VIII.      WhethersubjectshavebeenassignedbytheSarpanchtothePanchs:Yes/No       YES

IX.        Whethergrievancesredressalboxisinstalled:Yes/No      YES

X.         NoofgrievancesreceivedpertainingtoPanchayatlevel: 0

XI.        NoofgrievancesdisposedofatPanchayatlevel:  0

XII.       WhethertheSarpanch/PanchayatSecretaryhavedigitalsignatures:Yes/No         YES

XIII.      WhetherallMGNREGA/14thFCpayments arebeingmadebySarpanchthrough DigitalSignature

Certificate(DSC):Yes/No         YES

HUMAN RESOURCEAVAILABLEATTHEPANCHAYAT LEVEL:

| SRNO. | DEPARTMENTWISESTAFF | NUMBERS |  | NAMES |
| --- | --- | --- | --- | --- |
|  |  | SANCTIONED | ACTUAL |  |
|  | Ruraldevelopmentdepartment: BDO JE GRS TA, | 1 1 1 2 | 1 1 1 2 | VISHAL KUMAR SADHOTRA RAVI KUMAR RAKESH SHARMA SACHIN GUPTA&ANKUSH GUPTA |
|  | SCHOOLEDUCATION: TEACHER HEADMASTER ANYOTHER | 42(TOTAL) 7 2 2 | 18 4 2 2 | HSS DHAMMA, MS GHAR PARMASTA, PS CHANDI, PS THANI, PS WEHAR VIPIN KUMAR |
|  | JAL JEEVAN: | - | - | - |
|  | PDD: LINEMAN JE ANYOTHER | - | - | POST OF LINE MAN , METER READER ATRE FEEDER BASED, NEED BASED |
|  | FOOD&CIVILSUPPLIES | - | - | - |
|  | AGRICULTURE& ANIMALHUS- BANDARY | - | - | - |
|  | SOCIALWELFARE | - | - | - |
|  | HEALTH: ASHA ANM AYUSHDOCTOR ALLOPATHICDOCTOR | 2 1 1 | 1 1 1 | RENU KOTWAL- COMMUNITY HEALTH OFFICER, KAMLESH- ASHA WORKER DR RAKESH- MEDICAL OFFICER(AYURVEDIC) |
|  | ANYOTHERDEPARTMENT |  |  |  |

DAY2-ACTIVITIES

AGENDANO.1

DiscussionontheandassesstheprogressofdifferentschemesrelatingtothelocalizedSDGsprior-itizedforthatvillageaspertheresolutionpassedbythatGramPanchayaton21stApril22,onNational PanchayatiRajDay(Copyoftheresolutiontobetakenfromwww.jkpanchayat.inportalunderthelinkof GramSwarajMonth)

1.       SDGs AGREED FORTHATVILLAGE,TOBEIMPLEMENTED BYMARCH2024:

2.       STATUSOFWORKSUNDERTHEFOLLOWINGSCHEMES:

1      Cleanandgreenvillage

i.InitiativestakenbythePanchayatformanagingSolidandLiquidWaste     	NIL

ii.     InitiativestakenbythePanchayatforusinggreensourcesoffuellikesolar,biogas

NIL

iii.  Hasmappingoflanduse,waterbodies,forest,slopes,wetlands,degradedforestwithintheGram

Panchayatbeendone?Yes/No.IfNo,reason,thereof	NO

iv.    HastheClimateResiliencePlanbeendevelopedfortheGP?Yes/No      NO

v.     StepstakenbytheGramSabhaabouttheclimatechangemitigationfactorslikereducingenergy consumption,usageoffossilfuels,plastics,non-renewablebuildingmaterialsandalsotopromote measureslikeplantingoftrees,conservingforests,usageofgoodagriculturalpracticeslikedrip irrigation,waterconservationmeasuresandconservationofwetlands.    NO

vi.  Whetherschoolshavestartedsegregatingwaste   NO

vii. Whetherschoolshavetheirowncompost/soakagepitsforsolid/liquidwastemanagement   NO

2     Healthyvillage

i)    Aremeetings  relatedtoVillageHealthandSanitationCommitteebeingheldregularly?YES

ii)   DoalltheeligibleindividualsbeenprovidedtheGoldenCard?YES

iii)  ArealltheChildrenbeingimmunizedaspertheSchedulerecommendedbyGovt.ofIndia?YES

iv)  ArealltheeligibleindividualsbeenvaccinatedagainstCOVID-19?YES

v)   DoesGramPanchayatensurethatallpregnantwomenaregettingnecessaryprenatalcheckups?YES

vi)  WhetherallthedeliverieswereInstitutionalizedorconductedbytrainedMidwives?YES

3     Watersufficientvillage

i)    DoalltheIHHsintheGramPanchayathavewaterpipelineconnections?    NO

ii)   WhetherGramPanchayathastakenstepsforgreywatermanagement.     NO

IfYespleasespecify

iii)  DoalltheIHHsintheGramPanchayathavetoilets? YES

iv)  ArealltheIHHstoiletsfunctionalornot?   YES

v)   DoalltheSchools/Anganwadicentershavea toiletfacilityornot?  YES

vi)  Areallthetoiletsintheschools/Aaganwadifunctionalornot?  YES

vii) WhetherGramPachachayatBhawanhasseparate toiletsforwomenornotNO

4      ChildFriendlyvillage

i)	Doallthechildrenundertheageof0-6yearsbeenenrolledintheAnganwadicentersforpre- schooling?Yes/NOYES

ii)    HowmanyBalSabha’swereorganizedintheGramPanchayat------THREE-------------

iii)  WhethertheissuesraisedbyBalSabhaareaddressedduringtheGramSabha. Yes/NOYES

iv)	WhetherGramPanchayatistrackingthedatarelatedtodropoutchildrenandchildrenwithirregular attendance?Yes/NO. YES

v)   DoalltheschoolsundertheGramPanchayathaveseparate toiletsforgirlsandboys?Yes/NoYES

5      Villagewithgoodgovernance

i)    IsCSClocatedintheGramPanchayatBhawanornot?   NO

ii)	IsthelistofbeneficiariesrelatedtotheSchemes/ProgramsdisplayedontheGrampanchayatwallor not? YES

iii)  DoestheGramPanchayathasitsbuildingornot?   YES

iv)  IstheGramPanchayatofficefunctionalornot?    YES

v)   Aretheactivities approved undertheHalqaPanchayatDevelopmentPlandisplayedontheGram

Panchayatwallornot?    YES

vi)  IsSocialAuditofearlierSchemes/Programscarriedoutornot?    YES

6      Povertyfreeandenhancedlivelihoodvillage

i)    HasGramPanchayatdevelopedanycriteria fortheidentificationofthepoor?Yes/NoifyesspecifyNO

ii)   HavealltheeligiblehouseholdsregisteredinPDSornot?YES

iii)	HasGramPanchayatprovidedspaceforSelf-helpGroupsinPanchyatGharforholdingmeetings  or not?NO

iv)  HavealltheeligiblehouseholdsbeenregisteredforPensionornot?YES

v)   HasGramPanchayatfacilitatedYouthforSkillEnhancementCoursesandPlacement?YES

vi)  HasJobCardsbeendistributedtoalltheeligibleindividualsunderMGNREGA?YES

vii) HasGramPanchayatfacilitatedSHGsforBankAccountLinkages?NO

7     Sociallysecuredvillage

i)    WhetherGramPanchayatismaintainingdatarelatedtoDifferentlyAbledPeople?  NO

ii)   IsGramPanchayatOffice DisabledFriendlyornot?  YES

iii)	Areprovisionsfora separate BudgetundertheResourceEnvelopeforWomenandChildrenmadeor not? NO

iv)	DoalltheSchools intheGramPanchayathavefacilitiesforDifferentlyAbledChildrenliketoilets, barrier-freeaccess,etc.,ornot?  NO

v)   Arealltheeligibleindividualsaregettingpensions,likeoldagepension,widowpension,etc? YES

vi)  ArealltheeligiblehouseholdsgettingbenefitsfromIAYornot YES

8      EngenderedDevelopmentinVillage

i)    HowmanyMahilaSabha’swereorganizedintheGramPanchayat-----2------

ii)	WhetherSHGsfederationshavebeenprovidedspaceformeetings  inthePanchayatBhawan(Yes/ No) NO

iii)  WhetherGPshavetakenstepsforincreasingwomen’sparticipationinGramSabha(Yes/No)  YES

iv)  NumberofwomenbeneficiariesheadedhouseholdscoveredunderPDS

system…985……………………

v)   Numberofbeneficiaries(outoftotaleligiblepopulation)receivingsocialprotectionbenefitsunder

PradhanMantriMatritvaVandanaYojana…80……………….

9    Self-sufficientinfrastructureinthevillage

i.	WhetherGPhasa CommunityHallwithaccesstoelectricity,furniture,watersupply, toilet……NO COMMUNITY HALL………………….

ii.     WhethertheDisastermanagementplanisavailableattheGPLevel(Yes/No)NO

iii.  Whetherchild-friendlyparkwithrequiredfacilitiesisavailableinGP(Yes/No)   NO

iv.    WhethertheGPhaseasyaccesstoGodownforstorage(Yes/No)   NO

v.     Whetherstreetlightsareprovidedinpublicplacesforensuringsafety(Yes/No)  YES

DAY2ACTIVITIES

AGENDANO.2

SensitizevillageresidentsaboutmyScheme”portal(myscheme.in)whichincludesinformationaboutall theschemesbeingrunbyCentral/State/UT govtacrossthecountry

(SchemeMaterialavailablefromhttps://jkpanchayat.in/b2v4.php)

DAY2ACTIVITIES

AGENDANO.3

HoldmeetingoftheBiodiversityManagementCommitteestodeliberateonissues pertainingtoconserva- tionofbiodiversityandsustainableutilizationofbiologicalresources.HeshouldcheckPeopleBiodiversity register(PBR)ofthatpanchayatandreviewifBiodiversityManagementCommittee constitutedforthat panchayatis holdingminimum4meetings inayearandmeeting onceinevery3months (RoleofBMC availableathttps://jkpanchayat.in/b2v4.php)

COMMITTEEMEMBERS 7 MEMBERS

PRESENT 4 PRESENT

BIODIVERSITYREGISTERPHOTOS YES

PAST 4MEETINGDETAILS-DATES,MINUTESPHOTOS   ONLY RECORD OF 2 MEETING FOUND

DAY2ACTIVITIES

AGENDA4

Visitingofficershallalsoplanandconductpanchayatlevelconvergencemeeting  ofalldepartmentsand prepareVillagedevelopmentplanforvillage,inconsultancywithGrampanchayat,discussitingram sabhaandgetitapproved.

(GPDPformatavailableonhttps://jkpanchayat.in/b2v4.php)

InadditionGPDPplanshallalsoinclude:

           Touristplaceswhichneedtobedeveloped BABA BALOOR TEMPLE

           Specificproductwhichneedstobedeveloped

           Tourism-homestays

	20candidatesfortrainingunderHimayatschemealongwithtradeinwhich trainingistobegiven

DAY2ACTIVITIES

AGENDA5

Ensuresaturationoffollowingschemesandgivestatus:

S

| NAMEOFTHESCHEME | TOTALELIGIBLE BENEFICIARIESIN THE VILLAGE | TOTALBENEFICIARIESWHO AVAILEDTHEBENEFITSOFTHESCHEME | REASONSFOR PENDENCY |
| --- | --- | --- | --- |
| GoldenHealthCardunder AyushmanBharat | 2019 | 1959 | Pending 120, Migrant population, document incompletion |
| Jananisurakshayojana | 24 | 13 | Lack of funds |
| OLDAGEpension | 120 | 120 | - |
| Widowpension | 22 | 22 | - |
| Disabilitypension | 20 | 20 | - |
| Domicilecertificate | 1995 | 1800 | Not applied, old age |
| Kisancreditcard | 438 | 290 | Local people are applying for it |
| PMkisansammannidhi | 204 | 204 | - |

| Landpassbook | 1292 | 5 | partial |
| --- | --- | --- | --- |
| Registrationofvillageven- dorsonGEMportal | NIL | NIL | - |
| Registrationofvillagecon- tractorsonjktendersportal | 5 | 5 | - |
| Registrationofvillagecon- tractorsonPWDportal | 5 | 5 | - |
| Incompletebuildings/pro- jects | - | - | - |

DAY2ACTIVITIES

AGENDA6

NASHAMUKTABHIYAN

1.       Whethergramsabharesolutionpassed  YES

2.       Detailsofactivities conducted AWARENESS CAMPAIGN HELD

3.       Whetherallactivities andGSresolutionuploadedonjkpanchayats.inportal  YES

4.       Howmanydrugaddictsinthevillage 15

5.       WhetherreportedtotheDeputyCommissioner  NO

6.       Howmanyregisteredforrehabilitationundergovernmentprogramme NIL

DAY2ACTIVITIES

AGENDA7

SOCIALAUDIT

Conductsocialauditofatleast5workseachunderfollowingschemes:

| NAMEOFTHE SCHEME | DETAILSOFTHE WORKS | YEAROFWORK APPROVAL | AMOUNT APPROVED FORTHEWORK | WHETHER WORKEXECUTED SATISFACTORILY | GEO- TAGGED PHOTOS | ANY GRIEVANCE RECORDED RELATINGTOTHAT WORK |
| --- | --- | --- | --- | --- | --- | --- |
| MGNREGA | T ROAD | 2020-21 | 2.48LAC | YES | YES | NIL |
| PMAY | 5 | 2020-21 | 7.45LAC | YES | YES | NIL |
| IHHL UNDERSBM-G | 5 | 2021-22 | RS 60000 | YES | YES | NIL |
| CSCUNDER SBMG | - | - | - | - | - | - |
| AMRIT SAROVARS | - | - | - | - | - | - |

DAY2ACTIVITIES

AGENDA8

MAHILASABHA

Totalwomeninthevillageabovetheageof18 :       710(APPROX)

Totalattended: 25

Proceedings: ALL SCHEMES WERE DISCUSSED

(Plinsertpointerstobediscussedthere–referpalliproceedings)

DAY2ACTIVITIES

AGENDA9

BALSABHA

Holda balsabhaandrecordproceedings  YES

Totalchildreninthevillageabovetheageof 5-18: 270( aprox)

Totalattended 29

Proceedings: DISCUSSED ON SPORTS, NASHA MUKT, CORRUPTION FREE, SWATCH BHARAT, LESS USE OF MOBILE PHONES

(Plinsertpointerstobediscussedthere–referpalliproceedings)

DAY2ACTIVITIES

AGENDA10

INAUGURATIONS

| SR NO. | ASSETS/ACTIVITIES INAUGRATED | STATUSOFTHEASSET/AC- TIVITIES(NUMBER,OTHER DETAILS) | GEO-TAGGED PHOTOS |
| --- | --- | --- | --- |
|  | VILLAGEHAATunderJKSRLM (SUN- DAYMARKET) | 8, CHEESE FUNCTIONAL AT PANCHAYAT GHAR | YES |
|  | PMAYhousesifanyreadyforinaugra- tion | 2 | YES |
|  | Swachhgramprojects-segregation shedsetc | - | - |
|  | Amritsarovars | NIL | - |
|  | Sportskits | NIL | - |
|  | Villageculturalevents | 3 | YES |
|  | JJMassets/projects | NOT FUNCTIONAL | - |
|  | Anyothertobeidentifiedatdistrict level | - | - |

FOLLOWUPOF(B2V1,B2V2&B2V3):

(Prefilledexcelsheet tobetakenfromdistrictlevel/andalsotobedownloaded

fromwww.jkpanchayat.in)

| S.NO. |  | Particulars | Action taken |  | Remarks# |  |
| --- | --- | --- | --- | --- | --- | --- |
| I. UrgentPublicRequirements/Demands-B2V1 |  |  |  |  |  |  |
| 1 | 3 NO OF DUG WELL |  |  | No action |  |  |
| 2 | CHECK DAM FOR IRRIGATION |  |  | No action |  |  |
| 3 | VETY. CLINIC |  |  | No action |  |  |
| 4 | PHC . |  |  | No action |  |  |
| 5 | UPGRADATION OF ELECTRIC TRANSFORMER |  |  | No action |  |  |
| 6 | COMMUNITY HALL |  |  | No action |  |  |
| 7 | EXTENSION COUNTER OF BANK |  |  | No action |  |  |
| II. UrgentPublicRequirements/Demands-B2V2 |  |  |  |  |  |  |
| 1 | INADECUATE DRINKING WATER FACILITY |  |  |  |  |  |
| 2 | SHORTAGE OF STAFF IN HS DHAMMA |  |  |  |  |  |
| 3 | INCREASE LABOUR RATE UNDER MGNREGA |  |  | Started |  |  |
| 4 | ROAD CONNECTIVITY NOT SUFFICIENT |  |  |  |  |  |
| 5 | REPLACEMENT OF LOWER TYRANSFORMER |  |  | ALL TRANSFORMER ARE FUNCTIONAL BUT NOT REPLACED |  |  |
| 6 |  |  |  |  |  |  |
| 7 |  |  |  |  |  |  |
| S.NO. | Particulars |  |  | Actiontaken |  | Remarks# |
| III. MajorProblems–B2V1 |  |  |  |  |  |  |
| 1 | Drinking water |  |  | Adequate work not done |  |  |
| 2 | Panchayat not fully connected by road |  |  | yes |  |  |
| 3 | Requirement of staff in all deptt |  |  | Nil |  |  |

| 4 | INCREASE LABOUR RATE UNDER MGNREGA | No action |  |
| --- | --- | --- | --- |
| 5 | Demand of 5 no of transformer | Only 1 transformer is installed |  |
| IV. MajorProblems-B2V2 |  |  |  |
| 1 | SAME AS B2V1 |  |  |
| 2 |  |  |  |
| 3 |  |  |  |
| 4 |  |  |  |
| 5 |  |  |  |
| V. MajorProblems-B2V3 |  |  |  |
| 1 | SAME AS B2V2 |  |  |
| 2 |  |  |  |
| 3 |  |  |  |
| 4 |  |  |  |
| 5 |  |  |  |
| VI. MajorComplaints-B2V1 |  |  |  |
| 1 | SHORTAGE OF STAFF IN EDUCATION, ELECTRIC DEPTT | SHORTAGE STILL EXISTS |  |
| 2 | DRINKING WATER FACILITY | NOT SOLVED |  |
| 3 |  |  |  |
| VII. MajorComplaints-B2V2 |  |  |  |
| 1 | SAME AS B2V1 |  |  |
| 2 |  |  |  |
| 3 |  |  |  |
| VIII. MajorComplaints-B2V3 |  |  |  |
| 1 | 8 NO OF HAND PIMPS IN PANCHAYAT NEEDS REPAIRING | NIL |  |
| 2 | WATER SUPPLY IRREGULAR | NIL |  |
| 3 | Low voltage power, electric wires are loose | nil |  |

OVERALLPERCEPTIONOFFUCNTIONING OF GOVERNMENTDEPARTMENTS

1.         BEST DEPARTMENT: HEALTH DEPARTMENT & RDD

2.       LEASTRESPONSIVEDEPARTMENT: PHE, PDD ( DUE TO SHORTAGE OF STAFF)

GENERALASSESSMENTOFTHEVISTINGOFFICER

| I | AnymajorcomplaintbroughttothenoticeoftheVisitingOfficer: MOST OF B2V1 , B2V2 , B2V3 REMAIN UNFULLFILLED |
| --- | --- |
| II | Major/urgentpublicdemandsthatwas/werereflectedearlierbuthavenotbeenaddressedsofar: REQUIREMENT OF ELECTRIC POLES, 4 UNIT CULVERT AT BUMBOO MOHALLA, SHORTAGE OF STAFF IN EDUCATION DEPTT(SCHOOL) |
| III | Overallassessmentofthevisitandsuggestions: (Thevisitingofficertoensurethattheoverallassessmentisrecordedindetailsalongwithconcretesugges- tions) : There is a dire need of electric poles as electric wires level is down posing a threat to human lives, requirement of staff in hss dhamma. |
| IV | OverallRatingofgovtfunctioningas givenbythePanchayat(Scaleof0to10) : 6 |
| V | CertificatefromSarpanchthatthevisitingofficerhasstayedinthepanchayatfor 2 days : CERTIFIED THATVISITING OFFICER HAS STAYED IN PANCHAYAT FOR TWO DAYS. |

URGENT PUBLIC DEMANDS

- Requirement of app. 4 metres culvert/ tractor pass at chote sooti bimboo mohalla w no 3which makes connectivity with Pagyal w no 7, Nagola w no3, thereby providing benefits to 80 families by increasing their Agriculture Farming Income.

- Electric wires level are down posing a great threat to human as well as animal lives, requirement of poles in whole panchayat

- Shortage of maths, zoology, botany lecturers in H S S Dhamma

- Requirement of veternary dispensary

- Requirement of community hall

- Requirement of atleast 8 hand pumps in whole panchayat

- Problems of monkey in whole panchayat as they distroy agriculture crops

6 DOCUMENTS ENCLOSED:

DepartmentofRuralDevelompentandPanchayatiRaj

GovernmentofJammu &Kashmi