4

15TH OCTto3RD NOV,2022

KEYFEATURES

•     DeputyCommissionerstoleadtheinitiative

•    RuraldevelopmentDepartmenttobethenodaldepartment

•	PlanningDevelopment&MonitoringdepartmentandITtobethesupport departments

ACTIONSANDTIMELINES

| ACTION | RESPONSIBILITY | LATESTBY | REMARKS |
| --- | --- | --- | --- |
| Janabhiyan | Alldepartments | Oct15-26th | Goingon |
| DeputationofSecttstaff/ HoDs | GAD | Oct14 | Done |
| DeploymentofStaffto Panchayatsandservingof ordersondeployedofficers | DCs | Oct25 | DCswilldeployseniorlevelstaff fromthedistricts.Strictactionto betakenagainstabstentions.No exemptionstobegiven |
| Trainingofdistricttrainors onB2V4 | RDD | Oct26 |  |
| Trainingofvisitingofficers | DCs | Oct27 |  |
| FieldVisitstobecompleted by | VisitingOfficers | Nov3 | DCstosuperviseandensurethat eachPanchayatisvisitedwithin theperiodspecified |
| DataofB2V4tobe uploadedby | VisitingOfficers | Nov10 | DCstosuperviseandensurethat dataofallPanchayatsisupload- edbythevisitingofficerwithin theperiodspecified |

INSTRUCTIONSFORTHEVISITINGOFFICER(DAYWISE)

| DATE | INSTRUCTIONS | ACTIONPOINTS |
| --- | --- | --- |
| Day0 | Meetingwithdeputy commissionerandhis/her team | a. TakeprintoutsoffilledbookletsofB2V1,B2V2andB2V3from www.jkpanchayat.in b.Alsotakeprintoutsofthesummarizedexcelsheetsofthe previousphasesfromwww.jkpanchayat.in c. CollectATRsonissuesraisedduringprevious3phasesfromthe officeofDeputyCommissioner(Planningdeptt) d.Takeprintsofblank 2bookletsofB2V4fromwww.jkpanchayat.ine.Takeplansfor2previousyearsandATRsfromtheplanningdeptt f. CompletetrainingsondifferentcomponentsofB2V4being organizedbyrespectiveDeputyCommissioners g.CollectListofnewworksstarted/ongoing/completedduringthe previousandcurrentFinancialyearunderthefollowingheads: • PRIgrants • DistrictPlan • UTplan • MGNREGA • Otherschemesofotherdepartments • Anyotherwork h. Plans/beneficiarylists: • MGNREGAdraftplandocumentfortheyear2022-23. • ListofAwaas+beneficiariesalongwithIHHL Convergence • Listofpensionbeneficiaries. • ListofSHGs • Listofagricultureschemebeneficiaries i. Listsofbeneficiariesfor: • Variouscertificates/benefitstobedistributedbythe visitingofficer. • Anyotheractivitiesidentifiedbydifferentdepartments |

| Day1 | Reachthevillage | 1. | Ensurethatallfrontlineworkersofdifferentdepttsarepresent. |
| --- | --- | --- | --- |
|  |  | 2. | Ensureexhibitionbydifferentdepts.aboutindividualbeneficiary schemes |
|  |  | 3. | InspectJKB/PSBcounters/outlets |
|  |  | 4. | Participate/ensureorganizationofsportsactivityinplayfield,talent hunt/culturalevent/youthactivity |
|  |  | 5. | GandhiKatha(suggesteddetailsuploadedonjkpanchayat.in) |
|  |  | 6. | Visitatleast2amritsarovarsandgetitsgeotaggedphotos |
|  |  | 7. | InspectKhidmat(CSC)CentresandcreateGenerateawarenesson 225schemesparticularlyG2CschemeslikeBEAMS,Janbhagidari, AapkiZaminAapkiNigrani,DigitalJ&K |
|  |  | 8. | Visitingofficershallalsoplanandconductpanchayatlevelconver- gencemeetingofalldepartments |
|  |  | 9. | CheckeffectivenessofCentrallysponsoredschemes |
|  |  | 10. | VisitandinspectallgovernmentestablishmentsincludingPHE, AWC,FPS,schools,etc |
|  |  | 11. | Attemptsaturationofdeliverableso JanAbhiyanandwherever deficienciesfound,leadadrivetoachievealldeliverables |
|  |  | 12. | Assesseffectivenessofsanitationcampaigninthepanchayat |
|  |  | 13. | Ensureselfemploymentactivitiesfor15youthperpanchayat |
|  |  | 14. | Identify20potentialcandidatesperpanchayatforHIMAYATtraining alongwiththetradeonwhichtheywanttraining |
|  |  | 15. | Whereverpossible,distributeemploymentlettersforpeopleselect- edundervariousgovernmentemployments |
|  |  | 16. | Intheevening,holdnormalmeetingwith seniorcitizens,govtem- ployeesincludingretiredemployees,exservicemen,youthclub,and any citizens ofthevillagewhoareenrolledincollege/university |
|  |  | 17. | OpendiscussiononNashaMuktAbhiyan |

Day2            Haveameetingwithall stakeholders-depttofficials andpanchayatmembers

1.       Discussionontheandassesstheprogressofdifferentschemesrelating tothelocalizedSDGsprioritizedforthatvillageaspertheresolution passedby thatGramPanchayaton21st April22,onNationalPanchayti RajDay.

2.	Sensitizevillage residentsaboutmyScheme”portal(myscheme.in) whichincludesinformationaboutalltheschemesbeingrunbyCen- tral/State/UTgovtacrossthecountry

3.	Hold meeting of theBiodiversityManagementCommitteestodeliber- ateonissuespertaining toconservation of biodiversityandsustaina- bleutilizationof biologicalresources.

4.       PrepareVillagedevelopmentplan,inconsultancywithGrampanchayat, discussitingramsabhaandgetitapproved.

5.       Ensure saturationofsoilhealthcardandgoldenhealthcardunderGold- enHealthCardunderAyushmanBharat,

6.       Ensuresaturation  of OldAge PensionScheme

7.       EnsureDomicileSaturation.

8.       EnsureKCCSaturation

9.       Ensure saturationoflandpassbooks

10.     Ensureregistrationofvillagevendorsneededforanyscheme,onGEM

portal

11.     Ensurepanchayatcontractors registration

12.     EncouragePanchayatmembers forimportanceofplantationdrivein

PanchayatunderHarGaonHariyali

13.     Ensure paintingondigitalJ&Kinpanchayatghars

14.     Ensure paintingonpanchayatactivitesandCSSinpanchayatghars

15.	Thevisiting officeshallchecknoof kindergarten andplayfields present inthepanchayat for kidsandstudents,iftheinfrastructure present inthesearegoodenough.

16.     Holdmeeting withpanchayatmembers todiscussaboutcorruption menaceandstepsrequiredtomakeJ&Kcorruptionfree

17.     Obtaina candidassessmentaboutperformanceofvariousdeptts in- cludingfairfeedbackaboutdiscrepanciesinfunctioning

18.	Check thestatusof NashaMuktAbhiyanandreporting of drugad- dictstoDeputyCommissioner.

19.     IdentifyTouristDestinations,Circuits,ThemeTreks,IdentifyHomestays, providesupportfortourismactivities throughVillageCooperative

20.     OrganizeTalentHuntatPanchayatLevel

21.     Conductsocialauditofatleast5worksunderfollowingschemes:

a.       MGNREGA

b.PMAY

c.        IHHLtoiletsandpayments d.CSCs

e.AMRITSAROVARS

22.     Holda mahilasabha anda balsabhaandrecordproceedingsinthefor- matgiven

23.     InauguratevillagehaatunderJKSRLM

24.     Checkifyouthclubsareformedinthepanchayatandwhatactivities theyareengagedin

25.     Organizea villagelevelculturaleventtoengagepanchayatmembers

26.     SensitizeGPaboutE-kitabkoshaninitiativeofJ&KGovtforempowering youthsthrough onlinedigitalliteracy

GENERALINSTRUCTIONS

1.	Thevisitingofficershallrefrainhimself/herselfgivingorofferinganycommitmentonbehalfofthe governmentandshalladoptanunbiasedattitudeinreportingissues.As faraspossible,his/her observation shouldbebasedona fairandanalytical viewemergingfromhis/herinteractioninthe village.

2.	Heisgoingtothevillageasplanningofficer,notforsanctioninganyworksorformakinganycom- mitments.

3.	Whilepreparingvillagedevelopmentplan,hehastoensurethat,demandsareprioritizedandre- flectedunderavailableschemes,wherevernecessarythelargerworksaretobereferredtoadminis- trativedepttunderCSS/UTplansunderintimationtoDCsandrestoftheworkstoDCsforreflecting itunderdistrict/CSS plans

4.    His workshallbehardcoreplanningandauditandisnota PRexercise.

5.	EveryDeputyCommissionerhastoensurethatatleastoneRDDofficial(ideallyPanchayatSecre- tary)ispresent  ineverypanchayatwithrelevantpanchayatrecords,toensureconductofallactivi- tiesasplanned.Panchayatwiseorderneedstobeissuedinadvance.

6.	Visitingofficershouldideallycarryhis/herlaptoptocompletethereportsatthepanchayatlevel itselfanduploadthefinalreport,duly signedbothbythesarpanchandbythevisitingofficeron www.jkpanchayat.inportal,beforetheyleavepanchayat.

7.	Focus ofvisitareyouth,skills,self-employment,nashamukt,bhrashtracharmukt,Rozgaryukt J&K, besidestocarryforwardtheactivities duringJanAbhiyanandsaturatethem.

8.    Inadditionattentionmaybegiventothefollowingareas a.     MakefulluseofCentrallySponsoredSchemes

b.Saturationofindividualbeneficiaryschemes c.     Self-employmentschemes

d.Banklinkedschemes-includingdepartmentalsubsidyschemes e.Empowermentandtransparencythrough digitalinitiatives

f.       Effectivenessofgrassrootsmachinery–

i.       Patwari,VLWpresent  andavailable

ii.      AvailablefundsutilizedinpublicinterestandasperGramSabharesolutions

iii.   Fairness ingovernance

iv.    CSS/Individual beneficiaryschemesetc

v.      BrashtacharMuktJ&K

vi.   BhaiMuktJ&K

vii.  NashaMuktJ&K

9.	ThePRImembers (Sarpanchs,Panchs,BDCChairperson)shallbeattheforefrontofallactivities and givendueimportanceandtheapproach shouldbetostrengthenthemandmakethemfeelem- powered.He/sheshallensurethattheBDCchairpersonandSarpanch/Panch arepresent  atthetime ofinaugurationandceremonies.

10.	Visitingofficershallnotleavethedistrictwithoutuploadingthereport,duly signedonthewww. jkpanchayat.inportal.EveryDeputyCommissionerhastoensurethat.

A)   DetailsofReportingOfficer:

Name:   Dr. Syed Altaf Gilani

Designation: Poultry Development Officer, Srinagar.

Department/placeof  posting: Animal Huspandry Department, Srinagar.

MobileNo: 9419008623

EmailID: gilanismaltaf@gmail.com

HomeDistrict: Srinagar

Dates of  visit: 2nd and 3rd Nov. 2022

B)	LocationaldetailsofPanchayat:(tobepre-filled,informationtobetakenfromtheprevious phasesbooklets/summarizedexcelsheetuploadedonjkpanchayat.in/b2v4.php)(tobevali- datedbythevisitingofficerandmissingdetailstobefilled)

NameofthePanchayat: Faqir Gujree - B

Local Government Directory (LGD)code of  the Panchayat: 274482

Nameof  CDBlock: Harwan

NameofTehsil: Srinagar North

Nameof    District: Srinagar

C)     PanchayatProfile:

No.of revenue villages in the Panchayat: 01

No. of hamlets in the Panchayat: 01

No .of households in the Panchayat: 217

Population(approx)of  the Panchayat: 2066

Part-II:

(TobefilledupbytheVisitingOfficerduringhis/hertwodayvisittothePanchayat.AllFieldshavetobe

filledbytheVisitingOfficerbeforethebookletishandedovertotheDC

FrontlineOfficers/OfficialswhowereassignedtothePanchayatfortheprogramme:

| Department | Name | Designation |
| --- | --- | --- |
| J&k BANK | Ishtiyaq Ahmad | Branch Head |
| Floriculture | M. Hussain Parray | AFO |
| Sheep Husbandry | Dr. Sumiyah | VAS |
| Fisheries | Masood Ah Dar | F/S |
| Industries | Syed Zeeshan | IPO |
| Mission Shakti | Rehana Qadir | Gender Specialist |
| Labour Department | Abdul Hamid | Labour Inspector |
| Animal Husbandry | M. Saleem Bhat | SVP |
| Apiculture | Sajad Ahmad Wani | Lab. Assistant. |
| DIC | Ishfaq Ah. Wani | Employment Officer |
| Agriculture | Ajaz Ah. Bhat | Ic/ DAEO |
| PHE | Mukhtar Ahmad | Astt. Lineman |
| PDD | Bilal Ah. Bhat | Orderly |

Other Departments present: ICDS, Revenue, Youth Services & Sports, Social forestry, Urban Forestry, PWD, JKSRLM,  Sericulture, Apiculture, I&FC Deptt, CAPD, Geology and Mining

Details of absent employees vis-à-vis list furnished by the DC office:

| Department | Name | Designation |
| --- | --- | --- |
| PMGSY |  |  |
| Tribal Affaires |  |  |
| Skill Dev.& Entrepreneurship |  |  |
| Food Processing industries. |  |  |
| National Disaster Man. Authority |  |  |

DAY1-ACTIVITIES

AGENDA1:PANCHAYATASSETREGISTER

Infrastructure:

1.		PanchayatGharInfrastructure    Not Available

a.  Govtbuilding/private

b.  New/needingrepairs

2.       Furniture(Y/N)    Yes

3.       Computer/printer(Y/N)   No

4.       Internet(Y/N)    No

5.       Telephone(Y/N)    No

6.       Toilet(CSC/part of panchayat ghar)(Y/N )     No

7.       Water(Y/N)    No

8.       Electricity(Y/N)    No

9.       Bank branch(Y/N)    No

10.     CSC(Y/N)    No

11.     Patwarkhana(Y/N)    No

12.     Villagehaat(Y/N)    No

13.     Playground(Y/N)    Yes

14.     School-

a. Kindergarten(Y/N)    Yes

b. Primary(Y/N)    Yes

c. Secondary(Y/N)    No

d. College (Y/N)      No

e.University(Y/N)   No

15.     AnganwadiCentre(Y/N)   Yes

a.  (govt/private)     Private

b. Totalchildrenenrolled    171

15.     Amrit Sarovars–details, location, condition 01 No at Padshapal Dardkhover in Good Condition.

16.     Government offices-details , whether functional or not  NO

17.     Rationshop(Y/N)  Yes

18.      Placesoftourismimportance–names,littledetailsonhistorical/culturalimportance:

Paragliding at Astanmarg.

19.      Village heritage sites/treks-names ,little details on historical/cultural importance:

Mammat, Ladivas and Mahadev.

20.     VLWOffice (Y/N)  Yes

21.     PrimaryHealthcareCentre(Y/N), NO

22.     List of Incomplete Buildings-names, year of construction  Nil

23.     ListofUnderutilizedBuildings-names Nil

DAY1-ACTIVITIES

AGENDA2:

DIFFERENTINSTITUTIONS/INFRASTRUCTUREPROJECTSTOBEVISITED

| AMRITSAROVARS | Visit,verify | COMMENTS |
| --- | --- | --- |
| Khidmat Centres | Create/Generateawarenesson225schemes particularlyG2CschemsAapkiZaminAapkiNigrani, Beams,Janbhagidari,DigitalJ&K | Not Available |
| JKB/PSBcounters/outlets | a)Statusofcounter b)Numberofvisitors | Functional At Site 50 |
| Incompletebuildings/pro- jects | Verify whetheridentificationandredistribution done | Not Applicable |
| PDS | Visit,evaluate,onlinestatus | Requires Additions |
| PHC | Visit-evaluate,statusofstaff,equipmentand quality | Not Available |
| Youthclubs | Meet,interact,seeksuggestions | Interacted, Need Employment |
| SHG | Meet,identifyproblems,seeksuggestions | Interacted Seeks Market |
| PMAY | Inspect,Inaugurate | Only first installment released |
| Myschool,mypride progress;schools-water, toilets,staff | Visit,checkforwater,electricity,sanitation,meet studentsandstaff | Need Kitchen Sheds |
| Swachh SBM | Evaluate | Need more CSC and IHHL units. |
| Panchayatplayground, Sportskitsdistribution Villagegames | Ensure, verify. Participate in at least one game in the playground | Participated in Cricket. |
| Har Gaon Hariyali, Plantation drive | Evaluate status, feedback | Plantation drive held. |
| Village cultural event Dangal/Haat/Mela | Participatein;ensurethatitisheld | Inaugurated. |
| Exhibition of schemes | Ensure that every department participates and that it continues for the entire duration of B2V |  |
| JalJeewanMission verifica- tion- WSS/JSD Electricitysupply | Verify | Panchayat having tap water. Requires more electric poles. |

DAY1-ACTIVITIES

AGENDA3:SATURATEJANBHIYAN

DELIVERABLESANDRECORDDEFICIENCIESIFANY(INSERTDELIVERABLESLISTHEREASPERGADFORMAT

| S.No | DEPARTMENT | WORK/DELIVERABLE | ASSISTED BY | REMARKS |
| --- | --- | --- | --- | --- |
| 1. | RDD | ALL B2V WORKS- Document, Verify, Complete | DC | 100% (as reported by field functionaries present) Accomplished |
|  |  | All GPDPs to be prepared and |  |  |
|  |  | finalised under convergence |  |  |
|  |  | mode |  |  |
|  |  | Panchayat Awards to be finalised |  |  |
|  |  | VILLAGE HAATS –Establish | NRLM |  |
| 2. | IT | - CSC CAMPS- ONE PER PANCHAYAT - ALL 225 ONLINE SERVICES- Popularise, Inform - Beams, Jan Bhagidari- Assist in Access, Demonstrate, Educate, Inform, - Hoardings, Wall Paintings in all Panchayats about Digital J&K and services - Assist in enrollment of user services- Golden Cards, Domiciles, UDID etc | CSC | Accomplished |
| 3. | FINANCE | - SELF EMPLOYMENT TO AT LEAST 15 PERSONS/Panchayat - All INDIVIDUAL SUBSIDY SCHEMES- Counter to be set up by banks at Panchayat level to verify, Sanction, disburse cases and also accept fresh applications - ADHAAR SEEDING OF ALL INDIVIDUAL BENEFICIARY SCHEMES | J&K BANK EDI LABOUR | -- -- |
|  |  |  |  | 100% (As reported by field functionaries present) |

| 4. |  | REVENUE | - APKI ZAMIN APKI NIGRANI- Inform, popularise - PATWAR KHANA- Verify, Establish, Paint information and timings - INHERITANCE MUTATIONS- Complete - LAND PASSBOOKS-generate and Issue for undisputed entries | DC IT CSC | -- -- -- 100% (as reported by Field Staff Present) |
| --- | --- | --- | --- | --- | --- |
| 5. |  | HEALTH | 1)PMJAY GOLDEN CARDS- Saturate | NHM | 100% (as reported by Field Staff Present) |
|  |  |  | 2) Swachh hospitals- clean toilets, junk free premises |  |  |
| 6. |  | SOCIAL WELFARE | - DIVYANG CAMPS- Hold Camps, ensure fittings - DISABILITY CARDS (UDID) – All existing 2.5 lakhs UDID Cards to be made digital - NOAPS/ISSS PENSIONS- Audit, Saturation of wall paintings of pension beneficiaries - POSHAN VATIKA-ensure 100% plantation - 500 ANEMIA CHECK UP CAMPS-Conduct - AADHAR SEEDING- Ladli Beti beneficiaries, Aanganwadi beneficiaries - BBBP events, at least 5 in every district - Formation of Senior Citizens club in every Panchayat | Health | NIL NIL |
|  |  |  |  |  | -- |
|  |  |  |  |  | Available |
|  |  |  |  |  | Done on monthly basis |
|  |  |  |  |  | Done NA NA |
| 7. |  | FOREST | 1) GREEN J&K CAMAPAIGN – Jan Abhiyan - One Village One Beat Guard - Forest for Fodder and livelihood -Complete all preparatory plantation activities in winter Plantation areas - Audit of summer plantation in non summer plantation areas -Saturate |  | Started |
|  |  |  |  |  | ----- |

| 4 8. | TOURISM | - TOURIST DESTINATIONS/CIRCUITS/THE MES TREKS/- Identify, Delineate, Demarcate - HOMESTAYS- Identify - VILLAGE COOPERATIVE- Provide Support for Tourism activities | JKTDC | -- |
| --- | --- | --- | --- | --- |
| 9. | CULTURE | 1) TALENT HUNT AT PANCHAYAT LEVEL - Organise | JKAACL | -- |
| 10. | LABOUR | 1) e- SHRAM- Saturate | CSC | 90% approx. (as reported by field functionaries present) |
| 11. | SCHOOL EDUCATION | - Bringing back all out of school children - MY SCHOOL MY PRIDE- - PARENT TEACHER MEETING |  | 90 % 100% NA |
| 12. | HIGHER EDUCATION | 1) INTRODUCE AND START 30 CREDIT SKILL COURSE IN 50 DEGREE COLLEGES - INTRODUCE RESEARCH UNDER NEP in 30 GDCs - COMPLETE AND Launch HRM MODULE UNDER e-Samarth Gov suite - FEEEDBACK OF 1,00,000 STUDENTS OF GDCs across J&K - MY COLLEGE MY PRIDE- ClEANLINESS Drive in every GDC |  | NA NA NA NA NA |
| 13. | YOUTH AFFAIRS | 1) Games in every Panchayat- Organise |  | Done (as reported by field functionaries present) |
| 14. | TRANSPORT | - COMPLETE SURVEY OF ALL UNDERSERVED AREAS IN THE UT - 100 cases under MUMKIN scheme |  | -- |

| 15 . |  | TRIBAL | - ALL SCHOLARSHIP SCHEMES- Saturate - PLAN FORMULATION OF ALL VILLAGES UNDER PMAAGY (ADARSH GRAM SCHEME) – Complete | CSC | 4 NA |
| --- | --- | --- | --- | --- | --- |
| 16. |  | PDD | 1) DISTRIBUTION TRANSFORMERS- - Check unique no, - identify DTS with low oil and top up, - identify DTs with load imbalance, - replace non standard fuses with standard fuses, - identify DTs without earthing and ensure proper earthing - remove foliage around DTs 2) All cases of electrical accident claims pending to be resolved and put up for disbursement |  | 100 % achieve NIL NIL NIL NIL NA |
| 17. |  | CAPD | - SHIFT TO RATION CARD MANGEMENT SYSTEM (RCMS) - 100% GRIEVANCE REDRESSAL | IT | 100% (as reported by field functionaries present) NA |
| 18. |  | SKILL DEVELOPMENT | 1) SKILL TRAINING OF 13000 HEALTH STAFF AND ACCREDITATION TO NSDC/MSDE 2) COMPLETE ALL ADMISSIONS TO POLYTECHNICS |  | NA NA |
| 19. |  | COOPERATIVES | 1) 25000 COOPERATIVE MEMBERS TO BE TRAINED |  | -- |
| 20. |  | SCIENCE & TECHNOLOGY | 1) Reach out to 10000 farmers for PM KUSUM SCHEME |  | -- |
| 21. |  | PWD | - 100% ONLINE PAYMENTS WITH NO MANUAL INTERFACE- Implement - COMPLETE JKPCC MERGER PROCESS |  | -- |
| 22. |  | ARI &TRAININGS | 1) INSPECTION OF 100 OFFICES AT BLOCK LEVEL- Evaluate quality of work and grievance disposal, record keeping, inventory management |  | - - |

| 23. | MINING | 1) 100% IMPLEMENTTAION OF E- CHALLAN WITH ZERO MANUAL INTERFACE |  | -- |
| --- | --- | --- | --- | --- |
| 24. | DMRR | - DISPOSE OFF ALL PENDING GRIEVANCES on relief commissioner grievances portal - TRAIN 250 APDA MITRAs |  | -- |
| 25. | GAD | - 100% BIOMETRIC ATTENDANCE ENSURE - ENSURE EPM BY ALL EMPLOYEES - 100% PROPERTY RETURNS FILED IN - 100% ONLINE APRs - HRMS IMPLEMENTATION |  | -- |
| 26. | JAL SHAKTI | - ACTIVATE ALL PANI SAMITIS sensitise the local community/Gram Panchayats/Pani Samitis of their role and responsibilities in Planning,Implementation and Monitoring of JJM - Awareness generation regarding mechanism for Water Quality and testing of Water quality using Field Testing Kits (FTKs) as per JJM guidelines. |  | 100% done (as reported by field functionaries present) 100 % done (as reported by field functionaries present) |
| 27. | LAW | 1) 250 Awareness and Assistance camps through Legal Service Authority |  | -- |
| 28. | ESTATES | 1) Identify unauthorized occupants of government accommodation |  | -- |
| 29. | PUBLIC GRIEVANCES | 1) PERCEPTION OF DEPARTMENTS AMONG PUBLIC 2) 50 KEY ISSUES OF CONCERN LEADING TO GRIEVANCES- Identify |  | -- -- |
| 30. | HOSPITALITY | 1) Training of all |  |  |
|  | AND PROTOCOL | employees of the department 2) Introduce and Implement |  | -- |
|  |  | Quality policy for the |  | -- |
|  |  | department |  |  |

| 31. |  | AGRICULTURE AND ALLIED SECTORS | - Individual beneficiary schemes including bank loan schemes Soil Health Cards - 5 KISAN MELAS- Organise | CSC J&K BANK | 100% coverage -- |
| --- | --- | --- | --- | --- | --- |
| 32. |  | FLORICULTURE | 1) TRAINING AND AWARENESS CAMPS FOR 1000 FARMERS IN COMMERCIAL FLORICULTURE- Organise |  | -- |
| 33. |  | INDUSTRIES | - LAND ALLOTTMENT FOR PROJECTS WORTH Rs. 6000 crores - 100% PMEGP TARGETS TO BE ACHIEVED - PREPARATION AND SUBMISSION OF ALL 352 BRAP EVIDENCE POINTS UNDER EODB - CENTRAL INSPECTION SYSTEM TO BE MADE LIVE ONLINE |  |  |
|  |  |  |  |  | Accomplished |

DAY1-ACTIVITIES

AGENDA4:

SELFEMPLOYMENTACTIVITIES

EnsureSelf-employmentactivities foryouth,distributeemploymentlettersforpeopleselectedunder varioussocialschemes(15ISTHETARGETPERPANCHAYAT)

Numberofcasesindifferentcategoriessanctioned:  18 Cases Detailsofthebanksanctioningit:  J&K Bank New Theed, Shalimar Branch

Total amount involved: 40.10 lac

DAY1 ACTIVITIES

AGENDA5

Intheevening,holdinformalmeetings  withseniorcitizens,govtemployees,retdemployees,youthclub andothercitizenswhoareenrolledoncollege/universityandhavediscussiononGandhiKatha,Nasha MuktAbhiyan,corruptionfreegovernance,doublingfarmersincomeandrecordtheproceedings

DAY2

a.       NoofIndividualCompostPitsconstructed 04 b.        No of Individual Soak Pits constructed 04

V.          No.ofBiodiversitymanagementcommitteemeetingsheld: NA

VI.         IsthenameofSarpanchdisplayedoncitizeninformationboardsofallRD&PRschemes:Yes/No Yes

VII.       AreSarpanchsbeinginvolvedinstart/inaugurationofactivities:Yes/No Yes

VIII.      WhethersubjectshavebeenassignedbytheSarpanchtothePanchs:Yes/No Yes

IX.        Whethergrievancesredressalboxisinstalled:Yes/No Yes

X.         No of grievancesreceivedpertainingtoPanchayatlevel:  NIL

XI.        No of grievances disposed of at Panchayat level: NIL

XII.       WhethertheSarpanch/PanchayatSecretaryhavedigitalsignatures:Yes/No Yes

XIII.      WhetherallMGNREGA/14thFCpayments arebeingmadebySarpanchthrough DigitalSignature

Certificate(DSC):Yes/No Yes

HUMAN RESOURCEAVAILABLEATTHEPANCHAYAT LEVEL:

| SRNO. | DEPARTMENTWISESTAFF | NUMBERS |  | NAMES |
| --- | --- | --- | --- | --- |
|  |  | SANCTIONED | ACTUAL |  |
|  | Ruraldevelopmentdepartment: BDO JE GRS TA | 1 1 1 1 | 1 1 0 1 | Raja Majid Iqbal Mudasir Shafi Amir Haroon |
|  | SCHOOLEDUCATION: TEACHER HEADMASTER ANYOTHER | 16 | 16 | M Altaf Koli, Sgakeela Bano, Manzoor Ah Phanbra, Liyaqat Ah Phambra,Ashiq Hussain Khan, Amina Akhtar, Bashir Ah Khan, Riyaz Ah Khatana, Mehraj u Din Ganai, Snobar Aalin, Liyaqat Ali Khan, Bilal Ah. Lone, Showkat Ah Ganai, Dilawar Ah Bajran, Ruksana Qadir,Nusrat Akhtar. Razia Akhtar, ( on leave) Mubeena Akhtar (Deputed) |
|  | JAL JEEVAN: Asstt. Lineman Daily Wager | 2 3 | 2 3 | 1.Gami Bajran, 2.Zubair Ah Bajran 1.Javid Ah Phamda 2.Farooq Ah Bajran 3.M Aslam Bajran |
|  | PDD: LINEMAN JE ANYOTHER/M. R . | 3 1 1 | 3 1 1 | 1. Gh. Hassan Rather 2. M Lateef Khan 3.Bilal Ah Bhat 1.Ms. Kousar Shafi. 1. Gulzar Ah Ganai |
|  | FOOD&CIVILSUPPLIES T.S.O. S.K | 1 1 | 1 1 | Ab Hamid Kutoo Ab Gani Rather |
|  | AGRICULTURE&ANIMALHUSBANDARY: Agriculture: JAEO & GCO Animal Husbandry Sheep Husbandry: In charge and ASM Hoticulture : Tech. IV | 1+1 1 1+2 2 | 2 1 3 2 | 1.Aijaz Ah Bhat 2.Asadullah 1. M Saleem 1. Gulzar Ah Bhat 2. Mudasir Ah 3. Manzoor Ah. Baba. 1. Mohammad Amin 2. Shameem Ahmad. |
|  | SOCIALWELFARE | 0 | 0 | -- |
|  | HEALTH: ASHA ANM/ BHW AYUSHDOCTOR ALLOPATHICDOCTOR | 3 1 - - | 3 1 - - | 1. Naseema Ji (ASHA) 2. Shareefa Ji (ASHA) 3. Shameema Ji (ASHA) 1.Muhammad Hussain. (BHW) |
|  | ANYOTHERDEPARTMENT | 4 | 4 | 1. Syed Yasir Masood (BFO) 2. Shabir Ah Mir 3. Gh. Mohiu Din 4. Riyan Ah Bhat |

DAY2-ACTIVITIES

AGENDANO.1

DiscussionontheandassesstheprogressofdifferentschemesrelatingtothelocalizedSDGsprior-itizedforthatvillageaspertheresolutionpassedbythatGramPanchayaton21stApril22,onNational PanchayatiRajDay(Copyoftheresolutiontobetakenfromwww.jkpanchayat.inportalunderthelinkof GramSwarajMonth)

1.       SDGs AGREED FORTHATVILLAGE,TOBEIMPLEMENTED BYMARCH2024:

2.       STATUSOFWORKSUNDERTHEFOLLOWINGSCHEMES:

1      Cleanandgreenvillage

i.InitiativestakenbythePanchayatformanagingSolidandLiquidWaste Soakage Pit and Compost Pit.

ii.     Initiatives taken by the Panchayat for using green sources of fuel like solar,biogas Solar streat lights installed

iii.  Hasmappingoflanduse,waterbodies,forest,slopes,wetlands,degradedforestwithintheGram

Panchayatbeendone?Yes/No.IfNo,reason,thereof YES

iv.    Has the Climate Resilience Plan been developed for the GP? Yes/No NO

v.     StepstakenbytheGramSabhaabouttheclimatechangemitigationfactorslikereducingenergy consumption,usageoffossilfuels,plastics,non-renewablebuildingmaterialsandalsotopromote measureslikeplantingoftrees,conservingforests,usageofgoodagriculturalpracticeslikedrip irrigation,waterconservationmeasuresandconservationofwetlands.

vi.  Whether schools have started segregating waste YES

vii. Whether schools have their own compost/soakage pitsforsolid/liquidwastemanagement YES

2     Healthyvillage

i)    Aremeetings  relatedtoVillageHealthandSanitationCommitteebeingheldregularly? YES

ii)   DoalltheeligibleindividualsbeenprovidedtheGoldenCard? YES

iii)  ArealltheChildrenbeingimmunizedaspertheSchedulerecommendedbyGovt.ofIndia? YES

iv)  ArealltheeligibleindividualsbeenvaccinatedagainstCOVID-19? YES

v)   DoesGramPanchayatensurethatallpregnantwomenaregettingnecessaryprenatalcheckups? YES

vi)  WhetherallthedeliverieswereInstitutionalizedorconductedbytrainedMidwives? Institutionalized.

3     Watersufficientvillage

i)    DoalltheIHHsintheGramPanchayathavewaterpipelineconnections? YES

ii)   WhetherGramPanchayathastakenstepsforgreywatermanagement.IfYespleasespecify Soakage Pits Constructed

iii)  DoalltheIHHsintheGramPanchayathavetoilets? NA

iv)  ArealltheIHHstoiletsfunctionalornot?  YES

v)   DoalltheSchools/Anganwadicentershavea toiletfacilityornot? YES

vi)  Areallthetoiletsintheschools/Aaganwadifunctionalornot? YES

vii) WhetherGramPachachayatBhawanhasseparate toiletsforwomenornot? NA

4      ChildFriendlyvillage

i)	Doallthechildrenundertheageof0-6yearsbeenenrolledintheAnganwadicentersforpre- schooling?Yes/NO YES

ii)    HowmanyBalSabha’swereorganizedintheGramPanchayat    12----------------

iii)  WhethertheissuesraisedbyBalSabhaareaddressedduringtheGramSabha. Yes/NO YES

iv)	WhetherGramPanchayatistrackingthedatarelatedtodropoutchildrenandchildrenwithirregular attendance?Yes/NO. YES

v)   DoalltheschoolsundertheGramPanchayathaveseparate toiletsforgirlsandboys?Yes/No NA

5      Villagewithgoodgovernance

i)    IsCSClocatedintheGramPanchayatBhawanornot? NA

ii)	IsthelistofbeneficiariesrelatedtotheSchemes/ProgramsdisplayedontheGrampanchayatwallor not? YES

iii)  DoestheGramPanchayathasitsbuildingornot? NO

iv)  IstheGramPanchayatofficefunctionalornot? YES

v)   Aretheactivities approved undertheHalqaPanchayatDevelopmentPlandisplayedontheGram

Panchayatwallornot? YES

vi)  IsSocialAuditofearlierSchemes/Programscarriedoutornot? YES

6      Povertyfreeandenhancedlivelihoodvillage

i)    HasGramPanchayatdevelopedanycriteria fortheidentificationofthepoor?Yes/Noifyesspecify YES

Land Less and Low Income

ii)   HavealltheeligiblehouseholdsregisteredinPDSornot? YES

iii)	HasGramPanchayatprovidedspaceforSelf-helpGroupsinPanchyatGharforholdingmeetings  or not?NA

iv)  HavealltheeligiblehouseholdsbeenregisteredforPensionornot? YES

v)   HasGramPanchayatfacilitatedYouthforSkillEnhancementCoursesandPlacement? NO

vi)  HasJobCardsbeendistributedtoalltheeligibleindividualsunderMGNREGA? YES

vii) HasGramPanchayatfacilitatedSHGsforBankAccountLinkages? YES

7     Socially secured village

i)    WhetherGramPanchayatismaintainingdatarelatedtoDifferentlyAbledPeople? YES

ii)   IsGramPanchayatOffice DisabledFriendlyornot? YES

iii)	Areprovisionsfora separate BudgetundertheResourceEnvelopeforWomenandChildrenmadeor not? NO

iv)	DoalltheSchools intheGramPanchayathavefacilitiesforDifferentlyAbledChildrenliketoilets, barrier-freeaccess,etc.,ornot? NO

v)   Arealltheeligibleindividualsaregettingpensions,likeoldagepension,widowpension,etc? YES

vi)  ArealltheeligiblehouseholdsgettingbenefitsfromIAYornot? YES

8      EngenderedDevelopmentinVillage

i)    HowmanyMahilaSabha’swereorganizedintheGramPanchayat ______4_____

ii)	WhetherSHGsfederationshavebeenprovidedspaceformeetings  inthePanchayatBhawan(Yes/ No) NA

iii)  WhetherGPshavetakenstepsforincreasingwomen’sparticipationinGramSabha(Yes/No) YES

iv)  NumberofwomenbeneficiariesheadedhouseholdscoveredunderPDS

system……30…………………

v)   Numberofbeneficiaries(outoftotaleligiblepopulation)receivingsocialprotectionbenefitsunder

PradhanMantriMatritvaVandanaYojana………35………….

9    Self-sufficientinfrastructureinthevillage

i.	Whether GP has a Community Hall with access to electricity, furniture, water supply, toilet……NA………………….

ii.     Whether the Disaster management plan is available at the GP  Level(Yes/No)  NO

iii.  Whetherchild-friendlyparkwithrequiredfacilitiesisavailableinGP(Yes/No) NO

iv.    WhethertheGPhaseasyaccesstoGodownforstorage(Yes/No) NO

v.     Whetherstreetlightsareprovidedinpublicplacesforensuringsafety(Yes/No) YES

DAY 2 ACTIVITIES

AGENDANO.2

SensitizevillageresidentsaboutmyScheme”portal(myscheme.in)whichincludesinformationaboutall theschemesbeingrunbyCentral/State/UT govtacrossthecountry

(SchemeMaterialavailablefromhttps://jkpanchayat.in/b2v4.php)

DAY2ACTIVITIES

AGENDANO.3

HoldmeetingoftheBiodiversityManagementCommitteestodeliberateonissues pertainingtoconserva- tionofbiodiversityandsustainableutilizationofbiologicalresources.HeshouldcheckPeopleBiodiversity register(PBR)ofthatpanchayatandreviewifBiodiversityManagementCommittee constitutedforthat panchayatis holdingminimum4meetings inayearandmeeting onceinevery3months (RoleofBMC availableathttps://jkpanchayat.in/b2v4.php)

COMMITTEEMEMBERS NA PRESENT

BIODIVERSITYREGISTERPHOTOS

PAST 4MEETINGDETAILS-DATES,MINUTESPHOTOS

DAY2ACTIVITIES

AGENDA 4

Visitingofficershallalsoplanandconductpanchayatlevelconvergencemeeting  ofalldepartmentsand prepareVillagedevelopmentplanforvillage,inconsultancywithGrampanchayat,discussitingram sabhaandgetitapproved.

(GPDPformatavailableonhttps://jkpanchayat.in/b2v4.php)

InadditionGPDPplanshallalsoinclude:

           Tourist places which need to be developed Paragliding at Astanmarg.

           Specificproductwhichneedstobedeveloped

           Tourism-home stays Need to be initiated.

	20 candidatesfortrainingunderHimayatschemealongwithtradeinwhich training is to be given Tourism department requires list of 10 youth as tourist guides for trecking.

DAY2ACTIVITIES

AGENDA5

Ensuresaturationoffollowingschemesandgivestatus:

| NAMEOFTHESCHEME | TOTALELIGIBLE BENEFICIARIESIN THE VILLAGE | TOTALBENEFICIARIESWHO AVAILEDTHEBENEFITSOFTHESCHEME | REASONSFOR PENDENCY |
| --- | --- | --- | --- |
| GoldenHealthCardunder AyushmanBharat | 585 | 585 | 100% coverage |
| Jananisurakshayojana | 24 since April | 24 | 100% |
| OLDAGEpension | 120 | 100% | NIL |
| Widowpension | 15 | 100% | NIL |
| Disabilitypension | 25 | 100% | NIL |
| Domicilecertificate | 650 | 650 | NIL |
| Kisancreditcard | 210 | 62 | Due to less scale of finance in agriculture. |
| PM kisan sammannidhi | 210 | 210 | NIL |

| Landpassbook | 1200 | 1150 | Online generated |
| --- | --- | --- | --- |
| Registrationofvillageven- dorsonGEMportal | NA | NA | NA |
| Registrationofvillagecon- tractorsonjktendersportal | NA | NA | NA |
| Registrationofvillagecon- tractorsonPWDportal | NA | NA | NA |
| Incompletebuildings/pro- jects | NA | NA | NA |

DAY2ACTIVITIES

AGENDA6

NASHAMUKTABHIYAN

1.       Whether gram sabha resolution passed YES

2.       Detailsofactivities conducted Awareness, Pledge ceremony

3.       Whether all activities and GS resolution uploaded on jkpanchayats.in portal  YES

4.       Howmanydrugaddictsinthevillage NIL

5.       WhetherreportedtotheDeputyCommissioner NA

6.       Howmanyregisteredforrehabilitationundergovernmentprogramme NA

DAY2ACTIVITIES

AGENDA7

SOCIALAUDIT

Conductsocialauditofatleast5workseachunderfollowingschemes:

| NAMEOFTHE SCHEME | DETAILSOFTHE WORKS | YEAROFWORK APPROVAL | AMOUNT APPROVED FORTHEWORK | WHETHER WORKEXECUTED SATISFACTORILY | GEO- TAGGED PHOTOS | ANY GRIEVANCE RECORDED RELATINGTOTHAT WORK |
| --- | --- | --- | --- | --- | --- | --- |
| MGNREGA | Development of graveyard at faqir Gujri B | 2021-22 | 4.165 Lac | YES | YES | NO |
| PMAY | - | - | - | - | - | - |
| IHHL UNDERSBM-G | Construction of IHHL unit | 2021-22 | 12000 | YES | YES | NO |
| CSCUNDER SBMG | Construction of CSC at Astanmarg | 2021-22 | 3 Lac | YES | YES | NO |
| AMRIT SAROVARS | Restoration of Spring at Chirandara | 2022-23 | 1.44Lac | YES | YES | NO |

DAY2ACTIVITIES

AGENDA8

MAHILASABHA

Totalwomeninthevillageabovetheageof18

Total attended : 40

Proceedings: Enclosed

(Plinsertpointerstobediscussedthere–referpalliproceedings)

DAY2ACTIVITIES

AGENDA9

BALSABHA

Holda balsabhaandrecordproceedings

Totalchildreninthevillageabovetheageof….. Totalattended : 30

Proceedings: Enclosed

(Plinsertpointerstobediscussedthere–referpalliproceedings)

DAY2ACTIVITIES

AGENDA10

INAUGURATIONS

| SR NO. | ASSETS/ACTIVITIES INAUGRATED | STATUSOFTHEASSET/AC- TIVITIES(NUMBER,OTHER DETAILS) | GEO-TAGGED PHOTOS |
| --- | --- | --- | --- |
|  | VILLAGEHAATunderJKSRLM (SUN- DAYMARKET) | Existing | Done |
|  | PMAYhousesifanyreadyforinaugration | Under Construction | -- |
|  | Swachhgramprojects-segregation shedsetc | NA | -- |
|  | Amritsarovars | Inaugrated | Done |
|  | Sportskits | Nil | -- |
|  | Village cultural events | Nil | -- |
|  | JJMassets/projects | Need RCC Slab of PHE Scheme near Scholar School for cover up | Done |
|  | Anyothertobeidentifiedatdistrict level | -- | -- |

FOLLOW UP OF (B2V1,B2V2&B2V3):

(Prefilledexcelsheet tobetakenfromdistrictlevel/andalsotobedownloaded

fromwww.jkpanchayat.in)

| S.NO. | Particulars | Actiontaken | Remarks# |
| --- | --- | --- | --- |
| I. UrgentPublicRequirements/Demands-B2V1 |  |  |  |
| 1 | General Public Toilet / Installation of lights at graveyard | Not Available |  |
| 2 | Transport facility regularly | Not Available |  |
| 3 | Free Agriculture (availability inputs) | Not Available |  |
| 4 | Health centre with free medicines. | Not Available |  |
| 5 | Panchayatghar / playground / library | Not Available |  |
| 6 | Cow sheds under MGNREGA scheme | Not Available |  |
| 7 | Provision of financial assistance to SHG as the population is mostly BPL category. | Not Available |  |
| II. UrgentPublicRequirements/Demands-B2V2 |  |  |  |
| 1 |  |  |  |
| 2 |  |  |  |
| 3 |  |  |  |
| 4 |  |  |  |
| 5 |  |  |  |
| 6 |  |  |  |
| 7 |  |  |  |
| S.NO. | Particulars | Actiontaken | Remarks# |
| III. MajorProblems–B2V1 |  |  |  |
| 1 | Wild Animals | Not Available |  |
| 2 | Unemployment | Not Available |  |
| 3 | Dogs | Not Available |  |

| 4 | Polen (popular Trees) | Not Available |  |
| --- | --- | --- | --- |
| 5 |  |  |  |
| IV. MajorProblems-B2V2 |  |  |  |
| 1 | Shifting of transformer to Dardkhover | Not Available |  |
| 2 | Providing of lights to graveyard at Masha Pajan. | Not Available |  |
| 3 | Earth filling of graveyard at Mashe Pajan | Not Available |  |
| 4 | Improvement of roads. | Not Available |  |
| 5 |  |  |  |
| V. MajorProblems-B2V3 |  |  |  |
| 1 | NIL |  |  |
| 2 | NIL |  |  |
| 3 | NIL |  |  |
| 4 | NIL |  |  |
| 5 | NIL |  |  |
| VI. MajorComplaints-B2V1 |  |  |  |
| 1 | Unemployment and lack of health centre, bank , ATM Panchayat and Transport facility. | Not Available |  |
| 2 |  |  |  |
| 3 |  |  |  |
| VII. MajorComplaints-B2V2 |  |  |  |
| 1 | Drainage Roads and retaining wall for heavy snowfall | Not Available |  |
| 2 | Problem faced by concerned Pathwari | Not Available |  |
| 3 |  |  |  |
| VIII. MajorComplaints-B2V3 |  |  |  |
| 1 | Lack of cooperation from the bank branch | Not Available |  |
| 2 | Lack of adequate staff at PSM Dispensary | Not Available |  |
| 3 | A bulk of labour class are figuring in APL category of FCS and CA department. | Not Available |  |
| 4 | Pendency of SRO43 cases | Not Available |  |

OVERALLPERCEPTIONOFFUCNTIONING OF GOVERNMENTDEPARTMENTS

1.         BEST DEPARTMENT: RDD

2.       LEASTRESPONSIVEDEPARTMENT: Tribal Affaires

GENERALASSESSMENTOFTHEVISTINGOFFICER

| I | AnymajorcomplaintbroughttothenoticeoftheVisitingOfficer: Home Delivery of LPG Gas Cylinders |
| --- | --- |
| II | Major/urgentpublicdemandsthatwas/werereflectedearlierbuthavenotbeenaddressedsofar: ATM/Extention office of J&K bank |
| III | Overallassessmentofthevisitandsuggestions: Verymuch beneficial if followed up (Thevisitingofficertoensurethattheoverallassessmentisrecordedindetailsalongwithconcretesugges- tions) |
| IV | OverallRatingofgovtfunctioningas givenbythePanchayat(Scaleof0to10) 07 |
| V | CertificatefromSarpanchthatthevisitingofficerhasstayedinthepanchayatfor2days YES |

SignatureofSarpanch                                                                              SignatureoftheVisitingOfficer

Name………………………                                                                               Name………………………

DepartmentofRuralDevelompentandPanchayatiRaj

GovernmentofJammu &Kashmir