4





**15TH OCTto3RD NOV,2022**

**KEYFEATURES**

• DeputyCommissionerstoleadtheinitiative

• RuraldevelopmentDepartmenttobethenodaldepartment

• PlanningDevelopment&MonitoringdepartmentandITtobethesupport departments

**ACTIONSANDTIMELINES**

|  |  |  |  |
| --- | --- | --- | --- |
| **ACTION** | **RESPONSIBILITY** | **LATESTBY** | **REMARKS** |
| **Janabhiyan** | Alldepartments | Oct15-26th | Goingon |
| **DeputationofSecttstaff/ HoDs** | GAD | Oct14 | Done |
| **DeploymentofStaffto Panchayatsandservingof ordersondeployedofficers** | DCs | Oct25 | DCswilldeployseniorlevelstaff fromthedistricts.Strictactionto betakenagainstabstentions.No exemptionstobegiven |
| **Trainingofdistricttrainors onB2V4** | RDD | Oct26 |  |
| **Trainingofvisitingofficers** | DCs | Oct27 |  |
| **FieldVisitstobecompleted by** | VisitingOfficers | Nov3 | DCstosuperviseandensurethat eachPanchayatisvisitedwithin theperiodspecified |
| **DataofB2V4tobe uploadedby** | VisitingOfficers | Nov10 | DCstosuperviseandensurethat dataofallPanchayatsisupload- edbythevisitingofficerwithin theperiodspecified |

**INSTRUCTIONSFORTHEVISITINGOFFICER(DAYWISE)**

|  |  |  |
| --- | --- | --- |
| **DATE** | **INSTRUCTIONS** | **ACTIONPOINTS** |
| **Day0** | Meetingwithdeputy commissionerandhis/her team | a. TakeprintoutsoffilledbookletsofB2V1,B2V2andB2V3from [www.jkpanchayat.in](http://www.jkpanchayat.in)b.Alsotakeprintoutsofthesummarizedexcelsheetsofthe previousphasesfrom[www.jkpanchayat.in](http://www.jkpanchayat.in)c. CollectATRsonissuesraisedduringprevious3phasesfromthe officeofDeputyCommissioner(Planningdeptt)d.Takeprintsofblank 2bookletsofB2V4from[www.jkpanchayat.in](http://www.jkpanchayat.in)e.Takeplansfor2previousyearsandATRsfromtheplanningdeptt f. CompletetrainingsondifferentcomponentsofB2V4beingorganizedbyrespectiveDeputyCommissionersg.CollectListofnewworksstarted/ongoing/completedduringthe previousandcurrentFinancialyearunderthefollowingheads:• PRIgrants• DistrictPlan• UTplan• MGNREGA• Otherschemesofotherdepartments• Anyotherworkh. Plans/beneficiarylists:• MGNREGAdraftplandocumentfortheyear2022-23.• ListofAwaas+beneficiariesalongwithIHHL Convergence• Listofpensionbeneficiaries.• ListofSHGs• Listofagricultureschemebeneficiariesi. Listsofbeneficiariesfor:• Variouscertificates/benefitstobedistributedbythe visitingofficer.• Anyotheractivitiesidentifiedbydifferentdepartments |

|  |  |  |  |
| --- | --- | --- | --- |
| **Day1** | Reachthevillage | 1. | Ensurethatallfrontlineworkersofdifferentdepttsarepresent. |
|  |  | 2. | Ensureexhibitionbydifferentdepts.aboutindividualbeneficiary schemes |
|  |  | 3. | InspectJKB/PSBcounters/outlets |
|  |  | 4. | Participate/ensureorganizationofsportsactivityinplayfield,talent hunt/culturalevent/youthactivity |
|  |  | 5. | GandhiKatha(suggesteddetailsuploadedonjkpanchayat.in) |
|  |  | 6. | Visitatleast2amritsarovarsandgetitsgeotaggedphotos |
|  |  | 7. | InspectKhidmat(CSC)CentresandcreateGenerateawarenesson225schemesparticularlyG2CschemeslikeBEAMS,Janbhagidari, AapkiZaminAapkiNigrani,DigitalJ&K |
|  |  | 8. | Visitingofficershallalsoplanandconductpanchayatlevelconver- gencemeetingofalldepartments |
|  |  | 9. | CheckeffectivenessofCentrallysponsoredschemes |
|  |  | 10. | VisitandinspectallgovernmentestablishmentsincludingPHE, AWC,FPS,schools,etc |
|  |  | 11. | Attemptsaturationofdeliverableso JanAbhiyanandwherever deficienciesfound,leadadrivetoachievealldeliverables |
|  |  | 12. | Assesseffectivenessofsanitationcampaigninthepanchayat |
|  |  | 13. | Ensureselfemploymentactivitiesfor15youthperpanchayat |
|  |  | 14. | Identify20potentialcandidatesperpanchayatforHIMAYATtraining alongwiththetradeonwhichtheywanttraining |
|  |  | 15. | Whereverpossible,distributeemploymentlettersforpeopleselect- edundervariousgovernmentemployments |
|  |  | 16. | Intheevening,holdnormalmeetingwith seniorcitizens,govtem- ployeesincludingretiredemployees,exservicemen,youthclub,and any citizens ofthevillagewhoareenrolledincollege/university |
|  |  | 17. | OpendiscussiononNashaMuktAbhiyan |

Day2 Haveameetingwithall stakeholders-depttofficials andpanchayatmembers

1. Discussionontheandassesstheprogressofdifferentschemesrelating tothelocalizedSDGsprioritizedforthatvillageaspertheresolution passedby thatGramPanchayaton21st April22,onNationalPanchayti RajDay.

2. Sensitizevillage residentsaboutmyScheme”portal(myscheme.in) whichincludesinformationaboutalltheschemesbeingrunbyCen- tral/State/UTgovtacrossthecountry

3. Hold meeting of theBiodiversityManagementCommitteestodeliber- ateonissuespertaining toconservation of biodiversityandsustaina- bleutilizationof biologicalresources.

4. PrepareVillagedevelopmentplan,inconsultancywithGrampanchayat, discussitingramsabhaandgetitapproved.

5. Ensure saturationofsoilhealthcardandgoldenhealthcardunderGold- enHealthCardunderAyushmanBharat,

6. Ensuresaturation of OldAge PensionScheme

7. EnsureDomicileSaturation.

8. EnsureKCCSaturation

9. Ensure saturationoflandpassbooks

10. Ensureregistrationofvillagevendorsneededforanyscheme,onGEM

portal

11. Ensurepanchayatcontractors registration

12. EncouragePanchayatmembers forimportanceofplantationdrivein

PanchayatunderHarGaonHariyali

13. Ensure paintingondigitalJ&Kinpanchayatghars

14. Ensure paintingonpanchayatactivitesandCSSinpanchayatghars

15. Thevisiting officeshallchecknoof kindergarten andplayfields present inthepanchayat for kidsandstudents,iftheinfrastructure present inthesearegoodenough.

16. Holdmeeting withpanchayatmembers todiscussaboutcorruption menaceandstepsrequiredtomakeJ&Kcorruptionfree

17. Obtaina candidassessmentaboutperformanceofvariousdeptts in- cludingfairfeedbackaboutdiscrepanciesinfunctioning

18. Check thestatusof NashaMuktAbhiyanandreporting of drugad- dictstoDeputyCommissioner.

19. IdentifyTouristDestinations,Circuits,ThemeTreks,IdentifyHomestays, providesupportfortourismactivities throughVillageCooperative

20. OrganizeTalentHuntatPanchayatLevel

21. Conductsocialauditofatleast5worksunderfollowingschemes:

a. MGNREGA

b.PMAY

c. IHHLtoiletsandpayments d.CSCs

e.AMRITSAROVARS

22. Holda mahilasabha anda balsabhaandrecordproceedingsinthefor- matgiven

23. InauguratevillagehaatunderJKSRLM

24. Checkifyouthclubsareformedinthepanchayatandwhatactivities theyareengagedin

25. Organizea villagelevelculturaleventtoengagepanchayatmembers

26. SensitizeGPaboutE-kitabkoshaninitiativeofJ&KGovtforempowering youthsthrough onlinedigitalliteracy

**GENERALINSTRUCTIONS**

1. Thevisitingofficershallrefrainhimself/herselfgivingorofferinganycommitmentonbehalfofthe governmentandshalladoptanunbiasedattitudeinreportingissues.As faraspossible,his/her observation shouldbebasedona fairandanalytical viewemergingfromhis/herinteractioninthe village.

2. Heisgoingtothevillageasplanningofficer,notforsanctioninganyworksorformakinganycom- mitments.

3. Whilepreparingvillagedevelopmentplan,hehastoensurethat,demandsareprioritizedandre- flectedunderavailableschemes,wherevernecessarythelargerworksaretobereferredtoadminis- trativedepttunderCSS/UTplansunderintimationtoDCsandrestoftheworkstoDCsforreflecting itunderdistrict/CSS plans

4. His workshallbehardcoreplanningandauditandisnota PRexercise.

5. EveryDeputyCommissionerhastoensurethatatleastoneRDDofficial(ideallyPanchayatSecre- tary)ispresent ineverypanchayatwithrelevantpanchayatrecords,toensureconductofallactivi- tiesasplanned.Panchayatwiseorderneedstobeissuedinadvance.

6. Visitingofficershouldideallycarryhis/herlaptoptocompletethereportsatthepanchayatlevel itselfanduploadthefinalreport,duly signedbothbythesarpanchandbythevisitingofficeron [www.jkpanchayat.in](http://www.jkpanchayat.in)portal,beforetheyleavepanchayat.

7. Focus ofvisitareyouth,skills,self-employment,nashamukt,bhrashtracharmukt,Rozgaryukt J&K, besidestocarryforwardtheactivities duringJanAbhiyanandsaturatethem.

8. Inadditionattentionmaybegiventothefollowingareas a. MakefulluseofCentrallySponsoredSchemes

b.Saturationofindividualbeneficiaryschemes c. Self-employmentschemes

d.Banklinkedschemes-includingdepartmentalsubsidyschemes e.Empowermentandtransparencythrough digitalinitiatives

f. Effectivenessofgrassrootsmachinery–

i. Patwari,VLWpresent andavailable

ii. AvailablefundsutilizedinpublicinterestandasperGramSabharesolutions iii. Fairness ingovernance

iv. CSS/Individual beneficiaryschemesetc v. BrashtacharMuktJ&K

vi. BhaiMuktJ&K

vii. NashaMuktJ&K

9. ThePRImembers (Sarpanchs,Panchs,BDCChairperson)shallbeattheforefrontofallactivities and givendueimportanceandtheapproach shouldbetostrengthenthemandmakethemfeelem- powered.He/sheshallensurethattheBDCchairpersonandSarpanch/Panch arepresent atthetime ofinaugurationandceremonies.

10. Visitingofficershallnotleavethedistrictwithoutuploadingthereport,duly signedonthe**www. jkpanchayat.in**portal.EveryDeputyCommissionerhastoensurethat.

**A) DetailsofReportingOfficer:**

Name: ABDUL HAFIZ BUTT

Designation: SENIOR LECTURER

Department/placeof posting: School education/bhss Chadoora

MobileNo: 9149775745

EmailID: abdulhafiz6215@gmail.com

HomeDistrict: Doda

Datesof visit: 2nd and 3rd Nov 2022

**B) LocationaldetailsofPanchayat:(tobepre-filled,informationtobetakenfromtheprevious phasesbooklets/summarizedexcelsheetuploadedonjkpanchayat.in/b2v4.php)(tobevali- datedbythevisitingofficerandmissingdetailstobefilled)**

NameofthePanchayat: Nowhar

LocalGovernmentDirectory(LGD)codeof thePanchayat: 241506

Nameof CDBlock: Surasyar

NameofTehsil: Chadoora

Nameof District: Budagam

**C) PanchayatProfile:**

No.ofrevenuevillagesinthePanchayat:df 02

No.ofhamletsinthePanchayat: 07

No.ofhouseholdsinthePanchayat: 250

Population(approx)of thePanchayat: 1360

**Part-II:**

(TobefilledupbytheVisitingOfficerduringhis/hertwodayvisittothePanchayat.AllFieldshavetobe

filledbytheVisitingOfficerbeforethebookletishandedovertotheDC

**FrontlineOfficers/OfficialswhowereassignedtothePanchayatfortheprogramme:**

|  |  |  |
| --- | --- | --- |
| Department | Name | Designation |
| Heath | Dr Seema Qadri | Dental Surgeon |
| Animal Husbandary | Javid Ramzan | Supervisor |
| Handicraft | Sharief Ud Din Jahara | OCC |
| Forest | Ab Rehman Raina | Foretor |
| Agriculture | Altaf Hussain Raina | I/C MR |
| PDD | Gh Nabi Dar | AEA |
| R &B | Mohd Shafi Mir | Works Supervisor |
| Sheep Husbandary | Gh Nabi Bhat | Supervisor |
| Education | Mohd Latief Sheikh | Teacher |
| ICDS | Mumtaza Bano | Supervisor |
| Jal Shakti | GH Mohd Sheikh | ASSL |
| FCS&CA | Shabir Ahmad Shah | ASK |
| J and K NBank | Javid Yaqoob | BA |
|  |  |  |

**Detailsofabsentemployeesvis-à-vislistfurnishedbytheDCoffice:**

|  |  |  |
| --- | --- | --- |
| Department | Name | Designation |
|  |  |  |
|  |  |  |
|  |  |  |
|  |  |  |
|  |  |  |
|  |  |  |
|  |  |  |
|  |  |  |
|  |  |  |
|  |  |  |
|  |  |  |
|  |  |  |
|  |  |  |
|  |  |  |
|  |  |  |

**DAY1-ACTIVITIES**

**AGENDA1:PANCHAYATASSETREGISTER**

**Infrastructure:**

1. PanchayatGharInfrastructure a. Govtbuilding/private Govt

b. New/needingrepairs

2. Furniture(Y/N) Yes

3. Computer/printer(Y/N) Yes

4. Internet(Y/N) Yes

5. Telephone(Y/N) No

6. Toilet(CSC/partofpanchayatghar)(Y/N) No

7. Water(Y/N) NO

8. Electricity(Y/N) NO

9. Bankbranch(Y/N) No

10. CSC(Y/N) Yes

11. Patwarkhana(Y/N) No

12. Villagehaat(Y/N) No

13. Playground(Y/N) Yes

14. School-

a. Kindergarten(Y/N) No

b.Primary(Y/N) Yes

c. Secondary(Y/N) No

d. College (Y/N) No

e.University(Y/N) No

15. AnganwadiCentre(Y/N) Yes

a. (govt/private) Private

b.Totalchildrenenrolled 106

15. AmritSarovars–details,location,condition Nil

16. Governmentoffices-details,whetherfunctionalornot

17. Rationshop(Y/N) Yes

18. Placesoftourismimportance–names,littledetailsonhistorical/culturalimportance Near Fishries Farm

19. Villageheritagesites/treks-names,littledetailson historical/culturalimportance Nil

20. VLWOffice (Y/N) Yes

21. PrimaryHealthcareCentre(Y/N), No

22. ListofIncompleteBuildings-names,yearofconstruction Nil

23. ListofUnderutilizedBuildings-namesNil

**DAY1-ACTIVITIES**

**AGENDA2:**

**DIFFERENTINSTITUTIONS/INFRASTRUCTUREPROJECTSTOBEVISITED**

|  |  |  |
| --- | --- | --- |
| **AMRITSAROVARS** | **Visit,verify** | **COMMENTS** |
| KhidmatCentres | Create/Generateawarenesson225schemes particularlyG2CschemsAapkiZaminAapkiNigrani, Beams,Janbhagidari,DigitalJ&K | Not Available |
| JKB/PSBcounters/outlets | a)Statusofcounter b)Numberofvisitors | NA |
| Incompletebuildings/pro- jects | Verify whetheridentificationandredistribution done | Nowhar Bridge |
| PDS | Visit,evaluate,onlinestatus | 95%online |
| PHC | Visit-evaluate,statusofstaff,equipmentand quality | NA |
| Youthclubs | Meet,interact,seeksuggestions | Demanded play field |
| SHG | Meet,identifyproblems,seeksuggestions | Demanded tailoring center |
| PMAY | Inspect,Inaugurate | NA |
| Myschool,mypride progress;schools-water, toilets,staff | Visit,checkforwater,electricity,sanitation,meet studentsandstaff | Facility available, needs repairment  |
| SwachhSBM | Evaluate | Under Process |
| Panchayatplayground, Sportskitsdistribution Villagegames | Ensure,verify.Participateinatleastonegamein theplayground | Participated in cricket with the students  |
| HarGaonHariyali, Planta- tiondrive | Evaluatestatus,feedback | Yes, done |
| VillageculturaleventDangal/Haat/Mela | Participatein;ensurethatitisheld | Yes done |
| Exhibitionofschemes | Ensurethateverydepartmentparticipatesand thatitcontinuesfortheentiredurationofB2V | Yes |
| JalJeewanMission verifica- tion- WSS/JSDElectricitysupply | Verify | Needs more pipes/HT/LT poles |

**DAY1-ACTIVITIES**

**AGENDA3:SATURATEJANBHIYAN**

**DELIVERABLESANDRECORDDEFICIENCIESIFANY(INSERTDELIVERABLESLISTHEREASPERGADFORMAT**

**DAY1-ACTIVITIES**

**AGENDA4:**

**SELFEMPLOYMENTACTIVITIES**

EnsureSelf-employmentactivities foryouth,distributeemploymentlettersforpeopleselectedunder varioussocialschemes(15ISTHETARGETPERPANCHAYAT)

**Numberofcasesindifferentcategoriessanctioned:11 Detailsofthebanksanctioningit: J&K Bank Dadaompora**

**Totalamountinvolved:63.40 Lacs**

**DAY1ACTIVITIES**

**AGENDA5**

Intheevening,holdinformalmeetings withseniorcitizens,govtemployees,retdemployees,youthclub andothercitizenswhoareenrolledoncollege/universityandhavediscussiononGandhiKatha,Nasha MuktAbhiyan,corruptionfreegovernance,doublingfarmersincomeandrecordtheproceedings

**DAY2**

a. NoofIndividualCompostPitsconstructed7 b.NoofIndividualSoakPitsconstructed18

V. No.ofBiodiversitymanagementcommitteemeetingsheld:1

VI. IsthenameofSarpanchdisplayedoncitizeninformationboardsofallRD&PRschemes:Yes/No Yes

VII. AreSarpanchsbeinginvolvedinstart/inaugurationofactivities:Yes/No Yes

VIII. WhethersubjectshavebeenassignedbytheSarpanchtothePanchs:Yes/No Yes

IX. Whethergrievancesredressalboxisinstalled:Yes/No Yes

X. NoofgrievancesreceivedpertainingtoPanchayatlevel:3 XI. NoofgrievancesdisposedofatPanchayatlevel:3

XII. WhethertheSarpanch/PanchayatSecretaryhavedigitalsignatures:Yes/No Yes

XIII. WhetherallMGNREGA/14thFCpayments arebeingmadebySarpanchthrough DigitalSignature

Certificate(DSC):Yes/No Yes

**HUMAN RESOURCEAVAILABLEATTHEPANCHAYAT LEVEL:**

|  |  |  |  |
| --- | --- | --- | --- |
| **SRNO.** | **DEPARTMENTWISESTAFF** | **NUMBERS** | **NAMES** |
|  |  | SANCTIONED | ACTUAL |  |
|  | Ruraldevelopmentdepartment: BDOJE GRS TA | 01010101 | 01010101 | Dr Mudasir hmadZubair ul BashirRumysa Rafiq Shabir Ahmad Bhat |
|  | SCHOOLEDUCATION: TEACHERHEADMASTER ANYOTHER | 1104 | 1104 | Dilshada BanoMohd LatiefAltaf Huissain |
|  | JAL JEEVAN: | 02 | 02 | GH Mohd SheikhAb Rehman Sheikh |
|  | PDD: LINEMAN JEANYOTHER | 010101 | 010101 | Mohd Latief DarBilal Ahmad MirGh Nabi Dar |
|  | FOOD&CIVILSUPPLIES | 01 | 01 | Shabir Ahmad Shah |
|  | AGRICULTURE&ANIMALHUS- BANDARY | 01 | 01 | Altaf Hussain |
|  | SOCIALWELFARE | Nil | Nil |  |
|  | HEALTH: ASHA ANMAYUSHDOCTOR ALLOPATHICDOCTOR | 02NilNILNil | 02NilNilNil | Hajira / Mehmooda |
|  | ANYOTHERDEPARTMENT(Irrigation) | 02 | 02 | Bashir Ahmad Bhat/Mohd Yousuf Bhat |

**DAY2-ACTIVITIES**

**AGENDANO.1**

DiscussionontheandassesstheprogressofdifferentschemesrelatingtothelocalizedSDGsprior-itizedforthatvillageaspertheresolutionpassedbythatGramPanchayaton21stApril22,onNational PanchayatiRajDay(Copyoftheresolutiontobetakenfrom[www.jkpanchayat.in](http://www.jkpanchayat.in)portalunderthelinkof GramSwarajMonth)

1. SDGs AGREED FORTHATVILLAGE,TOBEIMPLEMENTED BYMARCH2024:Yes

2. STATUSOFWORKSUNDERTHEFOLLOWINGSCHEMES:

**1 Cleanandgreenvillage**

i.InitiativestakenbythePanchayatformanagingSolidandLiquidWaste Yes

ii. InitiativestakenbythePanchayatforusinggreensourcesoffuellikesolar,biogas

 Nil

iii. Hasmappingoflanduse,waterbodies,forest,slopes,wetlands,degradedforestwithintheGram

Panchayatbeendone?Yes/No.IfNo,reason,thereof Partially done

iv. HastheClimateResiliencePlanbeendevelopedfortheGP?Yes/No No

v. StepstakenbytheGramSabhaabouttheclimatechangemitigationfactorslikereducingenergy consumption,usageoffossilfuels,plastics,non-renewablebuildingmaterialsandalsotopromote measureslikeplantingoftrees,conservingforests,usageofgoodagriculturalpracticeslikedrip irrigation,waterconservationmeasuresandconservationofwetlands. Partially done

vi. Whetherschoolshavestartedsegregatingwaste Yes

vii. Whetherschoolshavetheirowncompost/soakagepitsforsolid/liquidwastemanagement No

**2 Healthyvillage**

i) Aremeetings relatedtoVillageHealthandSanitationCommitteebeingheldregularly? Yes

ii) DoalltheeligibleindividualsbeenprovidedtheGoldenCard? 96% Achieved

iii) ArealltheChildrenbeingimmunizedaspertheSchedulerecommendedbyGovt.ofIndia? Yes

iv) ArealltheeligibleindividualsbeenvaccinatedagainstCOVID-19? Yes

v) DoesGramPanchayatensurethatallpregnantwomenaregettingnecessaryprenatalcheckups? Yes

vi) WhetherallthedeliverieswereInstitutionalizedorconductedbytrainedMidwives? Yes

**3 Watersufficientvillage**

i) DoalltheIHHsintheGramPanchayathavewaterpipelineconnections? Yes

ii) WhetherGramPanchayathastakenstepsforgreywatermanagement.IfYespleasespecifyYes

iii) DoalltheIHHsintheGramPanchayathavetoilets? Yes

iv) ArealltheIHHstoiletsfunctionalornot?NO

v) DoalltheSchools/Anganwadicentershavea toiletfacilityornot? Yes

vi) Areallthetoiletsintheschools/Aaganwadifunctionalornot? No

vii) WhetherGramPachachayatBhawanhasseparate toiletsforwomenornot?

Yes

**4 ChildFriendlyvillage**

i) Doallthechildrenundertheageof0-6yearsbeenenrolledintheAnganwadicentersforpre- schooling?Yes/NO Yes

ii) HowmanyBalSabha’swereorganizedintheGramPanchayat------01-------------

iii) WhethertheissuesraisedbyBalSabhaareaddressedduringtheGramSabha. Yes/NO Yes

iv) WhetherGramPanchayatistrackingthedatarelatedtodropoutchildrenandchildrenwithirregular attendance?Yes/NO. Yes

v) DoalltheschoolsundertheGramPanchayathaveseparate toiletsforgirlsandboys?Yes/No Yes

**5 Villagewithgoodgovernance**

i) IsCSClocatedintheGramPanchayatBhawanornot? Yes

ii) IsthelistofbeneficiariesrelatedtotheSchemes/ProgramsdisplayedontheGrampanchayatwallor not?Yes

iii) DoestheGramPanchayathasitsbuildingornot? Yes

iv) IstheGramPanchayatofficefunctionalornot?No

v) Aretheactivities approved undertheHalqaPanchayatDevelopmentPlandisplayedontheGram

Panchayatwallornot?Yes

vi) IsSocialAuditofearlierSchemes/Programscarriedoutornot? Yes

**6 Povertyfreeandenhancedlivelihoodvillage**

1. HasGramPanchayatdevelopedanycriteria fortheidentificationofthepoor?Yes/NoifyesspecifyNo

 ii) HavealltheeligiblehouseholdsregisteredinPDSornot? Partially registered

iii) HasGramPanchayatprovidedspaceforSelf-helpGroupsinPanchyatGharforholdingmeetings or not?Yes

iv) HavealltheeligiblehouseholdsbeenregisteredforPensionornot? Partially registered

v) HasGramPanchayatfacilitatedYouthforSkillEnhancementCoursesandPlacement?Yes

vi) HasJobCardsbeendistributedtoalltheeligibleindividualsunderMGNREGA?Yes

vii) HasGramPanchayatfacilitatedSHGsforBankAccountLinkages?Yes

**7 Sociallysecuredvillage**

i) WhetherGramPanchayatismaintainingdatarelatedtoDifferentlyAbledPeople? Yes

ii) IsGramPanchayatOffice DisabledFriendlyornot? Ys

iii) Areprovisionsfora separate BudgetundertheResourceEnvelopeforWomenandChildrenmadeor not?No

iv) DoalltheSchools intheGramPanchayathavefacilitiesforDifferentlyAbledChildrenliketoilets, barrier-freeaccess,etc.,ornot?No

v) Arealltheeligibleindividualsaregettingpensions,likeoldagepension,widowpension,etc?Yes

vi) ArealltheeligiblehouseholdsgettingbenefitsfromIAYornot?

Partially Benifitted

**8 EngenderedDevelopmentinVillage**

i) HowmanyMahilaSabha’swereorganizedintheGramPanchayat 05

ii) WhetherSHGsfederationshavebeenprovidedspaceformeetings inthePanchayatBhawan(Yes/ No) Yes

iii) WhetherGPshavetakenstepsforincreasingwomen’sparticipationinGramSabha(Yes/No)Yes

iv) NumberofwomenbeneficiariesheadedhouseholdscoveredunderPDS 14

v) Numberofbeneficiaries(outoftotaleligiblepopulation)receivingsocialprotectionbenefitsunder

PradhanMantriMatritvaVandanaYojana 39

9 Self-sufficientinfrastructureinthevillage

i. WhetherGPhasa CommunityHallwithaccesstoelectricity,furniture,watersupply, toilet No

ii. WhethertheDisastermanagementplanisavailableattheGPLevel(Yes/No) No

 iii. Whetherchild-friendlyparkwithrequiredfacilitiesisavailableinGP(Yes/No) No

 iv. WhethertheGPhaseasyaccesstoGodownforstorage(Yes/No) No

v. Whetherstreetlightsareprovidedinpublicplacesforensuringsafety(Yes/No)Yes

**DAY2ACTIVITIES**

**AGENDANO.2**

SensitizevillageresidentsaboutmyScheme”portal(myscheme.in)whichincludesinformationaboutall theschemesbeingrunbyCentral/State/UT govtacrossthecountry

*(SchemeMaterialavailablefromhttps://jkpanchayat.in/b2v4.php)*

**DAY2ACTIVITIES**

**AGENDANO.3**

HoldmeetingoftheBiodiversityManagementCommitteestodeliberateonissues pertainingtoconserva- tionofbiodiversityandsustainableutilizationofbiologicalresources.HeshouldcheckPeopleBiodiversity register(PBR)ofthatpanchayatandreviewifBiodiversityManagementCommittee constitutedforthat panchayatis holdingminimum4meetings inayearandmeeting onceinevery3months *(RoleofBMC availableathttps://jkpanchayat.in/b2v4.php)*

COMMITTEEMEMBERS7PRESENT 7

BIODIVERSITYREGISTERPHOTOS NA

PAST 4MEETINGDETAILS-DATES,MINUTESPHOTOS NA

**DAY2ACTIVITIES**

**AGENDA4**

Visitingofficershallalsoplanandconductpanchayatlevelconvergencemeeting ofalldepartmentsand prepareVillagedevelopmentplanforvillage,inconsultancywithGrampanchayat,discussitingram sabhaandgetitapproved.

(GPDPformatavailableonhttps://jkpanchayat.in/b2v4.php)

**InadditionGPDPplanshallalsoinclude:**

 Touristplaceswhichneedtobedeveloped Yes near fisheries farm

 Specificproductwhichneedstobedeveloped Apple wallnur maize

 Tourism-homestays NIL

 20candidatesfortrainingunderHimayatschemealongwithtradeinwhich trainingistobegiven List enclosed

**DAY2ACTIVITIES**

**AGENDA5**

Ensuresaturationoffollowingschemesandgivestatus:

|  |  |  |  |
| --- | --- | --- | --- |
| **NAMEOFTHESCHEME** | **TOTALELIGIBLE BENEFICIARIESIN THE VILLAGE** | **TOTALBENEFICIARIESWHO AVAILEDTHEBENEFITSOFTHESCHEME** | **REASONSFOR PENDENCY** |
| GoldenHealthCardunderAyushmanBharat | 1233 | 1170 | Adhar issue |
| Jananisurakshayojana | 201 | 06 | Only for 1st child |
| OLDAGEpension | 92 | 92 | 100% |
| Widowpension | 16 | 16 | 100% |
| Disabilitypension | 16 | 16 | 1005 |
| Domicilecertificate | 1233 | 903 |  Under Process |
| Kisancreditcard | 233 | 56 | Disinterested |
| PMkisansammannidhi | 87 | 87 | 100% |

|  |  |  |  |
| --- | --- | --- | --- |
| Landpassbook | 652 | 10 | Generated , distribution under process |
| Registrationofvillageven- dorsonGEMportal | Nil | NIl |  |
| Registrationofvillagecon- tractorsonjktendersportal | 150 (Approx) | 04 | Disinterested |
| Registrationofvillagecon- tractorsonPWDportal | Nil | Nil | Nil |
| Incompletebuildings/pro- jects | Nowhar Bridge | Nowhar Bridge | Nowhar Bridge incomplete since three years |

**DAY2ACTIVITIES**

**AGENDA6**

**NASHAMUKTABHIYAN**

1. Whethergramsabharesolutionpassed Yes

2. Detailsofactivities conducted Pledge taken conducted various rallies

3. Whetherallactivities andGSresolutionuploadedonjkpanchayats.inportal Nil

4. Howmanydrugaddictsinthevillage NIl

5. WhetherreportedtotheDeputyCommissioner NIL

6. Howmanyregisteredforrehabilitationundergovernmentprogramme

NIL

**DAY2ACTIVITIES**

**AGENDA7**

**SOCIALAUDIT**

Conductsocialauditofatleast5workseachunderfollowingschemes:

|  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- |
| NAMEOFTHE SCHEME | DETAILSOFTHE WORKS | YEAROFWORK APPROVAL | AMOUNT APPROVEDFORTHEWORK | WHETHERWORKEXECUTED SATISFACTORILY | GEO- TAGGED PHOTOS | ANY GRIEVANCE RECORDED RELATINGTOTHAT WORK |
| MGNREGA | List enclosed |  |  |  |  |  |
| PMAY |  |  |  |  |  |  |
| IHHLUNDERSBM-G | List enclosed |  |  |  |  |  |
| CSCUNDER SBMG |  |  |  |  |  |  |
| AMRIT SAROVARS |  |  |  |  |  |  |

**DAY2ACTIVITIES**

**AGENDA8**

**MAHILASABHA**

Totalwomeninthevillageabovetheageof18 345

Totalattended 73

Proceedings: Demand cutting tailoring centre

*(Plinsertpointerstobediscussedthere–referpalliproceedings)*

**DAY2ACTIVITIES**

**AGENDA9**

**BALSABHA**

Holda balsabhaandrecordproceedings

Totalchildreninthevillageabovetheageof….. Totalattended 35

Proceedings: Demand playfield sports kit

*(Plinsertpointerstobediscussedthere–referpalliproceedings)*

**DAY2ACTIVITIES**

**AGENDA10**

**INAUGURATIONS**

|  |  |  |  |
| --- | --- | --- | --- |
| **SR NO.** | **ASSETS/ACTIVITIES INAUGRATED** | **STATUSOFTHEASSET/AC- TIVITIES(NUMBER,OTHER DETAILS)** | **GEO-TAGGED PHOTOS** |
|  | VILLAGEHAATunderJKSRLM (SUN- DAYMARKET) | NIL | NIL |
|  | PMAYhousesifanyreadyforinaugra- tion | NIL | NIL |
|  | Swachhgramprojects-segregation shedsetc | NIL | NIL |
|  | Amritsarovars | NIL | NIL |
|  | Sportskits | NIL | NIL |
|  | Villageculturalevents | 01 | Yes |
|  | JJMassets/projects | NIL | NIL |
|  | Anyothertobeidentifiedatdistrict level | Demand of cutting and tailoring centrre | NIL |

**FOLLOWUPOF(B2V1,B2V2&B2V3):**

*(Prefilledexcelsheet tobetakenfromdistrictlevel/andalsotobedownloaded*

*from*[*www.jkpanchayat.in)*](http://www.jkpanchayat.in)

|  |  |  |  |
| --- | --- | --- | --- |
| S.NO. | Particulars | Actiontaken | Remarks# |
| I. UrgentPublicRequirements/Demands-B2V1  |
| 1. Nonavailablity of PHC
2. Non Availablity of Sheep Husbadary Unit
3. **Non Availability of timber Depo**

4 . Non Availability of Jk Bank Branch1. NA of LT Poles and transfarmer

6 | NONO | Demand againDemand again |
|  |  |
| NO | Demand again |
| No | Demand again |
| Yes |  ---- |
|  |  |
| 7 |  |  |  |
| II. **UrgentPublicRequirements/Demands-B2V2** |
| 1. Road from main road to lashkalan
2. Upgradation of Middle school to High school
3. Foot bridge at Nallah Doodhganga Near Channa gund
4. Establishment of PHC and Jk Bank Branch
5. Establishment of Sale timber Depot
6. Pipeline from Kutbal to Nowhar
7. Supply two transformer 200KV and 100 LT Poles
 |
| S.NO. | Particulars | Actiontaken | Remarks# |
| III. **MajorProblems–B2V1** |
| 1. Unemployment problem and rectify errors in land settlement and registration of old age disable widows for financial assistance
 |

|  |  |  |  |
| --- | --- | --- | --- |
| 4 |  |  |  |
| 5 |  |  |  |
| IV. **MajorProblems-B2V2** |
| 1. Road from main road to Lashkalan

2 Foot bridge at Nallah Doodhganga at Chanagund3 Establishment of JK Bank and PHC 4 Pipeline from Kutbal to Nowhar5 Upgradationj of Miidle school into High School and its renovation of the same |
| V. **MajorProblems-B2V3** |
| 1. Road from main road to Lashkalan1. Foot bridge at Nallah Doodhganga at Chanagund

3. Establishment of JK Bank and PHC 4. Pipeline from Kutbal to Nowhar5 .Creation of 100 KV Sub station at Herpora Nowjhar |
| VI. **MajorComplaints-B2V1** |
| 1. Error in land settlement

2 Unemployment problem3 Registration of old age , widows and disabled for financial assistance |
| VII**. MajorComplaints-B2V2** |
| 1. 1 Error in land settlement

2 Unemployment problem3 Non availability of Higher sec school |
| VIII. **MajorComplaints-B2V3** |
| 1 Error in land settlement 2 Unemployment problem3 Registration of old age , widows and disabled for financial assistance |

**OVERALLPERCEPTIONOFFUCNTIONING OF GOVERNMENTDEPARTMENTS**

1. **BESTDEPARTMENT: RDD/EDUCATION/ICDS**

**2. LEASTRESPONSIVEDEPARTMENT:--**

**GENERALASSESSMENTOFTHEVISTINGOFFICER**

|  |  |
| --- | --- |
| I | AnymajorcomplaintbroughttothenoticeoftheVisitingOfficer:About road from Nowhar to LaskalanKLJLSKJLKLFKLDFD |
| II | Major/urgentpublicdemandsthatwas/werereflectedearlierbuthavenotbeenaddressedsofar  |
| III | Overallassessmentofthevisitandsuggestions: **7**(Thevisitingofficertoensurethattheoverallassessmentisrecordedindetailsalongwithconcretesugges- tions) |
| IV | OverallRatingofgovtfunctioningas givenbythePanchayat(Scaleof0to10) |
| V | **CertificatefromSarpanchthatthevisitingofficerhasstayedinthepanchayatfor2days Enclosed herewith** |

 II. Up gradation of Middle School to High School and renovation of the same/Establishment of JK Bannk Branch

 And PHC/ Installation pof Pipeline from kutbal to Nowhar for Agriculture Purposes/Repairment of irrigation canal

 Which is causing cracks to the houses.

 **SignatureofSarpanch SignatureoftheVisitingOfficer**

 S

**Name:\_-SHAHEENA AKHTER Name:-ABDUL HAFIZ BUTT**



**DepartmentofRuralDevelompentandPanchayatiRaj**

**GovernmentofJammu &Kashmir**