4





**15TH OCTto3RD NOV,2022**

**KEYFEATURES**

• DeputyCommissionerstoleadtheinitiative

• RuraldevelopmentDepartmenttobethenodaldepartment

• PlanningDevelopment&MonitoringdepartmentandITtobethesupport departments

**ACTIONSANDTIMELINES**

|  |  |  |  |
| --- | --- | --- | --- |
| **ACTION** | **RESPONSIBILITY** | **LATESTBY** | **REMARKS** |
| **Janabhiyan** | Alldepartments | Oct15-26th | Goingon |
| **DeputationofSecttstaff/ HoDs** | GAD | Oct14 | Done |
| **DeploymentofStaffto Panchayatsandservingof ordersondeployedofficers** | DCs | Oct25 | DCswilldeployseniorlevelstaff fromthedistricts.Strictactionto betakenagainstabstentions.No exemptionstobegiven |
| **Trainingofdistricttrainors onB2V4** | RDD | Oct26 |  |
| **Trainingofvisitingofficers** | DCs | Oct27 |  |
| **FieldVisitstobecompleted by** | VisitingOfficers | Nov3 | DCstosuperviseandensurethat eachPanchayatisvisitedwithin theperiodspecified |
| **DataofB2V4tobe uploadedby** | VisitingOfficers | Nov10 | DCstosuperviseandensurethat dataofallPanchayatsisupload- edbythevisitingofficerwithin theperiodspecified |

**INSTRUCTIONSFORTHEVISITINGOFFICER(DAYWISE)**

|  |  |  |
| --- | --- | --- |
| **DATE** | **INSTRUCTIONS** | **ACTIONPOINTS** |
| **Day0** | Meetingwithdeputy commissionerandhis/her team | a. TakeprintoutsoffilledbookletsofB2V1,B2V2andB2V3from [www.jkpanchayat.in](http://www.jkpanchayat.in)  b.Alsotakeprintoutsofthesummarizedexcelsheetsofthe previousphasesfrom[www.jkpanchayat.in](http://www.jkpanchayat.in)  c. CollectATRsonissuesraisedduringprevious3phasesfromthe officeofDeputyCommissioner(Planningdeptt)  d.Takeprintsofblank 2bookletsofB2V4from[www.jkpanchayat.in](http://www.jkpanchayat.in)e.Takeplansfor2previousyearsandATRsfromtheplanningdeptt f. CompletetrainingsondifferentcomponentsofB2V4being  organizedbyrespectiveDeputyCommissioners  g.CollectListofnewworksstarted/ongoing/completedduringthe previousandcurrentFinancialyearunderthefollowingheads:  • PRIgrants  • DistrictPlan  • UTplan  • MGNREGA  • Otherschemesofotherdepartments  • Anyotherwork  h. Plans/beneficiarylists:  • MGNREGAdraftplandocumentfortheyear2022-23.  • ListofAwaas+beneficiariesalongwithIHHL Convergence  • Listofpensionbeneficiaries.  • ListofSHGs  • Listofagricultureschemebeneficiaries  i. Listsofbeneficiariesfor:  • Variouscertificates/benefitstobedistributedbythe visitingofficer.  • Anyotheractivitiesidentifiedbydifferentdepartments |

|  |  |  |  |
| --- | --- | --- | --- |
| **Day1** | Reachthevillage | 1. | Ensurethatallfrontlineworkersofdifferentdepttsarepresent. |
|  |  | 2. | Ensureexhibitionbydifferentdepts.aboutindividualbeneficiary schemes |
|  |  | 3. | InspectJKB/PSBcounters/outlets |
|  |  | 4. | Participate/ensureorganizationofsportsactivityinplayfield,talent hunt/culturalevent/youthactivity |
|  |  | 5. | GandhiKatha(suggesteddetailsuploadedonjkpanchayat.in) |
|  |  | 6. | Visitatleast2amritsarovarsandgetitsgeotaggedphotos |
|  |  | 7. | InspectKhidmat(CSC)CentresandcreateGenerateawarenesson  225schemesparticularlyG2CschemeslikeBEAMS,Janbhagidari, AapkiZaminAapkiNigrani,DigitalJ&K |
|  |  | 8. | Visitingofficershallalsoplanandconductpanchayatlevelconver- gencemeetingofalldepartments |
|  |  | 9. | CheckeffectivenessofCentrallysponsoredschemes |
|  |  | 10. | VisitandinspectallgovernmentestablishmentsincludingPHE, AWC,FPS,schools,etc |
|  |  | 11. | Attemptsaturationofdeliverableso JanAbhiyanandwherever deficienciesfound,leadadrivetoachievealldeliverables |
|  |  | 12. | Assesseffectivenessofsanitationcampaigninthepanchayat |
|  |  | 13. | Ensureselfemploymentactivitiesfor15youthperpanchayat |
|  |  | 14. | Identify20potentialcandidatesperpanchayatforHIMAYATtraining alongwiththetradeonwhichtheywanttraining |
|  |  | 15. | Whereverpossible,distributeemploymentlettersforpeopleselect- edundervariousgovernmentemployments |
|  |  | 16. | Intheevening,holdnormalmeetingwith seniorcitizens,govtem- ployeesincludingretiredemployees,exservicemen,youthclub,and any citizens ofthevillagewhoareenrolledincollege/university |
|  |  | 17. | OpendiscussiononNashaMuktAbhiyan |

Day2 Haveameetingwithall stakeholders-depttofficials andpanchayatmembers

1. Discussionontheandassesstheprogressofdifferentschemesrelating tothelocalizedSDGsprioritizedforthatvillageaspertheresolution passedby thatGramPanchayaton21st April22,onNationalPanchayti RajDay.

2. Sensitizevillage residentsaboutmyScheme”portal(myscheme.in) whichincludesinformationaboutalltheschemesbeingrunbyCen- tral/State/UTgovtacrossthecountry

3. Hold meeting of theBiodiversityManagementCommitteestodeliber- ateonissuespertaining toconservation of biodiversityandsustaina- bleutilizationof biologicalresources.

4. PrepareVillagedevelopmentplan,inconsultancywithGrampanchayat, discussitingramsabhaandgetitapproved.

5. Ensure saturationofsoilhealthcardandgoldenhealthcardunderGold- enHealthCardunderAyushmanBharat,

6. Ensuresaturation of OldAge PensionScheme

7. EnsureDomicileSaturation.

8. EnsureKCCSaturation

9. Ensure saturationoflandpassbooks

10. Ensureregistrationofvillagevendorsneededforanyscheme,onGEM

portal

11. Ensurepanchayatcontractors registration

12. EncouragePanchayatmembers forimportanceofplantationdrivein

PanchayatunderHarGaonHariyali

13. Ensure paintingondigitalJ&Kinpanchayatghars

14. Ensure paintingonpanchayatactivitesandCSSinpanchayatghars

15. Thevisiting officeshallchecknoof kindergarten andplayfields present inthepanchayat for kidsandstudents,iftheinfrastructure present inthesearegoodenough.

16. Holdmeeting withpanchayatmembers todiscussaboutcorruption menaceandstepsrequiredtomakeJ&Kcorruptionfree

17. Obtaina candidassessmentaboutperformanceofvariousdeptts in- cludingfairfeedbackaboutdiscrepanciesinfunctioning

18. Check thestatusof NashaMuktAbhiyanandreporting of drugad- dictstoDeputyCommissioner.

19. IdentifyTouristDestinations,Circuits,ThemeTreks,IdentifyHomestays, providesupportfortourismactivities throughVillageCooperative

20. OrganizeTalentHuntatPanchayatLevel

21. Conductsocialauditofatleast5worksunderfollowingschemes:

a. MGNREGA

b.PMAY

c. IHHLtoiletsandpayments d.CSCs

e.AMRITSAROVARS

22. Holda mahilasabha anda balsabhaandrecordproceedingsinthefor- matgiven

23. InauguratevillagehaatunderJKSRLM

24. Checkifyouthclubsareformedinthepanchayatandwhatactivities theyareengagedin

25. Organizea villagelevelculturaleventtoengagepanchayatmembers

26. SensitizeGPaboutE-kitabkoshaninitiativeofJ&KGovtforempowering youthsthrough onlinedigitalliteracy

**GENERALINSTRUCTIONS**

1. Thevisitingofficershallrefrainhimself/herselfgivingorofferinganycommitmentonbehalfofthe governmentandshalladoptanunbiasedattitudeinreportingissues.As faraspossible,his/her observation shouldbebasedona fairandanalytical viewemergingfromhis/herinteractioninthe village.

2. Heisgoingtothevillageasplanningofficer,notforsanctioninganyworksorformakinganycom- mitments.

3. Whilepreparingvillagedevelopmentplan,hehastoensurethat,demandsareprioritizedandre- flectedunderavailableschemes,wherevernecessarythelargerworksaretobereferredtoadminis- trativedepttunderCSS/UTplansunderintimationtoDCsandrestoftheworkstoDCsforreflecting itunderdistrict/CSS plans

4. His workshallbehardcoreplanningandauditandisnota PRexercise.

5. EveryDeputyCommissionerhastoensurethatatleastoneRDDofficial(ideallyPanchayatSecre- tary)ispresent ineverypanchayatwithrelevantpanchayatrecords,toensureconductofallactivi- tiesasplanned.Panchayatwiseorderneedstobeissuedinadvance.

6. Visitingofficershouldideallycarryhis/herlaptoptocompletethereportsatthepanchayatlevel itselfanduploadthefinalreport,duly signedbothbythesarpanchandbythevisitingofficeron [www.jkpanchayat.in](http://www.jkpanchayat.in)portal,beforetheyleavepanchayat.

7. Focus ofvisitareyouth,skills,self-employment,nashamukt,bhrashtracharmukt,Rozgaryukt J&K, besidestocarryforwardtheactivities duringJanAbhiyanandsaturatethem.

8. Inadditionattentionmaybegiventothefollowingareas a. MakefulluseofCentrallySponsoredSchemes

b.Saturationofindividualbeneficiaryschemes c. Self-employmentschemes

d.Banklinkedschemes-includingdepartmentalsubsidyschemes e.Empowermentandtransparencythrough digitalinitiatives

f. Effectivenessofgrassrootsmachinery–

i. Patwari,VLWpresent andavailable

ii. AvailablefundsutilizedinpublicinterestandasperGramSabharesolutions iii. Fairness ingovernance

iv. CSS/Individual beneficiaryschemesetc v. BrashtacharMuktJ&K

vi. BhaiMuktJ&K

vii. NashaMuktJ&K

9. ThePRImembers (Sarpanchs,Panchs,BDCChairperson)shallbeattheforefrontofallactivities and givendueimportanceandtheapproach shouldbetostrengthenthemandmakethemfeelem- powered.He/sheshallensurethattheBDCchairpersonandSarpanch/Panch arepresent atthetime ofinaugurationandceremonies.

10. Visitingofficershallnotleavethedistrictwithoutuploadingthereport,duly signedonthe**www. jkpanchayat.in**portal.EveryDeputyCommissionerhastoensurethat.

**A) DetailsofReportingOfficer:**

Name: Er. Nissar Ahmed Wani :

Designation:- Assistant Executive Engineer PWD (R&B) Circle Ang/Kul

Department/place of posting: PWD (R&B) Circle Ang/Kul

MobileNo:7006422968

EmailID:nissarusman786@gmail.com

HomeDistrict:Anantnag

Datesof visit:02.11.2022 to 03.11.2022

**B) LocationaldetailsofPanchayat:(tobepre-filled,informationtobetakenfromtheprevious phasesbooklets/summarizedexcelsheetuploadedonjkpanchayat.in/b2v4.php)(tobevali- datedbythevisitingofficerandmissingdetailstobefilled)**

NameofthePanchayat:Dehwatoo

Local GovernmentDirectory(LGD)codeof thePanchayat:274685

Nameof CDBlock:Pahalgam

NameofTehsil:Sallar

Nameof District:Anantnag

**C) PanchayatProfile:**

No.ofrevenuevillagesinthePanchayat:df. (2) Dehatoo & Ladi

No.ofhamletsinthePanchayat:7

No.ofhouseholdsinthePanchayat:341

Population(approx)of thePanchayat:1597

**Part-II:**

(TobefilledupbytheVisitingOfficerduringhis/hertwodayvisittothePanchayat.AllFieldshavetobe

filledbytheVisitingOfficerbeforethebookletishandedovertotheDC

**FrontlineOfficers/OfficialswhowereassignedtothePanchayatfortheprogramme:**

|  |  |  |
| --- | --- | --- |
| Department | Name | Designation |
| Rural Development RDD | Mushtaq Ahmad Ganie | G.Rs |
| Irrigation | Mohd. Shafi Wani | Pathwari |
| Jal Shakti | Ab. Gani HaJAm | Assistant Line man |
| PWD R&B | Gh Qadir Shah | Road Supervisor |
| PDD | Jitandar Singh | Line man |
| Education | Aijaz Rasheed Wani | RREt |
| Food & Supplies | Mudasir Ah Bhat | Ask.cum clerk |
| Agriculture | Shujeet Aalam | JE/Eo |
| CSC | Shahmdevcel Iqbal | CSC VLE |
| Aanganwardi | Shabnam Akhter | Anaganwarid Worker |
| Forest | Mohd Yaseen Mir | Watcher |
| Health | Nusrat Aara | Aisha |
|  |  |  |

**Detailsofabsentemployeesvis-à-vislistfurnishedbytheDCoffice:**

|  |  |  |
| --- | --- | --- |
| Department | Name | Designation |
|  |  |  |
|  |  |  |
|  |  |  |
|  |  |  |
|  |  |  |
|  |  |  |
|  |  |  |
|  |  |  |
|  |  |  |
|  |  |  |
|  |  |  |
|  |  |  |
|  |  |  |
|  |  |  |
|  |  |  |

**DAY1-ACTIVITIES**

**AGENDA1:PANCHAYATASSETREGISTER**

**Infrastructure:**

1. PanchayatGharInfrastructure a. Govtbuilding/private Yes

b. New/needingrepairs: Needs Repairment

2. Furniture(Y/N) Yes

3. Computer/printer(Y/N) yes

4. Internet(Y/N) No

5. Telephone(Y/N) No

6. Toilet(CSC/partofpanchayatghar)(Y/N) Yes Needs repairment

7. Water(Y/N) Yes

8. Electricity(Y/N) No

9. Bankbranch(Y/N) Yes

10. CSC(Y/N) Yes

11. Patwarkhana(Y/N) Yes damaged

12. Villagehaat(Y/N) Yes

13. Playground(Y/N) Yes Needs further development

14. School-

a. Kindergarten(Y/N) No

b.Primary(Y/N) Yes

c. Secondary(Y/N) Yes

d. College (Y/N) No

e.University(Y/N) No

15. AnganwadiCentre(Y/N) Yes 05

a. (govt/private) Rented

b.Totalchildrenenrolled 145

15. AmritSarovars–details,location,condition 2 under construction

16. Governmentoffices-details,whetherfunctionalornot Functional

17. Rationshop(Y/N) Yes

18. Placesoftourismimportance–names,littledetailsonhistorical/culturalimportance Pat at Ladi

19. Villageheritagesites/treks-names, littledetailson historical/cultural importance

20. VLWOffice (Y/N) yes

21. PrimaryHealthcareCentre(Y/N), Wellness Centre

22. ListofIncompleteBuildings-names,yearofconstruction Nil

23. ListofUnderutilizedBuildings-names Pyt. & Govt.School building

**DAY1-ACTIVITIES**

**AGENDA2:**

**DIFFERENTINSTITUTIONS/INFRASTRUCTUREPROJECTSTOBEVISITED**

|  |  |  |
| --- | --- | --- |
| **AMRITSAROVARS** | **Visit,verify** | **COMMENTS** |
| KhidmatCentres | Create/Generateawarenesson225schemes particularlyG2CschemsAapkiZaminAapkiNigrani, Beams,Janbhagidari,DigitalJ&K | Functional  Visit and verified |
| JKB/PSBcounters/outlets | a)Statusofcounter 06b)Numberofvisitor 100+ | Functional ( Good)  Locals demand installation of ATM |
| Incompletebuildings/pro- jects | Verify whetheridentificationandredistribution done | --  Satisfactory |
| PDS | Visit,evaluate,onlinestatus | Satisfactory |
| PHC wellness center | Visit-evaluate,statusofstaff,equipmentand quality | Deficiency of staff |
| Youthclubs | Meet,interact,seeksuggestions | Needs Awareness |
| SHG Adolescence girls | Meet,identifyproblems,seeksuggestions | Needs Training |
| PMAY | Inspect,Inaugurate ( incomplete) | Lack of funds |
| Myschool,mypride progress;schools-water, toilets,staff | Visit,checkforwater,electricity,sanitation,meet studentsandstaff | Satisfactory |
| SwachhSBM | Evaluate | Poor sanitation |
| Panchayatplayground, Sportskitsdistribution Villagegames | Ensure,verify.Participateinatleastonegamein theplayground | Ply filed needs development |
| HarGaonHariyali, Planta- tiondrive | Evaluatestatus,feedback | Nill |
| Villageculturalevent  Dangal/Haat/Mela | Participatein;ensurethatitisheld | Good |
| Exhibitionofschemes | Ensurethateverydepartmentparticipatesand thatitcontinuesfortheentiredurationofB2V | PDD. Social Welfare & Forest Agriculture |
| JalJeewanMission verifica- tion- WSS/JSD  Electricitysupply | Verify | Needs water filtration Plant |

**DAY1-ACTIVITIES**

**AGENDA3:SATURATEJANBHIYAN**

**DELIVERABLESANDRECORDDEFICIENCIESIFANY(INSERTDELIVERABLESLISTHEREASPERGADFORMAT**

**DAY1-ACTIVITIES**

**AGENDA4:**

**SELFEMPLOYMENTACTIVITIES**

EnsureSelf-employmentactivities foryouth,distributeemploymentlettersforpeopleselectedunder varioussocialschemes(15ISTHETARGETPERPANCHAYAT)

**Numberofcasesindifferentcategoriessanctioned: 3 Detailsofthebanksanctioningit: 1**

**Totalamountinvolved:10.00 lakhs**

**DAY1ACTIVITIES**

**AGENDA5**

Intheevening,holdinformalmeetings withseniorcitizens,govtemployees,retdemployees,youthclub andothercitizenswhoareenrolledoncollege/universityandhavediscussiononGandhiKatha,Nasha MuktAbhiyan,corruptionfreegovernance,doublingfarmersincomeandrecordtheproceedings

**Activities done resolutions enclosed**

**DAY2**

a. NoofIndividualCompostPitsconstructed 80 b.NoofIndividualSoakPitsconstructed 90

V. No.ofBiodiversitymanagementcommitteemeetingsheld:2

VI. IsthenameofSarpanchdisplayedoncitizeninformationboardsofallRD&PRschemes:Yes/No Yes

VII. AreSarpanchsbeinginvolvedinstart/inaugurationofactivities:Yes/No Yes

VIII. WhethersubjectshavebeenassignedbytheSarpanchtothePanchs:Yes/No Yes

IX. Whethergrievancesredressalboxisinstalled:Yes/No No

X. NoofgrievancesreceivedpertainingtoPanchayatlevel: 4

XI. NoofgrievancesdisposedofatPanchayatlevel: Nill

XII. WhethertheSarpanch/PanchayatSecretaryhavedigitalsignatures:Yes/No Yes

XIII. WhetherallMGNREGA/14thFCpayments arebeingmadebySarpanchthrough DigitalSignature

Certificate(DSC):Yes/No Yes

**HUMAN RESOURCEAVAILABLEATTHEPANCHAYAT LEVEL:**

|  |  |  |  |  |
| --- | --- | --- | --- | --- |
| **SRNO.** | **DEPARTMENTWISESTAFF** | **NUMBERS** | | **NAMES** |
|  |  | SANCTIONED | ACTUAL  1 |  |
|  | Ruraldevelopmentdepartment: BDO  JE GRS TA | 1  1  1  1 | 1  1  1  1 | Malik Muzafar Ahmad |
|  | SCHOOLEDUCATION: TEACHER  HEADMASTER ANYOTHER | 19  1  5 | 19  1  5 |  |
|  | JAL JEEVAN: | 2 | 2 |  |
|  | PDD: LINEMAN JE  ANYOTHER | 2  1  3 | 2  1  3 |  |
|  | FOOD&CIVILSUPPLIES | 2 | 1 |  |
|  | AGRICULTURE&ANIMALHUS- BANDARY | 1 | 1 |  |
|  | SOCIALWELFARE | - | - |  |
|  | HEALTH: ASHA ANM  AYUSHDOCTOR ALLOPATHICDOCTOR | 1  1  1  - | 1  1  1  - |  |
|  | ANYOTHERDEPARTMENT | 5 | 5 | ICPS |

**DAY2-ACTIVITIES**

**AGENDANO.1**

DiscussionontheandassesstheprogressofdifferentschemesrelatingtothelocalizedSDGsprior-itizedforthatvillageaspertheresolutionpassedbythatGramPanchayaton21stApril22,onNational PanchayatiRajDay(Copyoftheresolutiontobetakenfrom[www.jkpanchayat.in](http://www.jkpanchayat.in)portalunderthelinkof GramSwarajMonth)

1. SDGs AGREED FORTHATVILLAGE,TOBEIMPLEMENTED BYMARCH2024:

2. STATUSOFWORKSUNDERTHEFOLLOWINGSCHEMES:

**1 Cleanandgreenvillage**

i.InitiativestakenbythePanchayatformanagingSolidandLiquidWaste Composite & Soakage pits. InitiativestakenbythePanchayatforusinggreensourcesoffuellikesolar,biogas NIL

iii. Hasmappingoflanduse,waterbodies,forest,slopes,wetlands,degradedforestwithintheGram

Panchayatbeendone?Yes/No.IfNo,reason,thereof Yes

iv. HastheClimateResiliencePlanbeendevelopedfortheGP?Yes/No No

v. StepstakenbytheGramSabhaabouttheclimatechangemitigationfactorslikereducingenergy consumption,usageoffossilfuels,plastics,non-renewablebuildingmaterialsandalsotopromote measureslikeplantingoftrees,conservingforests,usageofgoodagriculturalpracticeslikedrip irrigation,waterconservationmeasuresandconservationofwetlands.

vi. Whetherschoolshavestartedsegregatingwaste Yes

vii. Whetherschoolshavetheirowncompost/soakagepitsforsolid/liquidwastemanagement Yes

**2 Healthyvillage**

i) Aremeetings relatedtoVillageHealthandSanitationCommitteebeingheldregularly?

ii) DoalltheeligibleindividualsbeenprovidedtheGoldenCard? Yes 90%

iii) ArealltheChildrenbeingimmunizedaspertheSchedulerecommendedbyGovt.ofIndia? Yes

iv) ArealltheeligibleindividualsbeenvaccinatedagainstCOVID-19?Yes

v) DoesGramPanchayatensurethatallpregnantwomenaregettingnecessaryprenatalcheckups? Yes

vi) WhetherallthedeliverieswereInstitutionalizedorconductedbytrainedMidwives? Yes

**3 Watersufficientvillage**

i) DoalltheIHHsintheGramPanchayathavewaterpipelineconnections? Yes

ii) WhetherGramPanchayathastakenstepsforgreywatermanagement.IfYespleasespecify iii) No DoalltheIHHsintheGramPanchayathavetoilets? Yes

iv) ArealltheIHHstoiletsfunctionalornot? Yes

v) DoalltheSchools/Anganwadicentershavea toiletfacilityornot? Yes

vi) Areallthetoiletsintheschools/Aaganwadifunctionalornot? Yes

vii) WhetherGramPachachayatBhawanhasseparate toiletsforwomenornot?No

**4 ChildFriendlyvillage**

i) Doallthechildrenundertheageof0-6yearsbeenenrolledintheAnganwadicentersforpre- schooling?Yes/NO

ii) HowmanyBalSabha’swereorganizedintheGramPanchayat--01-----------------

iii) WhethertheissuesraisedbyBalSabhaareaddressedduringtheGramSabha. Yes/NO No

iv) WhetherGramPanchayatistrackingthedatarelatedtodropoutchildrenandchildrenwithirregular attendance?Yes/NO. No

v) DoalltheschoolsundertheGramPanchayathaveseparate toiletsforgirlsandboys?Yes/No Yes

**5 Villagewithgoodgovernance**

i) IsCSClocatedintheGramPanchayatBhawanornot? Yes

ii) IsthelistofbeneficiariesrelatedtotheSchemes/ProgramsdisplayedontheGrampanchayatwallor not?Yes

iii) DoestheGramPanchayathasitsbuildingornot?yes

iv) IstheGramPanchayatofficefunctionalornot?Yes

v) Aretheactivities approved undertheHalqaPanchayatDevelopmentPlandisplayedontheGram

Panchayatwallornot? Yes

vi) IsSocialAuditofearlierSchemes/Programscarriedoutornot? Yes

**6 Povertyfreeandenhancedlivelihoodvillage**

1. HasGramPanchayatdevelopedanycriteria fortheidentificationofthepoor?Yes/Noifyesspecify NO
2. HavealltheeligiblehouseholdsregisteredinPDSornot?Yes

iii) HasGramPanchayatprovidedspaceforSelf-helpGroupsinPanchyatGharforholdingmeetings or not?Yes

iv) HavealltheeligiblehouseholdsbeenregisteredforPensionornot?Yes

v) HasGramPanchayatfacilitatedYouthforSkillEnhancementCoursesandPlacement?No

vi) HasJobCardsbeendistributedtoalltheeligibleindividualsunderMGNREGA?Yes

vii) HasGramPanchayatfacilitatedSHGsforBankAccountLinkages?Yes

**7 Sociallysecuredvillage**

i) WhetherGramPanchayatismaintainingdatarelatedtoDifferentlyAbledPeople?Yes

ii) IsGramPanchayatOffice DisabledFriendlyornot?No

iii) Areprovisionsfora separate BudgetundertheResourceEnvelopeforWomenandChildrenmadeor not?No

iv) DoalltheSchools intheGramPanchayathavefacilitiesforDifferentlyAbledChildrenliketoilets, barrier-freeaccess,etc.,ornot?yes

v) Arealltheeligibleindividualsaregettingpensions,likeoldagepension,widowpension,etc?Yes

vi) ArealltheeligiblehouseholdsgettingbenefitsfromIAYornot?yes

**8 EngenderedDevelopmentinVillage**

i) HowmanyMahilaSabha’swereorganizedintheGramPanchayat-----01--------------

ii) WhetherSHGsfederationshavebeenprovidedspaceformeetings inthePanchayatBhawan(Yes/ No)No

iii) WhetherGPshavetakenstepsforincreasingwomen’sparticipationinGramSabha(Yes/No)Yes

iv) NumberofwomenbeneficiariesheadedhouseholdscoveredunderPDS

system…………08……………

v) Numberofbeneficiaries(outoftotaleligiblepopulation)receivingsocialprotectionbenefitsunder

PradhanMantriMatritvaVandanaYojana……40…………….

9 Self-sufficientinfrastructureinthevillage

i. WhetherGPhasa CommunityHallwithaccesstoelectricity,furniture,watersupply, toilet………No……………….

ii. WhethertheDisastermanagementplanisavailableattheGPLevel(Yes/No) No

iii. Whetherchild-friendlyparkwithrequiredfacilitiesisavailableinGP(Yes/No) No

iv. WhethertheGPhaseasyaccesstoGodownforstorage(Yes/No) No

v. Whetherstreetlightsareprovidedinpublicplacesforensuringsafety(Yes/No) Yes

**DAY2ACTIVITIES**

**AGENDANO.2**

SensitizevillageresidentsaboutmyScheme”portal(myscheme.in)whichincludesinformationaboutall theschemesbeingrunbyCentral/State/UT govtacrossthecountry

*(SchemeMaterialavailablefromhttps://jkpanchayat.in/b2v4.php) Done*

**DAY2ACTIVITIES**

**AGENDANO.3**

HoldmeetingoftheBiodiversityManagementCommitteestodeliberateonissues pertainingtoconserva- tionofbiodiversityandsustainableutilizationofbiologicalresources.HeshouldcheckPeopleBiodiversity register(PBR)ofthatpanchayatandreviewifBiodiversityManagementCommittee constitutedforthat panchayatis holdingminimum4meetings inayearandmeeting onceinevery3months *(RoleofBMC availableathttps://jkpanchayat.in/b2v4.php)*

COMMITTEEMEMBERS 15 PRESENT Nill

BIODIVERSITYREGISTERPHOTOS

PAST 4MEETINGDETAILS-DATES,MINUTESPHOTOS

Two meeting held

**DAY2ACTIVITIES**

**AGENDA4**

Visitingofficershallalsoplanandconductpanchayatlevelconvergencemeeting ofalldepartmentsand prepareVillagedevelopmentplanforvillage,inconsultancywithGrampanchayat,discussitingram sabhaandgetitapproved.

(GPDPformatavailableonhttps://jkpanchayat.in/b2v4.php)

|  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
| **Gram Panchayat Development Plan of Panchayat DEHWATOO (Mere Sapno ki Panchayat)** | | | | | | | |
|
| **S.no** | **Name of the Village** | **Name of the concerned Department** | **Scheme** |  | **Name of the proposed work** | **Ward.no** | **Estt Cost** |
|  | Dehwatoo | **Department of Rural Development** | MGNREGA | *1* | C/o Rwall from Manzoor Paswal to onwards via Babo Khushi |  | 1.20 |
|  | Ladi | *2* | R.wall near Gh Nabi Paswal and other |  | 1.20 |
|  | Shalbaren | *3* | C/po Rwall from Gawhar Hussain Mir and others | 1 | 1.20 |
|  | Kothbal | *4* | C/O Irr Ladh F H/O M Yousuf Mir to onwards via Land of Hassan Mir |  | 1.20 |
|  |  | *5* | C/o of L/Road from Dankad to onwards via House of Haneef |  | 1.20 |
|  |  |  | *6* | C/o Irr Ladh from Movera road to onwards via land of Ahmdula |  | 1.80 |
|  |  |  | *7* | wall NHO Bashir Ahmad Hajam Razak Mir Aziz Mir and others |  | 1.60 |
|  |  |  | *8* | Foot path with steps from Gh Rasool Qadri to Ramzan Sheikh |  | 0.60 |
|  |  |  | *9* | Constr;of irr ladh from Mushtaq Sheikh to onwards |  | 0.90 |
|  |  |  | *10* | C/o Rwall near Jamid Masjid Shjareif Dehwatoo |  | 0.60 |
|  |  |  | *11* | Coonst.of link road from Najar Mohallah to Onwards via Ali Najar |  | 1.80 |
|  |  |  | *12* | Constr;of irr kanal from Banji to Wohin kanal Shal baren |  | 0.90 |
|  |  |  | *13* | Const.of link road form Razak Laway to onwareds viad wohin kanal |  | 1.20 |
|  |  |  | *14* | Constr.of R.wall at Shal Barren |  | 0.60 |
|  |  |  | *15* | Foot path FHO Gul Mohd Mir to Rehman at Herpora Ladi |  | 0.90 |
|  |  |  | *16* | Renovation of steps at Herpora Ladi |  | 0.60 |
|  |  |  | *17* | Developemnt of Irr Ladh at Wared No. 2 | 2 | 1.20 |
|  |  |  | *18* | C/o of link road from main road to KGBV |  | 0.90 |
|  |  |  | *19* | Constr.of link road form Razak wani to Wohin Kanal at Ladi |  | 0.90 |
|  |  |  | *20* | C/o R.wall at Ladi NLO bashir Mir & ors |  | 0.60 |
|  |  |  | *21* | R.wall at differennt spots at Ladi |  | 0.90 |
|  |  |  | *22* | Constr.of Irr ladh from Land of Nissar Hajam to ownards via land of Yaqoob Mir |  | 0.60 |
|  |  |  | *23* | Constr;of link road from M. Shafi to ownards via H/O Shabir Shah |  | 1.20 |
|  |  |  | *24* | C/o R.wall NLO Ab. Rashid Mir and ors at Ladi |  | 1.20 |
|  |  |  | *25* | C/o R.wall near H/O Khazir chopan and ors at Ladi |  | 1.20 |
|  |  |  | *26* | C/o R.wall near Showkat Mir & ors at Ladi |  | 1.20 |
|  |  |  | *27* | Irr Ladh near LO Zaina Banoo Akbar Tenda & ors at Kothbal |  | 1.20 |
|  |  |  | *28* | C/o R.wall near H/o Farooq Ahmad Mir & Ors at Ladi |  | 1.20 |
|  |  |  | *29* | C/o of R.wall NHO Nazir Paswal at Chaeckpati Ladi |  | 1.20 |
|  |  |  | *30* | C/o R.wall different spots at Checkpati Ladi |  | 1.80 |
|  |  |  | *31* | C/o Drain near H/O Gh Qadir Reshi via Mian road |  | 1.20 |
|  |  |  | *32* | C/o R.wall NHO of Haneefa W/o Yaseen Shah Kothbal |  | 0.60 |
|  |  |  | *33* | C/o irr ladh FHO Maqbool Mir to Mohd Chopand Patpora Ladi |  | 0.90 |
|  |  |  | *34* | C/o Irr ladh land of Nissar Wani to Firdous Mir Wogin Path Ladi |  | 0.60 |
|  |  |  | *35* | Dev.of Irr Ladh from Mohs Shjafi to Boni Baghat |  | 1.20 |
|  |  |  | *36* | C/o link road from M.Shafi to Dal Pati Ladi |  | 0.60 |
|  |  |  | *37* | C/o R.wall NHO of Mushtaq Ah Mir Bona Bat Ladi |  | 0.60 |
|  |  |  | *38* | C/o Irr Ladh near land of Rashid Mir to Gaffar Reshi Ladi Kinoo Dal |  | 1.20 |
|  |  |  | *39* | C.o Drain near H/O Muma Checha and other at Patpora |  | 0.90 |
|  |  |  | *40* | C/o of Irr laDH FROM Wohin Kanal to Garden of Fayaz Mir |  | 1.20 |
|  |  | JKRLM (UMEED) | *1* | Creation of Self Help Groups |  | 5.00 |
|  |  | *2* |  |  |  |
|  |  | *3* |  |  |  |
|  |  | PMAY-G (10 beneficiaries to be identified) | *1* | Haleem Koli (JK13337262) |  | 2.00 |
|  |  | *2* | Saleema Banoo (JK143666441) |  | 2.00 |
|  |  | *3* | BaNI Begam (JK148391983) |  | 2.00 |
|  |  |  | *4* | Rafi Khoshay ( JK141587229) |  | 2.00 |
|  |  |  | *5* | Mohd. Shafi Amaan ( JK148389655) |  | 2.00 |
|  |  |  | *6* | Gh Mohd. Paswal ( JK149306918) |  | 2.00 |
|  |  |  | *7* | Ab. Rashid Sheikh ( JK133337428) |  | 2.00 |
|  |  |  | *8* | Arsheed Hussain Wani ( JK146652215) |  | 2.00 |
|  |  |  | *9* | Muzaffar Ah. Shah ( JK133335982) |  | 2.00 |
|  |  |  | *10* | Manzoor Ahmad Mir ( Jk133336997) |  | 2.00 |
|  |  | HIMAYAT (DDU-GKY) (20 candidates to be identified per panchayat) | *1* | Parveena Jan -- Qualif;12th Tailoring |  |  |
|  |  | *2* | Aabid Hussain Shah --10th Plumber |  |  |
|  |  | *3* | Humaira Jan -- B.A Computer |  |  |
|  |  | *4* | Mohd. Altaf Paswal -- 12th Plumber |  |  |
|  |  | *5* | Parvaiz Ahma Sood -- 10th Plumber |  |  |
|  |  | *6* | Jugnoo Jan -- B.A Computer |  |  |
|  |  | *7* | Lateef Ah. Paswal -- 10th Plumber |  |  |
|  |  | *8* | Surya Jan -- B.A computer |  |  |
|  |  | *9* | Shugfta -- 12th Tailoring |  |  |
|  |  | *10* | Tufail Khanday --12th electrician |  |  |
|  |  | *11* | Sheezan Ah. Wani --12th Electrician |  |  |
|  |  | *12* | Sajad Ah. Mir -- B.A computer |  |  |
|  |  | *13* | Hamid Ah. Mir -- 12th Eelctrician |  |  |
|  |  | *14* | Bilal Ah. Mir -- M.A Computer |  |  |
|  |  | *15* | Gulzar Ah., Mir - B.A Computer |  |  |
|  |  | *16* | Naseer Ah. Mir - B.A Computer |  |  |
|  |  | *17* | Tariq Ahmad Mir - 12th Electrician |  |  |
|  |  | SWACHH BHARAT MISSION (GRAMEEN ) | *1* | 10 No. CSC Units | All Wards | 20.00 |
|  |  | *2* | Repairing of Toilet unit at Pnchayat Ghar |  | 1.20 |
|  |  | *3* |  |  |  |
|  |  | Saansad Adarsh Gram Yojana (SAGY) | *1* | Sanitation campaign ( Dust Bins etc) |  | 0.50 |
|  |  | *2* |  |  |  |
|  |  | *3* |  |  |  |
|  |  | **Department of Agriculture,  Cooperation & Farmers Welfare  (DAC&FW)** | Pradhan Mantri Kisan Samman Nidhi Yojana(PM-KISAN) | *1* | F.O.F should be covered to all | All Wards | 2000 per family |
|  |  | *2* |  |  |  |
|  |  | *3* |  |  |  |
|  |  | Pradhan Mantri Kisan Maan Dhan Yojana(PM-KMY) | *1* | Applicable 40 year + old | All Wards | 3000 per applicant |
|  |  | *2* |  |  |  |
|  |  | *3* |  |  |  |
|  |  | Pradhan Mantri Annadata Aay Sanrakshan Abhiyan (PM-AASHA) | *1* | Procurment of Paddy | All Wards | 3.00 |
|  |  | *2* |  |  |  |
|  |  | *3* |  |  |  |
|  |  | Pradhan Mantri Fasal BimaYojana (PMFBY) | *1* | Crop insurance | all Wards |  |
|  |  | *2* |  |  |  |
|  |  | *3* |  |  |  |
|  |  | Pradhan Mantri Krishi Sinchayee Yojana (PMKSY) | *1* | Water harvesting tanks | All Wards | 7.80 |
|  |  | *2* | Tube well and bore well | 2 each | 4.00 |
|  |  | *3* |  |  |  |
|  |  | National Food Security Mission (NFSM) | *1* | Establishment of Godown |  | 5.00 |
|  |  | *2* | Power Sprayer | 2 No | 1.00 |
|  |  | *3* |  |  |  |
|  |  | Mission for Integrated Development of Horticulture (MIDH) | *1* | Ploy Creen House | 2 No | 0.50 |
|  |  | *2* | Vermi Compost unit | 4 No | 1.00 |
|  |  | *3* | Vermi Beds | 10 No | 0.50 |
|  |  | Rashtriya Krishi Vikas Yojana | *1* | Bursh cutter | 2 No | 0.60 |
|  |  | *2* |  |  |  |
|  |  | *3* |  |  |  |
|  |  | Paramparag at Krishi Vikas Yojana (PKVY) | *1* |  |  |  |
|  |  | *2* |  |  |  |
|  |  | *3* |  |  |  |
|  |  | Mission Organic Value Chain Development for North Eastern  Region (MOVCDNER) | *1* |  |  |  |
|  |  | *2* |  |  |  |
|  |  | *3* |  |  |  |
|  |  | **Department of Elementary  Education** | Samagra Shiksha | *1* | C/o builidng for Liabrary and Laboratary at HS Dehwatoo |  | 25.00 |
|  |  | *2* |  |  |  |
|  |  | *3* |  |  |  |
|  |  | National Program for Education of Girls at Elementary Education ( NPEGEL) | *1* |  |  |  |
|  |  | *2* |  |  |  |
|  |  | *3* |  |  |  |
|  |  | Mid-day Meal Scheme | *1* |  |  |  |
|  |  | *2* |  |  |  |
|  |  | *3* |  |  |  |
|  |  | National Means-cum-Merit Scholarship Scheme (NMMSS) | *1* |  |  |  |
|  |  | *2* |  |  |  |
|  |  | *3* |  |  |  |
|  |  | National Scheme of Incentive to Girls for Secondary  Education(NSIGSE) | *1* |  |  |  |
|  |  | *2* |  |  |  |
|  |  | *3* |  |  |  |
|  |  | **Deptt of social welfare** | Integrated Child Development Services (ICDS) | *1* |  |  |  |
|  |  | *2* |  |  |  |
|  |  | *3* |  |  |  |
|  |  | National Social Assistance Programme (NSAP) | *1* |  |  |  |
|  |  | *2* |  |  |  |
|  |  | *3* |  |  |  |
|  |  | POSHAN Abhiyan | *1* |  |  |  |
|  |  | *2* |  |  |  |
|  |  | *3* |  |  |  |
|  |  | **Department of Health and  Family Welfare** | Ayushman Bharat - Health and Wellness Centres (AB-HWCs) | *1* | Establishment of Anganwardi Center at Ladi |  | 10.00 |
|  |  | *2* |  |  |  |
|  |  | *3* |  |  |  |
|  |  | Janani Suraksha Yojana (JSY) | *1* | Achieve 100% target during the year |  |  |
|  |  | *2* |  |  |  |
|  |  | *3* |  |  |  |
|  |  | Janani Shishu Suraksha Karyakram (JSSK) | *1* | Achieve 100% target during the year |  |  |
|  |  | *2* |  |  |  |
|  |  | *3* |  |  |  |
|  |  | Universal Immunization Programme (UIP) | *1* |  |  |  |
|  |  | *2* |  |  |  |
|  |  | *3* |  |  |  |
|  |  | Home Based Care of Newborn and Young Children | *1* |  |  |  |
|  |  | *2* |  |  |  |
|  |  | *3* |  |  |  |
|  |  | (HBNC/HBYC) Rashtriya Bal Swasthya Karyakram (RBSK) | *1* |  |  |  |
|  |  | *2* |  |  |  |
|  |  | *3* |  |  |  |
|  |  | National Ambulance Service (NAS) | *1* | 01 No Ambulance Van |  | 15.00 |
|  |  | *2* |  |  |  |
|  |  | *3* |  |  |  |
|  |  | Disease Control Programs | *1* | Awareness programme / camps |  | 1.00 |
|  |  | *2* |  |  |  |
|  |  | *3* |  |  |  |
|  |  | **National Disaster  Management Authority (NDMA)** | National Cyclone Risk Mitigation Project | *1* | Fire & Emergency unit at Dehwatoo |  | 20.00 |
|  |  | *2* |  |  |  |
|  |  | *3* |  |  |  |
|  |  | **Department of Drinking water  and Sanitation** | Jal Jeevan Mission | *1* | Repairement of PHE pipe line |  | 10.00 |
|  |  | *2* | Filteration plant |  | 10.00 |
|  |  | *3* |  |  |  |
|  |  | **Department of Animal  Husbandry and Dairying** | Rashtriya Gokul Mission | *1* |  |  |  |
|  |  | *2* |  |  |  |
|  |  | *3* |  |  |  |
|  |  | National Dairy Plan-II | *1* |  |  |  |
|  |  | *2* |  |  |  |
|  |  | *3* |  |  |  |
|  |  | Dairy Processing and Infrastructure Development Fund | *1* |  |  |  |
|  |  | *2* |  |  |  |
|  |  | *3* |  |  |  |
|  |  | Supporting Dairy Cooperatives and Farmer Producer | *1* | Immunizaiton to Live stock |  | 1.00 |
|  |  | *2* |  |  |  |
|  |  | *3* |  |  |  |
|  |  | National Livestock Mission | *1* | Provide Sheep Units |  | 4.00 |
|  |  | *2* |  |  |  |
|  |  | *3* |  |  |  |
|  |  | Livestock Census and Integrated Sample Survey | *1* | Achieve 100% target during the year |  |  |
|  |  | *2* |  |  |  |
|  |  | *3* |  |  |  |
|  |  | **Food  Processing Industries** | Pradhan Pantri Kisan SamapdaYojana (PMKSY) | *1* |  |  |  |
|  |  | *2* |  |  |  |
|  |  | *3* |  |  |  |
|  |  | **Skill  Development and Entrepreneurship** | Pradhan Mantri Kaushal Vikas Yojana (PMKVY) | *1* |  |  |  |
|  |  | *2* |  |  |  |
|  |  | *3* |  |  |  |
|  |  | National Apprenticeship Promotion Scheme (NAPS) | *1* |  |  |  |
|  |  | *2* |  |  |  |
|  |  | *3* |  |  |  |
|  |  | Jan Shikshan Sansthan | *1* | Tailoring Center |  | 5.00 |
|  |  | *2* |  |  |  |
|  |  | *3* |  |  |  |
|  |  | Skills Acquisition and Knowledge Awareness for Livelihood  Promotion (SANKALP) | *1* |  |  |  |
|  |  | *2* |  |  |  |
|  |  | *3* |  |  |  |
|  |  | Mahatma Gandhi National Fellowship (MGNF) | *1* |  |  |  |
|  |  | *2* |  |  |  |
|  |  | *3* |  |  |  |
|  |  | **Tribal Affairs** | Inclusive and sustainable growth of tribal population | *1* | Construction of Hostel Block |  | 200.00 |
|  |  | *2* |  |  |  |
|  |  | *3* |  |  |  |
|  |  | **Capex Plan** | UT Capex | *1* | Constr;of School Building at Paswal Mohallah ( Edu) |  | 20.00 |
|  |  | *2* | C/o additional class rooms for Govt. Primary school /KGBV / GMS Ladi ( Edu) |  | 30.00 |
|  |  | *3* | Providing of ATM facility (JK Bank) |  | 50.00 |
|  |  | *4* | Shifting of HT/LT line through Kooli Mohallah and change of timber poles all over Dehwatoo Pyt. ( Electric Deptt.) |  | 100.00 |
|  |  | *5* | 2 no. Tranfomer at Ladi Nai basti and Kothbal ( Eelctric Deptt.) |  | 20.00 |
|  |  | *6* | Establishment of Angan wardi center at Ladi at Kothbal (Social Welfare Deptt) |  | 10.00 |
|  |  | *7* | C/o road from main road to Koshi-Mohalla Ziyarat sharief ( RDD Deptt) |  | 10.00 |
|  |  | *8* | C/o lift irrigation scheme Ladi ( Irrigation Deptt) |  |  |
|  |  | *9* | Development of Patin Kol from RD 614 to onwards ( Irrigation Deptt) |  |  |
|  |  | *10* |  |  |  |
|  |  | District Capex | *1* | C/o Boundary Wall at Govt. Middle School Ladi with levelling of Play ground ( Edu Deptt) |  | 10.00 |
|  |  | *2* | C/o Boundary wall around Primary School / High School Dehwatoo ( Edu Deptt) |  | 15.00 |
|  |  | *3* | Fencing around Wellness center at Dehwatoo ( Helath Deptt) |  | 5.00 |
|  |  | *4* | Repairmenet of CRC building for meeting hall ( Edu Dpett) |  | 10.00 |
|  |  | *5* | Fencing of Ziyarat Sharief Khoshi Mohalla (RDD) |  | 10.00 |
|  |  | *6* | Fencing of Jamia Masjid at Dehwatoo (RDD) |  | 10.00 |
|  |  | *7* | Development of Play fields at Dehwatoo , Ladi by way of fencing . R.wall and B/Walls (RDD) |  | 25.00 |
|  |  | *8* | C/o link from main road to KGBV (RDD) |  | 2.00 |
|  |  | *9* | C/o Public Parks near Ladi Tourism Hut ( Tourism Deptt) |  | 15.00 |
|  |  | *10* | Flood protection bund at various spotsd at Ladi and Shalbaren ( Flood Constrol Deptt) |  | 10.00 |
|  |  |  |  | *11* | C/o Patwari Khana at feasible locaiton ( Revenue) |  | 7.00 |
|  |  | **PMGSY** | Road connectivity projects | *1* | Road from Dehwatoo to Shalbaran PMGSY |  | 150.00 |
|  |  | *2* | Road from Ladi to Kotbal (R&B) Deptt; |  | 100.00 |
|  |  | *3* |  |  |  |

**InadditionGPDPplanshallalsoinclude:**

 Touristplaceswhichneedtobedeveloped Park near ply ground ladi

 Specificproductwhichneedstobedeveloped Park NeaR Tourism hut

 Tourism-homestays 02

 20 candidates for training under Himayat scheme alongwith trade in which trainingis to be given list below

|  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
| S.No | **Name of the Village** | **Name of the concerned Department** | **Scheme** |  | **Name of the proposed work** | **Ward.no** | **Estt Cost** |
|  | **Dehwatoo** |  |  |  |  |  |  |
|  |  | **Skilled Dev.Deptt;** | HIMAYAT (DDU-GKY) (20 candidates to be identified per panchayat) | *1* | Parveena Jan -- Qualif;12th Tailoring |  |  |
|  |  | *2* | Aabid Hussain Shah --10th Plumber |  |  |
|  |  | *3* | Humaira Jan -- B.A Computer |  |  |
|  |  | *4* | Mohd. Altaf Paswal -- 12th Plumber |  |  |
|  |  | *5* | Parvaiz Ahma Sood -- 10th Plumber |  |  |
|  |  | *6* | Jugnoo Jan -- B.A Computer |  |  |
|  |  | *7* | Lateef Ah. Paswal -- 10th Plumber |  |  |
|  |  | *8* | Surya Jan -- B.A computer |  |  |
|  |  | *9* | Shugfta -- 12th Tailoring |  |  |
|  |  | *10* | Tufail Khanday --12th electrician |  |  |
|  |  | *11* | Sheezan Ah. Wani --12th Electrician |  |  |
|  |  | *12* | Sajad Ah. Mir -- B.A computer |  |  |
|  |  | *13* | Hamid Ah. Mir -- 12th Eelctrician |  |  |
|  |  | *14* | Bilal Ah. Mir -- M.A Computer |  |  |
|  |  | *15* | Gulzar Ah., Mir - B.A Computer |  |  |
|  |  | *16* | Naseer Ah. Mir - B.A Computer |  |  |
|  |  | *17* | Tariq Ahmad Mir - 12th Electrician |  |  |

**DAY2ACTIVITIES**

**AGENDA5**

Ensuresaturationoffollowingschemesandgivestatus:

|  |  |  |  |
| --- | --- | --- | --- |
| **NAMEOFTHESCHEME** | **TOTALELIGIBLE BENEFICIARIESIN THE VILLAGE** | **TOTALBENEFICIARIESWHO AVAILEDTHEBENEFITSOFTHESCHEME** | **REASONSFOR PENDENCY** |
| GoldenHealthCardunder  AyushmanBharat | 1597 | 1430 | Adhaar Card mot linked with phone |
| Jananisurakshayojana | 20 | 20 |  |
| OLDAGEpension | 87 | 87 |  |
| Widowpension | 38 | 38 |  |
| Disabilitypension | 56 | 56 |  |
| Domicilecertificate | 1597 | 850  1085 |  |
| Kisancreditcard | 1240 | 1085 |  |
| PMkisansammannidhi | 300 | 285 |  |

|  |  |  |  |
| --- | --- | --- | --- |
| Landpassbook | 645 | 204 | Online generation |
| Registrationofvillageven- dorsonGEMportal |  |  |  |
| Registrationofvillagecon- tractorsonjktendersportal | 20 | 1  11 |  |
| Registrationofvillagecon- tractorsonPWDportal |  | 1 |  |
| Incompletebuildings/pro- jects | - |  |  |

**DAY2ACTIVITIES**

**AGENDA6**

**NASHAMUKTABHIYAN**

1. Whethergramsabharesolutionpassed yes

2. Detailsofactivities conducted Awareness campus

3. Whetherallactivities andGSresolutionuploadedonjkpanchayats.inportal Yes

4. Howmanydrugaddictsinthevillage Nil

5. WhetherreportedtotheDeputyCommissioner Nil

6. Howmanyregisteredforrehabilitationundergovernmentprogramme Nil

**DAY2ACTIVITIES**

**AGENDA7**

**SOCIALAUDIT**

Conductsocialauditofatleast5workseachunderfollowingschemes:

|  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- |
| NAMEOFTHE SCHEME | DETAILSOFTHE WORKS | YEAROFWORK APPROVAL | AMOUNT APPROVED  FORTHEWORK | WHETHER  WORKEXECUTED SATISFACTORILY | GEO- TAGGED PHOTOS | ANY GRIEVANCE RECORDED RELATINGTOTHAT WORK |
| MGNREGA | 5 | 21-22 | 18.50 | yes | yes | No |
| PMAY | 10 | 22.23 | 5.00 | U/C | yes | 2nd installment |
| IHHL  UNDERSBM-G | 7 | 2021-22 | 0.84 | Yes | Yes | -- |
| CSCUNDER SBMG | - | - | - | - |  |  |
| AMRIT SAROVARS | 4 | 22-23 | 4.00 | 2 No. U/C | Yes |  |

**DAY2ACTIVITIES**

**AGENDA8**


**MAHILASABHA**

Totalwomeninthevillageabovetheageof18 310

Totalattended 50

Proceedings:Awareness – Regarding health, Skill Development and Education

*(Plinsertpointerstobediscussedthere–referpalliproceedings)*



**DAY2ACTIVITIES**

**AGENDA9**


**BALSABHA**

Holda balsabhaandrecordproceedings Awareness

Totalchildreninthevillageabovetheageof 05= 184 Totalattended 30

Proceedings: Awareness of health , Edu. Sports

*(Plinsertpointerstobediscussedthere–referpalliproceedings)*



**DAY2ACTIVITIES**

**AGENDA10**

**INAUGURATIONS**

|  |  |  |  |
| --- | --- | --- | --- |
| **SR NO.** | **ASSETS/ACTIVITIES INAUGRATED** | **STATUSOFTHEASSET/AC- TIVITIES(NUMBER,OTHER DETAILS)** | **GEO-TAGGED PHOTOS** |
|  | VILLAGEHAATunderJKSRLM (SUN- DAYMARKET) | 2-Activites | Yes |
|  | PMAYhousesifanyreadyforinaugra- tion | All under Construction | Yes |
|  | Swachhgramprojects-segregation shedsetc | Composite & Soakage pits | Yes |
|  | Amritsarovars | 4 | Yes |
|  | Sportskits | 1 | Yes |
|  | Villageculturalevents | 1 | Yes |
|  | JJMassets/projects | - | - |
|  | Anyothertobeidentifiedatdistrict level |  |  |

**FOLLOWUPOF(B2V1,B2V2&B2V3):**

*(Prefilledexcelsheet tobetakenfromdistrictlevel/andalsotobedownloaded*

*from*[*www.jkpanchayat.in)*](http://www.jkpanchayat.in)

|  |  |  |  |
| --- | --- | --- | --- |
| S.NO. | Particulars | Actiontaken | Remarks# |
| I. UrgentPublicRequirements/Demands-B2V1 | | | |
| 1 | Power supply important | 2 No 63KV sub stations instllaed | Repariement pending |
| 2 | Improvement of water supply |  | Partially done |
| 3 | C/road from Ladi to Shalbaren | Pending | Yet to be taken |
| 4 | Lift of irrig. Project at Kothbal | Pending | \_ |
| 5 | C/road from Ladio to Dehwatoo | Pending | \_ |
| 6 | L/Road from Ladi to Kothabal | Pending |  |
| 7 | Establishment of Higher Sec.School | No feasible |  |
| II. UrgentPublicRequirements/Demands-B2V2 | | | |
| 1 | C/o Motorable road at Kothabal | Pending | Not taken up |
| 2 | Motorable road at Dehwatoo to Shalbaren | Pending |  |
| 3 | New pipe line by PHE | Partially taken up |  |
| 4 | Foot bridge badroo | Pending | Non availability of funds |
| 5 | Lift of Irr.Project Kothabal | Pending | - |
| 6 | Motorable roaed at Ladi Shalbaren | Pending |  |
| 7 | Improvement HT, LT line | Pending |  |
| S.NO. | Particulars | Actiontaken | Remarks# |
| III. MajorProblems–B2V1 | | | |
| 1 | Poor power Supply | Pending | Needed |
| 2 | Poor water supply | Pending | Urgent |
| 3 | Upgradation of L/Road | Pending | Urgent |

|  |  |  |  |
| --- | --- | --- | --- |
| IV. MajorProblems-B2V2 | | | |
| 1 | Poor Power supply | Pending | On priority |
| 2 | Poor water supply | Pending | On priority |
| 3 |  |  |  |
| 4 |  |  |  |
| 5 |  |  |  |
| V. MajorProblems-B2V3 | | | |
| 1 | Motroable road at Kothbal | Pending | Most urgent On priority |
| 2 | Improvement of water supply | Pending | Most urgent On priority |
| 3 |  |  |  |
| 4 |  |  |  |
| 5 |  |  |  |
| VI. MajorComplaints-B2V1 | | | |
| 1 | People of Ladi feels that they are deprived from benefits as compared to Dehwatoo |  | Equal share should be given |
| 2 |  |  |  |
| 3 |  |  |  |
| VII. MajorComplaints-B2V2 | | | |
| 1 | Same as above |  |  |
| 2 |  |  |  |
| 3 |  |  |  |
| VIII. MajorComplaints-B2V3 | | | |
| 1 | Same as above |  |  |
| 2 |  |  |  |
| 3 |  |  |  |

**OVERALLPERCEPTIONOFFUCNTIONING OF GOVERNMENTDEPARTMENTS**

1. **BESTDEPARTMENT: Education**

**2. LEASTRESPONSIVEDEPARTMENT:RDD**

**GENERALASSESSMENTOFTHEVISTINGOFFICER**

|  |  |
| --- | --- |
| I | Any major complaint broughttothenoticeoftheVisitingOfficer:   1. 2nd installment has not paid to PMAY beneficiaries 2. There is lackage of Pathin Kull 3. Internal link roads are not properly maintained 4. Poor sanitation in Pyt. Halqa 5. Poor electric supply and change of timber electric poles and shifting of 11 KV Line along Kooli Mohallah 6. All schools /wellness centre are in open premises. |
| II | Major/urgentpublicdemandsthatwas/werereflectedearlierbuthavenotbeenaddressedsofar:   1. Motorable road form Ladi to Kothbal and Dehwatoo to Shalbaren not taken up by any Deptt; 2. Poor Water supply ( works has been done partially) 3. Electricity works still pending 4. Lift irrigation scheme at Ladi not taken up |
| III | Overall assessment of the visit and suggestions:  (Thevisitingofficertoensurethattheoverallassessmentisrecordedindetailsalongwithconcretesugges- tions)   1. Internal link road need urgent attention for their construction by way of concrete lane , tile paths. 2. There is poor sanitation Rural Development should focus on its proper sanitation by way of awareness / construction of Drains and compost pits. 3. Dev.of ply fields at Ladi and Dehwatoo by way of R/wall and B/wall with fencing 4. Maintenance of L.T line by way of its shifting alignment and removal of timber poles 5. Boost horticulture , sheep rearing and skill dev. For upliftment of general public particularly ST to earn their livelihood 6. Const;of public parks and providing registration of home stays to uplift Tourism Sector in area 7. To develop schools and wellness center by way of providing Boundary walls around the periphery |
| IV | OverallRatingofgovtfunctioningas givenbythePanchayat(Scaleof0to10) 05 |
| V | CertificatefromSarpanchthatthevisitingofficerhasstayedinthepanchayatfor2days – Certified |


**SignatureofSarpanch SignatureoftheVisitingOfficer**

**Name: Sakeena Banoo Name: Nissar Ahmad Wani**

**( Asstt. Executive Engineer)**

**T.O to Suptdg; Engg.**

**PWD (R&B) Circle Ang/Kulgam**





**DepartmentofRuralDevelompentandPanchayatiRaj**

**GovernmentofJammu &Kashmir**