4

15TH OCTto3RD NOV,2022

KEYFEATURES

•     DeputyCommissionerstoleadtheinitiative

•    RuraldevelopmentDepartmenttobethenodaldepartment

•	PlanningDevelopment&MonitoringdepartmentandITtobethesupport departments

ACTIONSANDTIMELINES

| ACTION | RESPONSIBILITY | LATESTBY | REMARKS |
| --- | --- | --- | --- |
| Janabhiyan | Alldepartments | Oct15-26th | Goingon |
| DeputationofSecttstaff/ HoDs | GAD | Oct14 | Done |
| DeploymentofStaffto Panchayatsandservingof ordersondeployedofficers | DCs | Oct25 | DCswilldeployseniorlevelstaff fromthedistricts.Strictactionto betakenagainstabstentions.No exemptionstobegiven |
| Trainingofdistricttrainors onB2V4 | RDD | Oct26 |  |
| Trainingofvisitingofficers | DCs | Oct27 |  |
| FieldVisitstobecompleted by | VisitingOfficers | Nov3 | DCstosuperviseandensurethat eachPanchayatisvisitedwithin theperiodspecified |
| DataofB2V4tobe uploadedby | VisitingOfficers | Nov10 | DCstosuperviseandensurethat dataofallPanchayatsisupload- edbythevisitingofficerwithin theperiodspecified |

INSTRUCTIONSFORTHEVISITINGOFFICER(DAYWISE)

| DATE | INSTRUCTIONS | ACTIONPOINTS |
| --- | --- | --- |
| Day0 | Meetingwithdeputy commissionerandhis/her team | a. TakeprintoutsoffilledbookletsofB2V1,B2V2andB2V3from www.jkpanchayat.in b.Alsotakeprintoutsofthesummarizedexcelsheetsofthe previousphasesfromwww.jkpanchayat.in c. CollectATRsonissuesraisedduringprevious3phasesfromthe officeofDeputyCommissioner(Planningdeptt) d.Takeprintsofblank 2bookletsofB2V4fromwww.jkpanchayat.ine.Takeplansfor2previousyearsandATRsfromtheplanningdeptt f. CompletetrainingsondifferentcomponentsofB2V4being organizedbyrespectiveDeputyCommissioners g.CollectListofnewworksstarted/ongoing/completedduringthe previousandcurrentFinancialyearunderthefollowingheads: • PRIgrants • DistrictPlan • UTplan • MGNREGA • Otherschemesofotherdepartments • Anyotherwork h. Plans/beneficiarylists: • MGNREGAdraftplandocumentfortheyear2022-23. • ListofAwaas+beneficiariesalongwithIHHL Convergence • Listofpensionbeneficiaries. • ListofSHGs • Listofagricultureschemebeneficiaries i. Listsofbeneficiariesfor: • Variouscertificates/benefitstobedistributedbythe visitingofficer. • Anyotheractivitiesidentifiedbydifferentdepartments |

| Day1 | Reachthevillage | 1. | Ensurethatallfrontlineworkersofdifferentdepttsarepresent. |
| --- | --- | --- | --- |
|  |  | 2. | Ensureexhibitionbydifferentdepts.aboutindividualbeneficiary schemes |
|  |  | 3. | InspectJKB/PSBcounters/outlets |
|  |  | 4. | Participate/ensureorganizationofsportsactivityinplayfield,talent hunt/culturalevent/youthactivity |
|  |  | 5. | GandhiKatha(suggesteddetailsuploadedonjkpanchayat.in) |
|  |  | 6. | Visitatleast2amritsarovarsandgetitsgeotaggedphotos |
|  |  | 7. | InspectKhidmat(CSC)CentresandcreateGenerateawarenesson 225schemesparticularlyG2CschemeslikeBEAMS,Janbhagidari, AapkiZaminAapkiNigrani,DigitalJ&K |
|  |  | 8. | Visitingofficershallalsoplanandconductpanchayatlevelconver- gencemeetingofalldepartments |
|  |  | 9. | CheckeffectivenessofCentrallysponsoredschemes |
|  |  | 10. | VisitandinspectallgovernmentestablishmentsincludingPHE, AWC,FPS,schools,etc |
|  |  | 11. | Attemptsaturationofdeliverableso JanAbhiyanandwherever deficienciesfound,leadadrivetoachievealldeliverables |
|  |  | 12. | Assesseffectivenessofsanitationcampaigninthepanchayat |
|  |  | 13. | Ensureselfemploymentactivitiesfor15youthperpanchayat |
|  |  | 14. | Identify20potentialcandidatesperpanchayatforHIMAYATtraining alongwiththetradeonwhichtheywanttraining |
|  |  | 15. | Whereverpossible,distributeemploymentlettersforpeopleselect- edundervariousgovernmentemployments |
|  |  | 16. | Intheevening,holdnormalmeetingwith seniorcitizens,govtem- ployeesincludingretiredemployees,exservicemen,youthclub,and any citizens ofthevillagewhoareenrolledincollege/university |
|  |  | 17. | OpendiscussiononNashaMuktAbhiyan |

Day2            Haveameetingwithall stakeholders-depttofficials andpanchayatmembers

1.       Discussionontheandassesstheprogressofdifferentschemesrelating tothelocalizedSDGsprioritizedforthatvillageaspertheresolution passedby thatGramPanchayaton21st April22,onNationalPanchayti RajDay.

2.	Sensitizevillage residentsaboutmyScheme”portal(myscheme.in) whichincludesinformationaboutalltheschemesbeingrunbyCen- tral/State/UTgovtacrossthecountry

3.	Hold meeting of theBiodiversityManagementCommitteestodeliber- ateonissuespertaining toconservation of biodiversityandsustaina- bleutilizationof biologicalresources.

4.       PrepareVillagedevelopmentplan,inconsultancywithGrampanchayat, discussitingramsabhaandgetitapproved.

5.       Ensure saturationofsoilhealthcardandgoldenhealthcardunderGold- enHealthCardunderAyushmanBharat,

6.       Ensuresaturation  of OldAge PensionScheme

7.       EnsureDomicileSaturation.

8.       EnsureKCCSaturation

9.       Ensure saturationoflandpassbooks

10.     Ensureregistrationofvillagevendorsneededforanyscheme,onGEM

portal

11.     Ensurepanchayatcontractors registration

12.     EncouragePanchayatmembers forimportanceofplantationdrivein

PanchayatunderHarGaonHariyali

13.     Ensure paintingondigitalJ&Kinpanchayatghars

14.     Ensure paintingonpanchayatactivitesandCSSinpanchayatghars

15.	Thevisiting officeshallchecknoof kindergarten andplayfields present inthepanchayat for kidsandstudents,iftheinfrastructure present inthesearegoodenough.

16.     Holdmeeting withpanchayatmembers todiscussaboutcorruption menaceandstepsrequiredtomakeJ&Kcorruptionfree

17.     Obtaina candidassessmentaboutperformanceofvariousdeptts in- cludingfairfeedbackaboutdiscrepanciesinfunctioning

18.	Check thestatusof NashaMuktAbhiyanandreporting of drugad- dictstoDeputyCommissioner.

19.     IdentifyTouristDestinations,Circuits,ThemeTreks,IdentifyHomestays, providesupportfortourismactivities throughVillageCooperative

20.     OrganizeTalentHuntatPanchayatLevel

21.     Conductsocialauditofatleast5worksunderfollowingschemes:

a.       MGNREGA

b.PMAY

c.        IHHLtoiletsandpayments d.CSCs

e.AMRITSAROVARS

22.     Holda mahilasabha anda balsabhaandrecordproceedingsinthefor- matgiven

23.     InauguratevillagehaatunderJKSRLM

24.     Checkifyouthclubsareformedinthepanchayatandwhatactivities theyareengagedin

25.     Organizea villagelevelculturaleventtoengagepanchayatmembers

26.     SensitizeGPaboutE-kitabkoshaninitiativeofJ&KGovtforempowering youthsthrough onlinedigitalliteracy

GENERALINSTRUCTIONS

1.	Thevisitingofficershallrefrainhimself/herselfgivingorofferinganycommitmentonbehalfofthe governmentandshalladoptanunbiasedattitudeinreportingissues.As faraspossible,his/her observation shouldbebasedona fairandanalytical viewemergingfromhis/herinteractioninthe village.

2.	Heisgoingtothevillageasplanningofficer,notforsanctioninganyworksorformakinganycom- mitments.

3.	Whilepreparingvillagedevelopmentplan,hehastoensurethat,demandsareprioritizedandre- flectedunderavailableschemes,wherevernecessarythelargerworksaretobereferredtoadminis- trativedepttunderCSS/UTplansunderintimationtoDCsandrestoftheworkstoDCsforreflecting itunderdistrict/CSS plans

4.    His workshallbehardcoreplanningandauditandisnota PRexercise.

5.	EveryDeputyCommissionerhastoensurethatatleastoneRDDofficial(ideallyPanchayatSecre- tary)ispresent  ineverypanchayatwithrelevantpanchayatrecords,toensureconductofallactivi- tiesasplanned.Panchayatwiseorderneedstobeissuedinadvance.

6.	Visitingofficershouldideallycarryhis/herlaptoptocompletethereportsatthepanchayatlevel itselfanduploadthefinalreport,duly signedbothbythesarpanchandbythevisitingofficeron www.jkpanchayat.inportal,beforetheyleavepanchayat.

7.	Focus ofvisitareyouth,skills,self-employment,nashamukt,bhrashtracharmukt,Rozgaryukt J&K, besidestocarryforwardtheactivities duringJanAbhiyanandsaturatethem.

8.    Inadditionattentionmaybegiventothefollowingareas a.     MakefulluseofCentrallySponsoredSchemes

b.Saturationofindividualbeneficiaryschemes c.     Self-employmentschemes

d.Banklinkedschemes-includingdepartmentalsubsidyschemes e.Empowermentandtransparencythrough digitalinitiatives

f.       Effectivenessofgrassrootsmachinery–

i.       Patwari,VLWpresent  andavailable

ii.      AvailablefundsutilizedinpublicinterestandasperGramSabharesolutions iii.   Fairness ingovernance

iv.    CSS/Individual beneficiaryschemesetc v.      BrashtacharMuktJ&K

vi.   BhaiMuktJ&K

vii.  NashaMuktJ&K

9.	ThePRImembers (Sarpanchs,Panchs,BDCChairperson)shallbeattheforefrontofallactivities and givendueimportanceandtheapproach shouldbetostrengthenthemandmakethemfeelem- powered.He/sheshallensurethattheBDCchairpersonandSarpanch/Panch arepresent  atthetime ofinaugurationandceremonies.

10.	Visitingofficershallnotleavethedistrictwithoutuploadingthereport,duly signedonthewww. jkpanchayat.inportal.EveryDeputyCommissionerhastoensurethat.

A)   DetailsofReportingOfficer:

Name:  Er. Nissar Ahmed Wani :

Designation:- Assistant Executive Engineer PWD (R&B) Circle Ang/Kul

Department/place of  posting: PWD (R&B) Circle Ang/Kul

MobileNo:7006422968

EmailID:nissarusman786@gmail.com

HomeDistrict:Anantnag

Datesof  visit:02.11.2022 to 03.11.2022

B)	LocationaldetailsofPanchayat:(tobepre-filled,informationtobetakenfromtheprevious phasesbooklets/summarizedexcelsheetuploadedonjkpanchayat.in/b2v4.php)(tobevali- datedbythevisitingofficerandmissingdetailstobefilled)

NameofthePanchayat:Dehwatoo

Local GovernmentDirectory(LGD)codeof  thePanchayat:274685

Nameof  CDBlock:Pahalgam

NameofTehsil:Sallar

Nameof    District:Anantnag

C)     PanchayatProfile:

No.ofrevenuevillagesinthePanchayat:df. (2) Dehatoo & Ladi

No.ofhamletsinthePanchayat:7

No.ofhouseholdsinthePanchayat:341

Population(approx)of  thePanchayat:1597

Part-II:

(TobefilledupbytheVisitingOfficerduringhis/hertwodayvisittothePanchayat.AllFieldshavetobe

filledbytheVisitingOfficerbeforethebookletishandedovertotheDC

FrontlineOfficers/OfficialswhowereassignedtothePanchayatfortheprogramme:

| Department | Name | Designation |
| --- | --- | --- |
| Rural Development RDD | Mushtaq Ahmad Ganie | G.Rs |
| Irrigation | Mohd. Shafi Wani | Pathwari |
| Jal Shakti | Ab. Gani HaJAm | Assistant Line man |
| PWD R&B | Gh Qadir Shah | Road Supervisor |
| PDD | Jitandar Singh | Line man |
| Education | Aijaz Rasheed Wani | RREt |
| Food & Supplies | Mudasir Ah Bhat | Ask.cum clerk |
| Agriculture | Shujeet Aalam | JE/Eo |
| CSC | Shahmdevcel Iqbal | CSC VLE |
| Aanganwardi | Shabnam Akhter | Anaganwarid Worker |
| Forest | Mohd Yaseen Mir | Watcher |
| Health | Nusrat Aara | Aisha |

Detailsofabsentemployeesvis-à-vislistfurnishedbytheDCoffice:

| Department | Name | Designation |
| --- | --- | --- |

DAY1-ACTIVITIES

AGENDA1:PANCHAYATASSETREGISTER

Infrastructure:

1.		PanchayatGharInfrastructure a.  Govtbuilding/private  Yes

b.  New/needingrepairs: Needs Repairment

2.       Furniture(Y/N) Yes

3.       Computer/printer(Y/N) yes

4.       Internet(Y/N) No

5.       Telephone(Y/N) No

6.       Toilet(CSC/partofpanchayatghar)(Y/N) Yes Needs repairment

7.       Water(Y/N) Yes

8.       Electricity(Y/N) No

9.       Bankbranch(Y/N) Yes

10.     CSC(Y/N)              Yes

11.     Patwarkhana(Y/N) Yes damaged

12.     Villagehaat(Y/N) Yes

13.     Playground(Y/N) Yes Needs further development

14.     School-

a.        Kindergarten(Y/N) No

b.Primary(Y/N)                  Yes

c.         Secondary(Y/N)      Yes

d. College (Y/N)                 No

e.University(Y/N)               No

15.     AnganwadiCentre(Y/N)        Yes 05

a.        (govt/private)       Rented

b.Totalchildrenenrolled    145

15.     AmritSarovars–details,location,condition   2 under construction

16.     Governmentoffices-details,whetherfunctionalornot Functional

17.     Rationshop(Y/N)      Yes

18.      Placesoftourismimportance–names,littledetailsonhistorical/culturalimportance Pat at Ladi

19.      Villageheritagesites/treks-names, littledetailson historical/cultural importance

20.     VLWOffice (Y/N) yes

21.     PrimaryHealthcareCentre(Y/N), Wellness Centre

22.     ListofIncompleteBuildings-names,yearofconstruction        Nil

23.     ListofUnderutilizedBuildings-names Pyt. & Govt.School building

DAY1-ACTIVITIES

AGENDA2:

DIFFERENTINSTITUTIONS/INFRASTRUCTUREPROJECTSTOBEVISITED

| AMRITSAROVARS | Visit,verify | COMMENTS |
| --- | --- | --- |
| KhidmatCentres | Create/Generateawarenesson225schemes particularlyG2CschemsAapkiZaminAapkiNigrani, Beams,Janbhagidari,DigitalJ&K | Functional Visit and verified |
| JKB/PSBcounters/outlets | a)Statusofcounter 06b)Numberofvisitor 100+ | Functional ( Good) Locals demand installation of ATM |
| Incompletebuildings/pro- jects | Verify whetheridentificationandredistribution done | -- Satisfactory |
| PDS | Visit,evaluate,onlinestatus | Satisfactory |
| PHC wellness center | Visit-evaluate,statusofstaff,equipmentand quality | Deficiency of staff |
| Youthclubs | Meet,interact,seeksuggestions | Needs Awareness |
| SHG Adolescence girls | Meet,identifyproblems,seeksuggestions | Needs Training |
| PMAY | Inspect,Inaugurate ( incomplete) | Lack of funds |
| Myschool,mypride progress;schools-water, toilets,staff | Visit,checkforwater,electricity,sanitation,meet studentsandstaff | Satisfactory |
| SwachhSBM | Evaluate | Poor sanitation |
| Panchayatplayground, Sportskitsdistribution Villagegames | Ensure,verify.Participateinatleastonegamein theplayground | Ply filed needs development |
| HarGaonHariyali, Planta- tiondrive | Evaluatestatus,feedback | Nill |
| Villageculturalevent Dangal/Haat/Mela | Participatein;ensurethatitisheld | Good |
| Exhibitionofschemes | Ensurethateverydepartmentparticipatesand thatitcontinuesfortheentiredurationofB2V | PDD. Social Welfare & Forest Agriculture |
| JalJeewanMission verifica- tion- WSS/JSD Electricitysupply | Verify | Needs water filtration Plant |

DAY1-ACTIVITIES

AGENDA3:SATURATEJANBHIYAN

DELIVERABLESANDRECORDDEFICIENCIESIFANY(INSERTDELIVERABLESLISTHEREASPERGADFORMAT

DAY1-ACTIVITIES

AGENDA4:

SELFEMPLOYMENTACTIVITIES

EnsureSelf-employmentactivities foryouth,distributeemploymentlettersforpeopleselectedunder varioussocialschemes(15ISTHETARGETPERPANCHAYAT)

Numberofcasesindifferentcategoriessanctioned:     3 Detailsofthebanksanctioningit: 1

Totalamountinvolved:10.00 lakhs

DAY1ACTIVITIES

AGENDA5

Intheevening,holdinformalmeetings  withseniorcitizens,govtemployees,retdemployees,youthclub andothercitizenswhoareenrolledoncollege/universityandhavediscussiononGandhiKatha,Nasha MuktAbhiyan,corruptionfreegovernance,doublingfarmersincomeandrecordtheproceedings

Activities done resolutions enclosed

DAY2

a.       NoofIndividualCompostPitsconstructed 80 b.NoofIndividualSoakPitsconstructed             90

V.          No.ofBiodiversitymanagementcommitteemeetingsheld:2

VI.         IsthenameofSarpanchdisplayedoncitizeninformationboardsofallRD&PRschemes:Yes/No Yes

VII.       AreSarpanchsbeinginvolvedinstart/inaugurationofactivities:Yes/No Yes

VIII.      WhethersubjectshavebeenassignedbytheSarpanchtothePanchs:Yes/No Yes

IX.        Whethergrievancesredressalboxisinstalled:Yes/No No

X.         NoofgrievancesreceivedpertainingtoPanchayatlevel: 4

XI.        NoofgrievancesdisposedofatPanchayatlevel:  Nill

XII.       WhethertheSarpanch/PanchayatSecretaryhavedigitalsignatures:Yes/No Yes

XIII.      WhetherallMGNREGA/14thFCpayments arebeingmadebySarpanchthrough DigitalSignature

Certificate(DSC):Yes/No   Yes

HUMAN RESOURCEAVAILABLEATTHEPANCHAYAT LEVEL:

| SRNO. | DEPARTMENTWISESTAFF | NUMBERS |  | NAMES |
| --- | --- | --- | --- | --- |
|  |  | SANCTIONED | ACTUAL 1 |  |
|  | Ruraldevelopmentdepartment: BDO JE GRS TA | 1 1 1 1 | 1 1 1 1 | Malik Muzafar Ahmad |
|  | SCHOOLEDUCATION: TEACHER HEADMASTER ANYOTHER | 19 1 5 | 19 1 5 |  |
|  | JAL JEEVAN: | 2 | 2 |  |
|  | PDD: LINEMAN JE ANYOTHER | 2 1 3 | 2 1 3 |  |
|  | FOOD&CIVILSUPPLIES | 2 | 1 |  |
|  | AGRICULTURE&ANIMALHUS- BANDARY | 1 | 1 |  |
|  | SOCIALWELFARE | - | - |  |
|  | HEALTH: ASHA ANM AYUSHDOCTOR ALLOPATHICDOCTOR | 1 1 1 - | 1 1 1 - |  |
|  | ANYOTHERDEPARTMENT | 5 | 5 | ICPS |

DAY2-ACTIVITIES

AGENDANO.1

DiscussionontheandassesstheprogressofdifferentschemesrelatingtothelocalizedSDGsprior-itizedforthatvillageaspertheresolutionpassedbythatGramPanchayaton21stApril22,onNational PanchayatiRajDay(Copyoftheresolutiontobetakenfromwww.jkpanchayat.inportalunderthelinkof GramSwarajMonth)

1.       SDGs AGREED FORTHATVILLAGE,TOBEIMPLEMENTED BYMARCH2024:

2.       STATUSOFWORKSUNDERTHEFOLLOWINGSCHEMES:

1      Cleanandgreenvillage

i.InitiativestakenbythePanchayatformanagingSolidandLiquidWaste Composite & Soakage pits.     InitiativestakenbythePanchayatforusinggreensourcesoffuellikesolar,biogas NIL

iii.  Hasmappingoflanduse,waterbodies,forest,slopes,wetlands,degradedforestwithintheGram

Panchayatbeendone?Yes/No.IfNo,reason,thereof Yes

iv.    HastheClimateResiliencePlanbeendevelopedfortheGP?Yes/No No

v.     StepstakenbytheGramSabhaabouttheclimatechangemitigationfactorslikereducingenergy consumption,usageoffossilfuels,plastics,non-renewablebuildingmaterialsandalsotopromote measureslikeplantingoftrees,conservingforests,usageofgoodagriculturalpracticeslikedrip irrigation,waterconservationmeasuresandconservationofwetlands.

vi.  Whetherschoolshavestartedsegregatingwaste Yes

vii. Whetherschoolshavetheirowncompost/soakagepitsforsolid/liquidwastemanagement Yes

2     Healthyvillage

i)    Aremeetings  relatedtoVillageHealthandSanitationCommitteebeingheldregularly?

ii)   DoalltheeligibleindividualsbeenprovidedtheGoldenCard? Yes 90%

iii)  ArealltheChildrenbeingimmunizedaspertheSchedulerecommendedbyGovt.ofIndia? Yes

iv)  ArealltheeligibleindividualsbeenvaccinatedagainstCOVID-19?Yes

v)   DoesGramPanchayatensurethatallpregnantwomenaregettingnecessaryprenatalcheckups? Yes

vi)  WhetherallthedeliverieswereInstitutionalizedorconductedbytrainedMidwives? Yes

3     Watersufficientvillage

i)    DoalltheIHHsintheGramPanchayathavewaterpipelineconnections? Yes

ii)   WhetherGramPanchayathastakenstepsforgreywatermanagement.IfYespleasespecify iii)  No DoalltheIHHsintheGramPanchayathavetoilets? Yes

iv)  ArealltheIHHstoiletsfunctionalornot? Yes

v)   DoalltheSchools/Anganwadicentershavea toiletfacilityornot? Yes

vi)  Areallthetoiletsintheschools/Aaganwadifunctionalornot? Yes

vii) WhetherGramPachachayatBhawanhasseparate toiletsforwomenornot?No

4      ChildFriendlyvillage

i)	Doallthechildrenundertheageof0-6yearsbeenenrolledintheAnganwadicentersforpre- schooling?Yes/NO

ii)    HowmanyBalSabha’swereorganizedintheGramPanchayat--01-----------------

iii)  WhethertheissuesraisedbyBalSabhaareaddressedduringtheGramSabha. Yes/NO No

iv)	WhetherGramPanchayatistrackingthedatarelatedtodropoutchildrenandchildrenwithirregular attendance?Yes/NO. No

v)   DoalltheschoolsundertheGramPanchayathaveseparate toiletsforgirlsandboys?Yes/No Yes

5      Villagewithgoodgovernance

i)    IsCSClocatedintheGramPanchayatBhawanornot? Yes

ii)	IsthelistofbeneficiariesrelatedtotheSchemes/ProgramsdisplayedontheGrampanchayatwallor not?Yes

iii)  DoestheGramPanchayathasitsbuildingornot?yes

iv)  IstheGramPanchayatofficefunctionalornot?Yes

v)   Aretheactivities approved undertheHalqaPanchayatDevelopmentPlandisplayedontheGram

Panchayatwallornot? Yes

vi)  IsSocialAuditofearlierSchemes/Programscarriedoutornot? Yes

6      Povertyfreeandenhancedlivelihoodvillage

- HasGramPanchayatdevelopedanycriteria fortheidentificationofthepoor?Yes/Noifyesspecify NO

- HavealltheeligiblehouseholdsregisteredinPDSornot?Yes

iii)	HasGramPanchayatprovidedspaceforSelf-helpGroupsinPanchyatGharforholdingmeetings  or not?Yes

iv)  HavealltheeligiblehouseholdsbeenregisteredforPensionornot?Yes

v)   HasGramPanchayatfacilitatedYouthforSkillEnhancementCoursesandPlacement?No

vi)  HasJobCardsbeendistributedtoalltheeligibleindividualsunderMGNREGA?Yes

vii) HasGramPanchayatfacilitatedSHGsforBankAccountLinkages?Yes

7     Sociallysecuredvillage

i)    WhetherGramPanchayatismaintainingdatarelatedtoDifferentlyAbledPeople?Yes

ii)   IsGramPanchayatOffice DisabledFriendlyornot?No

iii)	Areprovisionsfora separate BudgetundertheResourceEnvelopeforWomenandChildrenmadeor not?No

iv)	DoalltheSchools intheGramPanchayathavefacilitiesforDifferentlyAbledChildrenliketoilets, barrier-freeaccess,etc.,ornot?yes

v)   Arealltheeligibleindividualsaregettingpensions,likeoldagepension,widowpension,etc?Yes

vi)  ArealltheeligiblehouseholdsgettingbenefitsfromIAYornot?yes

8      EngenderedDevelopmentinVillage

i)    HowmanyMahilaSabha’swereorganizedintheGramPanchayat-----01--------------

ii)	WhetherSHGsfederationshavebeenprovidedspaceformeetings  inthePanchayatBhawan(Yes/ No)No

iii)  WhetherGPshavetakenstepsforincreasingwomen’sparticipationinGramSabha(Yes/No)Yes

iv)  NumberofwomenbeneficiariesheadedhouseholdscoveredunderPDS

system…………08……………

v)   Numberofbeneficiaries(outoftotaleligiblepopulation)receivingsocialprotectionbenefitsunder

PradhanMantriMatritvaVandanaYojana……40…………….

9    Self-sufficientinfrastructureinthevillage

i.	WhetherGPhasa CommunityHallwithaccesstoelectricity,furniture,watersupply, toilet………No……………….

ii.     WhethertheDisastermanagementplanisavailableattheGPLevel(Yes/No)  No

iii.  Whetherchild-friendlyparkwithrequiredfacilitiesisavailableinGP(Yes/No) No

iv.    WhethertheGPhaseasyaccesstoGodownforstorage(Yes/No) No

v.     Whetherstreetlightsareprovidedinpublicplacesforensuringsafety(Yes/No) Yes

DAY2ACTIVITIES

AGENDANO.2

SensitizevillageresidentsaboutmyScheme”portal(myscheme.in)whichincludesinformationaboutall theschemesbeingrunbyCentral/State/UT govtacrossthecountry

(SchemeMaterialavailablefromhttps://jkpanchayat.in/b2v4.php) Done

DAY2ACTIVITIES

AGENDANO.3

HoldmeetingoftheBiodiversityManagementCommitteestodeliberateonissues pertainingtoconserva- tionofbiodiversityandsustainableutilizationofbiologicalresources.HeshouldcheckPeopleBiodiversity register(PBR)ofthatpanchayatandreviewifBiodiversityManagementCommittee constitutedforthat panchayatis holdingminimum4meetings inayearandmeeting onceinevery3months (RoleofBMC availableathttps://jkpanchayat.in/b2v4.php)

COMMITTEEMEMBERS 15  PRESENT Nill

BIODIVERSITYREGISTERPHOTOS

PAST 4MEETINGDETAILS-DATES,MINUTESPHOTOS

Two meeting held

DAY2ACTIVITIES

AGENDA4

Visitingofficershallalsoplanandconductpanchayatlevelconvergencemeeting  ofalldepartmentsand prepareVillagedevelopmentplanforvillage,inconsultancywithGrampanchayat,discussitingram sabhaandgetitapproved.

(GPDPformatavailableonhttps://jkpanchayat.in/b2v4.php)

| Gram Panchayat Development Plan of Panchayat DEHWATOO (Mere Sapno ki Panchayat) |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
| S.no | Name of the Village | Name of the concerned Department | Scheme |  | Name of the proposed work | Ward.no | Estt Cost |
|  | Dehwatoo | Department of Rural Development | MGNREGA | 1 | C/o Rwall from Manzoor Paswal to onwards via Babo Khushi |  | 1.20 |
|  | Ladi |  |  | 2 | R.wall near Gh Nabi Paswal and other |  | 1.20 |
|  | Shalbaren |  |  | 3 | C/po Rwall from Gawhar Hussain Mir and others | 1 | 1.20 |
|  | Kothbal |  |  | 4 | C/O Irr Ladh F H/O M Yousuf Mir to onwards via Land of Hassan Mir |  | 1.20 |
|  |  |  |  | 5 | C/o of L/Road from Dankad to onwards via House of Haneef |  | 1.20 |
|  |  |  |  | 6 | C/o Irr Ladh from Movera road to onwards via land of Ahmdula |  | 1.80 |
|  |  |  |  | 7 | wall NHO Bashir Ahmad Hajam Razak Mir Aziz Mir and others |  | 1.60 |
|  |  |  |  | 8 | Foot path with steps from Gh Rasool Qadri to Ramzan Sheikh |  | 0.60 |
|  |  |  |  | 9 | Constr;of irr ladh from Mushtaq Sheikh to onwards |  | 0.90 |
|  |  |  |  | 10 | C/o Rwall near Jamid Masjid Shjareif Dehwatoo |  | 0.60 |
|  |  |  |  | 11 | Coonst.of link road from Najar Mohallah to Onwards via Ali Najar |  | 1.80 |
|  |  |  |  | 12 | Constr;of irr kanal from Banji to Wohin kanal Shal baren |  | 0.90 |
|  |  |  |  | 13 | Const.of link road form Razak Laway to onwareds viad wohin kanal |  | 1.20 |
|  |  |  |  | 14 | Constr.of R.wall at Shal Barren |  | 0.60 |
|  |  |  |  | 15 | Foot path FHO Gul Mohd Mir to Rehman at Herpora Ladi |  | 0.90 |
|  |  |  |  | 16 | Renovation of steps at Herpora Ladi |  | 0.60 |
|  |  |  |  | 17 | Developemnt of Irr Ladh at Wared No. 2 | 2 | 1.20 |
|  |  |  |  | 18 | C/o of link road from main road to KGBV |  | 0.90 |
|  |  |  |  | 19 | Constr.of link road form Razak wani to Wohin Kanal at Ladi |  | 0.90 |
|  |  |  |  | 20 | C/o R.wall at Ladi NLO bashir Mir & ors |  | 0.60 |
|  |  |  |  | 21 | R.wall at differennt spots at Ladi |  | 0.90 |
|  |  |  |  | 22 | Constr.of Irr ladh from Land of Nissar Hajam to ownards via land of Yaqoob Mir |  | 0.60 |
|  |  |  |  | 23 | Constr;of link road from M. Shafi to ownards via H/O Shabir Shah |  | 1.20 |
|  |  |  |  | 24 | C/o R.wall NLO Ab. Rashid Mir and ors at Ladi |  | 1.20 |
|  |  |  |  | 25 | C/o R.wall near H/O Khazir chopan and ors at Ladi |  | 1.20 |
|  |  |  |  | 26 | C/o R.wall near Showkat Mir & ors at Ladi |  | 1.20 |
|  |  |  |  | 27 | Irr Ladh near LO Zaina Banoo Akbar Tenda & ors at Kothbal |  | 1.20 |
|  |  |  |  | 28 | C/o R.wall near H/o Farooq Ahmad Mir & Ors at Ladi |  | 1.20 |
|  |  |  |  | 29 | C/o of R.wall NHO Nazir Paswal at Chaeckpati Ladi |  | 1.20 |
|  |  |  |  | 30 | C/o R.wall different spots at Checkpati Ladi |  | 1.80 |
|  |  |  |  | 31 | C/o Drain near H/O Gh Qadir Reshi via Mian road |  | 1.20 |
|  |  |  |  | 32 | C/o R.wall NHO of Haneefa W/o Yaseen Shah Kothbal |  | 0.60 |
|  |  |  |  | 33 | C/o irr ladh FHO Maqbool Mir to Mohd Chopand Patpora Ladi |  | 0.90 |
|  |  |  |  | 34 | C/o Irr ladh land of Nissar Wani to Firdous Mir Wogin Path Ladi |  | 0.60 |
|  |  |  |  | 35 | Dev.of Irr Ladh from Mohs Shjafi to Boni Baghat |  | 1.20 |
|  |  |  |  | 36 | C/o link road from M.Shafi to Dal Pati Ladi |  | 0.60 |
|  |  |  |  | 37 | C/o R.wall NHO of Mushtaq Ah Mir Bona Bat Ladi |  | 0.60 |
|  |  |  |  | 38 | C/o Irr Ladh near land of Rashid Mir to Gaffar Reshi Ladi Kinoo Dal |  | 1.20 |
|  |  |  |  | 39 | C.o Drain near H/O Muma Checha and other at Patpora |  | 0.90 |
|  |  |  |  | 40 | C/o of Irr laDH FROM Wohin Kanal to Garden of Fayaz Mir |  | 1.20 |
|  |  |  | JKRLM (UMEED) | 1 | Creation of Self Help Groups |  | 5.00 |
|  |  |  |  | 2 |  |  |  |
|  |  |  |  | 3 |  |  |  |
|  |  |  | PMAY-G (10 beneficiaries to be identified) | 1 | Haleem Koli (JK13337262) |  | 2.00 |
|  |  |  |  | 2 | Saleema Banoo (JK143666441) |  | 2.00 |
|  |  |  |  | 3 | BaNI Begam (JK148391983) |  | 2.00 |
|  |  |  |  | 4 | Rafi Khoshay ( JK141587229) |  | 2.00 |
|  |  |  |  | 5 | Mohd. Shafi Amaan ( JK148389655) |  | 2.00 |
|  |  |  |  | 6 | Gh Mohd. Paswal ( JK149306918) |  | 2.00 |
|  |  |  |  | 7 | Ab. Rashid Sheikh ( JK133337428) |  | 2.00 |
|  |  |  |  | 8 | Arsheed Hussain Wani ( JK146652215) |  | 2.00 |
|  |  |  |  | 9 | Muzaffar Ah. Shah ( JK133335982) |  | 2.00 |
|  |  |  |  | 10 | Manzoor Ahmad Mir ( Jk133336997) |  | 2.00 |
|  |  |  | HIMAYAT (DDU-GKY) (20 candidates to be identified per panchayat) | 1 | Parveena Jan -- Qualif;12th Tailoring |  |  |
|  |  |  |  | 2 | Aabid Hussain Shah --10th Plumber |  |  |
|  |  |  |  | 3 | Humaira Jan -- B.A Computer |  |  |
|  |  |  |  | 4 | Mohd. Altaf Paswal -- 12th Plumber |  |  |
|  |  |  |  | 5 | Parvaiz Ahma Sood -- 10th Plumber |  |  |
|  |  |  |  | 6 | Jugnoo Jan -- B.A Computer |  |  |
|  |  |  |  | 7 | Lateef Ah. Paswal -- 10th Plumber |  |  |
|  |  |  |  | 8 | Surya Jan -- B.A computer |  |  |
|  |  |  |  | 9 | Shugfta -- 12th Tailoring |  |  |
|  |  |  |  | 10 | Tufail Khanday --12th electrician |  |  |
|  |  |  |  | 11 | Sheezan Ah. Wani --12th Electrician |  |  |
|  |  |  |  | 12 | Sajad Ah. Mir -- B.A computer |  |  |
|  |  |  |  | 13 | Hamid Ah. Mir -- 12th Eelctrician |  |  |
|  |  |  |  | 14 | Bilal Ah. Mir -- M.A Computer |  |  |
|  |  |  |  | 15 | Gulzar Ah., Mir - B.A Computer |  |  |
|  |  |  |  | 16 | Naseer Ah. Mir - B.A Computer |  |  |
|  |  |  |  | 17 | Tariq Ahmad Mir - 12th Electrician |  |  |
|  |  |  | SWACHH BHARAT MISSION (GRAMEEN ) | 1 | 10 No. CSC Units | All Wards | 20.00 |
|  |  |  |  | 2 | Repairing of Toilet unit at Pnchayat Ghar |  | 1.20 |
|  |  |  |  | 3 |  |  |  |
|  |  |  | Saansad Adarsh Gram Yojana (SAGY) | 1 | Sanitation campaign ( Dust Bins etc) |  | 0.50 |
|  |  |  |  | 2 |  |  |  |
|  |  |  |  | 3 |  |  |  |
|  |  | Department of Agriculture, Cooperation & Farmers Welfare (DAC&FW) | Pradhan Mantri Kisan Samman Nidhi Yojana(PM-KISAN) | 1 | F.O.F should be covered to all | All Wards | 2000 per family |
|  |  |  |  | 2 |  |  |  |
|  |  |  |  | 3 |  |  |  |
|  |  |  | Pradhan Mantri Kisan Maan Dhan Yojana(PM-KMY) | 1 | Applicable 40 year + old | All Wards | 3000 per applicant |
|  |  |  |  | 2 |  |  |  |
|  |  |  |  | 3 |  |  |  |
|  |  |  | Pradhan Mantri Annadata Aay Sanrakshan Abhiyan (PM-AASHA) | 1 | Procurment of Paddy | All Wards | 3.00 |
|  |  |  |  | 2 |  |  |  |
|  |  |  |  | 3 |  |  |  |
|  |  |  | Pradhan Mantri Fasal BimaYojana (PMFBY) | 1 | Crop insurance | all Wards |  |
|  |  |  |  | 2 |  |  |  |
|  |  |  |  | 3 |  |  |  |
|  |  |  | Pradhan Mantri Krishi Sinchayee Yojana (PMKSY) | 1 | Water harvesting tanks | All Wards | 7.80 |
|  |  |  |  | 2 | Tube well and bore well | 2 each | 4.00 |
|  |  |  |  | 3 |  |  |  |
|  |  |  | National Food Security Mission (NFSM) | 1 | Establishment of Godown |  | 5.00 |
|  |  |  |  | 2 | Power Sprayer | 2 No | 1.00 |
|  |  |  |  | 3 |  |  |  |
|  |  |  | Mission for Integrated Development of Horticulture (MIDH) | 1 | Ploy Creen House | 2 No | 0.50 |
|  |  |  |  | 2 | Vermi Compost unit | 4 No | 1.00 |
|  |  |  |  | 3 | Vermi Beds | 10 No | 0.50 |
|  |  |  | Rashtriya Krishi Vikas Yojana | 1 | Bursh cutter | 2 No | 0.60 |
|  |  |  |  | 2 |  |  |  |
|  |  |  |  | 3 |  |  |  |
|  |  |  | Paramparag at Krishi Vikas Yojana (PKVY) | 1 |  |  |  |
|  |  |  |  | 2 |  |  |  |
|  |  |  |  | 3 |  |  |  |
|  |  |  | Mission Organic Value Chain Development for North Eastern Region (MOVCDNER) | 1 |  |  |  |
|  |  |  |  | 2 |  |  |  |
|  |  |  |  | 3 |  |  |  |
|  |  | Department of Elementary Education | Samagra Shiksha | 1 | C/o builidng for Liabrary and Laboratary at HS Dehwatoo |  | 25.00 |
|  |  |  |  | 2 |  |  |  |
|  |  |  |  | 3 |  |  |  |
|  |  |  | National Program for Education of Girls at Elementary Education ( NPEGEL) | 1 |  |  |  |
|  |  |  |  | 2 |  |  |  |
|  |  |  |  | 3 |  |  |  |
|  |  |  | Mid-day Meal Scheme | 1 |  |  |  |
|  |  |  |  | 2 |  |  |  |
|  |  |  |  | 3 |  |  |  |
|  |  |  | National Means-cum-Merit Scholarship Scheme (NMMSS) | 1 |  |  |  |
|  |  |  |  | 2 |  |  |  |
|  |  |  |  | 3 |  |  |  |
|  |  |  | National Scheme of Incentive to Girls for Secondary Education(NSIGSE) | 1 |  |  |  |
|  |  |  |  | 2 |  |  |  |
|  |  |  |  | 3 |  |  |  |
|  |  | Deptt of social welfare | Integrated Child Development Services (ICDS) | 1 |  |  |  |
|  |  |  |  | 2 |  |  |  |
|  |  |  |  | 3 |  |  |  |
|  |  |  | National Social Assistance Programme (NSAP) | 1 |  |  |  |
|  |  |  |  | 2 |  |  |  |
|  |  |  |  | 3 |  |  |  |
|  |  |  | POSHAN Abhiyan | 1 |  |  |  |
|  |  |  |  | 2 |  |  |  |
|  |  |  |  | 3 |  |  |  |
|  |  | Department of Health and Family Welfare | Ayushman Bharat - Health and Wellness Centres (AB-HWCs) | 1 | Establishment of Anganwardi Center at Ladi |  | 10.00 |
|  |  |  |  | 2 |  |  |  |
|  |  |  |  | 3 |  |  |  |
|  |  |  | Janani Suraksha Yojana (JSY) | 1 | Achieve 100% target during the year |  |  |
|  |  |  |  | 2 |  |  |  |
|  |  |  |  | 3 |  |  |  |
|  |  |  | Janani Shishu Suraksha Karyakram (JSSK) | 1 | Achieve 100% target during the year |  |  |
|  |  |  |  | 2 |  |  |  |
|  |  |  |  | 3 |  |  |  |
|  |  |  | Universal Immunization Programme (UIP) | 1 |  |  |  |
|  |  |  |  | 2 |  |  |  |
|  |  |  |  | 3 |  |  |  |
|  |  |  | Home Based Care of Newborn and Young Children | 1 |  |  |  |
|  |  |  |  | 2 |  |  |  |
|  |  |  |  | 3 |  |  |  |
|  |  |  | (HBNC/HBYC) Rashtriya Bal Swasthya Karyakram (RBSK) | 1 |  |  |  |
|  |  |  |  | 2 |  |  |  |
|  |  |  |  | 3 |  |  |  |
|  |  |  | National Ambulance Service (NAS) | 1 | 01 No Ambulance Van |  | 15.00 |
|  |  |  |  | 2 |  |  |  |
|  |  |  |  | 3 |  |  |  |
|  |  |  | Disease Control Programs | 1 | Awareness programme / camps |  | 1.00 |
|  |  |  |  | 2 |  |  |  |
|  |  |  |  | 3 |  |  |  |
|  |  | National Disaster Management Authority (NDMA) | National Cyclone Risk Mitigation Project | 1 | Fire & Emergency unit at Dehwatoo |  | 20.00 |
|  |  |  |  | 2 |  |  |  |
|  |  |  |  | 3 |  |  |  |
|  |  | Department of Drinking water and Sanitation | Jal Jeevan Mission | 1 | Repairement of PHE pipe line |  | 10.00 |
|  |  |  |  | 2 | Filteration plant |  | 10.00 |
|  |  |  |  | 3 |  |  |  |
|  |  | Department of Animal Husbandry and Dairying | Rashtriya Gokul Mission | 1 |  |  |  |
|  |  |  |  | 2 |  |  |  |
|  |  |  |  | 3 |  |  |  |
|  |  |  | National Dairy Plan-II | 1 |  |  |  |
|  |  |  |  | 2 |  |  |  |
|  |  |  |  | 3 |  |  |  |
|  |  |  | Dairy Processing and Infrastructure Development Fund | 1 |  |  |  |
|  |  |  |  | 2 |  |  |  |
|  |  |  |  | 3 |  |  |  |
|  |  |  | Supporting Dairy Cooperatives and Farmer Producer | 1 | Immunizaiton to Live stock |  | 1.00 |
|  |  |  |  | 2 |  |  |  |
|  |  |  |  | 3 |  |  |  |
|  |  |  | National Livestock Mission | 1 | Provide Sheep Units |  | 4.00 |
|  |  |  |  | 2 |  |  |  |
|  |  |  |  | 3 |  |  |  |
|  |  |  | Livestock Census and Integrated Sample Survey | 1 | Achieve 100% target during the year |  |  |
|  |  |  |  | 2 |  |  |  |
|  |  |  |  | 3 |  |  |  |
|  |  | Food Processing Industries | Pradhan Pantri Kisan SamapdaYojana (PMKSY) | 1 |  |  |  |
|  |  |  |  | 2 |  |  |  |
|  |  |  |  | 3 |  |  |  |
|  |  | Skill Development and Entrepreneurship | Pradhan Mantri Kaushal Vikas Yojana (PMKVY) | 1 |  |  |  |
|  |  |  |  | 2 |  |  |  |
|  |  |  |  | 3 |  |  |  |
|  |  |  | National Apprenticeship Promotion Scheme (NAPS) | 1 |  |  |  |
|  |  |  |  | 2 |  |  |  |
|  |  |  |  | 3 |  |  |  |
|  |  |  | Jan Shikshan Sansthan | 1 | Tailoring Center |  | 5.00 |
|  |  |  |  | 2 |  |  |  |
|  |  |  |  | 3 |  |  |  |
|  |  |  | Skills Acquisition and Knowledge Awareness for Livelihood Promotion (SANKALP) | 1 |  |  |  |
|  |  |  |  | 2 |  |  |  |
|  |  |  |  | 3 |  |  |  |
|  |  |  | Mahatma Gandhi National Fellowship (MGNF) | 1 |  |  |  |
|  |  |  |  | 2 |  |  |  |
|  |  |  |  | 3 |  |  |  |
|  |  | Tribal Affairs | Inclusive and sustainable growth of tribal population | 1 | Construction of Hostel Block |  | 200.00 |
|  |  |  |  | 2 |  |  |  |
|  |  |  |  | 3 |  |  |  |
|  |  | Capex Plan | UT Capex | 1 | Constr;of School Building at Paswal Mohallah ( Edu) |  | 20.00 |
|  |  |  |  | 2 | C/o additional class rooms for Govt. Primary school /KGBV / GMS Ladi ( Edu) |  | 30.00 |
|  |  |  |  | 3 | Providing of ATM facility (JK Bank) |  | 50.00 |
|  |  |  |  | 4 | Shifting of HT/LT line through Kooli Mohallah and change of timber poles all over Dehwatoo Pyt. ( Electric Deptt.) |  | 100.00 |
|  |  |  |  | 5 | 2 no. Tranfomer at Ladi Nai basti and Kothbal ( Eelctric Deptt.) |  | 20.00 |
|  |  |  |  | 6 | Establishment of Angan wardi center at Ladi at Kothbal (Social Welfare Deptt) |  | 10.00 |
|  |  |  |  | 7 | C/o road from main road to Koshi-Mohalla Ziyarat sharief ( RDD Deptt) |  | 10.00 |
|  |  |  |  | 8 | C/o lift irrigation scheme Ladi ( Irrigation Deptt) |  |  |
|  |  |  |  | 9 | Development of Patin Kol from RD 614 to onwards ( Irrigation Deptt) |  |  |
|  |  |  |  | 10 |  |  |  |
|  |  |  | District Capex | 1 | C/o Boundary Wall at Govt. Middle School Ladi with levelling of Play ground ( Edu Deptt) |  | 10.00 |
|  |  |  |  | 2 | C/o Boundary wall around Primary School / High School Dehwatoo ( Edu Deptt) |  | 15.00 |
|  |  |  |  | 3 | Fencing around Wellness center at Dehwatoo ( Helath Deptt) |  | 5.00 |
|  |  |  |  | 4 | Repairmenet of CRC building for meeting hall ( Edu Dpett) |  | 10.00 |
|  |  |  |  | 5 | Fencing of Ziyarat Sharief Khoshi Mohalla (RDD) |  | 10.00 |
|  |  |  |  | 6 | Fencing of Jamia Masjid at Dehwatoo (RDD) |  | 10.00 |
|  |  |  |  | 7 | Development of Play fields at Dehwatoo , Ladi by way of fencing . R.wall and B/Walls (RDD) |  | 25.00 |
|  |  |  |  | 8 | C/o link from main road to KGBV (RDD) |  | 2.00 |
|  |  |  |  | 9 | C/o Public Parks near Ladi Tourism Hut ( Tourism Deptt) |  | 15.00 |
|  |  |  |  | 10 | Flood protection bund at various spotsd at Ladi and Shalbaren ( Flood Constrol Deptt) |  | 10.00 |
|  |  |  |  | 11 | C/o Patwari Khana at feasible locaiton ( Revenue) |  | 7.00 |
|  |  | PMGSY | Road connectivity projects | 1 | Road from Dehwatoo to Shalbaran PMGSY |  | 150.00 |
|  |  |  |  | 2 | Road from Ladi to Kotbal (R&B) Deptt; |  | 100.00 |
|  |  |  |  | 3 |  |  |  |

InadditionGPDPplanshallalsoinclude:

           Touristplaceswhichneedtobedeveloped Park near ply ground ladi

           Specificproductwhichneedstobedeveloped Park NeaR Tourism hut

           Tourism-homestays 02

	20 candidates for training under Himayat scheme alongwith trade in which trainingis to be given list below

| S.No | Name of the Village | Name of the concerned Department | Scheme |  | Name of the proposed work | Ward.no | Estt Cost |
| --- | --- | --- | --- | --- | --- | --- | --- |
|  | Dehwatoo |  |  |  |  |  |  |
|  |  | Skilled Dev.Deptt; | HIMAYAT (DDU-GKY) (20 candidates to be identified per panchayat) | 1 | Parveena Jan -- Qualif;12th Tailoring |  |  |
|  |  |  |  | 2 | Aabid Hussain Shah --10th Plumber |  |  |
|  |  |  |  | 3 | Humaira Jan -- B.A Computer |  |  |
|  |  |  |  | 4 | Mohd. Altaf Paswal -- 12th Plumber |  |  |
|  |  |  |  | 5 | Parvaiz Ahma Sood -- 10th Plumber |  |  |
|  |  |  |  | 6 | Jugnoo Jan -- B.A Computer |  |  |
|  |  |  |  | 7 | Lateef Ah. Paswal -- 10th Plumber |  |  |
|  |  |  |  | 8 | Surya Jan -- B.A computer |  |  |
|  |  |  |  | 9 | Shugfta -- 12th Tailoring |  |  |
|  |  |  |  | 10 | Tufail Khanday --12th electrician |  |  |
|  |  |  |  | 11 | Sheezan Ah. Wani --12th Electrician |  |  |
|  |  |  |  | 12 | Sajad Ah. Mir -- B.A computer |  |  |
|  |  |  |  | 13 | Hamid Ah. Mir -- 12th Eelctrician |  |  |
|  |  |  |  | 14 | Bilal Ah. Mir -- M.A Computer |  |  |
|  |  |  |  | 15 | Gulzar Ah., Mir - B.A Computer |  |  |
|  |  |  |  | 16 | Naseer Ah. Mir - B.A Computer |  |  |
|  |  |  |  | 17 | Tariq Ahmad Mir - 12th Electrician |  |  |

DAY2ACTIVITIES

AGENDA5

Ensuresaturationoffollowingschemesandgivestatus:

| NAMEOFTHESCHEME | TOTALELIGIBLE BENEFICIARIESIN THE VILLAGE | TOTALBENEFICIARIESWHO AVAILEDTHEBENEFITSOFTHESCHEME | REASONSFOR PENDENCY |
| --- | --- | --- | --- |
| GoldenHealthCardunder AyushmanBharat | 1597 | 1430 | Adhaar Card mot linked with phone |
| Jananisurakshayojana | 20 | 20 |  |
| OLDAGEpension | 87 | 87 |  |
| Widowpension | 38 | 38 |  |
| Disabilitypension | 56 | 56 |  |
| Domicilecertificate | 1597 | 850 1085 |  |
| Kisancreditcard | 1240 | 1085 |  |
| PMkisansammannidhi | 300 | 285 |  |

| Landpassbook | 645 | 204 | Online generation |
| --- | --- | --- | --- |
| Registrationofvillageven- dorsonGEMportal |  |  |  |
| Registrationofvillagecon- tractorsonjktendersportal | 20 | 1 11 |  |
| Registrationofvillagecon- tractorsonPWDportal |  | 1 |  |
| Incompletebuildings/pro- jects | - |  |  |

DAY2ACTIVITIES

AGENDA6

NASHAMUKTABHIYAN

1.       Whethergramsabharesolutionpassed yes

2.       Detailsofactivities conducted Awareness campus

3.       Whetherallactivities andGSresolutionuploadedonjkpanchayats.inportal Yes

4.       Howmanydrugaddictsinthevillage Nil

5.       WhetherreportedtotheDeputyCommissioner Nil

6.       Howmanyregisteredforrehabilitationundergovernmentprogramme Nil

DAY2ACTIVITIES

AGENDA7

SOCIALAUDIT

Conductsocialauditofatleast5workseachunderfollowingschemes:

| NAMEOFTHE SCHEME | DETAILSOFTHE WORKS | YEAROFWORK APPROVAL | AMOUNT APPROVED FORTHEWORK | WHETHER WORKEXECUTED SATISFACTORILY | GEO- TAGGED PHOTOS | ANY GRIEVANCE RECORDED RELATINGTOTHAT WORK |
| --- | --- | --- | --- | --- | --- | --- |
| MGNREGA | 5 | 21-22 | 18.50 | yes | yes | No |
| PMAY | 10 | 22.23 | 5.00 | U/C | yes | 2nd installment |
| IHHL UNDERSBM-G | 7 | 2021-22 | 0.84 | Yes | Yes | -- |
| CSCUNDER SBMG | - | - | - | - |  |  |
| AMRIT SAROVARS | 4 | 22-23 | 4.00 | 2 No. U/C | Yes |  |

DAY2ACTIVITIES

AGENDA8

MAHILASABHA

Totalwomeninthevillageabovetheageof18 310

Totalattended  50

Proceedings:Awareness – Regarding health, Skill Development and Education

(Plinsertpointerstobediscussedthere–referpalliproceedings)

DAY2ACTIVITIES

AGENDA9

BALSABHA

Holda balsabhaandrecordproceedings Awareness

Totalchildreninthevillageabovetheageof 05= 184 Totalattended 30

Proceedings: Awareness of health , Edu. Sports

(Plinsertpointerstobediscussedthere–referpalliproceedings)

DAY2ACTIVITIES

AGENDA10

INAUGURATIONS

| SR NO. | ASSETS/ACTIVITIES INAUGRATED | STATUSOFTHEASSET/AC- TIVITIES(NUMBER,OTHER DETAILS) | GEO-TAGGED PHOTOS |
| --- | --- | --- | --- |
|  | VILLAGEHAATunderJKSRLM (SUN- DAYMARKET) | 2-Activites | Yes |
|  | PMAYhousesifanyreadyforinaugra- tion | All under Construction | Yes |
|  | Swachhgramprojects-segregation shedsetc | Composite & Soakage pits | Yes |
|  | Amritsarovars | 4 | Yes |
|  | Sportskits | 1 | Yes |
|  | Villageculturalevents | 1 | Yes |
|  | JJMassets/projects | - | - |
|  | Anyothertobeidentifiedatdistrict level |  |  |

FOLLOWUPOF(B2V1,B2V2&B2V3):

(Prefilledexcelsheet tobetakenfromdistrictlevel/andalsotobedownloaded

fromwww.jkpanchayat.in)

| S.NO. | Particulars | Actiontaken | Remarks# |
| --- | --- | --- | --- |
| I. UrgentPublicRequirements/Demands-B2V1 |  |  |  |
| 1 | Power supply important | 2 No 63KV sub stations instllaed | Repariement pending |
| 2 | Improvement of water supply |  | Partially done |
| 3 | C/road from Ladi to Shalbaren | Pending | Yet to be taken |
| 4 | Lift of irrig. Project at Kothbal | Pending | _ |
| 5 | C/road from Ladio to Dehwatoo | Pending | _ |
| 6 | L/Road from Ladi to Kothabal | Pending |  |
| 7 | Establishment of Higher Sec.School | No feasible |  |
| II. UrgentPublicRequirements/Demands-B2V2 |  |  |  |
| 1 | C/o Motorable road at Kothabal | Pending | Not taken up |
| 2 | Motorable road at Dehwatoo to Shalbaren | Pending |  |
| 3 | New pipe line by PHE | Partially taken up |  |
| 4 | Foot bridge badroo | Pending | Non availability of funds |
| 5 | Lift of Irr.Project Kothabal | Pending | - |
| 6 | Motorable roaed at Ladi Shalbaren | Pending |  |
| 7 | Improvement HT, LT line | Pending |  |
| S.NO. | Particulars | Actiontaken | Remarks# |
| III. MajorProblems–B2V1 |  |  |  |
| 1 | Poor power Supply | Pending | Needed |
| 2 | Poor water supply | Pending | Urgent |
| 3 | Upgradation of L/Road | Pending | Urgent |

| IV. MajorProblems-B2V2 |  |  |  |
| --- | --- | --- | --- |
| 1 | Poor Power supply | Pending | On priority |
| 2 | Poor water supply | Pending | On priority |
| 3 |  |  |  |
| 4 |  |  |  |
| 5 |  |  |  |
| V. MajorProblems-B2V3 |  |  |  |
| 1 | Motroable road at Kothbal | Pending | Most urgent On priority |
| 2 | Improvement of water supply | Pending | Most urgent On priority |
| 3 |  |  |  |
| 4 |  |  |  |
| 5 |  |  |  |
| VI. MajorComplaints-B2V1 |  |  |  |
| 1 | People of Ladi feels that they are deprived from benefits as compared to Dehwatoo |  | Equal share should be given |
| 2 |  |  |  |
| 3 |  |  |  |
| VII. MajorComplaints-B2V2 |  |  |  |
| 1 | Same as above |  |  |
| 2 |  |  |  |
| 3 |  |  |  |
| VIII. MajorComplaints-B2V3 |  |  |  |
| 1 | Same as above |  |  |
| 2 |  |  |  |
| 3 |  |  |  |

OVERALLPERCEPTIONOFFUCNTIONING OF GOVERNMENTDEPARTMENTS

1.         BESTDEPARTMENT: Education

2.       LEASTRESPONSIVEDEPARTMENT:RDD

GENERALASSESSMENTOFTHEVISTINGOFFICER

| I | Any major complaint broughttothenoticeoftheVisitingOfficer: - 2nd installment has not paid to PMAY beneficiaries - There is lackage of Pathin Kull - Internal link roads are not properly maintained - Poor sanitation in Pyt. Halqa - Poor electric supply and change of timber electric poles and shifting of 11 KV Line along Kooli Mohallah - All schools /wellness centre are in open premises. |
| --- | --- |
| II | Major/urgentpublicdemandsthatwas/werereflectedearlierbuthavenotbeenaddressedsofar: - Motorable road form Ladi to Kothbal and Dehwatoo to Shalbaren not taken up by any Deptt; - Poor Water supply ( works has been done partially) - Electricity works still pending - Lift irrigation scheme at Ladi not taken up |
| III | Overall assessment of the visit and suggestions: (Thevisitingofficertoensurethattheoverallassessmentisrecordedindetailsalongwithconcretesugges- tions) - Internal link road need urgent attention for their construction by way of concrete lane , tile paths. - There is poor sanitation Rural Development should focus on its proper sanitation by way of awareness / construction of Drains and compost pits. - Dev.of ply fields at Ladi and Dehwatoo by way of R/wall and B/wall with fencing - Maintenance of L.T line by way of its shifting alignment and removal of timber poles - Boost horticulture , sheep rearing and skill dev. For upliftment of general public particularly ST to earn their livelihood - Const;of public parks and providing registration of home stays to uplift Tourism Sector in area - To develop schools and wellness center by way of providing Boundary walls around the periphery |
| IV | OverallRatingofgovtfunctioningas givenbythePanchayat(Scaleof0to10) 05 |
| V | CertificatefromSarpanchthatthevisitingofficerhasstayedinthepanchayatfor2days – Certified |

SignatureofSarpanch                                                                              SignatureoftheVisitingOfficer

Name: Sakeena Banoo                                                                              Name: Nissar Ahmad Wani

( Asstt. Executive Engineer)

T.O to Suptdg; Engg.

PWD (R&B) Circle Ang/Kulgam

DepartmentofRuralDevelompentandPanchayatiRaj

GovernmentofJammu &Kashmir