4

15TH OCTto3RD NOV,2022

KEYFEATURES

•     DeputyCommissionerstoleadtheinitiative

•    RuraldevelopmentDepartmenttobethenodaldepartment

•	PlanningDevelopment&MonitoringdepartmentandITtobethesupport departments

ACTIONSANDTIMELINES

| ACTION | RESPONSIBILITY | LATESTBY | REMARKS |
| --- | --- | --- | --- |
| Janabhiyan | Alldepartments | Oct15-26th | Goingon |
| DeputationofSecttstaff/ HoDs | GAD | Oct14 | Done |
| DeploymentofStaffto Panchayatsandservingof ordersondeployedofficers | DCs | Oct25 | DCswilldeployseniorlevelstaff fromthedistricts.Strictactionto betakenagainstabstentions.No exemptionstobegiven |
| Trainingofdistricttrainors onB2V4 | RDD | Oct26 |  |
| Trainingofvisitingofficers | DCs | Oct27 |  |
| FieldVisitstobecompleted by | VisitingOfficers | Nov3 | DCstosuperviseandensurethat eachPanchayatisvisitedwithin theperiodspecified |
| DataofB2V4tobe uploadedby | VisitingOfficers | Nov10 | DCstosuperviseandensurethat dataofallPanchayatsisupload- edbythevisitingofficerwithin theperiodspecified |

INSTRUCTIONSFORTHEVISITINGOFFICER(DAYWISE)

| DATE | INSTRUCTIONS | ACTIONPOINTS |
| --- | --- | --- |
| Day0 | Meetingwithdeputy commissionerandhis/her team | a. TakeprintoutsoffilledbookletsofB2V1,B2V2andB2V3from www.jkpanchayat.in b.Alsotakeprintoutsofthesummarizedexcelsheetsofthe previousphasesfromwww.jkpanchayat.in c. CollectATRsonissuesraisedduringprevious3phasesfromthe officeofDeputyCommissioner(Planningdeptt) d.Takeprintsofblank 2bookletsofB2V4fromwww.jkpanchayat.ine.Takeplansfor2previousyearsandATRsfromtheplanningdeptt f. CompletetrainingsondifferentcomponentsofB2V4being organizedbyrespectiveDeputyCommissioners g.CollectListofnewworksstarted/ongoing/completedduringthe previousandcurrentFinancialyearunderthefollowingheads: • PRIgrants • DistrictPlan • UTplan • MGNREGA • Otherschemesofotherdepartments • Anyotherwork h. Plans/beneficiarylists: • MGNREGAdraftplandocumentfortheyear2022-23. • ListofAwaas+beneficiariesalongwithIHHL Convergence • Listofpensionbeneficiaries. • ListofSHGs • Listofagricultureschemebeneficiaries i. Listsofbeneficiariesfor: • Variouscertificates/benefitstobedistributedbythe visitingofficer. • Anyotheractivitiesidentifiedbydifferentdepartments |

| Day1 | Reachthevillage | 1. | Ensurethatallfrontlineworkersofdifferentdepttsarepresent. |
| --- | --- | --- | --- |
|  |  | 2. | Ensureexhibitionbydifferentdepts.aboutindividualbeneficiary schemes |
|  |  | 3. | InspectJKB/PSBcounters/outlets |
|  |  | 4. | Participate/ensureorganizationofsportsactivityinplayfield,talent hunt/culturalevent/youthactivity |
|  |  | 5. | GandhiKatha(suggesteddetailsuploadedonjkpanchayat.in) |
|  |  | 6. | Visitatleast2amritsarovarsandgetitsgeotaggedphotos |
|  |  | 7. | InspectKhidmat(CSC)CentresandcreateGenerateawarenesson 225schemesparticularlyG2CschemeslikeBEAMS,Janbhagidari, AapkiZaminAapkiNigrani,DigitalJ&K |
|  |  | 8. | Visitingofficershallalsoplanandconductpanchayatlevelconver- gencemeetingofalldepartments |
|  |  | 9. | CheckeffectivenessofCentrallysponsoredschemes |
|  |  | 10. | VisitandinspectallgovernmentestablishmentsincludingPHE, AWC,FPS,schools,etc |
|  |  | 11. | Attemptsaturationofdeliverableso JanAbhiyanandwherever deficienciesfound,leadadrivetoachievealldeliverables |
|  |  | 12. | Assesseffectivenessofsanitationcampaigninthepanchayat |
|  |  | 13. | Ensureselfemploymentactivitiesfor15youthperpanchayat |
|  |  | 14. | Identify20potentialcandidatesperpanchayatforHIMAYATtraining alongwiththetradeonwhichtheywanttraining |
|  |  | 15. | Whereverpossible,distributeemploymentlettersforpeopleselect- edundervariousgovernmentemployments |
|  |  | 16. | Intheevening,holdnormalmeetingwith seniorcitizens,govtem- ployeesincludingretiredemployees,exservicemen,youthclub,and any citizens ofthevillagewhoareenrolledincollege/university |
|  |  | 17. | OpendiscussiononNashaMuktAbhiyan |

Day2            Haveameetingwithall stakeholders-depttofficials andpanchayatmembers

1.       Discussionontheandassesstheprogressofdifferentschemesrelating tothelocalizedSDGsprioritizedforthatvillageaspertheresolution passedby thatGramPanchayaton21st April22,onNationalPanchayti RajDay.

2.	Sensitizevillage residentsaboutmyScheme”portal(myscheme.in) whichincludesinformationaboutalltheschemesbeingrunbyCen- tral/State/UTgovtacrossthecountry

3.	Hold meeting of theBiodiversityManagementCommitteestodeliber- ateonissuespertaining toconservation of biodiversityandsustaina- bleutilizationof biologicalresources.

4.       PrepareVillagedevelopmentplan,inconsultancywithGrampanchayat, discussitingramsabhaandgetitapproved.

5.       Ensure saturationofsoilhealthcardandgoldenhealthcardunderGold- enHealthCardunderAyushmanBharat,

6.       Ensuresaturation  of OldAge PensionScheme

7.       EnsureDomicileSaturation.

8.       EnsureKCCSaturation

9.       Ensure saturationoflandpassbooks

10.     Ensureregistrationofvillagevendorsneededforanyscheme,onGEM

portal

11.     Ensurepanchayatcontractors registration

12.     EncouragePanchayatmembers forimportanceofplantationdrivein

PanchayatunderHarGaonHariyali

13.     Ensure paintingondigitalJ&Kinpanchayatghars

14.     Ensure paintingonpanchayatactivitesandCSSinpanchayatghars

15.	Thevisiting officeshallchecknoof kindergarten andplayfields present inthepanchayat for kidsandstudents,iftheinfrastructure present inthesearegoodenough.

16.     Holdmeeting withpanchayatmembers todiscussaboutcorruption menaceandstepsrequiredtomakeJ&Kcorruptionfree

17.     Obtaina candidassessmentaboutperformanceofvariousdeptts in- cludingfairfeedbackaboutdiscrepanciesinfunctioning

18.	Check thestatusof NashaMuktAbhiyanandreporting of drugad- dictstoDeputyCommissioner.

19.     IdentifyTouristDestinations,Circuits,ThemeTreks,IdentifyHomestays, providesupportfortourismactivities throughVillageCooperative

20.     OrganizeTalentHuntatPanchayatLevel

21.     Conductsocialauditofatleast5worksunderfollowingschemes:

a.       MGNREGA

b.PMAY

c.        IHHLtoiletsandpayments d.CSCs

e.AMRITSAROVARS

22.     Holda mahilasabha anda balsabhaandrecordproceedingsinthefor- matgiven

23.     InauguratevillagehaatunderJKSRLM

24.     Checkifyouthclubsareformedinthepanchayatandwhatactivities theyareengagedin

25.     Organizea villagelevelculturaleventtoengagepanchayatmembers

26.     SensitizeGPaboutE-kitabkoshaninitiativeofJ&KGovtforempowering youthsthrough onlinedigitalliteracy

GENERALINSTRUCTIONS

1.	Thevisitingofficershallrefrainhimself/herselfgivingorofferinganycommitmentonbehalfofthe governmentandshalladoptanunbiasedattitudeinreportingissues.As faraspossible,his/her observation shouldbebasedona fairandanalytical viewemergingfromhis/herinteractioninthe village.

2.	Heisgoingtothevillageasplanningofficer,notforsanctioninganyworksorformakinganycom- mitments.

3.	Whilepreparingvillagedevelopmentplan,hehastoensurethat,demandsareprioritizedandre- flectedunderavailableschemes,wherevernecessarythelargerworksaretobereferredtoadminis- trativedepttunderCSS/UTplansunderintimationtoDCsandrestoftheworkstoDCsforreflecting itunderdistrict/CSS plans

4.    His workshallbehardcoreplanningandauditandisnota PRexercise.

5.	EveryDeputyCommissionerhastoensurethatatleastoneRDDofficial(ideallyPanchayatSecre- tary)ispresent  ineverypanchayatwithrelevantpanchayatrecords,toensureconductofallactivi- tiesasplanned.Panchayatwiseorderneedstobeissuedinadvance.

6.	Visitingofficershouldideallycarryhis/herlaptoptocompletethereportsatthepanchayatlevel itselfanduploadthefinalreport,duly signedbothbythesarpanchandbythevisitingofficeron www.jkpanchayat.inportal,beforetheyleavepanchayat.

7.	Focus ofvisitareyouth,skills,self-employment,nashamukt,bhrashtracharmukt,Rozgaryukt J&K, besidestocarryforwardtheactivities duringJanAbhiyanandsaturatethem.

8.    Inadditionattentionmaybegiventothefollowingareas a.     MakefulluseofCentrallySponsoredSchemes

b.Saturationofindividualbeneficiaryschemes c.     Self-employmentschemes

d.Banklinkedschemes-includingdepartmentalsubsidyschemes e.Empowermentandtransparencythrough digitalinitiatives

f.       Effectivenessofgrassrootsmachinery–

i.       Patwari,VLWpresent  andavailable

ii.      AvailablefundsutilizedinpublicinterestandasperGramSabharesolutions iii.   Fairness ingovernance

iv.    CSS/Individual beneficiaryschemesetc v.      BrashtacharMuktJ&K

vi.   BhaiMuktJ&K

vii.  NashaMuktJ&K

9.	ThePRImembers (Sarpanchs,Panchs,BDCChairperson)shallbeattheforefrontofallactivities and givendueimportanceandtheapproach shouldbetostrengthenthemandmakethemfeelem- powered.He/sheshallensurethattheBDCchairpersonandSarpanch/Panch arepresent  atthetime ofinaugurationandceremonies.

10.	Visitingofficershallnotleavethedistrictwithoutuploadingthereport,duly signedonthewww. jkpanchayat.inportal.EveryDeputyCommissionerhastoensurethat.

A)   DetailsofReportingOfficer:

Name:  Babu Ram Tandan

Designation:Deputy District Election Officer

Department/placeof  posting: Election Department Rajouri

MobileNo:9419150265

EmailID: tandanb3@gmail.com

HomeDistrict: Samba

Datesof  visit: 30 & 31st of Oct 2022

B)	LocationaldetailsofPanchayat:(tobepre-filled,informationtobetakenfromtheprevious phasesbooklets/summarizedexcelsheetuploadedonjkpanchayat.in/b2v4.php)(tobevali- datedbythevisitingofficerandmissingdetailstobefilled)

NameofthePanchayat:Balakote

LocalGovernmentDirectory(LGD)codeof  thePanchayat:7411

Nameof  CDBlock: Balakote

NameofTehsil:Balakote

Nameof    District:Poonch

C)     PanchayatProfile:

No.ofrevenuevillagesinthePanchayat:04

No.ofhamletsinthePanchayat:9

No.ofhouseholdsinthePanchayat:700

Population(approx)of  thePanchayat:4299

Part-II:

(TobefilledupbytheVisitingOfficerduringhis/hertwodayvisittothePanchayat.AllFieldshavetobe

filledbytheVisitingOfficerbeforethebookletishandedovertotheDC

FrontlineOfficers/OfficialswhowereassignedtothePanchayatfortheprogramme:

| Department | Name | Designation |
| --- | --- | --- |
| Agriculture | Basant Ram | Agri. Exttension Assistant |
| Revenue | Iftkhar Ahmed | Patwari |
| RDD | Mehnaz Kouser | GRS |
| PWD | Idrees Ahmed | JE |
| Animal Husbandry | Mohd Khurshid | Pharmacist |
| ICDS | Nazir Farooq | AWW |
| Ayush ISM | Nayaz Ahmed | NO |

Detailsofabsentemployeesvis-à-vislistfurnishedbytheDCoffice:

| Department | Name | Designation |
| --- | --- | --- |

DAY1-ACTIVITIES

AGENDA1:PANCHAYATASSETREGISTER

Infrastructure:

1.		PanchayatGharInfrastructure a.  Govtbuilding/private Govt

b.  New/needingrepairs

2.       Furniture(Y/N) Y

3.       Computer/printer(Y/N) Y

4.       Internet(Y/N) Y

5.       Telephone(Y/N) N

6.       Toilet(CSC/partofpanchayatghar)(Y/N) Y

7.       Water(Y/N) N

8.       Electricity(Y/N) N

9.       Bankbranch(Y/N) N

10.     CSC(Y/N) N

11.     Patwarkhana(Y/N) Y

12.     Villagehaat(Y/N) N

13.     Playground(Y/N) Y

14.     School-

a.        Kindergarten(Y/N) N

b.Primary(Y/N) Y

c.         Secondary(Y/N) N

d. College (Y/N) N

e.University(Y/N) N

15.     AnganwadiCentre(Y/N) Y

a.        (govt/private) PRIVATE

b.Totalchildrenenrolled 156

15.     AmritSarovars–details,location,condition 2 WARD NO 7

16.     Governmentoffices-details,whetherfunctionalornot YES FUNCTIONAL

17.     Rationshop(Y/N) Y

18.      Placesoftourismimportance–names,littledetailsonhistorical/culturalimportance NILL

19.      Villageheritagesites/treks-names,littledetailson historical/culturalimportance NILL

20.     VLWOffice (Y/N) Y

21.     PrimaryHealthcareCentre(Y/N), N

22.     ListofIncompleteBuildings-names,yearofconstruction Building of AWC W.NO 8 FROM 2008

23.     ListofUnderutilizedBuildings-names

NILL

DAY1-ACTIVITIES

AGENDA2:

DIFFERENTINSTITUTIONS/INFRASTRUCTUREPROJECTSTOBEVISITED

| AMRITSAROVARS | Visit,verify | COMMENTS |
| --- | --- | --- |
| KhidmatCentres | Create/Generateawarenesson225schemes particularlyG2CschemsAapkiZaminAapkiNigrani, Beams,Janbhagidari,DigitalJ&K | NOT AVAILABLE IN GP |
| JKB/PSBcounters/outlets | a)Statusofcounter b)Numberofvisitors | NOT AVAILABLE IN GP |
| Incompletebuildings/pro- jects | Verify whetheridentificationandredistribution done | 1 Building of AWC W.NO 8/NIL |
| PDS | Visit,evaluate,onlinestatus | Evaluated |
| PHC | Visit-evaluate,statusofstaff,equipmentand quality | NA |
| Youthclubs | Meet,interact,seeksuggestions | DONE |
| SHG | Meet,identifyproblems,seeksuggestions | DONE |
| PMAY | Inspect,Inaugurate | Insoected 1 inaguration nill |
| Myschool,mypride progress;schools-water, toilets,staff | Visit,checkforwater,electricity,sanitation,meet studentsandstaff | DONE |
| SwachhSBM | Evaluate | DONE |
| Panchayatplayground, Sportskitsdistribution Villagegames | Ensure,verify.Participateinatleastonegamein theplayground | DONE |
| HarGaonHariyali, Planta- tiondrive | Evaluatestatus,feedback | Satisfactory |
| Villageculturalevent Dangal/Haat/Mela | Participatein;ensurethatitisheld | NILL |
| Exhibitionofschemes | Ensurethateverydepartmentparticipatesand thatitcontinuesfortheentiredurationofB2V | NILL |
| JalJeewanMission verifica- tion- WSS/JSD Electricitysupply | Verify | Inspected |

DAY1-ACTIVITIES

AGENDA3:SATURATEJANBHIYAN

DELIVERABLESANDRECORDDEFICIENCIESIFANY(INSERTDELIVERABLESLISTHEREASPERGADFORMAT

DAY1-ACTIVITIES

AGENDA4:

SELFEMPLOYMENTACTIVITIES

EnsureSelf-employmentactivities foryouth,distributeemploymentlettersforpeopleselectedunder varioussocialschemes(15ISTHETARGETPERPANCHAYAT)

Numberofcasesindifferentcategoriessanctioned: NILL

Detailsofthebanksanctioningit: NILL

Totalamountinvolved:NILL

DAY1ACTIVITIES

AGENDA5

Intheevening,holdinformalmeetings  withseniorcitizens,govtemployees,retdemployees,youthclub andothercitizenswhoareenrolledoncollege/universityandhavediscussiononGandhiKatha,Nasha MuktAbhiyan,corruptionfreegovernance,doublingfarmersincomeandrecordtheproceedings

DAY2

a.       NoofIndividualCompostPitsconstructed 20

b.NoofIndividualSoakPitsconstructed 250

V.          No.ofBiodiversitymanagementcommitteemeetingsheld: 2

VI.         IsthenameofSarpanchdisplayedoncitizeninformationboardsofallRD&PRschemes:Yes/No YES

VII.       AreSarpanchsbeinginvolvedinstart/inaugurationofactivities:Yes/No YES

VIII.      WhethersubjectshavebeenassignedbytheSarpanchtothePanchs:Yes/No YES

IX.        Whethergrievancesredressalboxisinstalled:Yes/No YES

X.         NoofgrievancesreceivedpertainingtoPanchayatlevel: NILL

XI.        NoofgrievancesdisposedofatPanchayatlevel: NILL

XII.       WhethertheSarpanch/PanchayatSecretaryhavedigitalsignatures:Yes/No YES

XIII.      WhetherallMGNREGA/14thFCpayments arebeingmadebySarpanchthrough DigitalSignature

Certificate(DSC):Yes/No YES

HUMAN RESOURCEAVAILABLEATTHEPANCHAYAT LEVEL:

| SRNO. | DEPARTMENTWISESTAFF | NUMBERS |  | NAMES |
| --- | --- | --- | --- | --- |
|  |  | SANCTIONED | ACTUAL |  |
|  | Ruraldevelopmentdepartment: BDO JE GRS TA | 1 | 1 | Mahnaz Kouser |
|  | SCHOOLEDUCATION: TEACHER HEADMASTER ANYOTHER | 48 1 | 41 1 | Shokit Ahmed |
|  | JAL JEEVAN: Lineman | 7 | 7 | Shabir Ahmed Javed Ahmed Rohoof Ahmed |
|  | PDD: LINEMAN JE ANYOTHER | 5 | 5 | Mohd Yasir Mohd Nawaz |
|  | FOOD&CIVILSUPPLIES Ration Dealer | 3 | 3 | Mohd Rayaz, Mohd Majeed, Mehbob Ahmed |
|  | AGRICULTURE&ANIMALHUS- BANDARY AEA | 01 | 01 | Basant Ram |
|  | SOCIALWELFARE AWW | 9 | 9 | Nazir Farooq Azmit Bi |
|  | HEALTH: ASHA ANM AYUSHDOCTOR ALLOPATHICDOCTOR | 3 2 1 | 3 2 1 | Mukhtar Ahmed |
|  | ANYOTHERDEPARTMENT |  |  |  |

DAY2-ACTIVITIES

AGENDANO.1

DiscussionontheandassesstheprogressofdifferentschemesrelatingtothelocalizedSDGsprior-itizedforthatvillageaspertheresolutionpassedbythatGramPanchayaton21stApril22,onNational PanchayatiRajDay(Copyoftheresolutiontobetakenfromwww.jkpanchayat.inportalunderthelinkof GramSwarajMonth)

1.       SDGs AGREED FORTHATVILLAGE,TOBEIMPLEMENTED BYMARCH2024:

2.       STATUSOFWORKSUNDERTHEFOLLOWINGSCHEMES:

1      Cleanandgreenvillage

i.InitiativestakenbythePanchayatformanagingSolidandLiquidWaste NIL

ii.     InitiativestakenbythePanchayatforusinggreensourcesoffuellikesolar,biogas NILL

iii.  Hasmappingoflanduse,waterbodies,forest,slopes,wetlands,degradedforestwithintheGram

Panchayatbeendone?Yes/No.IfNo,reason,thereof	NO NOT YET FINALIZED

iv.    HastheClimateResiliencePlanbeendevelopedfortheGP?Yes/No NO

v.     StepstakenbytheGramSabhaabouttheclimatechangemitigationfactorslikereducingenergy consumption,usageoffossilfuels,plastics,non-renewablebuildingmaterialsandalsotopromote measureslikeplantingoftrees,conservingforests,usageofgoodagriculturalpracticeslikedrip irrigation,waterconservationmeasuresandconservationofwetlands. NILL

vi.  Whetherschoolshavestartedsegregatingwaste YES

vii. Whetherschoolshavetheirowncompost/soakagepitsforsolid/liquidwastemanagement NO

2     Healthyvillage

i)    Aremeetings  relatedtoVillageHealthandSanitationCommitteebeingheldregularly? YES

ii)   DoalltheeligibleindividualsbeenprovidedtheGoldenCard? YES

iii)  ArealltheChildrenbeingimmunizedaspertheSchedulerecommendedbyGovt.ofIndia? YES

iv)  ArealltheeligibleindividualsbeenvaccinatedagainstCOVID-19? YES

v)   DoesGramPanchayatensurethatallpregnantwomenaregettingnecessaryprenatalcheckups? YES

vi)  WhetherallthedeliverieswereInstitutionalizedorconductedbytrainedMidwives? YES

3     Watersufficientvillage

i)    DoalltheIHHsintheGramPanchayathavewaterpipelineconnections? NO

ii)   WhetherGramPanchayathastakenstepsforgreywatermanagement.IfYespleasespecify NILL

iii)  DoalltheIHHsintheGramPanchayathavetoilets? YES

iv)  ArealltheIHHstoiletsfunctionalornot? YES

v)   DoalltheSchools/Anganwadicentershavea toiletfacilityornot?YES

vi)  Areallthetoiletsintheschools/Aaganwadifunctionalornot?YES

vii) WhetherGramPachachayatBhawanhasseparate toiletsforwomenornot?

YES

4      ChildFriendlyvillage

i)	Doallthechildrenundertheageof0-6yearsbeenenrolledintheAnganwadicentersforpre- schooling?Yes/NO YES

ii)    HowmanyBalSabha’swereorganizedintheGramPanchayat-------------------01 During visit

iii)  WhethertheissuesraisedbyBalSabhaareaddressedduringtheGramSabha. Yes/NO To be projected

iv)	WhetherGramPanchayatistrackingthedatarelatedtodropoutchildrenandchildrenwithirregular attendance?Yes/NO. NO

v)   DoalltheschoolsundertheGramPanchayathaveseparate toiletsforgirlsandboys?Yes/No YES

5      Villagewithgoodgovernance

i)    IsCSClocatedintheGramPanchayatBhawanornot? NOT

ii)	IsthelistofbeneficiariesrelatedtotheSchemes/ProgramsdisplayedontheGrampanchayatwallor not? YES

iii)  DoestheGramPanchayathasitsbuildingornot? YES

iv)  IstheGramPanchayatofficefunctionalornot?YES

v)   Aretheactivities approved undertheHalqaPanchayatDevelopmentPlandisplayedontheGram

Panchayatwallornot?

YES

vi)  IsSocialAuditofearlierSchemes/Programscarriedoutornot? YES

6      Povertyfreeandenhancedlivelihoodvillage

- HasGramPanchayatdevelopedanycriteria fortheidentificationofthepoor?Yes/NoifyesspecifyYES

- ii)   HavealltheeligiblehouseholdsregisteredinPDSornot?YES

iii)	HasGramPanchayatprovidedspaceforSelf-helpGroupsinPanchyatGharforholdingmeetings  or not?YES

iv)  HavealltheeligiblehouseholdsbeenregisteredforPensionornot?YES

v)   HasGramPanchayatfacilitatedYouthforSkillEnhancementCoursesandPlacement?NILL

vi)  HasJobCardsbeendistributedtoalltheeligibleindividualsunderMGNREGA?YES

vii) HasGramPanchayatfacilitatedSHGsforBankAccountLinkages?NILL

7     Sociallysecuredvillage

i)    WhetherGramPanchayatismaintainingdatarelatedtoDifferentlyAbledPeople?NO

ii)   IsGramPanchayatOffice DisabledFriendlyornot?NO

iii)	Areprovisionsfora separate BudgetundertheResourceEnvelopeforWomenandChildrenmadeor not?NILL

iv)	DoalltheSchools intheGramPanchayathavefacilitiesforDifferentlyAbledChildrenliketoilets, barrier-freeaccess,etc.,ornot? NO

v)   Arealltheeligibleindividualsaregettingpensions,likeoldagepension,widowpension,etc?YES

vi)  ArealltheeligiblehouseholdsgettingbenefitsfromIAYornot?

NO

8      EngenderedDevelopmentinVillage

i)    HowmanyMahilaSabha’swereorganizedintheGramPanchayat------------------01-

ii)	WhetherSHGsfederationshavebeenprovidedspaceformeetings  inthePanchayatBhawan(Yes/ No)YES

iii)  WhetherGPshavetakenstepsforincreasingwomen’sparticipationinGramSabha(Yes/No)NONOT SPECIFIED

iv)  NumberofwomenbeneficiariesheadedhouseholdscoveredunderPDS

system………………………NA

v)   Numberofbeneficiaries(outoftotaleligiblepopulation)receivingsocialprotectionbenefitsunder

PradhanMantriMatritvaVandanaYojana………………….

9    Self-sufficientinfrastructureinthevillage

i.	WhetherGPhasa CommunityHallwithaccesstoelectricity,furniture,watersupply, toilet……………………….NILL

ii.     WhethertheDisastermanagementplanisavailableattheGPLevel(Yes/No) YES

iii.  Whetherchild-friendlyparkwithrequiredfacilitiesisavailableinGP(Yes/No) NO

iv.    WhethertheGPhaseasyaccesstoGodownforstorage(Yes/No)NO

v.     Whetherstreetlightsareprovidedinpublicplacesforensuringsafety(Yes/No)NO

DAY2ACTIVITIES

AGENDANO.2

SensitizevillageresidentsaboutmyScheme”portal(myscheme.in)whichincludesinformationaboutall theschemesbeingrunbyCentral/State/UT govtacrossthecountry Participants were senthesized about the myscheme portal

(SchemeMaterialavailablefromhttps://jkpanchayat.in/b2v4.php)

DAY2ACTIVITIES

AGENDANO.3

HoldmeetingoftheBiodiversityManagementCommitteestodeliberateonissues pertainingtoconserva- tionofbiodiversityandsustainableutilizationofbiologicalresources.HeshouldcheckPeopleBiodiversity register(PBR)ofthatpanchayatandreviewifBiodiversityManagementCommittee constitutedforthat panchayatis holdingminimum4meetings inayearandmeeting onceinevery3months (RoleofBMC availableathttps://jkpanchayat.in/b2v4.php)

COMMITTEEMEMBERS Committee has not been constructed

PRESENT

BIODIVERSITYREGISTERPHOTOS

PAST 4MEETINGDETAILS-DATES,MINUTESPHOTOS

DAY2ACTIVITIES

AGENDA4

Visitingofficershallalsoplanandconductpanchayatlevelconvergencemeeting  ofalldepartmentsand prepareVillagedevelopmentplanforvillage,inconsultancywithGrampanchayat,discussitingram sabhaandgetitapproved.Already approved by GP/GS Discussed in Gram Sabha meeting

(GPDPformatavailableonhttps://jkpanchayat.in/b2v4.php)

InadditionGPDPplanshallalsoinclude:

           Touristplaceswhichneedtobedeveloped

           Specificproductwhichneedstobedeveloped

           Tourism-homestays

	20candidatesfortrainingunderHimayatschemealongwithtradeinwhich trainingistobegiven

DAY2ACTIVITIES

AGENDA5

Ensuresaturationoffollowingschemesandgivestatus:

| NAMEOFTHESCHEME | TOTALELIGIBLE BENEFICIARIESIN THE VILLAGE | TOTALBENEFICIARIESWHO AVAILEDTHEBENEFITSOFTHESCHEME | REASONSFOR PENDENCY |
| --- | --- | --- | --- |
| GoldenHealthCardunder AyushmanBharat | 1480 | 1280 | Mismatching of data |
| Jananisurakshayojana |  |  |  |
| OLDAGEpension | 141 | 141 |  |
| Widowpension | 54 | 54 |  |
| Disabilitypension | 56 | 56 |  |
| Domicilecertificate | 2754 | 2190 | Not applied |
| Kisancreditcard | 359 | 132 | Some people not interested/eligible |
| PMkisansammannidhi | 359 | 197 | Not registered |

| Landpassbook | 2072 | 560 | Under process |
| --- | --- | --- | --- |
| Registrationofvillageven- dorsonGEMportal |  |  |  |
| Registrationofvillagecon- tractorsonjktendersportal |  | 07 |  |
| Registrationofvillagecon- tractorsonPWDportal |  |  | NA |
| Incompletebuildings/pro- jects | One building of AWC namely Balakote W.No. 8 |  |  |

DAY2ACTIVITIES

AGENDA6

NASHAMUKTABHIYAN

1.       Whethergramsabharesolutionpassed YES

2.       Detailsofactivities conducted Oath was administered to participants

3.       Whetherallactivities andGSresolutionuploadedonjkpanchayats.inportal To be uploaded

4.       Howmanydrugaddictsinthevillage NILL

5.       WhetherreportedtotheDeputyCommissioner NILL

6.       Howmanyregisteredforrehabilitationundergovernmentprogramme

NILL

DAY2ACTIVITIES

AGENDA7

SOCIALAUDIT

Conductsocialauditofatleast5workseachunderfollowingschemes:

| NAMEOFTHE SCHEME | DETAILSOFTHE WORKS | YEAROFWORK APPROVAL | AMOUNT APPROVED FORTHEWORK | WHETHER WORKEXECUTED SATISFACTORILY | GEO- TAGGED PHOTOS | ANY GRIEVANCE RECORDED RELATINGTOTHAT WORK |
| --- | --- | --- | --- | --- | --- | --- |
| MGNREGA | Water tank W.No 3 | 2021-22 | 1 lakh | YES | YES |  |
| PMAY | Mansa Bi | 2021-22 | 1.5 lakh | YES | YES |  |
| IHHL UNDERSBM-G | Mohd Aftab S/o Nor Mohd | 2021-22 | 12000 | YES | YES |  |
| CSCUNDER SBMG |  |  |  |  |  |  |
| AMRIT SAROVARS | Khala Draman | 2022-23 | 5 lakh | YES | YES |  |

DAY2ACTIVITIES

AGENDA8

MAHILASABHA

Totalwomeninthevillageabovetheageof18 1042

Totalattended 85

Proceedings:

(Plinsertpointerstobediscussedthere–referpalliproceedings)

DAY2ACTIVITIES

AGENDA9

BALSABHA

Holda balsabhaandrecordproceedings

Totalchildreninthevillageabovetheageof….. Totalattended 35

Proceedings:

(Plinsertpointerstobediscussedthere–referpalliproceedings)

DAY2ACTIVITIES

AGENDA10

INAUGURATIONS

| SR NO. | ASSETS/ACTIVITIES INAUGRATED | STATUSOFTHEASSET/AC- TIVITIES(NUMBER,OTHER DETAILS) | GEO-TAGGED PHOTOS |
| --- | --- | --- | --- |
|  | VILLAGEHAATunderJKSRLM (SUN- DAYMARKET) |  |  |
|  | PMAYhousesifanyreadyforinaugra- tion |  |  |
|  | Swachhgramprojects-segregation shedsetc |  |  |
|  | Amritsarovars at W.No 7 | 1 | YES |
|  | Sportskits |  |  |
|  | Villageculturalevents in school | 2 | YES |
|  | JJMassets/projects |  |  |
|  | Anyothertobeidentifiedatdistrict level |  |  |

FOLLOWUPOF(B2V1,B2V2&B2V3):

(Prefilledexcelsheet tobetakenfromdistrictlevel/andalsotobedownloaded

fromwww.jkpanchayat.in)

| S.NO. | Particulars | Actiontaken | Remarks# |
| --- | --- | --- | --- |
| I. UrgentPublicRequirements/Demands-B2V1 |  |  |  |
| 1 Construction of road from Satoli Cheer to Naions |  | NO |  |
| 2Construction of road from Plama Puti to Strriko gopal |  | NO |  |
| 3Play ground at village Balakote, Sandote and Basoni |  | NO |  |
| 4Upgradation of two no of Medical sub centre |  | NO |  |
| 5Upgradation of MS Girls to HS bALAKOTE |  | NO |  |
| 6 |  |  |  |
| 7 |  |  |  |
| II. UrgentPublicRequirements/Demands-B2V2 |  |  |  |
| 1Requirement of 300 of individual bunkers |  | NILL |  |
| 2 Upgradation of MS Bherote to HS |  | NILL |  |
| 3Upgradation of PS Basoni to MS |  | NILL |  |
| 4Road from Satoli cheer to Nauri via Langiote |  | NILL |  |
| 5Upgradation of MS Basoni to HS |  | NILL |  |
| 6 ONE community hall for Balakote |  | NILL |  |
| 7four transformer along with 200 poles |  | NILL |  |
| S.NO. | Particulars | Actiontaken | Remarks# |
| III. MajorProblems–B2V1 |  |  |  |
| 1Lack of road connectivity in GP |  | NILL |  |
| 2Non availability of health faculty |  | NILL |  |
| 3Lack of electricity |  | NILL |  |

| 4Lack of drinking water |  | NILL |  |
| --- | --- | --- | --- |
| 5Lack of education/sport infrastructure |  | NILL | Work of sport stadium is now under process |
| IV. MajorProblems-B2V2 |  |  |  |
| 1Improvement in road connectivity upto the last corner of panchayat |  | NILL |  |
| 2Upgradation of health sub centre |  | NILL |  |
| 3Improvement in MDM IN school |  | NILL |  |
| 4Improvementin electricity infrastructure |  | NILL |  |
| 5 |  |  |  |
| V. MajorProblems-B2V3 |  |  |  |
| 1Requirement of individual bunkers |  | NILL |  |
| 2Lack of road connectivity |  | NILL |  |
| 3Lack of drinking facility |  | 1 Water tank constructed |  |
| 4Non availability of ambulance |  | NILL NILL |  |
| 5Electricity issue in area |  |  |  |
| VI. MajorComplaints-B2V1 |  |  |  |
| 1Imrovement in road connectivity |  | NILL |  |
| 2Establishment of health centre |  | NILL |  |
| 3Establidhment of Vet. centre |  | NILL |  |
| VII. MajorComplaints-B2V2 |  |  |  |
| 1Improvemen/extension of road upto last corner of panchayat |  | NILL |  |
| 2Upgradation of sub centre |  | NILL |  |
| 3 |  |  |  |
| VIII. MajorComplaints-B2V3 |  |  |  |
| 1Community individual bunkers |  | Few bunkers has been constructed |  |
| 2Road connectivity |  |  |  |
| 3Poor functioning of PHE department |  |  |  |

OVERALLPERCEPTIONOFFUCNTIONING OF GOVERNMENTDEPARTMENTS

1.         BESTDEPARTMENT:

2.       LEASTRESPONSIVEDEPARTMENT:

GENERALASSESSMENTOFTHEVISTINGOFFICER

| I | AnymajorcomplaintbroughttothenoticeoftheVisitingOfficer: |
| --- | --- |
| II | Major/urgentpublicdemandsthatwas/werereflectedearlierbuthavenotbeenaddressedsofar: |
| III | Overallassessmentofthevisitandsuggestions: (Thevisitingofficertoensurethattheoverallassessmentisrecordedindetailsalongwithconcretesugges- tions) |
| IV | OverallRatingofgovtfunctioningas givenbythePanchayat(Scaleof0to10) |
| V | CertificatefromSarpanchthatthevisitingofficerhasstayedinthepanchayatfor2days |

SignatureofSarpanch                                                                              SignatureoftheVisitingOfficer

Name………………………                                                                               Name………………………

DepartmentofRuralDevelompentandPanchayatiRaj

GovernmentofJammu &Kashmir

DepartmentofRuralDevelompentandPanchayatiRaj

GovernmentofJammu &Kashmir