4





**15TH OCTto3RD NOV,2022**

**KEYFEATURES**

• DeputyCommissionerstoleadtheinitiative

• RuraldevelopmentDepartmenttobethenodaldepartment

• PlanningDevelopment&MonitoringdepartmentandITtobethesupport departments

**ACTIONSANDTIMELINES**

|  |  |  |  |
| --- | --- | --- | --- |
| **ACTION** | **RESPONSIBILITY** | **LATESTBY** | **REMARKS** |
| **Janabhiyan** | Alldepartments | Oct15-26th | Goingon |
| **DeputationofSecttstaff/ HoDs** | GAD | Oct14 | Done |
| **DeploymentofStaffto Panchayatsandservingof ordersondeployedofficers** | DCs | Oct25 | DCswilldeployseniorlevelstaff fromthedistricts.Strictactionto betakenagainstabstentions.No exemptionstobegiven |
| **Trainingofdistricttrainors onB2V4** | RDD | Oct26 |  |
| **Trainingofvisitingofficers** | DCs | Oct27 |  |
| **FieldVisitstobecompleted by** | VisitingOfficers | Nov3 | DCstosuperviseandensurethat eachPanchayatisvisitedwithin theperiodspecified |
| **DataofB2V4tobe uploadedby** | VisitingOfficers | Nov10 | DCstosuperviseandensurethat dataofallPanchayatsisupload- edbythevisitingofficerwithin theperiodspecified |

**INSTRUCTIONSFORTHEVISITINGOFFICER(DAYWISE)**

|  |  |  |
| --- | --- | --- |
| **DATE** | **INSTRUCTIONS** | **ACTIONPOINTS** |
| **Day0** | Meetingwithdeputy commissionerandhis/her team | a. TakeprintoutsoffilledbookletsofB2V1,B2V2andB2V3from [www.jkpanchayat.in](http://www.jkpanchayat.in)b.Alsotakeprintoutsofthesummarizedexcelsheetsofthe previousphasesfrom[www.jkpanchayat.in](http://www.jkpanchayat.in)c. CollectATRsonissuesraisedduringprevious3phasesfromthe officeofDeputyCommissioner(Planningdeptt)d.Takeprintsofblank 2bookletsofB2V4from[www.jkpanchayat.in](http://www.jkpanchayat.in)e.Takeplansfor2previousyearsandATRsfromtheplanningdeptt f. CompletetrainingsondifferentcomponentsofB2V4beingorganizedbyrespectiveDeputyCommissionersg.CollectListofnewworksstarted/ongoing/completedduringthe previousandcurrentFinancialyearunderthefollowingheads:• PRIgrants• DistrictPlan• UTplan• MGNREGA• Otherschemesofotherdepartments• Anyotherworkh. Plans/beneficiarylists:• MGNREGAdraftplandocumentfortheyear2022-23.• ListofAwaas+beneficiariesalongwithIHHL Convergence• Listofpensionbeneficiaries.• ListofSHGs• Listofagricultureschemebeneficiariesi. Listsofbeneficiariesfor:• Variouscertificates/benefitstobedistributedbythe visitingofficer.• Anyotheractivitiesidentifiedbydifferentdepartments |

|  |  |  |  |
| --- | --- | --- | --- |
| **Day1** | Reachthevillage | 1. | Ensurethatallfrontlineworkersofdifferentdepttsarepresent. |
|  |  | 2. | Ensureexhibitionbydifferentdepts.aboutindividualbeneficiary schemes |
|  |  | 3. | InspectJKB/PSBcounters/outlets |
|  |  | 4. | Participate/ensureorganizationofsportsactivityinplayfield,talent hunt/culturalevent/youthactivity |
|  |  | 5. | GandhiKatha(suggesteddetailsuploadedonjkpanchayat.in) |
|  |  | 6. | Visitatleast2amritsarovarsandgetitsgeotaggedphotos |
|  |  | 7. | InspectKhidmat(CSC)CentresandcreateGenerateawarenesson225schemesparticularlyG2CschemeslikeBEAMS,Janbhagidari, AapkiZaminAapkiNigrani,DigitalJ&K |
|  |  | 8. | Visitingofficershallalsoplanandconductpanchayatlevelconver- gencemeetingofalldepartments |
|  |  | 9. | CheckeffectivenessofCentrallysponsoredschemes |
|  |  | 10. | VisitandinspectallgovernmentestablishmentsincludingPHE, AWC,FPS,schools,etc |
|  |  | 11. | Attemptsaturationofdeliverableso JanAbhiyanandwherever deficienciesfound,leadadrivetoachievealldeliverables |
|  |  | 12. | Assesseffectivenessofsanitationcampaigninthepanchayat |
|  |  | 13. | Ensureselfemploymentactivitiesfor15youthperpanchayat |
|  |  | 14. | Identify20potentialcandidatesperpanchayatforHIMAYATtraining alongwiththetradeonwhichtheywanttraining |
|  |  | 15. | Whereverpossible,distributeemploymentlettersforpeopleselect- edundervariousgovernmentemployments |
|  |  | 16. | Intheevening,holdnormalmeetingwith seniorcitizens,govtem- ployeesincludingretiredemployees,exservicemen,youthclub,and any citizens ofthevillagewhoareenrolledincollege/university |
|  |  | 17. | OpendiscussiononNashaMuktAbhiyan |

Day2 Haveameetingwithall stakeholders-depttofficials andpanchayatmembers

1. Discussionontheandassesstheprogressofdifferentschemesrelating tothelocalizedSDGsprioritizedforthatvillageaspertheresolution passedby thatGramPanchayaton21st April22,onNationalPanchayti RajDay.

2. Sensitizevillage residentsaboutmyScheme”portal(myscheme.in) whichincludesinformationaboutalltheschemesbeingrunbyCen- tral/State/UTgovtacrossthecountry

3. Hold meeting of theBiodiversityManagementCommitteestodeliber- ateonissuespertaining toconservation of biodiversityandsustaina- bleutilizationof biologicalresources.

4. PrepareVillagedevelopmentplan,inconsultancywithGrampanchayat, discussitingramsabhaandgetitapproved.

5. Ensure saturationofsoilhealthcardandgoldenhealthcardunderGold- enHealthCardunderAyushmanBharat,

6. Ensuresaturation of OldAge PensionScheme

7. EnsureDomicileSaturation.

8. EnsureKCCSaturation

9. Ensure saturationoflandpassbooks

10. Ensureregistrationofvillagevendorsneededforanyscheme,onGEM

portal

11. Ensurepanchayatcontractors registration

12. EncouragePanchayatmembers forimportanceofplantationdrivein

PanchayatunderHarGaonHariyali

13. Ensure paintingondigitalJ&Kinpanchayatghars

14. Ensure paintingonpanchayatactivitesandCSSinpanchayatghars

15. Thevisiting officeshallchecknoof kindergarten andplayfields present inthepanchayat for kidsandstudents,iftheinfrastructure present inthesearegoodenough.

16. Holdmeeting withpanchayatmembers todiscussaboutcorruption menaceandstepsrequiredtomakeJ&Kcorruptionfree

17. Obtaina candidassessmentaboutperformanceofvariousdeptts in- cludingfairfeedbackaboutdiscrepanciesinfunctioning

18. Check thestatusof NashaMuktAbhiyanandreporting of drugad- dictstoDeputyCommissioner.

19. IdentifyTouristDestinations,Circuits,ThemeTreks,IdentifyHomestays, providesupportfortourismactivities throughVillageCooperative

20. OrganizeTalentHuntatPanchayatLevel

21. Conductsocialauditofatleast5worksunderfollowingschemes:

a. MGNREGA

b.PMAY

c. IHHLtoiletsandpayments d.CSCs

e.AMRITSAROVARS

22. Holda mahilasabha anda balsabhaandrecordproceedingsinthefor- matgiven

23. InauguratevillagehaatunderJKSRLM

24. Checkifyouthclubsareformedinthepanchayatandwhatactivities theyareengagedin

25. Organizea villagelevelculturaleventtoengagepanchayatmembers

26. SensitizeGPaboutE-kitabkoshaninitiativeofJ&KGovtforempowering youthsthrough onlinedigitalliteracy

**GENERALINSTRUCTIONS**

1. Thevisitingofficershallrefrainhimself/herselfgivingorofferinganycommitmentonbehalfofthe governmentandshalladoptanunbiasedattitudeinreportingissues.As faraspossible,his/her observation shouldbebasedona fairandanalytical viewemergingfromhis/herinteractioninthe village.

2. Heisgoingtothevillageasplanningofficer,notforsanctioninganyworksorformakinganycom- mitments.

3. Whilepreparingvillagedevelopmentplan,hehastoensurethat,demandsareprioritizedandre- flectedunderavailableschemes,wherevernecessarythelargerworksaretobereferredtoadminis- trativedepttunderCSS/UTplansunderintimationtoDCsandrestoftheworkstoDCsforreflecting itunderdistrict/CSS plans

4. His workshallbehardcoreplanningandauditandisnota PRexercise.

5. EveryDeputyCommissionerhastoensurethatatleastoneRDDofficial(ideallyPanchayatSecre- tary)ispresent ineverypanchayatwithrelevantpanchayatrecords,toensureconductofallactivi- tiesasplanned.Panchayatwiseorderneedstobeissuedinadvance.

6. Visitingofficershouldideallycarryhis/herlaptoptocompletethereportsatthepanchayatlevel itselfanduploadthefinalreport,duly signedbothbythesarpanchandbythevisitingofficeron [www.jkpanchayat.in](http://www.jkpanchayat.in)portal,beforetheyleavepanchayat.

7. Focus ofvisitareyouth,skills,self-employment,nashamukt,bhrashtracharmukt,Rozgaryukt J&K, besidestocarryforwardtheactivities duringJanAbhiyanandsaturatethem.

8. Inadditionattentionmaybegiventothefollowingareas a. MakefulluseofCentrallySponsoredSchemes

b.Saturationofindividualbeneficiaryschemes c. Self-employmentschemes

d.Banklinkedschemes-includingdepartmentalsubsidyschemes e.Empowermentandtransparencythrough digitalinitiatives

f. Effectivenessofgrassrootsmachinery–

i. Patwari,VLWpresent andavailable

ii. AvailablefundsutilizedinpublicinterestandasperGramSabharesolutions iii. Fairness ingovernance

iv. CSS/Individual beneficiaryschemesetc v. BrashtacharMuktJ&K

vi. BhaiMuktJ&K

vii. NashaMuktJ&K

9. ThePRImembers (Sarpanchs,Panchs,BDCChairperson)shallbeattheforefrontofallactivities and givendueimportanceandtheapproach shouldbetostrengthenthemandmakethemfeelem- powered.He/sheshallensurethattheBDCchairpersonandSarpanch/Panch arepresent atthetime ofinaugurationandceremonies.

10. Visitingofficershallnotleavethedistrictwithoutuploadingthereport,duly signedonthe**www. jkpanchayat.in**portal.EveryDeputyCommissionerhastoensurethat.

**A) DetailsofReportingOfficer:**

Name: KHALEEQ AHMED

Designation: ASSISTANT PROFESSOR

Department/placeof posting: HIGHER EDUCATION DEPT. / GDC SURANKOTE

MobileNo:7006343893& 9018890180

EmailID: WRITE TO KHALEEQ@GMAIL.COM

HomeDistrict: RAJOURI

Datesof visit: 30-31st oct 2022

**B) LocationaldetailsofPanchayat:(tobepre-filled,informationtobetakenfromtheprevious phasesbooklets/summarizedexcelsheetuploadedonjkpanchayat.in/b2v4.php)(tobevali- datedbythevisitingofficerandmissingdetailstobefilled)**

NameofthePanchayat: Nar

LocalGovernmentDirectory(LGD)codeof thePanchayat: 7420

Nameof CDBlock: Balakote

NameofTehsil: Mendhar

Nameof District: Poonch

**C) PanchayatProfile:**

No.ofrevenuevillagesinthePanchayat:df 01

No.ofhamletsinthePanchayat: 12

No.ofhouseholdsinthePanchayat: 489

Population(approx)of thePanchayat: 2316

**Part-II:**

(TobefilledupbytheVisitingOfficerduringhis/hertwodayvisittothePanchayat.AllFieldshavetobe

filledbytheVisitingOfficerbeforethebookletishandedovertotheDC

**FrontlineOfficers/OfficialswhowereassignedtothePanchayatfortheprogramme:**

|  |  |  |
| --- | --- | --- |
| Department | Name | Designation |
| Youth Service & Sports | Sarfraz Ahmed | PET |
| Animal Husbandry | Abrar Ahmed |  |
| Social Welfare | Shufta Koser | Asha Worker |
| Health | Jatoon Bi | MPHW |
| ICDS | Tanveer Kouser | Supervisior |
| PDD | Sharafat Ali | lineman |
| Education | Liaqat Ali Khan | Teacher |
| ICDS | Naseem Akhter | AWW |
| Social Welfare (Asha) | Nusrat Jabeen | Supervisior |
| PMGSY | Sadam Hussain | JE |
| PHE | Mohd. Tahir | lineman |
| PWD | Waseem Ahmed | JE |
| Agriculture | Waqar Zaidi | JEO |

**Detailsofabsentemployeesvis-à-vislistfurnishedbytheDCoffice:**

|  |  |  |
| --- | --- | --- |
| Department | Name | Designation |
|  |  |  |
|  |  |  |
|  |  |  |
|  |  |  |
|  |  |  |
|  |  |  |
|  |  |  |
|  |  |  |
|  |  |  |
|  |  |  |
|  |  |  |
|  |  |  |
|  |  |  |
|  |  |  |
|  |  |  |

**DAY1-ACTIVITIES**

**AGENDA1:PANCHAYATASSETREGISTER**

**Infrastructure:**

1. PanchayatGharInfrastructure a. **Govtbuilding**/private

b. New/**needingrepairs**

2. Furniture(**Y**/N)

3. Computer/printer(Y/N)

4. Internet(**Y**/N)

5. Telephone(Y/**N**)

6. Toilet(CSC/partofpanchayatghar)(Y/**N)**

7. Water(**Y**/N)

8. Electricity(**Y**/N)

9. Bankbranch(Y**/N**)

10. CSC(Y/**N**)

11. Patwarkhana(Y**/N**)

12. Villagehaat**(Y**/N)

13. Playground(Y/**N**)

14. School-

a. Kindergarten(Y/**N)**

b.Primary(**Y**/N)

c. Secondary(Y**/N**)

d. College (Y/**N**)

e.University(Y/**N)**

15. AnganwadiCentre(**Y**/N)

a. **(govt/private**)

b.Totalchildrenenrolled

15. AmritSarovars–details,location,condition one est cost. 2.00 F.Y 2020-2021

16. Governmentoffices-details,whetherfunctionalornot

17. Rationshop(**Y/**N)

18. Placesoftourismimportance–names,littledetailsonhistorical/culturalimportance yes

19. Villageheritagesites/treks-names,littledetailson historical/culturalimportance YES

20. VLWOffice (**Y**/N)

21. PrimaryHealthcareCentre(**Y**/N),

22. ListofIncompleteBuildings-names,yearofconstruction

23. ListofUnderutilizedBuildings-names Panhayat store at Tota Gali illegally occupied

**DAY1-ACTIVITIES**

**AGENDA2:**

**DIFFERENTINSTITUTIONS/INFRASTRUCTUREPROJECTSTOBEVISITED**

|  |  |  |
| --- | --- | --- |
| **AMRITSAROVARS** | **Visit,verify** | **COMMENTS** |
| KhidmatCentres | Create/Generateawarenesson225schemes particularlyG2CschemsAapkiZaminAapkiNigrani, Beams,Janbhagidari,DigitalJ&K |  |
| JKB/PSBcounters/outlets | a)Statusofcounter b)Numberofvisitors | NIL |
| Incompletebuildings/pro- jects | Verify whetheridentificationandredistribution done | PHC NAR BUILDING UNDER CONSTRUTION |
| PDS | Visit,evaluate,onlinestatus | YES  |
| PHC | Visit-evaluate,statusofstaff,equipmentand quality | Functional in one room |
| Youthclubs | Meet,interact,seeksuggestions | Demanded play ground |
| SHG | Meet,identifyproblems,seeksuggestions | Yet to be active |
| PMAY | Inspect,Inaugurate | Inaugurated Mehmood Hussain |
| Myschool,mypride progress;schools-water, toilets,staff | Visit,checkforwater,electricity,sanitation,meet studentsandstaff | M/S Dhara Nar requires repair M/S Samooti requires Building |
| SwachhSBM | Evaluate | IHHL Unit, Soak Pits, Composit Pits |
| Panchayatplayground, Sportskitsdistribution Villagegames | Ensure,verify.Participateinatleastonegamein theplayground | Play Ground is not available |
| HarGaonHariyali, Planta- tiondrive | Evaluatestatus,feedback | 30 Plants were Planted |
| VillageculturaleventDangal/Haat/Mela | Participatein;ensurethatitisheld | Yes |
| Exhibitionofschemes | Ensurethateverydepartmentparticipatesand thatitcontinuesfortheentiredurationofB2V | RDD,ICDS, Social Welfare , Social Forestry & Horticulture |
| JalJeewanMission verifica- tion- WSS/JSDElectricitysupply | Verify | Lifting Scheme is under process |

**DAY1-ACTIVITIES**

**AGENDA3:SATURATEJANBHIYAN**

**DELIVERABLESANDRECORDDEFICIENCIESIFANY(INSERTDELIVERABLESLISTHEREASPERGADFORMAT**

1. Golden Health Cards : 620/1100
2. Land Passbook: 10/280
3. Inheritance Mutation 60
4. CSC-IT NA
5. Awareness of Jan Bhagidari: undertaken
6. Pani Sammities Meeting : Yes
7. Field Testing kit : Not Provided
8. Implementation of Swatch Gram Plan: Yes
9. UDID Cards : 17/251
10. E-Sharam Cards 1010/1100
11. Information of Officials: Displayed
12. Youth Club : 01
13. Amrit Sarovar : 01
14. KCC Cards : 110/336
15. Soil Health Cards : 315/336

**DAY1-ACTIVITIES**

**AGENDA4:**

**SELFEMPLOYMENTACTIVITIES**

EnsureSelf-employmentactivities foryouth,distributeemploymentlettersforpeopleselectedunder varioussocialschemes(15ISTHETARGETPERPANCHAYAT)

 **Numberofcasesindifferentcategoriessanctioned: 01under mission Youth**

 **Detailsofthebanksanctioningit: JKbank Bhatadhurian**

**Totalamountinvolved:10lakh**

**DAY1ACTIVITIES**

**AGENDA5**

Intheevening,holdinformalmeetings withseniorcitizens,govtemployees,retdemployees,youthclub andothercitizenswhoareenrolledoncollege/universityandhavediscussiononGandhiKatha,Nasha MuktAbhiyan,corruptionfreegovernance,doublingfarmersincomeandrecordtheproceedings

**DAY2**

a. NoofIndividualCompostPitsconstructe 04

b. NoofIndividualSoakPitsconstructed 120

V. No.ofBiodiversitymanagementcommitteemeetingsheld: 01

VI. IsthenameofSarpanchdisplayedoncitizeninformationboardsofallRD&PRschemes: Yes/

VII. AreSarpanchsbeinginvolvedinstart/inaugurationofactivities: YeS

VIII. WhethersubjectshavebeenassignedbytheSarpanchtothePanchs: Yes

IX. Whethergrievancesredressalboxisinstalled: Yes

X. Noofgrievancesreceivedpertainingto Panchayat level:

XI. NoofgrievancesdisposedofatPanchayatlevel:10

XII. WhethertheSarpanch/PanchayatSecretaryhavedigitalsignatures: YeS

XIII. WhetherallMGNREGA/14thFCpayments arebeingmadebySarpanchthrough DigitalSignature

Certificate(DSC): Yes

**HUMAN RESOURCEAVAILABLEATTHEPANCHAYAT LEVEL:**

|  |  |  |  |
| --- | --- | --- | --- |
| **SRNO.** | **DEPARTMENTWISESTAFF** | **NUMBERS** | **NAMES** |
|  |  | SANCTIONED | ACTUAL |  |
|  | Ruraldevelopmentdepartment: BDOJE GRS TA | NILNIL0101 | NILNIL0101 |  |
|  | SCHOOLEDUCATION: TEACHERHEADMASTER ANYOTHER | 5201 | 5201 |  |
|  | JAL JEEVAN: | NIL01 | NIL01 |  |
|  | PDD: LINEMAN JEANYOTHER | 0101 | 0101 |  |
|  | FOOD&CIVILSUPPLIES | NIL | NIL |  |
|  | AGRICULTURE&ANIMALHUS- BANDARY | 01 | 01 |  |
|  | SOCIALWELFARE | NIL | NIL |  |
|  | HEALTH: ASHA ANMAYUSHDOCTOR ALLOPATHICDOCTOR | 03NILNILNIL | 03NILNILNIL |  |
|  | A.WA.HICDS SUPERVISIOR | 070701 | 070701 |  |

**DAY2-ACTIVITIES**

**AGENDANO.1**

DiscussionontheandassesstheprogressofdifferentschemesrelatingtothelocalizedSDGsprior-itizedforthatvillageaspertheresolutionpassedbythatGramPanchayaton21stApril22,onNational PanchayatiRajDay(Copyoftheresolutiontobetakenfrom[www.jkpanchayat.in](http://www.jkpanchayat.in)portalunderthelinkof GramSwarajMonth)

1. SDGs AGREED FORTHATVILLAGE,TOBEIMPLEMENTED BYMARCH2024: Child Friendly Village

2. STATUSOFWORKSUNDERTHEFOLLOWINGSCHEMES:

**1 Cleanandgreenvillage**

i.InitiativestakenbythePanchayatformanagingSolidandLiquidWaste: Soak &Composit Pits

ii. InitiativestakenbythePanchayatforusinggreensourcesoffuellikesolar,biogas

 NIL

iii. Hasmappingoflanduse,waterbodies,forest,slopes,wetlands,degradedforestwithintheGram

Panchayatbeendone?Yes/**No**.IfNo,reason,thereof - **Lack of Initiative**

iv. HastheClimateResiliencePlanbeendevelopedfortheGP?Yes/**No**

v. StepstakenbytheGramSabhaabouttheclimatechangemitigationfactorslikereducingenergy consumption,usageoffossilfuels,plastics,non-renewablebuildingmaterialsandalsotopromote measureslikeplantingoftrees,conservingforests,usageofgoodagriculturalpracticeslikedrip irrigation,waterconservationmeasuresandconservationofwetlands**. Plantation drives &10 water Tanks**

vi. Whetherschoolshavestartedsegregatingwaste nil

vii. Whetherschoolshavetheirowncompost/soakagepitsforsolid/liquidwastemanagement nil

**2 Healthyvillage**

i) Aremeetings relatedtoVillageHealthandSanitationCommitteebeingheldregularly? YES

ii) DoalltheeligibleindividualsbeenprovidedtheGoldenCard? NO

iii) ArealltheChildrenbeingimmunizedaspertheSchedulerecommendedbyGovt.ofIndia? YES

iv) ArealltheeligibleindividualsbeenvaccinatedagainstCOVID-19? YES

v) DoesGramPanchayatensurethatallpregnantwomenaregettingnecessaryprenatalcheckups? YES

vi) WhetherallthedeliverieswereInstitutionalizedorconductedbytrainedMidwives? YES

**3 Watersufficientvillage**

i) DoalltheIHHsintheGramPanchayathavewaterpipelineconnections? NO

ii) WhetherGramPanchayathastakenstepsforgreywatermanagement.IfYespleasespecify SOAK PITS iii) DoalltheIHHsintheGramPanchayathavetoilets? NO

iv) ArealltheIHHstoiletsfunctionalornot? YES

v) DoalltheSchools/Anganwadicentershavea toiletfacilityornot? YES

vi) Areallthetoiletsintheschools/Aaganwadifunctionalornot? YES

vii) WhetherGramPachachayatBhawanhasseparate toiletsforwomenornot?NO

**4 ChildFriendlyvillage**

i) Doallthechildrenundertheageof0-6yearsbeenenrolledintheAnganwadicentersforpre- schooling?Yes/NO YES

ii) HowmanyBalSabha’swereorganizedintheGramPanchayat----01---------------

iii) WhethertheissuesraisedbyBalSabhaareaddressedduringtheGramSabha. Yes/NO YES

iv) WhetherGramPanchayatistrackingthedatarelatedtodropoutchildrenandchildrenwithirregular attendance?Yes/NO. YES

v) DoalltheschoolsundertheGramPanchayathaveseparate toiletsforgirlsandboys?Yes/No YES

**5 Villagewithgoodgovernance**

i) IsCSClocatedintheGramPanchayatBhawanornot? NO

ii) IsthelistofbeneficiariesrelatedtotheSchemes/ProgramsdisplayedontheGrampanchayatwallor not?YES

iii) DoestheGramPanchayathasitsbuildingornot? YES

iv) IstheGramPanchayatofficefunctionalornot? YES

v) Aretheactivities approved undertheHalqaPanchayatDevelopmentPlandisplayedontheGram

Panchayatwallornot? NO

vi) IsSocialAuditofearlierSchemes/Programscarriedoutornot? YES

**6 Povertyfreeandenhancedlivelihoodvillage**

1. HasGramPanchayatdevelopedanycriteria fortheidentificationofthepoor?Yes/Noifyesspecify NO
2. ii) HavealltheeligiblehouseholdsregisteredinPDSornot? YES

iii) HasGramPanchayatprovidedspaceforSelf-helpGroupsinPanchyatGharforholdingmeetings or not?YES

iv) HavealltheeligiblehouseholdsbeenregisteredforPensionornot? YES

v) HasGramPanchayatfacilitatedYouthforSkillEnhancementCoursesandPlacement? NO

vi) HasJobCardsbeendistributedtoalltheeligibleindividualsunderMGNREGA? YES

vii) HasGramPanchayatfacilitatedSHGsforBankAccountLinkages? YES

**7 Sociallysecuredvillage**

i) WhetherGramPanchayatismaintainingdatarelatedtoDifferentlyAbledPeople? YES

ii) IsGramPanchayatOffice DisabledFriendlyornot? YES

iii) Areprovisionsfora separate BudgetundertheResourceEnvelopeforWomenandChildrenmadeor not?NO

iv) DoalltheSchools intheGramPanchayathavefacilitiesforDifferentlyAbledChildrenliketoilets, barrier-freeaccess,etc.,ornot? NO

v) Arealltheeligibleindividualsaregettingpensions,likeoldagepension,widowpension,etc? YES

vi) ArealltheeligiblehouseholdsgettingbenefitsfromIAYornot? YES

**8 EngenderedDevelopmentinVillage**

i) HowmanyMahilaSabha’swereorganizedintheGramPanchayat----01---------------

ii) WhetherSHGsfederationshavebeenprovidedspaceformeetings inthePanchayatBhawan(Yes/ No) YES

iii) WhetherGPshavetakenstepsforincreasingwomen’sparticipationinGramSabha(Yes/No) YES

iv) NumberofwomenbeneficiariesheadedhouseholdscoveredunderPDS

system………YES 60………………

v) Numberofbeneficiaries(outoftotaleligiblepopulation)receivingsocialprotectionbenefitsunder

PradhanMantriMatritvaVandanaYojana……YES 05…………….

9 Self-sufficientinfrastructureinthevillage

i. WhetherGPhasa CommunityHallwithaccesstoelectricity,furniture,watersupply, toilet……………YES………….

ii. WhethertheDisastermanagementplanisavailableattheGPLevel(Yes/No) YES

 iii. Whetherchild-friendlyparkwithrequiredfacilitiesisavailableinGP(Yes/No) NO

 iv. WhethertheGPhaseasyaccesstoGodownforstorage(Yes/No) NO

v. Whetherstreetlightsareprovidedinpublicplacesforensuringsafety(Yes/No) NO

**DAY2ACTIVITIES**

**AGENDANO.2**

SensitizevillageresidentsaboutmyScheme”portal(myscheme.in)whichincludesinformationaboutall theschemesbeingrunbyCentral/State/UT govtacrossthecountry

*(SchemeMaterialavailablefromhttps://jkpanchayat.in/b2v4.php)*

**DAY2ACTIVITIES**

**AGENDANO.3**

HoldmeetingoftheBiodiversityManagementCommitteestodeliberateonissues pertainingtoconserva- tionofbiodiversityandsustainableutilizationofbiologicalresources.HeshouldcheckPeopleBiodiversity register(PBR)ofthatpanchayatandreviewifBiodiversityManagementCommittee constitutedforthat panchayatis holdingminimum4meetings inayearandmeeting onceinevery3months *(RoleofBMC availableathttps://jkpanchayat.in/b2v4.php)*

COMMITTEE MEMBER 07

PRESENT SARPANCH AFTAB AHMED KHAN

BIODIVERSITYREGISTERPHOTOS NIL

PAST 4MEETINGDETAILS-DATES,MINUTESPHOTOS

 NIL

**DAY2ACTIVITIES**

**AGENDA4**

Visitingofficershallalsoplanandconductpanchayatlevelconvergencemeeting ofalldepartmentsand prepareVillagedevelopmentplanforvillage,inconsultancywithGrampanchayat,discussitingram sabhaandgetitapproved.

(GPDPformatavailableonhttps://jkpanchayat.in/b2v4.php)

**InadditionGPDPplanshallalsoinclude:**

 Touristplaceswhichneedtobedeveloped

 Specificproductwhichneedstobedeveloped

 Tourism-homestays

 20candidatesfortrainingunderHimayatschemealongwithtradeinwhich trainingistobegiven

**DAY2ACTIVITIES**

**AGENDA5**

Ensuresaturationoffollowingschemesandgivestatus:

|  |  |  |  |
| --- | --- | --- | --- |
| **NAMEOFTHESCHEME** | **TOTALELIGIBLE BENEFICIARIESIN THE VILLAGE** | **TOTALBENEFICIARIESWHO AVAILEDTHEBENEFITSOFTHESCHEME** | **REASONSFOR PENDENCY** |
| GoldenHealthCardunderAyushmanBharat | 1100 | 620 |  |
| Jananisurakshayojana |  |  |  |
| OLDAGEpension | 251 | 129 |  |
| Widowpension | 36 | 36 |  |
| Disabilitypension | 86 | 86 |  |
| Domicilecertificate | 2316 | 1807 |  |
| Kisancreditcard | 236 | 110 |  |
| PMkisansammannidhi | 236 | 221 |  |

|  |  |  |  |
| --- | --- | --- | --- |
| Landpassbook | 280 | 10 |  |
| Registrationofvillageven- dorsonGEMportal | 02 | 02 |  |
| Registrationofvillagecon- tractorsonjktendersportal | 10 | 10 |  |
| Registrationofvillagecon- tractorsonPWDportal | 10 | 10 |  |
| Incompletebuildings/pro- jects | NTPHC | NTPHC |  |

**DAY2ACTIVITIES**

**AGENDA6**

**NASHAMUKTABHIYAN**

1. Whethergramsabharesolutionpassed YES

2. Detailsofactivities conducted PLEDGE, RALLY,AWARENESS LECTURE

3. Whetherallactivities andGSresolutionuploadedonjkpanchayats.inportal YES

4. Howmanydrugaddictsinthevillage NIL

5. WhetherreportedtotheDeputyCommissioner NIL

6. Howmanyregisteredforrehabilitationundergovernmentprogramme NIL

**DAY2ACTIVITIES**

**AGENDA7**

**SOCIALAUDIT**

Conductsocialauditofatleast5workseachunderfollowingschemes:

|  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- |
| NAMEOFTHE SCHEME | DETAILSOFTHE WORKS | YEAROFWORK APPROVAL | AMOUNT APPROVEDFORTHEWORK | WHETHERWORKEXECUTED SATISFACTORILY | GEO- TAGGED PHOTOS | ANY GRIEVANCE RECORDED RELATINGTOTHAT WORK |
| MGNREGA | Water Tank bakarwalan | 2021-22 | 1.00 | Yes  | Yes  | Payment pending |
| PMAY | Mehmood Hussain | 2021 | 1.20 | Yes  | Yes  | 4th installment pending |
| IHHLUNDERSBM-G | Tasveer Begum | 2022 | .12 | Yes  | Yes  |  |
| CSCUNDER SBMG | Nil  |  |  |  |  |  |
| AMRIT SAROVARS | Renovation of water tank totagali | 2021-22 | 2.00 | Yes  | Yes  |  |

**DAY2ACTIVITIES**

**AGENDA8**

**MAHILASABHA**

Totalwomeninthevillageabovetheageof18

Totalattended

Proceedings:

*(Plinsertpointerstobediscussedthere–referpalliproceedings)*

**DAY2ACTIVITIES**

**AGENDA9**

**BALSABHA**

Holda balsabhaandrecordproceedings

Totalchildreninthevillageabovetheageof….. Totalattended

Proceedings:

*(Plinsertpointerstobediscussedthere–referpalliproceedings)*

**DAY2ACTIVITIES**

**AGENDA10**

**INAUGURATIONS**

|  |  |  |  |
| --- | --- | --- | --- |
| **SR NO.** | **ASSETS/ACTIVITIES INAUGRATED** | **STATUSOFTHEASSET/AC- TIVITIES(NUMBER,OTHER DETAILS)** | **GEO-TAGGED PHOTOS** |
|  | VILLAGEHAATunderJKSRLM (SUN- DAYMARKET) |  Inaugurated  | Yes  |
|  | PMAYhousesifanyreadyforinaugra- tion | 01 | Yes  |
|  | Swachhgramprojects-segregation shedsetc | No such plan | No  |
|  | Amritsarovars | 01 | Yes  |
|  | Sportskits | 01 held  | Yes  |
|  | Villageculturalevents | held  | Yes  |
|  | JJMassets/projects | Lift scheme in process | Yes  |
|  | Anyothertobeidentifiedatdistrict level |  |  |

**FOLLOWUPOF(B2V1,B2V2&B2V3):**

*(Prefilledexcelsheet tobetakenfromdistrictlevel/andalsotobedownloaded*

*from*[*www.jkpanchayat.in)*](http://www.jkpanchayat.in)

|  |  |  |  |
| --- | --- | --- | --- |
| S.NO. | Particulars | Actiontaken | Remarks# |
| I. UrgentPublicRequirements/Demands-B2V1 |
| 1 | Road from Galutta to Keri Top | Not Taken |  |
| 2 | Road from Keri Top to Margain | Not Taken |  |
| 3 | Borewells in different wards | Not Taken |  |
| 4 | Destruction of rice & maize by wild Pigs | Not Taken |  |
| 5 | Primary health centre | Not Taken |  |
| 6 | Dispensary in different wards | Not Taken |  |
| 7 |  |  |  |
| II. UrgentPublicRequirements/Demands-B2V2 |
| 1 | Road from Galutta to Keri top to Margain Gali | Not Taken |  |
| 2 | Road from Top to tota gali upper nar | Not Taken |  |
| 3 | Road from M/s Dhara nar to Kanyali | Action Taken |  |
| 4 | Lift scheme water from HS Nar Dhurar to Manda Tota Gali | Not Taken |  |
| 5 | Borewell in all wards | Not Taken |  |
| 6 | Tap water to all Houses | Not Taken |  |
| 7 | Transformer in all Wards | Action Taken |  |
| S.NO. | Particulars | Actiontaken | Remarks# |
| III. MajorProblems–B2V1 |
| 1 | Shortage of portable Water | Not Taken |  |
| 2 | Shortage of Electricity | Not Taken |  |
| 3 | Non-Availability of health Facilities | Not Taken |  |

|  |  |  |  |
| --- | --- | --- | --- |
| 4 | Road connecting to different wards | Action Taken |  |
| 5 |  |  |  |
| IV. MajorProblems-B2V2 |
| 1 | The problems during B2V2 remains the same as B2V1 as none of the problem solved during and after B2V1 Programme |  |  |
| 2 |  |  |
| 3 |  |  |
| 4 |  |  |  |
| 5 |  |  |  |
| V. MajorProblems-B2V3 |
| 1 | The problems during B2V3 remains the same as B2V1 as none of the problem solved during and after B2V1 Programme. PRI members and Sarpanch bycotted the B2V3 and then NAIB TEHSILDHAR assured the Sarpanch that the problrms would be solved at earliest. |  |  |
| 2 |  |  |  |
| 3 |  |  |  |
| 4 |  |  |  |
| 5 |  |  |  |
| VI. MajorComplaints-B2V1 |
| 1 | Mr. Abdul Hamid S/O Allah Ditta Khan claimed that he didn’t get regularization at Panchayat Ghar. |  |  |
| 2 | Payments for projects not on time |  |  |
| 3 |  |  |  |
| VII. MajorComplaints-B2V2 |
| 1 | Destruction of maize by wild pigs |  |  |
| 2 | Medical facilities not available. |  |  |
| 3 |  |  |  |
| VIII. MajorComplaints-B2V3 |
| 1 | B2V demands have not been meet so that resources should be given to panchayats for completion of languishing projects. B2V3 was bycotted and Naib Tehsildar assured for completion of works. |  |  |
| 2 |  |  |  |
| 3 |  |  |  |

**OVERALLPERCEPTIONOFFUCNTIONING OF GOVERNMENTDEPARTMENTS**

1. **BESTDEPARTMENT: RDD**

**2. LEASTRESPONSIVEDEPARTMENT:NIL**

**GENERALASSESSMENTOFTHEVISTINGOFFICER**

|  |  |
| --- | --- |
| I | AnymajorcomplaintbroughttothenoticeoftheVisitingOfficer: |
| II | Major/urgentpublicdemandsthatwas/werereflectedearlierbuthavenotbeenaddressedsofar: |
| III | Overallassessmentofthevisitandsuggestions:(Thevisitingofficertoensurethattheoverallassessmentisrecordedindetailsalongwithconcretesugges- tions) **7.5** |
| IV | OverallRatingofgovtfunctioningas givenbythePanchayat(Scaleof0to10)  |
| V | CertificatefromSarpanchthatthevisitingofficerhasstayedinthepanchayatfor2days |

**SignatureofSarpanch SignatureoftheVisitingOfficer**

**Name……………………… Name………………………**



**DepartmentofRuralDevelompentandPanchayatiRaj**

**GovernmentofJammu &Kashmir**

