4

15TH OCTto3RD NOV,2022

KEYFEATURES

•     DeputyCommissionerstoleadtheinitiative

•    RuraldevelopmentDepartmenttobethenodaldepartment

•	PlanningDevelopment&MonitoringdepartmentandITtobethesupport departments

ACTIONSANDTIMELINES

| ACTION | RESPONSIBILITY | LATESTBY | REMARKS |
| --- | --- | --- | --- |
| Janabhiyan | Alldepartments | Oct15-26th | Goingon |
| DeputationofSecttstaff/ HoDs | GAD | Oct14 | Done |
| DeploymentofStaffto Panchayatsandservingof ordersondeployedofficers | DCs | Oct25 | DCswilldeployseniorlevelstaff fromthedistricts.Strictactionto betakenagainstabstentions.No exemptionstobegiven |
| Trainingofdistricttrainors onB2V4 | RDD | Oct26 |  |
| Trainingofvisitingofficers | DCs | Oct27 |  |
| FieldVisitstobecompleted by | VisitingOfficers | Nov3 | DCstosuperviseandensurethat eachPanchayatisvisitedwithin theperiodspecified |
| DataofB2V4tobe uploadedby | VisitingOfficers | Nov10 | DCstosuperviseandensurethat dataofallPanchayatsisupload- edbythevisitingofficerwithin theperiodspecified |

INSTRUCTIONSFORTHEVISITINGOFFICER(DAYWISE)

| DATE | INSTRUCTIONS | ACTIONPOINTS |
| --- | --- | --- |
| Day0 | Meetingwithdeputy commissionerandhis/her team | a. TakeprintoutsoffilledbookletsofB2V1,B2V2andB2V3from www.jkpanchayat.in b.Alsotakeprintoutsofthesummarizedexcelsheetsofthe previousphasesfromwww.jkpanchayat.in c. CollectATRsonissuesraisedduringprevious3phasesfromthe officeofDeputyCommissioner(Planningdeptt) d.Takeprintsofblank 2bookletsofB2V4fromwww.jkpanchayat.ine.Takeplansfor2previousyearsandATRsfromtheplanningdeptt f. CompletetrainingsondifferentcomponentsofB2V4being organizedbyrespectiveDeputyCommissioners g.CollectListofnewworksstarted/ongoing/completedduringthe previousandcurrentFinancialyearunderthefollowingheads: • PRIgrants • DistrictPlan • UTplan • MGNREGA • Otherschemesofotherdepartments • Anyotherwork h. Plans/beneficiarylists: • MGNREGAdraftplandocumentfortheyear2022-23. • ListofAwaas+beneficiariesalongwithIHHL Convergence • Listofpensionbeneficiaries. • ListofSHGs • Listofagricultureschemebeneficiaries i. Listsofbeneficiariesfor: • Variouscertificates/benefitstobedistributedbythe visitingofficer. • Anyotheractivitiesidentifiedbydifferentdepartments |

| Day1 | Reachthevillage | 1. | Ensurethatallfrontlineworkersofdifferentdepttsarepresent. |
| --- | --- | --- | --- |
|  |  | 2. | Ensureexhibitionbydifferentdepts.aboutindividualbeneficiary schemes |
|  |  | 3. | InspectJKB/PSBcounters/outlets |
|  |  | 4. | Participate/ensureorganizationofsportsactivityinplayfield,talent hunt/culturalevent/youthactivity |
|  |  | 5. | GandhiKatha(suggesteddetailsuploadedonjkpanchayat.in) |
|  |  | 6. | Visitatleast2amritsarovarsandgetitsgeotaggedphotos |
|  |  | 7. | InspectKhidmat(CSC)CentresandcreateGenerateawarenesson 225schemesparticularlyG2CschemeslikeBEAMS,Janbhagidari, AapkiZaminAapkiNigrani,DigitalJ&K |
|  |  | 8. | Visitingofficershallalsoplanandconductpanchayatlevelconver- gencemeetingofalldepartments |
|  |  | 9. | CheckeffectivenessofCentrallysponsoredschemes |
|  |  | 10. | VisitandinspectallgovernmentestablishmentsincludingPHE, AWC,FPS,schools,etc |
|  |  | 11. | Attemptsaturationofdeliverableso JanAbhiyanandwherever deficienciesfound,leadadrivetoachievealldeliverables |
|  |  | 12. | Assesseffectivenessofsanitationcampaigninthepanchayat |
|  |  | 13. | Ensureselfemploymentactivitiesfor15youthperpanchayat |
|  |  | 14. | Identify20potentialcandidatesperpanchayatforHIMAYATtraining alongwiththetradeonwhichtheywanttraining |
|  |  | 15. | Whereverpossible,distributeemploymentlettersforpeopleselect- edundervariousgovernmentemployments |
|  |  | 16. | Intheevening,holdnormalmeetingwith seniorcitizens,govtem- ployeesincludingretiredemployees,exservicemen,youthclub,and any citizens ofthevillagewhoareenrolledincollege/university |
|  |  | 17. | OpendiscussiononNashaMuktAbhiyan |

Day2            Haveameetingwithall stakeholders-depttofficials andpanchayatmembers

1.       Discussionontheandassesstheprogressofdifferentschemesrelating tothelocalizedSDGsprioritizedforthatvillageaspertheresolution passedby thatGramPanchayaton21st April22,onNationalPanchayti RajDay.

2.	Sensitizevillage residentsaboutmyScheme”portal(myscheme.in) whichincludesinformationaboutalltheschemesbeingrunbyCen- tral/State/UTgovtacrossthecountry

3.	Hold meeting of theBiodiversityManagementCommitteestodeliber- ateonissuespertaining toconservation of biodiversityandsustaina- bleutilizationof biologicalresources.

4.       PrepareVillagedevelopmentplan,inconsultancywithGrampanchayat, discussitingramsabhaandgetitapproved.

5.       Ensure saturationofsoilhealthcardandgoldenhealthcardunderGold- enHealthCardunderAyushmanBharat,

6.       Ensuresaturation  of OldAge PensionScheme

7.       EnsureDomicileSaturation.

8.       EnsureKCCSaturation

9.       Ensure saturationoflandpassbooks

10.     Ensureregistrationofvillagevendorsneededforanyscheme,onGEM

portal

11.     Ensurepanchayatcontractors registration

12.     EncouragePanchayatmembers forimportanceofplantationdrivein

PanchayatunderHarGaonHariyali

13.     Ensure paintingondigitalJ&Kinpanchayatghars

14.     Ensure paintingonpanchayatactivitesandCSSinpanchayatghars

15.	Thevisiting officeshallchecknoof kindergarten andplayfields present inthepanchayat for kidsandstudents,iftheinfrastructure present inthesearegoodenough.

16.     Holdmeeting withpanchayatmembers todiscussaboutcorruption menaceandstepsrequiredtomakeJ&Kcorruptionfree

17.     Obtaina candidassessmentaboutperformanceofvariousdeptts in- cludingfairfeedbackaboutdiscrepanciesinfunctioning

18.	Check thestatusof NashaMuktAbhiyanandreporting of drugad- dictstoDeputyCommissioner.

19.     IdentifyTouristDestinations,Circuits,ThemeTreks,IdentifyHomestays, providesupportfortourismactivities throughVillageCooperative

20.     OrganizeTalentHuntatPanchayatLevel

21.     Conductsocialauditofatleast5worksunderfollowingschemes:

a.       MGNREGA

b.PMAY

c.        IHHLtoiletsandpayments d.CSCs

e.AMRITSAROVARS

22.     Holda mahilasabha anda balsabhaandrecordproceedingsinthefor- matgiven

23.     InauguratevillagehaatunderJKSRLM

24.     Checkifyouthclubsareformedinthepanchayatandwhatactivities theyareengagedin

25.     Organizea villagelevelculturaleventtoengagepanchayatmembers

26.     SensitizeGPaboutE-kitabkoshaninitiativeofJ&KGovtforempowering youthsthrough onlinedigitalliteracy

GENERALINSTRUCTIONS

1.	Thevisitingofficershallrefrainhimself/herselfgivingorofferinganycommitmentonbehalfofthe governmentandshalladoptanunbiasedattitudeinreportingissues.As faraspossible,his/her observation shouldbebasedona fairandanalytical viewemergingfromhis/herinteractioninthe village.

2.	Heisgoingtothevillageasplanningofficer,notforsanctioninganyworksorformakinganycom- mitments.

3.	Whilepreparingvillagedevelopmentplan,hehastoensurethat,demandsareprioritizedandre- flectedunderavailableschemes,wherevernecessarythelargerworksaretobereferredtoadminis- trativedepttunderCSS/UTplansunderintimationtoDCsandrestoftheworkstoDCsforreflecting itunderdistrict/CSS plans

4.    His workshallbehardcoreplanningandauditandisnota PRexercise.

5.	EveryDeputyCommissionerhastoensurethatatleastoneRDDofficial(ideallyPanchayatSecre- tary)ispresent  ineverypanchayatwithrelevantpanchayatrecords,toensureconductofallactivi- tiesasplanned.Panchayatwiseorderneedstobeissuedinadvance.

6.	Visitingofficershouldideallycarryhis/herlaptoptocompletethereportsatthepanchayatlevel itselfanduploadthefinalreport,duly signedbothbythesarpanchandbythevisitingofficeron www.jkpanchayat.inportal,beforetheyleavepanchayat.

7.	Focus ofvisitareyouth,skills,self-employment,nashamukt,bhrashtracharmukt,Rozgaryukt J&K, besidestocarryforwardtheactivities duringJanAbhiyanandsaturatethem.

8.    Inadditionattentionmaybegiventothefollowingareas a.     MakefulluseofCentrallySponsoredSchemes

b.Saturationofindividualbeneficiaryschemes c.     Self-employmentschemes

d.Banklinkedschemes-includingdepartmentalsubsidyschemes e.Empowermentandtransparencythrough digitalinitiatives

f.       Effectivenessofgrassrootsmachinery–

i.       Patwari,VLWpresent  andavailable

ii.      AvailablefundsutilizedinpublicinterestandasperGramSabharesolutions iii.   Fairness ingovernance

iv.    CSS/Individual beneficiaryschemesetc v.      BrashtacharMuktJ&K

vi.   BhaiMuktJ&K

vii.  NashaMuktJ&K

9.	ThePRImembers (Sarpanchs,Panchs,BDCChairperson)shallbeattheforefrontofallactivities and givendueimportanceandtheapproach shouldbetostrengthenthemandmakethemfeelem- powered.He/sheshallensurethattheBDCchairpersonandSarpanch/Panch arepresent  atthetime ofinaugurationandceremonies.

10.	Visitingofficershallnotleavethedistrictwithoutuploadingthereport,duly signedonthewww. jkpanchayat.inportal.EveryDeputyCommissionerhastoensurethat.

A)   DetailsofReportingOfficer:

Name:   Sabir Hussain Shah

Designation:Sr. Lecturer

Department/placeof  posting:H.S.S. (B) , Mendhar

MobileNo:8491909981

EmailID:sabirhussain619@gmail.com

HomeDistrict:Poonch

Datesof  visit:30th - 31st Oct 2022

B)	LocationaldetailsofPanchayat:(tobepre-filled,informationtobetakenfromtheprevious phasesbooklets/summarizedexcelsheetuploadedonjkpanchayat.in/b2v4.php)(tobevali- datedbythevisitingofficerandmissingdetailstobefilled)

NameofthePanchayat:Kasblari Lower

LocalGovernmentDirectory(LGD)codeof  thePanchayat:239305

Nameof  CDBlock:Mankote

NameofTehsil:Mankote

Nameof    District:Poonch

C)     PanchayatProfile:

No.ofrevenuevillagesinthePanchayat:01

No.ofhamletsinthePanchayat:09

No.ofhouseholdsinthePanchayat:332

Population(approx)of  thePanchayat:2160

Part-II:

(TobefilledupbytheVisitingOfficerduringhis/hertwodayvisittothePanchayat.AllFieldshavetobe

filledbytheVisitingOfficerbeforethebookletishandedovertotheDC

FrontlineOfficers/OfficialswhowereassignedtothePanchayatfortheprogramme:

| Department | Name | Designation |
| --- | --- | --- |
| RDD | Jasmeet Singh | Pyt Secratary |
| Social Forestry | Nazir Hussain | Guard |
| Revenue | Mohd Rafi | Patwari |
| Health Dept | Inderjeet Singh | FMPW |
| Jal Shakti | Mohd Javed | Lineman |
| ICDS | Zahida Akhtar | AWW |
| Youth Services & Sports | Asif Mustafa Khan | PET |
| Youth Clubs | Mohd Alyas | BLO |
| Grameen Bank | Sourash Sharma | BA |
|  | Anil Singh | Bank Manager |
| Agriculture | Sudheer Sharma | AEA |
| Sericulture | Mohd Taj | Technician |
| RDD | Mehmood Shah | Accounts Assistant( Pyt) |

Detailsofabsentemployeesvis-à-vislistfurnishedbytheDCoffice:

| Department | Name | Designation |
| --- | --- | --- |

DAY1-ACTIVITIES

AGENDA1:PANCHAYATASSETREGISTER

Infrastructure:

1.		PanchayatGharInfrastructure a.  Govtbuilding/private.       - Private

b.  New/needingrepairs

2.       Furniture(Y/N) - Yes

3.       Computer/printer(Y/N) - Yes

4.       Internet(Y/N) - No

5.       Telephone(Y/N) - No

6.       Toilet(CSC/partofpanchayatghar)(Y/N) - No

7.       Water(Y/N) - No

8.       Electricity(Y/N) - No

9.       Bankbranch(Y/N) - No

10.     CSC(Y/N) - No

11.     Patwarkhana(Y/N) - No

12.     Villagehaat(Y/N) - Yes

13.     Playground(Y/N) - Yes

14.     School-

a.        Kindergarten(Y/N) Yes ICDS Anganwadi

b.Primary(Y/N) - Yes

c.         Secondary(Y/N) - No

d. College (Y/N) - No

e.University(Y/N) - No

15.     AnganwadiCentre(Y/N) Yes

a.        (govt/private) - Govt

b.Totalchildrenenrolled - 22+21+26= 67

15.     AmritSarovars–details,location,condition - No

16.     Governmentoffices-details,whetherfunctionalornot - Functional

17.     Rationshop(Y/N) - Rented

18.      Placesoftourismimportance–names,littledetailsonhistorical/culturalimportance - Ziarat Pathara Pir.

19.      Villageheritagesites/treks-names,littledetailson historical/culturalimportance

20.     VLWOffice (Y/N) - In Rented Building

21.     PrimaryHealthcareCentre(Y/N), - Yes

22.     ListofIncompleteBuildings-names,yearofconstructionPS Garang, PS Parat, PS Bandi Nar.

23.     ListofUnderutilizedBuildings-names

DAY1-ACTIVITIES

AGENDA2:

DIFFERENTINSTITUTIONS/INFRASTRUCTUREPROJECTSTOBEVISITED

| AMRITSAROVARS | Visit,verify | COMMENTS |
| --- | --- | --- |
| KhidmatCentres | Create/Generateawarenesson225schemes particularlyG2CschemsAapkiZaminAapkiNigrani, Beams,Janbhagidari,DigitalJ&K | Not Available |
| JKB/PSBcounters/outlets | a)Statusofcounter b)Numberofvisitors | Not Available |
| Incompletebuildings/pro- jects | Verify whetheridentificationandredistribution done | 1. PS Garang 2. P S. Parat 3. Pyt Ghar |
| PDS | Visit,evaluate,onlinestatus | Rented Building |
| PHC | Visit-evaluate,statusofstaff,equipmentand quality | Unsafe building+ Without Electricity and Water Supply, Doctor vacancy. |
| Youthclubs | Meet,interact,seeksuggestions | Yes Meeting Held |
| SHG | Meet,identifyproblems,seeksuggestions | Not Available |
| PMAY | Inspect,Inaugurate | Inspected & Inaugurated H/O Saida Bi |
| Myschool,mypride progress;schools-water, toilets,staff | Visit,checkforwater,electricity,sanitation,meet studentsandstaff | Repairing required. Toilet+ Drinking water needed |
| SwachhSBM | Evaluate | IHHL Constructed |
| Panchayatplayground, Sportskitsdistribution Villagegames | Ensure,verify.Participateinatleastonegamein theplayground | Sport Kit issued |
| HarGaonHariyali, Planta- tiondrive | Evaluatestatus,feedback | Plantation Drive Done |
| Villageculturalevent Dangal/Haat/Mela | Participatein;ensurethatitisheld | Location identified |
| Exhibitionofschemes | Ensurethateverydepartmentparticipatesand thatitcontinuesfortheentiredurationofB2V | All intracted with locals and aware rhem |
| JalJeewanMission verifica- tion- WSS/JSD Electricitysupply | Verify |  |

DAY1-ACTIVITIES

AGENDA3:SATURATEJANBHIYAN

DELIVERABLESANDRECORDDEFICIENCIESIFANY(INSERTDELIVERABLESLISTHEREASPERGADFORMAT

DAY1-ACTIVITIES

AGENDA4:

SELFEMPLOYMENTACTIVITIES

EnsureSelf-employmentactivities foryouth,distributeemploymentlettersforpeopleselectedunder varioussocialschemes(15ISTHETARGETPERPANCHAYAT) - J&K Bank and youth club is providing self employment.

Numberofcasesindifferentcategories- 26 by j& k bank.

sanctioned: Detailsofthebanksanctioningit

Shuttering, KCC Loans etc

Totalamountinvolved: 23.50 lacks

DAY1ACTIVITIES

AGENDA5

Intheevening,holdinformalmeetings  withseniorcitizens,govtemployees,retdemployees,youthclub andothercitizenswhoareenrolledoncollege/universityandhavediscussiononGandhiKatha,Nasha MuktAbhiyan,corruptionfreegovernance,doublingfarmersincomeandrecordtheproceedings

DAY2

a.       NoofIndividualCompostPits

constructed  - 02

b.NoofIndividualSoakPitsconstructed - 180

V.          No.ofBiodiversitymanagementcommitteemeetingsheld: 1

VI.         IsthenameofSarpanchdisplayedoncitizeninformationboardsofallRD&PRschemes:Yes/No - yes

VII.       AreSarpanchsbeinginvolvedinstart/inaugurationofactivities:Yes/No - Yes

VIII.      WhethersubjectshavebeenassignedbytheSarpanchtothePanchs:Yes/No - Yes

IX.        Whethergrievancesredressalboxisinstalled:Yes/No - No

X.         NoofgrievancesreceivedpertainingtoPanchayatlevel: 05.

XI.NoofgrievancesdisposedofatPanchayatlevel: 05

XII.       WhethertheSarpanch/PanchayatSecretaryhavedigitalsignatures:Yes/No - Yes

XIII.      WhetherallMGNREGA/14thFCpayments arebeingmadebySarpanchthrough DigitalSignature

Certificate(DSC):Yes/No- Yes

HUMAN RESOURCEAVAILABLEATTHEPANCHAYAT LEVEL:

| SRNO. | DEPARTMENTWISESTAFF | NUMBERS |  | NAMES |
| --- | --- | --- | --- | --- |
|  |  | SANCTIONED | ACTUAL |  |
|  | Ruraldevelopmentdepartment: BDO JE GRS TA | 01 01 01 01 | 01 01 01 01 |  |
|  | SCHOOLEDUCATION: TEACHER HEADMASTER ANYOTHER | 19 02 01 | 13 02 00 |  |
|  | JAL JEEVAN: | 01 04 01 | 0 0 01 |  |
|  | PDD: LINEMAN JE ANYOTHER | 01 01 01 | 01 01 01 |  |
|  | FOOD&CIVILSUPPLIES | 01 | 01 |  |
|  | AGRICULTURE&ANIMALHUS- BANDARY | 01 | 01 |  |
|  | SOCIALWELFARE | 02 | 02 |  |
|  | HEALTH: ASHA ANM AYUSHDOCTOR ALLOPATHICDOCTOR | 02 01 00 01 | 02 01 00 00 |  |
|  | ANYOTHERDEPARTMENT |  |  |  |

DAY2-ACTIVITIES

AGENDANO.1

DiscussionontheandassesstheprogressofdifferentschemesrelatingtothelocalizedSDGsprior-itizedforthatvillageaspertheresolutionpassedbythatGramPanchayaton21stApril22,onNational PanchayatiRajDay(Copyoftheresolutiontobetakenfromwww.jkpanchayat.inportalunderthelinkof GramSwarajMonth)

1.       SDGs AGREED FORTHATVILLAGE,TOBEIMPLEMENTED BYMARCH2024:

2.       STATUSOFWORKSUNDERTHEFOLLOWINGSCHEMES:

1      Cleanandgreenvillage

i.InitiativestakenbythePanchayatformanagingSolidandLiquidWaste- Yes

ii.     InitiativestakenbythePanchayatforusinggreensourcesoffuellikesolar,biogas - Yes

iii.  Hasmappingoflanduse,waterbodies,forest,slopes,wetlands,degradedforestwithintheGram

Panchayatbeendone?Yes/No.IfNo,reason,thereof No

iv.    HastheClimateResiliencePlanbeendevelopedfortheGP?Yes/No - No

v.     StepstakenbytheGramSabhaabouttheclimatechangemitigationfactorslikereducingenergy consumption,usageoffossilfuels,plastics,non-renewablebuildingmaterialsandalsotopromote measureslikeplantingoftrees,conservingforests,usageofgoodagriculturalpracticeslikedrip irrigation,waterconservationmeasuresandconservationofwetlands. - Yes , Plantation Drive

vi.  Whetherschoolshavestartedsegregatingwaste - No

vii. Whetherschoolshavetheirowncompost/soakagepitsforsolid/liquidwastemanagement - Some Have

2     Healthyvillage

i)    Aremeetings  relatedtoVillageHealthandSanitationCommitteebeingheldregularly? - Yes

ii)   DoalltheeligibleindividualsbeenprovidedtheGoldenCard? - Yes

iii)  ArealltheChildrenbeingimmunizedaspertheSchedulerecommendedbyGovt.ofIndia? -  Yes

iv)  ArealltheeligibleindividualsbeenvaccinatedagainstCOVID-19?Yes

v)   DoesGramPanchayatensurethatallpregnantwomenaregettingnecessaryprenatalcheckups? yes

vi)  WhetherallthedeliverieswereInstitutionalizedorconductedbytrainedMidwives? Institutionalised

3     Watersufficientvillage

i)    DoalltheIHHsintheGramPanchayathavewaterpipelineconnections? No

ii)   WhetherGramPanchayathastakenstepsforgreywatermanagement.IfYespleasespecify Soak Pits

iii)  DoalltheIHHsintheGramPanchayathavetoilets? yes

iv)  ArealltheIHHstoiletsfunctionalornot? Yes

v)   DoalltheSchools/Anganwadicentershavea toiletfacilityornot? No

vi)  Areallthetoiletsintheschools/Aaganwadifunctionalornot? NO

vii) WhetherGramPachachayatBhawanhasseparate toiletsforwomenornot?

No Pyt Ghar

4      ChildFriendlyvillage

i)	Doallthechildrenundertheageof0-6yearsbeenenrolledintheAnganwadicentersforpre- schooling?Yes/NO - Yes

ii)    HowmanyBalSabha’swereorganizedintheGramPanchayat----------02---------

iii)  WhethertheissuesraisedbyBalSabhaareaddressedduringtheGramSabha. Yes/NO - Yes

iv)	WhetherGramPanchayatistrackingthedatarelatedtodropoutchildrenandchildrenwithirregular attendance?Yes/NO. - Yes

v)   DoalltheschoolsundertheGramPanchayathaveseparate toiletsforgirlsandboys?Yes/No some have & some have not

5      Villagewithgoodgovernance

i)    IsCSClocatedintheGramPanchayatBhawanornot? - No pyt Ghar

ii)	IsthelistofbeneficiariesrelatedtotheSchemes/ProgramsdisplayedontheGrampanchayatwallor not? not

iii)  DoestheGramPanchayathasitsbuildingornot? - No

iv)  IstheGramPanchayatofficefunctionalornot? - Functional

v)   Aretheactivities approved undertheHalqaPanchayatDevelopmentPlandisplayedontheGram

Panchayatwallornot? - No

vi)  IsSocialAuditofearlierSchemes/Programscarriedoutornot? - Yes

6      Povertyfreeandenhancedlivelihoodvillage

i)    HasGramPanchayatdevelopedanycriteria fortheidentificationofthepoor?Yes/Noifyesspecify  - Yes

ii)   HavealltheeligiblehouseholdsregisteredinPDSornot? - Yes

iii)	HasGramPanchayatprovidedspaceforSelf-helpGroupsinPanchyatGharforholdingmeetings  or not? - No

iv)  HavealltheeligiblehouseholdsbeenregisteredforPensionornot? - Yes

v)   HasGramPanchayatfacilitatedYouthforSkillEnhancementCoursesandPlacement? - Yes

vi)  HasJobCardsbeendistributedtoalltheeligibleindividualsunderMGNREGA? - Yes

vii) HasGramPanchayatfacilitatedSHGsforBankAccountLinkages? - No SHG

7     Sociallysecuredvillage

i)    WhetherGramPanchayatismaintainingdatarelatedtoDifferentlyAbledPeople? - Yes

ii)   IsGramPanchayatOffice DisabledFriendlyornot? - Friendly

iii)	Areprovisionsfora separate BudgetundertheResourceEnvelopeforWomenandChildrenmadeor not? - No

iv)	DoalltheSchools intheGramPanchayathavefacilitiesforDifferentlyAbledChildrenliketoilets, barrier-freeaccess,etc.,ornot? - No

v)   Arealltheeligibleindividualsaregettingpensions,likeoldagepension,widowpension,etc?Yes

vi)  ArealltheeligiblehouseholdsgettingbenefitsfromIAYornot?

- Yes , Now known as PMAY.

8      EngenderedDevelopmentinVillage

i)    HowmanyMahilaSabha’swereorganizedintheGramPanchayat------------02-------

ii)	WhetherSHGsfederationshavebeenprovidedspaceformeetings  inthePanchayatBhawan(Yes/ No)- No

iii)  WhetherGPshavetakenstepsforincreasingwomen’sparticipationinGramSabha(Yes/No) Yes

iv)  NumberofwomenbeneficiariesheadedhouseholdscoveredunderPDS

system…………42……………

v)   Numberofbeneficiaries(outoftotaleligiblepopulation)receivingsocialprotectionbenefitsunder

PradhanMantriMatritvaVandanaYojana…………28……….

9    Self-sufficientinfrastructureinthevillage

i.	WhetherGPhasa CommunityHallwithaccesstoelectricity,furniture,watersupply, toilet…………No, …………….

ii.     WhethertheDisastermanagementplanisavailableattheGPLevel(Yes/No) - No

iii.  Whetherchild-friendlyparkwithrequiredfacilitiesisavailableinGP(Yes/No) - No

iv.    WhethertheGPhaseasyaccesstoGodownforstorage(Yes/No)- Yes but Private

v.     Whetherstreetlightsareprovidedinpublicplacesforensuringsafety(Yes/No) - No

DAY2ACTIVITIES

AGENDANO.2

SensitizevillageresidentsaboutmyScheme”portal(myscheme.in)whichincludesinformationaboutall theschemesbeingrunbyCentral/State/UT govtacrossthecountry

(SchemeMaterialavailablefromhttps://jkpanchayat.in/b2v4.php)

DAY2ACTIVITIES

AGENDANO.3

HoldmeetingoftheBiodiversityManagementCommitteestodeliberateonissues pertainingtoconserva- tionofbiodiversityandsustainableutilizationofbiologicalresources.HeshouldcheckPeopleBiodiversity register(PBR)ofthatpanchayatandreviewifBiodiversityManagementCommittee constitutedforthat panchayatis holdingminimum4meetings inayearandmeeting onceinevery3months (RoleofBMC availableathttps://jkpanchayat.in/b2v4.php)

COMMITTEEMEMBERS - Yes

PRESENT :-

BIODIVERSITYREGISTERPHOTOS : Maintained

PAST 4MEETINGDETAILS-DATES,MINUTESPHOTOS

' Discussion regarding role and responsibilities of BMV is done.

DAY2ACTIVITIES

AGENDA4

Visitingofficershallalsoplanandconductpanchayatlevelconvergencemeeting  ofalldepartmentsand prepareVillagedevelopmentplanforvillage,inconsultancywithGrampanchayat,discussitingram sabhaandgetitapproved. Plan is already made and no chances required.

(GPDPformatavailableonhttps://jkpanchayat.in/b2v4.php)

InadditionGPDPplanshallalsoinclude:

           Touristplaceswhichneedtobedeveloped

           Specificproductwhichneedstobedeveloped

           Tourism-homestays

	20candidatesfortrainingunderHimayatschemealongwithtradeinwhich trainingistobegiven - List of 15 candidates as submitted but sanction is pending.

DAY2ACTIVITIES

AGENDA5

Ensuresaturationoffollowingschemesandgivestatus:

| NAMEOFTHESCHEME | TOTALELIGIBLE BENEFICIARIESIN THE VILLAGE | TOTALBENEFICIARIESWHO AVAILEDTHEBENEFITSOFTHESCHEME | REASONSFOR PENDENCY |
| --- | --- | --- | --- |
| GoldenHealthCardunder AyushmanBharat | 2082 | 1630 | Child< 7 years not included. Some are in saudi thumb problem |
| Jananisurakshayojana | 25 | 20 | New Delivery Account not opened |
| OLDAGEpension | 150 | 140 | Documents incomplete |
| Widowpension | 33 | 39 | Under process |
| Disabilitypension | 55 | 50 | Adhaar not generated |
| Domicilecertificate | 2160 | 1920 | Under process |
| Kisancreditcard | 332 | 185 | Old age laborer under process |
| PMkisansammannidhi | 277 | 190 | Under process Incomplete document |

| Landpassbook | 750 | 220 | Under process |
| --- | --- | --- | --- |
| Registrationofvillageven- dorsonGEMportal |  |  |  |
| Registrationofvillagecon- tractorsonjktendersportal |  |  |  |
| Registrationofvillagecon- tractorsonPWDportal |  |  |  |
| Incompletebuildings/pro- jects |  |  |  |

DAY2ACTIVITIES

AGENDA6

NASHAMUKTABHIYAN

1.       Whethergramsabharesolutionpassed - Yes

2.       Detailsofactivities conducted - Awareness compaign and sports activities done

3.       Whetherallactivities andGSresolutionuploadedonjkpanchayats.inportal- Yes

4.       Howmanydrugaddictsinthevillage - No

5.       WhetherreportedtotheDeputyCommissioner - NA

6.       Howmanyregisteredforrehabilitationundergovernmentprogramme

- NA

DAY2ACTIVITIES

AGENDA7

SOCIALAUDIT

Conductsocialauditofatleast5workseachunderfollowingschemes:

| NAMEOFTHE SCHEME | DETAILSOFTHE WORKS | YEAROFWORK APPROVAL | AMOUNT APPROVED FORTHEWORK | WHETHER WORKEXECUTED SATISFACTORILY | GEO- TAGGED PHOTOS | ANY GRIEVANCE RECORDED RELATINGTOTHAT WORK |
| --- | --- | --- | --- | --- | --- | --- |
| MGNREGA | P/wall Moh Hill | 2021-22 | 2.00 lakh | Yes | Yes | Ni |
| PMAY | Saidi Bi w/o Mohd Rashid | 2919-20 | 1.30 lakhs | Yes | Yes | No |
| IHHL UNDERSBM-G | Ab. Khaliq s/o Akbar Hussain | 2020-21 | 12000 | Yes | Yes | Mo |
| CSCUNDER SBMG | NA |  |  |  |  |  |
| AMRIT SAROVARS | NA |  |  |  |  |  |

DAY2ACTIVITIES

AGENDA8

MAHILASABHA

Totalwomeninthevillageabovetheageof18 - 1052

Totalattended - 12

Proceedings: Awareness regarding sanitation, vaccination, nutrition and other govt schemes discussed.

(Plinsertpointerstobediscussedthere–referpalliproceedings)

DAY2ACTIVITIES

AGENDA9

BALSABHA

Holda balsabhaandrecordproceedings

Totalchildreninthevillageabovetheageof - 14 - 223 in nos.

….. Totalattended - 120

Proceedings: Awareness regarding sanitation, vaccination, nutrition and other govt schemes discussed.

(Plinsertpointerstobediscussedthere–referpalliproceedings)

DAY2ACTIVITIES

AGENDA10

INAUGURATIONS

| SR NO. | ASSETS/ACTIVITIES INAUGRATED | STATUSOFTHEASSET/AC- TIVITIES(NUMBER,OTHER DETAILS) | GEO-TAGGED PHOTOS |
| --- | --- | --- | --- |
|  | VILLAGEHAATunderJKSRLM (SUN- DAYMARKET) | Location has been identified |  |
|  | PMAYhousesifanyreadyforinaugra- tion | Inauguration of h/o Saida Bi w/o Mohd Rashid Done | Online Process |
|  | Swachhgramprojects-segregation shedsetc | Soak Pit. Compost Puts are under construction. | Online Process |
|  | Amritsarovars | NA |  |
|  | Sportskits | 01 |  |
|  | Villageculturalevents | Singing Competition at school level is done |  |
|  | JJMassets/projects | WSS Dangar Danna Jandi Dhara Project sanctioned |  |
|  | Anyothertobeidentifiedatdistrict level |  |  |

FOLLOWUPOF(B2V1,B2V2&B2V3):

(Prefilledexcelsheet tobetakenfromdistrictlevel/andalsotobedownloaded

fromwww.jkpanchayat.in)

| S.NO. | Particulars | Actiontaken | Remarks# |
| --- | --- | --- | --- |
| I. UrgentPublicRequirements/Demands-B2V1 |  |  |  |
| 1. Patra Bridge to be upgraded | No Action Taken | Urgently required |  |
| 2. Bridge near NTPHC to be upgraded | No Action Taken | Urgently required |  |
| 3. Required Electricity and Water Supply. | Some improvement has done | More effort needed |  |
| 4. Infrastructure of school upgradation. | NoActionTaken | Administration shou6pay attention |  |
| 5. Increase in road connectivity. | Yes, but more to go | More effort needed |  |
| 6. Need of more electric poles. | Yes, but more to go | Good |  |
| 7. Need of more PHE piles | Yes,butmoretogo | Good |  |
| II. UrgentPublicRequirements/Demands-B2V2 |  |  |  |
| 1. Poor road connectivity. | More effect required. | Urgent need |  |
| 2. Requirements of Electrc Poles | Some improvement needed | Good |  |
| 3. Inadequate water supply & Pipes | Some improvement needed | Good |  |
| 4. Lacm of educational infrastructure | No action taken | Repairing required |  |
| 5. Poor condition of NTPHC. | No action taken | Attention required |  |
| 6. Upgradation of all schools. | No action taken | Urgent need |  |
| 7 |  |  |  |
| S.NO. | Particulars | Actiontaken | Remarks# |
| III. MajorProblems–B2V1 |  |  |  |
| 1.Upgradation of through out pyt | Yes but more to go | Urgent need |  |
| 2. Electricity and water supply problems | '' |  |  |
| 3. Infrastructure of school to be upgraded | No action taken | Urgently required |  |

| 4. Poor condition of NTPHC | No action taken |  |  |
| --- | --- | --- | --- |
| 5 |  |  |  |
| IV. MajorProblems-B2V2 |  |  |  |
| 1. Some school building need repairing. | No action taken | Need attention |  |
| 2. Road to be upgraded. | More improvement required | Urgent need |  |
| 3. Need of more electric poles. | Some improvement needed | Do |  |
| 4. Need of PHE pipes | Yes but more to go | Do |  |
| 5 |  |  |  |
| V. MajorProblems-B2V3 |  |  |  |
| 1. Need of More Electric Poles. | Yes , but more to go. | Good |  |
| 2. Need of PHE Pipes | Yes , but more to go | Good |  |
| 3. Upgradation of School | No action taken | Needs attention |  |
| 4. Poor condition of NTPHC | No action taken | Urgent |  |
| 5. Poor road conditions | Yes but more to go | Urgent |  |
| VI. MajorComplaints-B2V1 |  |  |  |
| 1. Road connectivity should increase | Yes but more to go | Good |  |
| 2. Upgradation of school | No action taken | Urgent need |  |
| 3. Inadequate electric poles + poles pipes | No action taken | Urgent need |  |
| VII. MajorComplaints-B2V2 |  |  |  |
| 1. 1. Road connectivity should increase 2. Upgradation of school 3. Inadequate electric poles + poles pipes | Yesbutmoretogo No action taken Noactiontaken |  |  |
| VIII. MajorComplaints-B2V3 |  |  |  |
| 1. Regular supply of electricity | Yes, But more to go | Need attention |  |
| 2. Shortage of PHE staff | No action taken | Urgent need |  |
| 3. Poor Road Conditions | Yes but more to go | Urgent need |  |

TV

OVERALLPERCEPTIONOFFUCNTIONING OF GOVERNMENTDEPARTMENTS

1.         BESTDEPARTMENT:

2.       LEASTRESPONSIVEDEPARTMENT:

GENERALASSESSMENTOFTHEVISTINGOFFICER

| I | AnymajorcomplaintbroughttothenoticeoftheVisitingOfficer: |
| --- | --- |
| II | Major/urgentpublicdemandsthatwas/werereflectedearlierbuthavenotbeenaddressedsofar: |
| III | Overallassessmentofthevisitandsuggestions: (Thevisitingofficertoensurethattheoverallassessmentisrecordedindetailsalongwithconcretesugges- tions) |
| IV | OverallRatingofgovtfunctioningas givenbythePanchayat(Scaleof0to10) |
| V | CertificatefromSarpanchthatthevisitingofficerhasstayedinthepanchayatfor2days |

Signature of Sarpanch                                                                              Signatureof theVisitingOfficer

Name…Abdul Rashid……………………                                                   Name Sabir hussain shah……