4





**15TH OCTto3RD NOV,2022**

**KEY FEATURES**

• Deputy Commissioners to lead the initiative

• Rural development Department to be the nodal department

• Planning Development & Monitoring department and IT to be the support departments

**ACTIONSANDTIMELINES**

|  |  |  |  |
| --- | --- | --- | --- |
| **ACTION** | **RESPONSIBILITY** | **LATESTBY** | **REMARKS** |
| **Janabhiyan** | All departments | Oct15-26th | Going on |
| **Deputation of Sectt staff/ HoDs** | GAD | Oct14 | Done |
| **Deployment of Staff to Panchayats and serving of orders on deployed officers** | DCs | Oct25 | DCswildeployseniorlevelstaff fromthedistricts.Strictactionto betakenagainstabstentions.No exemptionstobegiven |
| **Training of district trainors on B2V4** | RDD | Oct26 |  |
| **Training of visiting officers** | DCs | Oct27 |  |
| **Field Visits to be completed by** | Visiting Officers | Nov3 | DCs to supervise and ensure that each Panchayat is visited within the period specified |
| **DataofB2V4tobe uploaded by** | Visiting Officers | Nov10 | DCs to supervise and ensure that data of all Panchayats is upload- ed by the visiting officer within the period specified |

**INSTRUCTIONS FORTHEVISITINGOFFICER(DAYWISE)**

|  |  |  |
| --- | --- | --- |
| **DATE** | **INSTRUCTIONS** | **ACTIONPOINTS** |
| **Day0** | Meeting with deputy commissioner and his/her team | a. Take printout so filled booklets ofB2V1,B2V2andB2V3from [www.jkpanchayat.in](http://www.jkpanchayat.in)  b .Also take printouts of the summarizedexcelsheetsofthe previousphasesfrom[www.jkpanchayat.in](http://www.jkpanchayat.in)  c. CollectATRsonissuesraisedduringprevious3phasesfromthe office of Deputy Commissioner(Planning deptt)  d.Takeprintsofblank 2bookletsofB2V4from[www.jkpanchayat.in](http://www.jkpanchayat.in)e.Takeplansfor2previousyearsandATRsfromtheplanningdeptt f. CompletetrainingsondifferentcomponentsofB2V4being  organizedbyrespectiveDeputyCommissioners  g.CollectListofnewworksstarted/ongoing/completedduringthe previousandcurrentFinancialyearunderthefollowingheads:  • PRIgrants  • DistrictPlan  • UTplan  • MGNREGA  • Otherschemesofotherdepartments  • Anyotherwork  h. Plans/beneficiarylists:  • MGNREGAdraftplandocumentfortheyear2022-23.  • ListofAwaas+beneficiariesalongwithIHHL Convergence  • Listofpensionbeneficiaries.  • ListofSHGs  • Listofagricultureschemebeneficiaries  i. Listsofbeneficiariesfor:  • Variouscertificates/benefitstobedistributedbythe visitingofficer.  • Anyotheractivitiesidentifiedbydifferentdepartments |

|  |  |  |  |
| --- | --- | --- | --- |
| **Day1** | Reachthevillage | 1. | Ensurethatallfrontlineworkersofdifferentdepttsarepresent. |
|  |  | 2. | Ensureexhibitionbydifferentdepts.aboutindividualbeneficiary schemes |
|  |  | 3. | InspectJKB/PSBcounters/outlets |
|  |  | 4. | Participate/ensureorganizationofsportsactivityinplayfield,talent hunt/culturalevent/youthactivity |
|  |  | 5. | GandhiKatha(suggesteddetailsuploadedonjkpanchayat.in) |
|  |  | 6. | Visitatleast2amritsarovarsandgetitsgeotaggedphotos |
|  |  | 7. | InspectKhidmat(CSC)CentresandcreateGenerateawarenesson  225schemesparticularlyG2CschemeslikeBEAMS,Janbhagidari, AapkiZaminAapkiNigrani,DigitalJ&K |
|  |  | 8. | Visitingofficershallalsoplanandconductpanchayatlevelconver- gencemeetingofalldepartments |
|  |  | 9. | CheckeffectivenessofCentrallysponsoredschemes |
|  |  | 10. | VisitandinspectallgovernmentestablishmentsincludingPHE, AWC,FPS,schools,etc |
|  |  | 11. | Attemptsaturationofdeliverableso JanAbhiyanandwherever deficienciesfound,leadadrivetoachievealldeliverables |
|  |  | 12. | Assesseffectivenessofsanitationcampaigninthepanchayat |
|  |  | 13. | Ensureselfemploymentactivitiesfor15youthperpanchayat |
|  |  | 14. | Identify20potentialcandidatesperpanchayatforHIMAYATtraining alongwiththetradeonwhichtheywanttraining |
|  |  | 15. | Whereverpossible,distributeemploymentlettersforpeopleselect- edundervariousgovernmentemployments |
|  |  | 16. | Intheevening,holdnormalmeetingwith seniorcitizens,govtem- ployeesincludingretiredemployees,exservicemen,youthclub,and any citizens ofthevillagewhoareenrolledincollege/university |
|  |  | 17. | OpendiscussiononNashaMuktAbhiyan |

Day2 Haveameetingwithall stakeholders-depttofficials andpanchayatmembers

1. Discussionontheandassesstheprogressofdifferentschemesrelating tothelocalizedSDGsprioritizedforthatvillageaspertheresolution passedby thatGramPanchayaton21st April22,onNationalPanchayti RajDay.

2. Sensitizevillage residentsaboutmyScheme”portal(myscheme.in) whichincludesinformationaboutalltheschemesbeingrunbyCen- tral/State/UTgovtacrossthecountry

3. Hold meeting of theBiodiversityManagementCommitteestodeliber- ateonissuespertaining toconservation of biodiversityandsustaina- bleutilizationof biologicalresources.

4. PrepareVillagedevelopmentplan,inconsultancywithGrampanchayat, discussitingramsabhaandgetitapproved.

5. Ensure saturationofsoilhealthcardandgoldenhealthcardunderGold- enHealthCardunderAyushmanBharat,

6. Ensuresaturation of OldAge PensionScheme

7. EnsureDomicileSaturation.

8. EnsureKCCSaturation

9. Ensure saturationoflandpassbooks

10. Ensureregistrationofvillagevendorsneededforanyscheme,onGEM

portal

11. Ensurepanchayatcontractors registration

12. EncouragePanchayatmembers forimportanceofplantationdrivein

PanchayatunderHarGaonHariyali

13. Ensure paintingondigitalJ&Kinpanchayatghars

14. Ensure paintingonpanchayatactivitesandCSSinpanchayatghars

15. Thevisiting officeshallchecknoof kindergarten andplayfields present inthepanchayat for kidsandstudents,iftheinfrastructure present inthesearegoodenough.

16. Holdmeeting withpanchayatmembers todiscussaboutcorruption menaceandstepsrequiredtomakeJ&Kcorruptionfree

17. Obtaina candidassessmentaboutperformanceofvariousdeptts in- cludingfairfeedbackaboutdiscrepanciesinfunctioning

18. Check thestatusof NashaMuktAbhiyanandreporting of drugad- dictstoDeputyCommissioner.

19. IdentifyTouristDestinations,Circuits,ThemeTreks,IdentifyHomestays, providesupportfortourismactivities throughVillageCooperative

20. OrganizeTalentHuntatPanchayatLevel

21. Conductsocialauditofatleast5worksunderfollowingschemes:

a. MGNREGA

b.PMAY

c. IHHLtoiletsandpayments d.CSCs

e.AMRITSAROVARS

22. Holda mahilasabha anda balsabhaandrecordproceedingsinthefor- matgiven

23. InauguratevillagehaatunderJKSRLM

24. Checkifyouthclubsareformedinthepanchayatandwhatactivities theyareengagedin

25. Organizea villagelevelculturaleventtoengagepanchayatmembers

26. SensitizeGPaboutE-kitabkoshaninitiativeofJ&KGovtforempowering youthsthrough onlinedigitalliteracy

**GENERALINSTRUCTIONS**

1. Thevisitingofficershallrefrainhimself/herselfgivingorofferinganycommitmentonbehalfofthe governmentandshalladoptanunbiasedattitudeinreportingissues.As faraspossible,his/her observation shouldbebasedona fairandanalytical viewemergingfromhis/herinteractioninthe village.

2. Heisgoingtothevillageasplanningofficer,notforsanctioninganyworksorformakinganycom- mitments.

3. Whilepreparingvillagedevelopmentplan,hehastoensurethat,demandsareprioritizedandre- flectedunderavailableschemes,wherevernecessarythelargerworksaretobereferredtoadminis- trativedepttunderCSS/UTplansunderintimationtoDCsandrestoftheworkstoDCsforreflecting itunderdistrict/CSS plans

4. His workshallbehardcoreplanningandauditandisnota PRexercise.

5. EveryDeputyCommissionerhastoensurethatatleastoneRDDofficial(ideallyPanchayatSecre- tary)ispresent ineverypanchayatwithrelevantpanchayatrecords,toensureconductofallactivi- tiesasplanned.Panchayatwiseorderneedstobeissuedinadvance.

6. Visitingofficershouldideallycarryhis/herlaptoptocompletethereportsatthepanchayatlevel itselfanduploadthefinalreport,duly signedbothbythesarpanchandbythevisitingofficeron [www.jkpanchayat.in](http://www.jkpanchayat.in)portal,beforetheyleavepanchayat.

7. Focus ofvisitareyouth,skills,self-employment,nashamukt,bhrashtracharmukt,Rozgaryukt J&K, besidestocarryforwardtheactivities duringJanAbhiyanandsaturatethem.

8. Inadditionattentionmaybegiventothefollowingareas a. MakefulluseofCentrallySponsoredSchemes

b.Saturationofindividualbeneficiaryschemes c. Self-employmentschemes

d.Banklinkedschemes-includingdepartmentalsubsidyschemes e.Empowermentandtransparencythrough digitalinitiatives

f. Effectivenessofgrassrootsmachinery–

i. Patwari,VLWpresent andavailable

ii. AvailablefundsutilizedinpublicinterestandasperGramSabharesolutions iii. Fairness ingovernance

iv. CSS/Individual beneficiaryschemesetc v. BrashtacharMuktJ&K

vi. BhaiMuktJ&K

vii. NashaMuktJ&K

9. ThePRImembers (Sarpanchs,Panchs,BDCChairperson)shallbeattheforefrontofallactivities and givendueimportanceandtheapproach shouldbetostrengthenthemandmakethemfeelem- powered.He/sheshallensurethattheBDCchairpersonandSarpanch/Panch arepresent atthetime ofinaugurationandceremonies.

10. Visitingofficershallnotleavethedistrictwithoutuploadingthereport,duly signedonthe**www. jkpanchayat.in**portal.EveryDeputyCommissionerhastoensurethat.

**A) DetailsofReportingOfficer:**

**Imtaiz Ahmed Shah**

Name:

Designation: **Principal**

Department/placeof posting: **Education HSS (Salwah)**

MobileNo: **7780952250**

EmailID: **ShahImtaz569@gmail.com**

HomeDistrict: **Poonch**

Datesof visit: **28-10-2022 to 29-10-22**

**B) LocationaldetailsofPanchayat:(tobepre-filled,informationtobetakenfromtheprevious phasesbooklets/summarizedexcelsheetuploadedonjkpanchayat.in/b2v4.php)(tobevali- datedbythevisitingofficerandmissingdetailstobefilled)**

NameofthePanchayat: **Chandak B**

LocalGovernmentDirectory(LGD)codeof thePanchayat: **289174**

Nameof CDBlock: **Nangali Sahib Sain Baba**

NameofTehsil: **Haveli**

Nameof District: **Poonch**

**C) PanchayatProfile:**

No.ofrevenuevillagesinthePanchayat:df **Chandak B**

No.ofhamletsinthePanchayat:  **7**

No.ofhouseholdsinthePanchayat: **520**

**2200**

Population(approx)of thePanchayat:

**Part-II:**

(TobefilledupbytheVisitingOfficerduringhis/hertwodayvisittothePanchayat.AllFieldshavetobe

filledbytheVisitingOfficerbeforethebookletishandedovertotheDC

**FrontlineOfficers/OfficialswhowereassignedtothePanchayatfortheprogramme:**

|  |  |  |
| --- | --- | --- |
| Department | Name | Designation |
| **Health** | **Ch. Mohd Ayoub** | **Sub Pharmacist (9622279700)** |
| **Sports** | **Aurangzeb Khan** | **PET Teacher (9596626628)** |
| **Animal Husbandry** | **Harjinder Singh** | **Animal Husbandry V.P. (9797693050)** |
| **Education** | **Zabir Hussain** | **Teacher (9596686704)** |
| **Revenue** | **Aamir Khan** | **Patwari (9797301033)** |
| **Agriculture** | **Resmeet Singh** | **Bee Keeper (9906347620)** |
| **Health** | **Balvinder Singh** | **Zonal Technician(9596831581)** |
| **Social Forestry** | **Abdul Kabir** | **7051151854** |
| **PWD** | **Ghulam Rasool** | **JE (9596747158)** |
| **PDD** | **Mehmood Raiz** | **JE(9797500921)** |
| **J&K Bank Chandak** | **Gurdeep Singh** | **J&k bank(9682150891)** |
| **PHE** | **Mohd Bashir** | **Supervisor** |
|  |  |  |

**Detailsofabsentemployeesvis-à-vislistfurnishedbytheDCoffice:**

|  |  |  |
| --- | --- | --- |
| Department | Name | Designation |
| **Distt. Employment Department Poonch** |  | **Distt. Employment Officer Poonch** |
| **PDD Department** |  |  |
| **Irrigation and Flood Control** |  |  |
| **PWD Department** |  |  |
| **Sheep Husbandry Department** |  |  |
| **DIC Poonch** |  |  |
|  |  |  |
|  |  |  |
|  |  |  |
|  |  |  |
|  |  |  |
|  |  |  |
|  |  |  |
|  |  |  |
|  |  |  |

**DAY1-ACTIVITIES**

**AGENDA1:PANCHAYATASSETREGISTER**

**Infrastructure:**

1. Panchayat Ghar Infrastructure a. **Govtbuilding-YES**

b. needing repairs -**YES**

2. Furniture - **YES**

3. Computer/printer -**YES**

4. Internet -**NIL**

5. Telephone -**NO**

6. Toilet(CSC/partofpanchayatghar) -**NIL**

7. Water - **NIL**

8. Electricity - **NIL**

9. Bankbranch -**YES**

10. CSC **- NO**

11. Patwarkhana -**NO**

12. Villagehaat -**YES**

13. Playground -- **NO**

14. School-

a. Kindergarten -**NO**

b.Primary -**YES**

c. Secondary -**YES**

d. College -**NO**

e.University -**NO**

15. AnganwadiCentre -**YES**

a. (govt/private) -**PRIVAT**E

b.Total children enrolled -**237**

15. Amrit Sarovars–details, location, condition - **NO**

16. Government offices-details ,whether functional or not

17. Ration shop -**YES**

18. Places of tourism importance–names, little details on historical/cultural importance -

19. Village heritage sites/treks-names, little details on historical/cultural importance**- Tomi Peer Baba Nerhad Chandak**

20. VLW Office -**YES**

21. Primary Healthcare Centre -**YES**

22. List of Incomplete Buildings-names, year of construction **- Building of M/S Nerhad**

23. List of Underutilized Buildings-names

**-Nil**

**DAY1-ACTIVITIES**

**AGENDA2:**

**DIFFERENTINSTITUTIONS/INFRASTRUCTUREPROJECTSTOBEVISITED**

|  |  |  |
| --- | --- | --- |
| **AMRITSAROVARS** | **Visit,verify** | **COMMENTS** |
| Khidmat Centres | Create/Generateawarenesson225schemes particularlyG2CschemsAapkiZaminAapkiNigrani, Beams,Janbhagidari,DigitalJ&K | **Nil** |
| JKB/PSBcounters/outlets | a)Status of counter - Active  b)Number of visitors 48 | **Satisfactory** |
| Incomplete buildings/pro- jects | Verify whether identification and redistribution done | **Patwar khana**  **Nabiat Chandak** |
| PDS | Visit, evaluate, online status |  |
| PHC | Visit-evaluate, status of staff, equipment and quality | **PHC Chandak is very impressive and full equipped.** |
| Youthclubs | Meet,interact,seeksuggestions | **One youth club is functioning** |
| SHG | Meet,identifyproblems,seeksuggestions | **Nil** |
| PMAY | Inspect,Inaugurate | **1 PMAYG is inspected and inagurated** |
| Myschool,mypride progress;schools-water, toilets,staff | Visit,checkforwater,electricity,sanitation,meet studentsandstaff | **Visited in GH School Chandak and HSS Chandak. Water, electricity, Toilet is available.** |
| SwachhSBM | Evaluate | **Swacch Bharat Mission in two school is going on.** |
| Panchayatplayground, Sportskitsdistribution Villagegames | Ensure,verify.Participateinatleastonegamein theplayground | **Sports Kits is already distributed, Volley Ball game in the ground of HSS Chandak.** |
| HarGaonHariyali, Planta- tiondrive | Evaluatestatus,feedback | **Yes Good** |
| Villageculturalevent  Dangal/Haat/Mela | Participatein;ensurethatitisheld | **No** |
| Exhibitionofschemes | Ensurethateverydepartmentparticipatesand thatitcontinuesfortheentiredurationofB2V | **Yes** |
| JalJeewanMission verifica- tion- WSS/JSD  Electricitysupply | Verify | **Good Construction** |

Visited

**DAY1-ACTIVITIES**

**AGENDA3:SATURATEJANBHIYAN**

**DELIVERABLESANDRECORDDEFICIENCIESIFANY(INSERTDELIVERABLESLISTHEREASPERGADFORMAT**

**Delivered Successfully.**

.

**DAY1-ACTIVITIES**

**AGENDA4:**

**SELFEMPLOYMENTACTIVITIES**

EnsureSelf-employmentactivities foryouth,distributeemploymentlettersforpeopleselectedunder varioussocialschemes(15ISTHETARGETPERPANCHAYAT)

**Numberofcasesindifferentcategoriessanctioned: Detailsofthebanksanctioningit:**

**Totalamountinvolved:**

**DAY1ACTIVITIES**

**AGENDA5**

Intheevening,holdinformalmeetings withseniorcitizens,govtemployees,retdemployees,youthclub andothercitizenswhoareenrolledoncollege/universityandhavediscussiononGandhiKatha,Nasha MuktAbhiyan,corruptionfreegovernance,doublingfarmersincomeandrecordtheproceedings – **Held a meeting with senior citizens, youth for Nasha Mukt Abhayan and discuss the burning situation of the area of the panchayat.**

**DAY2**

a. No of Individual Compost Pits constructed- **20.**

b. No of Individual SoakPits constructed-**215.**

V. No. of Biodiversity management committee meetings held: **Yes, 2**.

VI. IsthenameofSarpanchdisplayedoncitizeninformationboardsofallRD&PRschemes:**Yes**

VII. Are Sarpanchs being involved in start/inauguration of activities: **Yes**

VIII. Whether subjects have been assigned by the Sarpanch to the Panchs:**Yes**

IX. Whether grievances redressal box is installed: **Yes**

X. No of grievances received pertaining to Panchayat level: **Nil**

XI. No of grievances disposed of at Panchayat level: **Nil**

XII. Whether the Sarpanch/Panchayat Secretary have digital signatures: **Yes**

XIII. Whether all MGNREGA/14thFCpayments are being made by Sarpanch through Digital Signature

Certificate(DSC):**Yes**

**HUMAN RESOURCEAVAILABLEATTHEPANCHAYAT LEVEL:**

|  |  |  |  |  |
| --- | --- | --- | --- | --- |
| **SRNO.** | **DEPARTMENTWISESTAFF** | **NUMBERS** | | **NAMES** |
|  |  | SANCTIONED | ACTUAL |  |
|  | Ruraldevelopmentdepartment: BDO  JE GRS TA | **1**  **1**  **1**  **1** | **1**  **1**  **1**  **1** | **Ajaz Ahmed Bhatt**  **Bashar Anjum**  **Lal Hussain**  **Rahimullah khan** |
|  | SCHOOLEDUCATION: TEACHER  HEADMASTER ANYOTHER | **53**  **01** | **35**  **01** | **Rita Kumari** |
|  | JAL JEEVAN: | 01 | **01** | **Mohd Bashir Supervisor** |
|  | PDD: LINEMAN JE  ANYOTHER | 01  01 | **01**  **01** | **Ghulam Rasool** |
|  | FOOD&CIVILSUPPLIES | **Nil** | **Nil** |  |
|  | AGRICULTURE&ANIMALHUS- BANDARY | **Animal Husbandry-01**  **Agriculture- 01** | **01**  **01** | **Harjinder Singh (VP)**  **Rasmet Singh (Bee Keeper)** |
|  | SOCIALWELFARE | **03** | **03** | **Shamim Akhter**  **Sharda Parveen**  **Farzan koser** |
|  | HEALTH: ASHA ANM  AYUSHDOCTOR ALLOPATHICDOCTOR | **03**  **02**  **01**  **04** | **03**  **02**  **01**  **nil** |  |
|  | ANYOTHERDEPARTMENT |  |  |  |

**DAY2-ACTIVITIES**

**AGENDANO.1**

DiscussionontheandassesstheprogressofdifferentschemesrelatingtothelocalizedSDGsprior-itizedforthatvillageaspertheresolutionpassedbythatGramPanchayaton21stApril22,onNational PanchayatiRajDay(Copyoftheresolutiontobetakenfrom[www.jkpanchayat.in](http://www.jkpanchayat.in)portalunderthelinkof GramSwarajMonth)

1. SDGs AGREED FORTHATVILLAGE,TOBEIMPLEMENTED BYMARCH2024:

2. STATUSOFWORKSUNDERTHEFOLLOWINGSCHEMES:

**1 Cleanandgreenvillage**

i.InitiativestakenbythePanchayatformanagingSolidandLiquidWaste **Constructed Compost Pit**

ii. InitiativestakenbythePanchayatforusinggreensourcesoffuellikesolar,biogas

**NIL**

iii. Has mapping of landuse, waterbodies forest, slopes, wetlands, degraded forest within the Gram

Panchayat been done? Yes/No. IfNo,reason, thereof **YES**

iv. HastheClimateResiliencePlanbeendevelopedfortheGP**? NO**

v. StepstakenbytheGramSabhaabouttheclimatechangemitigationfactorslikereducingenergy consumption,usageoffossilfuels,plastics,non-renewablebuildingmaterialsandalsotopromote measureslikeplantingoftrees,conservingforests,usageofgoodagriculturalpracticeslikedrip irrigation,waterconservationmeasuresandconservationofwetlands**. NO**

vi. Whetherschoolshavestartedsegregatingwaste NO

vii. Whetherschoolshavetheirowncompost/soakagepitsforsolid/liquidwastemanagement NO

**2 Healthyvillage**

i) Aremeetings relatedtoVillageHealthandSanitationCommitteebeingheldregularly? **YES**

ii) DoalltheeligibleindividualsbeenprovidedtheGoldenCard? **NO**

iii) ArealltheChildrenbeingimmunizedaspertheSchedulerecommendedbyGovt.ofIndia? **YES**

iv) ArealltheeligibleindividualsbeenvaccinatedagainstCOVID-19? **YES**

v) DoesGramPanchayatensurethatallpregnantwomenaregettingnecessaryprenatalcheckups? **YES**

vi) WhetherallthedeliverieswereInstitutionalizedorconductedbytrainedMidwives**? YES**

**3 Watersufficientvillage**

i) DoalltheIHHsintheGramPanchayathavewaterpipelineconnections? **YES**

ii) WhetherGramPanchayathastakenstepsforgreywatermanagement.IfYespleasespecify iii) **NO**

DoalltheIHHsintheGramPanchayathavetoilets? **65%**

iv) ArealltheIHHstoiletsfunctionalornot? **YES**

v) DoalltheSchools/Anganwadicentershavea toiletfacilityornot? **NO**

vi) Areallthetoiletsintheschools/Aaganwadifunctionalornot? **FUNCTIONAL IN SCHOOLS ONLY**

vii) WhetherGramPachachayatBhawanhasseparate toiletsforwomenornot?

**NO**

**4 ChildFriendlyvillage**

i) Doallthechildrenundertheageof0-6yearsbeenenrolledintheAnganwadicentersforpre- schooling? **Yes**

ii) HowmanyBalSabha’swereorganizedintheGramPanchayat -- NO

iii) WhethertheissuesraisedbyBalSabhaareaddressedduringtheGramSabha**. ---- NO**

iv) WhetherGramPanchayatistrackingthedatarelatedtodropoutchildrenandchildrenwithirregular attendance**? ---- NO**

v) DoalltheschoolsundertheGramPanchayathaveseparate toiletsforgirlsandboys? ------**YES**

**5 Villagewithgoodgovernance**

i) IsCSClocatedintheGramPanchayatBhawanornot? ---- **NO**

ii) IsthelistofbeneficiariesrelatedtotheSchemes/ProgramsdisplayedontheGrampanchayatwallor not? --**NO**

iii) DoestheGramPanchayathasitsbuildingornot? -- **YES**

iv) IstheGramPanchayatofficefunctionalornot?---**YES**

v) Aretheactivities approved undertheHalqaPanchayatDevelopmentPlandisplayedontheGram

Panchayatwallornot?---**YES**

vi) IsSocialAuditofearlierSchemes/Programscarriedoutornot?---**YES**

**6 Povertyfreeandenhancedlivelihoodvillage**

i) HasGramPanchayatdevelopedanycriteria fortheidentificationofthepoor? ---**NO**

ii) HavealltheeligiblehouseholdsregisteredinPDSornot? ---**YES**

iii) HasGramPanchayatprovidedspaceforSelf-helpGroupsinPanchyatGharforholdingmeetings or not?-**NO, SHG in Panchayat.**

iv) HavealltheeligiblehouseholdsbeenregisteredforPensionornot? **---YES**

v) HasGramPanchayatfacilitatedYouthforSkillEnhancementCoursesandPlacement?--**NO**

vi) HasJobCardsbeendistributedtoalltheeligibleindividualsunderMGNREGA?---**YES**

vii) HasGramPanchayatfacilitatedSHGsforBankAccountLinkages?----**NO**

**7 Sociallysecuredvillage**

i) WhetherGramPanchayatismaintainingdatarelatedtoDifferentlyAbledPeople? --**YES**

ii) IsGramPanchayatOffice DisabledFriendlyornot? --**YES**

iii) Areprovisionsfora separate BudgetundertheResourceEnvelopeforWomenandChildrenmadeor not?---**NO**

iv) DoalltheSchools intheGramPanchayathavefacilitiesforDifferentlyAbledChildrenliketoilets, barrier-freeaccess,etc.,ornot? ---**YES**

v) Arealltheeligibleindividualsaregettingpensions,likeoldagepension,widowpension,etc? ---**YES**

vi) ArealltheeligiblehouseholdsgettingbenefitsfromIAYornot?

--**YES**

**8 EngenderedDevelopmentinVillage**

i) HowmanyMahilaSabha’swereorganizedintheGramPanchayat-- **04**

ii) WhetherSHGsfederationshavebeenprovidedspaceformeetings inthePanchayatBhawan -----**NO**

iii) WhetherGPshavetakenstepsforincreasingwomen’sparticipationinGramSabha ---**YES**

iv) NumberofwomenbeneficiariesheadedhouseholdscoveredunderPDS

system…**32**

v) Numberofbeneficiaries(outoftotaleligiblepopulation)receivingsocialprotectionbenefitsunder

PradhanMantriMatritvaVandanaYojana ----**NIL**

9 Self-sufficientinfrastructureinthevillage

i. WhetherGPhasa CommunityHallwithaccesstoelectricity,furniture,watersupply, toilet ---**NO**

ii. WhethertheDisastermanagementplanisavailableattheGPLevel --**NO**

iii. Whetherchild-friendlyparkwithrequiredfacilitiesisavailableinGP ---**NO**

iv. WhethertheGPhaseasyaccesstoGodownforstorage --**NO**

v. Whetherstreetlightsareprovidedinpublicplacesforensuringsafety ---**NO**

**DAY2ACTIVITIES**

**AGENDANO.2**

SensitizevillageresidentsaboutmyScheme”portal(myscheme.in)whichincludesinformationaboutall theschemesbeingrunbyCentral/State/UT govtacrossthecountry

*(SchemeMaterialavailablefromhttps://jkpanchayat.in/b2v4.php)*

**DAY2ACTIVITIES**

**AGENDANO.3**

HoldmeetingoftheBiodiversityManagementCommitteestodeliberateonissues pertainingtoconserva- tionofbiodiversityandsustainableutilizationofbiologicalresources.HeshouldcheckPeopleBiodiversity register(PBR)ofthatpanchayatandreviewifBiodiversityManagementCommittee constitutedforthat panchayatis holdingminimum4meetings inayearandmeeting onceinevery3months *(RoleofBMC availableathttps://jkpanchayat.in/b2v4.php)*

COMMITTEEMEMBERS PRESENT

BIODIVERSITYREGISTERPHOTOS

PAST 4MEETINGDETAILS-DATES,MINUTESPHOTOS

**DAY2ACTIVITIES**

**AGENDA4**

Visitingofficershallalsoplanandconductpanchayatlevelconvergencemeeting ofalldepartmentsand prepareVillagedevelopmentplanforvillage,inconsultancywithGrampanchayat,discussitingram sabhaandgetitapproved.

(GPDPformatavailableonhttps://jkpanchayat.in/b2v4.php)

**InadditionGPDPplanshallalsoinclude:**

 Touristplaceswhichneedtobedeveloped

 Specificproductwhichneedstobedeveloped

 Tourism-homestays

 20candidatesfortrainingunderHimayatschemealongwithtradeinwhich trainingistobegiven

**DAY2ACTIVITIES**

**AGENDA5**

Ensuresaturationoffollowingschemesandgivestatus:

|  |  |  |  |
| --- | --- | --- | --- |
| **NAMEOFTHESCHEME** | **TOTALELIGIBLE BENEFICIARIESIN THE VILLAGE** | **TOTALBENEFICIARIESWHO AVAILEDTHEBENEFITSOFTHESCHEME** | **REASONSFOR PENDENCY** |
| GoldenHealthCardunder  AyushmanBharat | **2527** | **2436** | **Out of Country and not matching Fingerprint.** |
| Jananisurakshayojana | **85** | **25** | **Funds not available** |
| OLDAGEpension | **55** | **55** | **Nil** |
| Widowpension | **22** | **22** | **Nil** |
| Disabilitypension | **55** | **55** | **Nil** |
| Domicilecertificate | **2527** | **1900** | **People not Cooperate** |
| Kisancreditcard | **250** | **250** | **Nil** |
| PMkisansammannidhi | **252** | **252** | **Nil** |

|  |  |  |  |
| --- | --- | --- | --- |
| Landpassbook | **2527** | **600** | **35-40% Under process** |
| Registrationofvillageven- dorsonGEMportal | **---** | **----** | **----** |
| Registrationofvillagecon- tractorsonjktendersportal | **06** | **06** | **---** |
| Registrationofvillagecon- tractorsonPWDportal | **10** | **10** | **-------** |
| Incompletebuildings/pro- jects | **01 Patwar Khana** |  | **Incomplete Patwar Khana at Chandak** |

**DAY2ACTIVITIES**

**AGENDA6**

**NASHAMUKTABHIYAN**

1. Whethergramsabharesolutionpassed **YES**

2. Detailsofactivities conducted **Bal Sabha-aware public about disadvantage of Drugs.**

3. Whetherallactivities andGSresolutionuploadedonjkpanchayats.inportal **YES**

4. Howmanydrugaddictsinthevillage **NIL**

5. WhetherreportedtotheDeputyCommissioner **NIL**

6. Howmanyregisteredforrehabilitationundergovernmentprogramme-S **NIL**

**DAY2ACTIVITIES**

**AGENDA7**

**SOCIALAUDIT**

Conductsocialauditofatleast5workseachunderfollowingschemes:

|  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- |
| NAMEOFTHE SCHEME | DETAILSOFTHE WORKS | YEAROFWORK APPROVAL | AMOUNT APPROVED  FORTHEWORK | WHETHER  WORKEXECUTED SATISFACTORILY | GEO- TAGGED PHOTOS | ANY GRIEVANCE RECORDED RELATINGTOTHAT WORK |
| **MGNREGA** | **R/wall H/oKafeel Meru w no.4** | **2021-22** | **1.00 lac** | **yes** | **YES** | **NIL** |
| **PMAY** | **Mohd Sharief S/o Said Mohd** | **2021-22** | **1.30 lac** | **yes** | **yes** | **NIL** |
| **IHHL**  **UNDERSBM-G** | **Mohd Azam khan** | **2019-20** | **0.12 lac** | **yes** | **yes** | **Nil** |
| **CSCUNDER SBMG** | **CSC nr Masjid Sharief Bhallian** | **2020-21** | **1.80 lac** | **yes** | **yes** | **Nil** |
| **AMRIT SAROVARS** | **nil** | **nil** | **nil** | **nil** | **nil** | **Nil** |

**DAY2ACTIVITIES**

**AGENDA8**

**MAHILASABHA**

Totalwomeninthevillageabovetheageof18 ---**180**

Totalattended ---**62**

Proceedings:

*(Plinsertpointerstobediscussedthere–referpalliproceedings)*

**DAY2ACTIVITIES**

**AGENDA9**

**BALSABHA**

Holda balsabhaandrecordproceedings

Totalchildreninthevillageabovetheageof **03 to 06 years ---237**

Totalattended ---**15**

Proceedings:

*(Plinsertpointerstobediscussedthere–referpalliproceedings)*

**DAY2ACTIVITIES**

**AGENDA10**

**INAUGURATIONS**

|  |  |  |  |
| --- | --- | --- | --- |
| **SR NO.** | **ASSETS/ACTIVITIES INAUGRATED** | **STATUSOFTHEASSET/AC- TIVITIES(NUMBER,OTHER DETAILS)** | **GEO-TAGGED PHOTOS** |
|  | VILLAGEHAATunderJKSRLM (SUN- DAYMARKET) | **YES** |  |
|  | PMAYhousesifanyreadyforinaugra- tion | **Mohd Sharif**  **S/o Said Mohd** |  |
|  | Swachhgramprojects-segregation shedsetc | **NIL** |  |
|  | Amritsarovars | **NIL** | ------ |
|  | Sportskits | **YES** | -------- |
|  | Villageculturalevents | **NIL** |  |
|  | JJMassets/projects | **NIL** |  |
|  | Anyothertobeidentifiedatdistrict level | **NIL** |  |


**FOLLOWUPOF(B2V1,B2V2&B2V3):**

*(Prefilledexcelsheet tobetakenfromdistrictlevel/andalsotobedownloaded*

*from*[*www.jkpanchayat.in)*](http://www.jkpanchayat.in)

|  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| S.NO. | | Particulars | Actiontaken | | Remarks# |
| I. UrgentPublicRequirements/Demands-B2V1 | | | | | |
| 1 | **Tehsil status to Chandak** | | |  |  |
| 2 | **Block should be situated at Nangali Road.** | | |  |  |
| 3 | **Payment of Panchayat Ghar (Pending).** | | |  |  |
| 4 | **Repairing of One Hall at Girls H. School Chandak.** | | |  |  |
| 5 | **Upgradation of Road Connectivity Chandak to Nerhad.** | | |  |  |
| 6 |  | | |  |  |
| 7 |  | | |  |  |
| II. UrgentPublicRequirements/Demands-B2V2 | | | | | |
| 1 | **Tehsil Status to Chandak.** | | |  |  |
| 2 | **Government** **Depot and Boring facility at w no. 4,6 and 7.** | | |  |  |
| 3 | **Hand Pump 5 no. at w no. 4 at Nerhad Tangla.** | | |  |  |
| 4 | **Urgent need of Govt. Primary School w no. 7** | | |  |  |
| 5 | **Urgent need of Water reservoir 20,000 Gallons**. | | |  |  |
| 6 | P**ayment of Panchayat Ghar .** | | |  |  |
| 7 | **Pending payment of GHSS CHANDAK.**  **Upgradation road Chandak to Nerhad.** | | |  |  |
| S.NO. | Particulars | | | Actiontaken | Remarks# |
| III. MajorProblems–B2V1 | | | | | |
| 1 | **Lack of awareness Camp regarding all new schemes.** | | |  |  |
| 2 | **Depleted condition of roads on uphill area.** | | |  |  |
| 3 |  | | |  |  |

|  |  |  |  |
| --- | --- | --- | --- |
| 4 |  |  |  |
| 5 |  |  |  |
| IV. MajorProblems-B2V2 | | | |
| 1 | **One residential Quarter for medical staff at PHC Chandak.** |  |  |
| 2 | **Upgradation of road fron Chandak to Nerhad.** |  |  |
| 3 | **Infrastructure development at different schemes in Chandak.** |  |  |
| 4 |  |  |  |
| 5 |  |  |  |
| V. MajorProblems-B2V3 | | | |
| 1 | **Boundary** **wall Pacca at Graveyard ward no. 1** |  |  |
| 2 | **Transformer at Moh. Chowk ward no. 1.** |  |  |
| 3 | **Protection wall near Mohalla Chowk ward no. 1.** |  |  |
| 4 | **Road from Talab to Zairat Tomi Peer.** |  |  |
| 5 | **Road from Tangla to Nerhad.** |  |  |
| VI. MajorComplaints-B2V1 | | | |
| 1 | **Handloom and handicraft can improve.** |  |  |
| 2 | **Economic condition of the G.P.** |  |  |
| 3 | Inadequate **power supply.**  **Unemployment.**  **Lack of Awareness Camp from Line Department.** |  |  |
| VII. MajorComplaints-B2V2 | | | |
| 1 | **Lack of awareness camps by the Department to display schemes.** |  |  |
| 2 | **Depleted condition of Irrigation.** |  |  |
| 3 | **Need of survey of leftout Kaccha hous under PMAYG.** |  |  |
| VIII. MajorComplaints-B2V3 | | | |
| 1 | **----------------------------** |  |  |
| 2 | ------------------------------ |  |  |
| 3 | ---------------------------------- |  |  |





**DepartmentofRuralDevelompentandPanchayatiRaj**

**GovernmentofJammu &Kashmir**