4

15TH OCTto3RD NOV,2022

KEYFEATURES

•     DeputyCommissionerstoleadtheinitiative

•    RuraldevelopmentDepartmenttobethenodaldepartment

•	PlanningDevelopment&MonitoringdepartmentandITtobethesupport departments

ACTIONSANDTIMELINES

| ACTION | RESPONSIBILITY | LATESTBY | REMARKS |
| --- | --- | --- | --- |
| Janabhiyan | Alldepartments | Oct15-26th | Goingon |
| DeputationofSecttstaff/ HoDs | GAD | Oct14 | Done |
| DeploymentofStaffto Panchayatsandservingof ordersondeployedofficers | DCs | Oct25 | DCswilldeployseniorlevelstaff fromthedistricts.Strictactionto betakenagainstabstentions.No exemptionstobegiven |
| Trainingofdistricttrainors onB2V4 | RDD | Oct26 |  |
| Trainingofvisitingofficers | DCs | Oct27 |  |
| FieldVisitstobecompleted by | VisitingOfficers | Nov3 | DCstosuperviseandensurethat eachPanchayatisvisitedwithin theperiodspecified |
| DataofB2V4tobe uploadedby | VisitingOfficers | Nov10 | DCstosuperviseandensurethat dataofallPanchayatsisupload- edbythevisitingofficerwithin theperiodspecified |

INSTRUCTIONSFORTHEVISITINGOFFICER(DAYWISE)

| DATE | INSTRUCTIONS | ACTIONPOINTS |
| --- | --- | --- |
| Day0 | Meetingwithdeputy commissionerandhis/her team | a. TakeprintoutsoffilledbookletsofB2V1,B2V2andB2V3from www.jkpanchayat.in b.Alsotakeprintoutsofthesummarizedexcelsheetsofthe previousphasesfromwww.jkpanchayat.in c. CollectATRsonissuesraisedduringprevious3phasesfromthe officeofDeputyCommissioner(Planningdeptt) d.Takeprintsofblank 2bookletsofB2V4fromwww.jkpanchayat.ine.Takeplansfor2previousyearsandATRsfromtheplanningdeptt f. CompletetrainingsondifferentcomponentsofB2V4being organizedbyrespectiveDeputyCommissioners g.CollectListofnewworksstarted/ongoing/completedduringthe previousandcurrentFinancialyearunderthefollowingheads: • PRIgrants • DistrictPlan • UTplan • MGNREGA • Otherschemesofotherdepartments • Anyotherwork h. Plans/beneficiarylists: • MGNREGAdraftplandocumentfortheyear2022-23. • ListofAwaas+beneficiariesalongwithIHHL Convergence • Listofpensionbeneficiaries. • ListofSHGs • Listofagricultureschemebeneficiaries i. Listsofbeneficiariesfor: • Variouscertificates/benefitstobedistributedbythe visitingofficer. • Anyotheractivitiesidentifiedbydifferentdepartments |

| Day1 | Reachthevillage | 1. | Ensurethatallfrontlineworkersofdifferentdepttsarepresent. |
| --- | --- | --- | --- |
|  |  | 2. | Ensureexhibitionbydifferentdepts.aboutindividualbeneficiary schemes |
|  |  | 3. | InspectJKB/PSBcounters/outlets |
|  |  | 4. | Participate/ensureorganizationofsportsactivityinplayfield,talent hunt/culturalevent/youthactivity |
|  |  | 5. | GandhiKatha(suggesteddetailsuploadedonjkpanchayat.in) |
|  |  | 6. | Visitatleast2amritsarovarsandgetitsgeotaggedphotos |
|  |  | 7. | InspectKhidmat(CSC)CentresandcreateGenerateawarenesson 225schemesparticularlyG2CschemeslikeBEAMS,Janbhagidari, AapkiZaminAapkiNigrani,DigitalJ&K |
|  |  | 8. | Visitingofficershallalsoplanandconductpanchayatlevelconver- gencemeetingofalldepartments |
|  |  | 9. | CheckeffectivenessofCentrallysponsoredschemes |
|  |  | 10. | VisitandinspectallgovernmentestablishmentsincludingPHE, AWC,FPS,schools,etc |
|  |  | 11. | Attemptsaturationofdeliverableso JanAbhiyanandwherever deficienciesfound,leadadrivetoachievealldeliverables |
|  |  | 12. | Assesseffectivenessofsanitationcampaigninthepanchayat |
|  |  | 13. | Ensureselfemploymentactivitiesfor15youthperpanchayat |
|  |  | 14. | Identify20potentialcandidatesperpanchayatforHIMAYATtraining alongwiththetradeonwhichtheywanttraining |
|  |  | 15. | Whereverpossible,distributeemploymentlettersforpeopleselect- edundervariousgovernmentemployments |
|  |  | 16. | Intheevening,holdnormalmeetingwith seniorcitizens,govtem- ployeesincludingretiredemployees,exservicemen,youthclub,and any citizens ofthevillagewhoareenrolledincollege/university |
|  |  | 17. | OpendiscussiononNashaMuktAbhiyan |

Day2            Haveameetingwithall stakeholders-depttofficials andpanchayatmembers

1.       Discussionontheandassesstheprogressofdifferentschemesrelating tothelocalizedSDGsprioritizedforthatvillageaspertheresolution passedby thatGramPanchayaton21st April22,onNationalPanchayti RajDay.

2.	Sensitizevillage residentsaboutmyScheme”portal(myscheme.in) whichincludesinformationaboutalltheschemesbeingrunbyCen- tral/State/UTgovtacrossthecountry

3.	Hold meeting of theBiodiversityManagementCommitteestodeliber- ateonissuespertaining toconservation of biodiversityandsustaina- bleutilizationof biologicalresources.

4.       PrepareVillagedevelopmentplan,inconsultancywithGrampanchayat, discussitingramsabhaandgetitapproved.

5.       Ensure saturationofsoilhealthcardandgoldenhealthcardunderGold- enHealthCardunderAyushmanBharat,

6.       Ensuresaturation  of OldAge PensionScheme

7.       EnsureDomicileSaturation.

8.       EnsureKCCSaturation

9.       Ensure saturationoflandpassbooks

10.     Ensureregistrationofvillagevendorsneededforanyscheme,onGEM

portal

11.     Ensurepanchayatcontractors registration

12.     EncouragePanchayatmembers forimportanceofplantationdrivein

PanchayatunderHarGaonHariyali

13.     Ensure paintingondigitalJ&Kinpanchayatghars

14.     Ensure paintingonpanchayatactivitesandCSSinpanchayatghars

15.	Thevisiting officeshallchecknoof kindergarten andplayfields present inthepanchayat for kidsandstudents,iftheinfrastructure present inthesearegoodenough.

16.     Holdmeeting withpanchayatmembers todiscussaboutcorruption menaceandstepsrequiredtomakeJ&Kcorruptionfree

17.     Obtaina candidassessmentaboutperformanceofvariousdeptts in- cludingfairfeedbackaboutdiscrepanciesinfunctioning

18.	Check thestatusof NashaMuktAbhiyanandreporting of drugad- dictstoDeputyCommissioner.

19.     IdentifyTouristDestinations,Circuits,ThemeTreks,IdentifyHomestays, providesupportfortourismactivities throughVillageCooperative

20.     OrganizeTalentHuntatPanchayatLevel

21.     Conductsocialauditofatleast5worksunderfollowingschemes:

a.       MGNREGA

b.PMAY

c.        IHHLtoiletsandpayments d.CSCs

e.AMRITSAROVARS

22.     Holda mahilasabha anda balsabhaandrecordproceedingsinthefor- matgiven

23.     InauguratevillagehaatunderJKSRLM

24.     Checkifyouthclubsareformedinthepanchayatandwhatactivities theyareengagedin

25.     Organizea villagelevelculturaleventtoengagepanchayatmembers

26.     SensitizeGPaboutE-kitabkoshaninitiativeofJ&KGovtforempowering youthsthrough onlinedigitalliteracy

GENERALINSTRUCTIONS

1.	Thevisitingofficershallrefrainhimself/herselfgivingorofferinganycommitmentonbehalfofthe governmentandshalladoptanunbiasedattitudeinreportingissues.As faraspossible,his/her observation shouldbebasedona fairandanalytical viewemergingfromhis/herinteractioninthe village.

2.	Heisgoingtothevillageasplanningofficer,notforsanctioninganyworksorformakinganycom- mitments.

3.	Whilepreparingvillagedevelopmentplan,hehastoensurethat,demandsareprioritizedandre- flectedunderavailableschemes,wherevernecessarythelargerworksaretobereferredtoadminis- trativedepttunderCSS/UTplansunderintimationtoDCsandrestoftheworkstoDCsforreflecting itunderdistrict/CSS plans

4.    His workshallbehardcoreplanningandauditandisnota PRexercise.

5.	EveryDeputyCommissionerhastoensurethatatleastoneRDDofficial(ideallyPanchayatSecre- tary)ispresent  ineverypanchayatwithrelevantpanchayatrecords,toensureconductofallactivi- tiesasplanned.Panchayatwiseorderneedstobeissuedinadvance.

6.	Visitingofficershouldideallycarryhis/herlaptoptocompletethereportsatthepanchayatlevel itselfanduploadthefinalreport,duly signedbothbythesarpanchandbythevisitingofficeron www.jkpanchayat.inportal,beforetheyleavepanchayat.

7.	Focus ofvisitareyouth,skills,self-employment,nashamukt,bhrashtracharmukt,Rozgaryukt J&K, besidestocarryforwardtheactivities duringJanAbhiyanandsaturatethem.

8.    Inadditionattentionmaybegiventothefollowingareas a.     MakefulluseofCentrallySponsoredSchemes

b.Saturationofindividualbeneficiaryschemes c.     Self-employmentschemes

d.Banklinkedschemes-includingdepartmentalsubsidyschemes e.Empowermentandtransparencythrough digitalinitiatives

f.       Effectivenessofgrassrootsmachinery–

i.       Patwari,VLWpresent  andavailable

ii.      AvailablefundsutilizedinpublicinterestandasperGramSabharesolutions iii.   Fairness ingovernance

iv.    CSS/Individual beneficiaryschemesetc v.      BrashtacharMuktJ&K

vi.   BhaiMuktJ&K

vii.  NashaMuktJ&K

9.	ThePRImembers (Sarpanchs,Panchs,BDCChairperson)shallbeattheforefrontofallactivities and givendueimportanceandtheapproach shouldbetostrengthenthemandmakethemfeelem- powered.He/sheshallensurethattheBDCchairpersonandSarpanch/Panch arepresent  atthetime ofinaugurationandceremonies.

10.	Visitingofficershallnotleavethedistrictwithoutuploadingthereport,duly signedonthewww. jkpanchayat.inportal.EveryDeputyCommissionerhastoensurethat.

A)   DetailsofReportingOfficer:

Name:   MOHD SADEEQ  KHOLI

Designation:  HEADMASTER

Department/placeof  posting:  EDUCATION

MobileNo:9906347066

EmailID: Mohdsadeeqkholikholi@gmail.com

HomeDistrict: POONCH

Datesof  visit:  28th of October 2022 to 29th of October 2022

B)	LocationaldetailsofPanchayat:(tobepre-filled,informationtobetakenfromtheprevious phasesbooklets/summarizedexcelsheetuploadedonjkpanchayat.in/b2v4.php)(tobevali- datedbythevisitingofficerandmissingdetailstobefilled)

NameofthePanchayat:  SARAL

LocalGovernmentDirectory(LGD)codeof  thePanchayat:  239249

Nameof  CDBlock:  NSSB

NameofTehsil: HAVELI

Nameof    District: -  POONCH

C)     PanchayatProfile:

No.ofrevenuevillagesinthePanchayat:df 01+01 (PARTLY)

No.ofhamletsinthePanchayat: 18

No.ofhouseholdsinthePanchayat: 375

Population (approx)of  the Panchayat: 2635

Part-II:

(TobefilledupbytheVisitingOfficerduringhis/hertwodayvisittothePanchayat.AllFieldshavetobe

filledbytheVisitingOfficerbeforethebookletishandedovertotheDC

FrontlineOfficers/OfficialswhowereassignedtothePanchayatfortheprogramme:

| Department | Name | Designation |
| --- | --- | --- |
| Revenue | Randhir Singh | Naib Tehsildar |
| Sports | Mohd saleem | pet |
| ICDS | Parvaiz akther | Supervisor |
| Health P | Rehmat jan | MPW |
| PHE | Mushtaq ahmed | Line man |
| Agriculture | Usman sayeed | F/Asstt |
| PDD | Rashied hussain | Line man |
| Soil con. | Abdul rashied | Guard |
| Horticulture | Nassar ahmed | Hdo |
| Education | Muzaffar hussain | Teacher |
| Jarmeen Bank | Vipan sarngal | Manager |
| PWD R&B | Mohd Sharief | lineman |
| Sheep Husbandry Deptt | Vinod Kumar | S.A |
| Animal Husbandry | Shazoon ahmed khan | TVP |
| RDD | Sharaz ahmed | GRS |

Detailsofabsentemployeesvis-à-vislistfurnishedbytheDCoffice:

| Department | Name | Designation |
| --- | --- | --- |
| NIL | NIL | NIL |
| NIL | NIL | NIL |

DAY1-ACTIVITIES

AGENDA1:PANCHAYATASSETREGISTER

Infrastructure:

1.		PanchayatGharInfrastructure a.  Private Building (own building )

b.  New

2.       Furniture(Y)

3.       Computer/printer(Y)

4.       Internet(N)

5.       Telephone(N)

6.       Toilet(CSC/partofpanchayatghar)(Y)

7.       Water(Y)

8.       Electricity(Y)

9.       Bankbranch(N)

10.     CSC(N)

11.     Patwarkhana(N)

12.     Villagehaat(Y)

13.     Playground(N)

14.     School-Y

a.        Kindergarten(N)

b.Primary(Y)/ Middle (Y)

c.         Secondary(N)

d. College (N)

e.University(N)

15.     AnganwadiCentre(Y)

a.        (private)

b.Totalchildrenenrolled   140

15.     AmritSarovars–details,location,condition (2 in good condition but no water available

16.     Governmentoffices-details,whetherfunctional  Yes

17.     Rationshop(Y)

18.      Placesoftourismimportance–names,littledetailsonhistorical/culturalimportance NIL

19.      Villageheritagesites/treks-names ,little detailson historical/cultural importance NIL

20.     VLWOffice (Y)

21.     PrimaryHealthcareCentre(N),

22.     ListofIncompleteBuildings-names,yearofconstruction(Y)1 BUILDING OF HIGH SCHOOL SARAL

23.     ListofUnderutilizedBuildings-name (NIL)

DAY1-ACTIVITIES

AGENDA2:

DIFFERENTINSTITUTIONS/INFRASTRUCTUREPROJECTSTOBEVISITED

| AMRITSAROVARS | Visit,verify | COMMENTS |
| --- | --- | --- |
| KhidmatCentres | Create/Generateawarenesson225schemes particularlyG2CschemsAapkiZaminAapkiNigrani, Beams,Janbhagidari,DigitalJ&K | Does not exist But required N |
| JKB/PSBcounters/outlets | a)Statusofcounter b)Numberofvisitors | Does not exist but J&K bank branch Along ATM facility Required |
| Incompletebuildings/pro- jects | Verify whetheridentificationandredistribution done | BUILDING OF HIGH SCHOOL SARAL |
| PDS | Visit,evaluate,onlinestatus | (Yes) 01 dealer shop exist with online system |
| PHC | Visit-evaluate,statusofstaff,equipmentand quality | NIL .But required on urgent basis |
| Youthclubs | Meet,interact,seeksuggestions | Yes Interacted with them |
| SHG | Meet,identifyproblems,seeksuggestions | NIL |
| PMAY | Inspect,Inaugurate | Inaugurated 05 houses |
| Myschool,mypride progress;schools-water, toilets,staff | Visit,checkforwater,electricity,sanitation,meet studentsandstaff | Visited P/S ,M/S&H/S. Building of M/S SARAL is Unsafe |
| SwachhSBM | Evaluate | Consituted Commitee ssSBMeeeeeeexistexistipanchayat |
| Panchayatplayground, Sportskitsdistribution Villagegames | Ensure,verify.Participateinatleastonegamein theplayground | NO . Participated In caram board Game |
| HarGaonHariyali, Planta- tiondrive | Evaluatestatus,feedback | YES Planted Tress in the Panchayat |
| Villageculturalevent Dangal/Haat/Mela | Participatein;ensurethatitisheld | Nil |
| Exhibitionofschemes | Ensurethateverydepartmentparticipatesand thatitcontinuesfortheentiredurationofB2V | YES |
| JalJeewanMission verifica- tion- WSS/JSD Electricitysupply | Verify | YES |

DAY1-ACTIVITIES

AGENDA3:SATURATEJANBHIYAN

DELIVERABLESANDRECORDDEFICIENCIESIFANY(INSERTDELIVERABLESLISTHEREASPERGADFORMAT

PROGRESS REPORT OF ACTIVITIES CARRIED OUT IN PYT. SARAL 15/10/2022 TO 29/10/2022

LIST OF DELEVERABLES IN PANCHAYAT SARAL.

| Ayushman Golden Card | E- shram Cards | Land Passboo k | Inheritance Mutation | Credit Card | Health Card | KCC Card | Awareness of 70 G20 services | JAN BAGIADARI | AP KI ZAMEEEN AP KI NIGRANI | PANI SDAMI TI | ENROLE MENT SELF EMPLOY MENT | SPORTS ACTIVITY |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| 40 | 0 | 7 | 11 | 0 | 0 | 25 | 10 | 36 | 25 | 5 | 0 | 3 |

DAY1-ACTIVITIES

AGENDA4:

SELFEMPLOYMENTACTIVITIES

EnsureSelf-employmentactivities foryouth,distributeemploymentlettersforpeopleselectedunder varioussocialschemes(15ISTHETARGETPERPANCHAYAT)

Numberofcasesindifferentcategoriessanctioned: 01 (SHAKEEL AHMED)

Detailsofthebanksanctioningit:JRB POONCH

Totalamountinvolved: 3.00 lAC

DAY1ACTIVITIES

AGENDA5

Intheevening,holdinformalmeetings  withseniorcitizens,govtemployees,retdemployees,youthclub andothercitizenswhoareenrolledoncollege/universityandhavediscussiononGandhiKatha,Nasha MuktAbhiyan,corruptionfreegovernance,doublingfarmersincomeandrecordtheproceedings_Meetings Held.

DAY2

a.       NoofIndividualCompostPitsconstructed(20) b.        NoofIndividualSoakPitsconstructed(344)

V.          No.ofBiodiversitymanagementcommitteemeetingsheld(03)

VI.         IsthenameofSarpanchdisplayedoncitizeninformationboardsofallRD&PRschemes:Yes

VII.       AreSarpanchsbeinginvolvedinstart/inaugurationofactivities:Yes

VIII.      WhethersubjectshavebeenassignedbytheSarpanchtothePanchs:Yes

IX.        Whethergrievancesredressalboxisinstalled:Yes

X.      NoofgrievancesreceivedpertainingtoPanchayatlevel:02

XI.        NoofgrievancesdisposedofatPanchayatlevel:02

XII.       WhethertheSarpanch/PanchayatSecretaryhavedigitalsignatures:Yes/

XIII.      WhetherallMGNREGA/14thFCpayments arebeingmadebySarpanchthrough DigitalSignature

Certificate (DSC): Yes

HUMAN RESOURCEAVAILABLEATTHEPANCHAYAT LEVEL:

| SRNO. | DEPARTMENTWISESTAFF | NUMBERS |  | NAMES |
| --- | --- | --- | --- | --- |
|  |  | SANCTIONED | ACTUAL |  |
|  | Ruraldevelopmentdepartment: BDO JE GRS TA | 01 01 01 | Add.charg 01 01 01 | Ayaz Bhatt Arjun Singh Sharaz Ahmed Shahied latief |
|  | SCHOOLEDUCATION: TEACHER HEADMASTER ANYOTHER | 45 01 | 33 01 |  |
|  | JAL JEEVAN: | ______ | ______ | ______ |
|  | PDD: LINEMAN JE ANYOTHER | 01 01 | 01 01 | MOHD SHARIEF RAIZ AHMED |
|  | FOOD&CIVILSUPPLIES | 01 | 02 |  |
|  | AGRICULTURE&ANIMALHUS- BANDARY | 01 | 01 | USMAN SAYEED |
|  | SOCIALWELFARE | 05 | 05 |  |
|  | HEALTH: ASHA ANM AYUSHDOCTOR ALLOPATHICDOCTOR | 04 01 Nil Nil | 03 01 | REHMAT JAN |
|  | ANYOTHERDEPARTMENT |  |  |  |

DAY2-ACTIVITIES

AGENDANO.1

DiscussionontheandassesstheprogressofdifferentschemesrelatingtothelocalizedSDGsprior-itizedforthatvillageaspertheresolutionpassedbythatGramPanchayaton21stApril22,onNational PanchayatiRajDay(Copyoftheresolutiontobetakenfromwww.jkpanchayat.inportalunderthelinkof GramSwarajMonth)  Discussion Held

1.       SDGs AGREED FORTHATVILLAGE,TOBEIMPLEMENTED BYMARCH2024:

2.       STATUSOFWORKSUNDERTHEFOLLOWINGSCHEMES:

1      Cleanandgreenvillage

i.InitiativestakenbythePanchayatformanagingSolidandLiquidWaste soak pits constt.in the panchayat

ii.     InitiativestakenbythePanchayatforusinggreensourcesoffuellikesolar, biogas initiative taken by pyt.by creating awareness composit pits constt. At different halmet in the panchayat.

iii.  Hasmappingoflanduse,waterbodies,forest,slopes,wetlands,degradedforestwithintheGram

Panchayatbeendone?Yes/No.IfNo,reason,thereof YES

iv.    HastheClimateResiliencePlanbeendevelopedfortheGP?Yes

v.     StepstakenbytheGramSabhaabouttheclimatechangemitigationfactorslikereducingenergy consumption,usageoffossilfuels,plastics,non-renewablebuildingmaterialsandalsotopromote measureslikeplantingoftrees,conservingforests,usageofgoodagriculturalpracticeslikedrip irrigation,waterconservationmeasuresandconservationofwetlands. YES

vi.  Whetherschoolshavestartedsegregatingwaste YES

vii. Whetherschoolshavetheirowncompost/soakagepitsforsolid/liquidwastemanagement Yes

2     Healthyvillage

i)    Aremeetings  relatedtoVillageHealthandSanitationCommitteebeingheldregularly? YES

ii)   DoalltheeligibleindividualsbeenprovidedtheGoldenCard? Yes

iii)  ArealltheChildrenbeingimmunizedaspertheSchedulerecommendedbyGovt.ofIndia? Yes

iv)  ArealltheeligibleindividualsbeenvaccinatedagainstCOVID-19? YES

v)   DoesGramPanchayatensurethatallpregnantwomenaregettingnecessaryprenatalcheckups? Yes

vi)  WhetherallthedeliverieswereInstitutionalizedorconductedbytrainedMidwives? Yes

3     Watersufficientvillage

i)    DoalltheIHHsintheGramPanchayathavewaterpipelineconnections?Yes

ii)   WhetherGramPanchayathastakenstepsforgreywatermanagement.IfYespleasespecify YES

iii)  DoalltheIHHsintheGramPanchayathavetoilets?YES

iv)  ArealltheIHHstoiletsfunctionalornot? YES

v)   DoalltheSchools/Anganwadicentershavea toiletfacilityornot? Yes

vi)  Areallthetoiletsintheschools/Aaganwadifunctionalornot?YES

vii) WhetherGramPachachayatBhawanhasseparate toiletsforwomenornot?YES

4      ChildFriendlyvillage

i)	Doallthechildrenundertheageof0-6yearsbeenenrolledintheAnganwadicentersforpre- schooling?Yes/

ii)    HowmanyBalSabha’swereorganizedintheGramPanchayat-4

iii)  WhethertheissuesraisedbyBalSabhaareaddressedduringtheGramSabha. No

iv)	WhetherGramPanchayatistrackingthedatarelatedtodropoutchildrenandchildrenwithirregular attendance?Yes

v)   DoalltheschoolsundertheGramPanchayathaveseparate toiletsforgirlsandboys?Yes

5      Villagewithgoodgovernance

i)    IsCSClocatedintheGramPanchayatBhawanornot? NO

ii)	IsthelistofbeneficiariesrelatedtotheSchemes/ProgramsdisplayedontheGrampanchayatwallor not? YES

iii)  DoestheGramPanchayathasitsbuildingornot? YES not taken over yet

iv)  IstheGramPanchayatofficefunctionalornot? YES

v)   Aretheactivities approved undertheHalqaPanchayatDevelopmentPlandisplayedontheGram

Panchayatwallornot? YES

vi)  IsSocialAuditofearlierSchemes/Programscarriedoutornot?YES

6      Povertyfreeandenhancedlivelihoodvillage

i)    HasGramPanchayatdevelopedanycriteria fortheidentificationofthepoor?Yes

ii)   HavealltheeligiblehouseholdsregisteredinPDSornot?YES

iii)	HasGramPanchayatprovidedspaceforSelf-helpGroupsinPanchyatGharforholdingmeetings  or not?NO

iv)  HavealltheeligiblehouseholdsbeenregisteredforPensionornot? YES

v)   HasGramPanchayatfacilitatedYouthforSkillEnhancementCoursesandPlacement? No

vi)  HasJobCardsbeendistributedtoalltheeligibleindividualsunderMGNREGA?YES

vii) HasGramPanchayatfacilitatedSHGsforBankAccountLinkages?Bank employee Not visited

7     Sociallysecuredvillage

i)    WhetherGramPanchayatismaintainingdatarelatedtoDifferentlyAbledPeople?YES

ii)   IsGramPanchayatOffice DisabledFriendlyornot?YES

iii)	Areprovisionsfora separate BudgetundertheResourceEnvelopeforWomenandChildrenmadeor not?NO

iv)	DoalltheSchools intheGramPanchayathavefacilitiesforDifferentlyAbledChildrenliketoilets, barrier-freeaccess,etc.,ornot?YES

v)   Arealltheeligibleindividualsaregettingpensions,likeoldagepension,widowpension,etc?YES

vi)  ArealltheeligiblehouseholdsgettingbenefitsfromIAYornot?YES

8      EngenderedDevelopmentinVillage

i)    HowmanyMahilaSabha’swereorganizedintheGramPanchayat--04

ii)	WhetherSHGsfederationshavebeenprovidedspaceformeetings  inthePanchayatBhawan(Yes)

iii)  WhetherGPshavetakenstepsforincreasingwomen’sparticipationinGramSabha(Yes)

iv)  NumberofwomenbeneficiariesheadedhouseholdscoveredunderPDS

system10

v)   Numberofbeneficiaries(outoftotaleligiblepopulation)receivingsocialprotectionbenefitsunder

PradhanMantriMatritvaVandanaYojana…0

9    Self-sufficientinfrastructureinthevillage

i.	WhetherGPhasa CommunityHallwithaccesstoelectricity,furniture,watersupply, toilet…YES

ii.     WhethertheDisastermanagementplanisavailableattheGPLevel(No)

iii.  Whetherchild-friendlyparkwithrequiredfacilitiesisavailableinGP(Yes)

iv.    WhethertheGPhaseasyaccesstoGodownforstorage(Yes)

v.     Whetherstreetlightsareprovidedinpublicplacesforensuringsafety(Yes)

DAY2ACTIVITIES

AGENDANO.2

SensitizevillageresidentsaboutmyScheme”portal(myscheme.in)whichincludesinformationaboutall theschemesbeingrunbyCentral/State/UT govtacrossthecountry

(SchemeMaterialavailablefromhttps://jkpanchayat.in/b2v4.php)

DAY2ACTIVITIES

AGENDANO.3

HoldmeetingoftheBiodiversityManagementCommitteestodeliberateonissues pertainingtoconserva- tionofbiodiversityandsustainableutilizationofbiologicalresources.HeshouldcheckPeopleBiodiversity register(PBR)ofthatpanchayatandreviewifBiodiversityManagement Committee constitutedforthat panchayatis holdingminimum4meetings inayearandmeeting onceinevery3months YES (RoleofBMC availableathttps://jkpanchayat.in/b2v4.php)

COMMITTEEMEMBERS 05 Including senior citizen and women

PRESENT   01

BIODIVERSITYREGISTERPHOTOS

PAST 4 MEETINGDETAILS-DATES,MINUTES PHOTOS

YES

DAY2ACTIVITIES

AGENDA4

Visitingofficershallalsoplanandconductpanchayatlevelconvergencemeeting  ofalldepartmentsand prepareVillagedevelopmentplanforvillage,inconsultancywithGrampanchayat,discussitingram sabhaandgetitapproved. Gram sabha conducted photo uplaoded

(GPDPformatavailableonhttps://jkpanchayat.in/b2v4.php)

InadditionGPDPplanshallalsoinclude:

           Touristplaceswhichneedtobedeveloped 2 tourist places identified in panchayat

           Specificproductwhichneedstobedeveloped  ultra high apples

           Tourism-homestays

	20 candidatesfortrainingunderHimayatschemealongwithtradeinwhich trainingistobegiven

DAY2ACTIVITIES

AGENDA5

Ensuresaturationoffollowingschemesandgivestatus:

| NAMEOFTHESCHEME | TOTALELIGIBLE BENEFICIARIESIN THE VILLAGE | TOTALBENEFICIARIESWHO AVAILEDTHEBENEFITSOFTHESCHEME | REASONSFOR PENDENCY |
| --- | --- | --- | --- |
| GoldenHealthCardunder AyushmanBharat | 2000 | 300 |  |
| Jananisurakshayojana | --- | ----- |  |
| OLDAGEpension | 500 | 61 |  |
| Widowpension | 45 | 19 |  |
| Disabilitypension | 60 | 54 |  |
| Domicilecertificate | 1345 | 1265 |  |
| Kisancreditcard |  |  |  |
| PMkisansammannidhi | 0 | 0 |  |

| Landpassbook | 300 | 07 | Pending for prints outs |
| --- | --- | --- | --- |
| Registrationofvillageven- dorsonGEMportal | __ | _ |  |
| Registrationofvillagecon- tractorsonjktendersportal | 12 | 12 |  |
| Registrationofvillagecon- tractorsonPWDportal | 12 | 12 |  |
| Incompletebuildings/pro- jects | 01 | ___01 | H/S SARAL M/S TASSA MS NARI NEW BUILDING DAMAGE DUE FLOOD |

DAY2ACTIVITIES

AGENDA6

NASHAMUKTABHIYAN

1.       Whethergramsabharesolutionpassed YES

2.       Detailsofactivities conducted various persons spoke against nasha

3.       Whetherallactivities andGSresolutionuploadedonjkpanchayats.inportal YES

4.       Howmanydrugaddictsinthevillage NIL

5.       WhetherreportedtotheDeputyCommissioner NIL

6.       Howmanyregisteredforrehabilitationundergovernmentprogramme

NIL

DAY2ACTIVITIES

AGENDA7

SOCIALAUDIT

Conductsocialauditofatleast5workseachunderfollowingschemes:

| NAMEOFTHE SCHEME | DETAILSOFTHE WORKS | YEAROFWORK APPROVAL | AMOUNT APPROVED FORTHEWORK | WHETHER WORKEXECUTED SATISFACTORILY | GEO- TAGGED PHOTOS | ANY GRIEVANCE RECORDED RELATINGTOTHAT WORK |
| --- | --- | --- | --- | --- | --- | --- |
| MGNREGA | 55 | 2021-22 | 27.72LAKH | YES | YES | NO |
| PMAY | 315 | 2021-22 | 1.30LAKHSPERHOUSE | YES | YES | DELAY IN PAYMENTS |
| IHHL UNDERSBM-G | 263 | 12THOUSAND /UNIT | 12000/UNIT | YES | YES |  |
| CSCUNDER SBMG | ___ | ___ | _____ | ___ | ___ |  |
| AMRIT SAROVARS | 02 | 2021-2022 | 4.00 Lakhs | YES | YES | REQUIRED REPAIR OF DUNGA SARAL |

DAY2ACTIVITIES

AGENDA80277 6

9\

MAHILASABHA

Totalwomeninthevillageabovetheageof18 400

Totalattended 50

Proceedings:  Discussion Held about role of women

(Plinsertpointerstobediscussedthere–referpalliproceedings)

DAY2ACTIVITIES

AGENDA9

BALSABHA

Holda balsabhaandrecordproceedings Held

Totalchildreninthevillageabovetheageof…..10

Totalattended 50

Proceedings: held discussion about role of children in society photo uploaded

(Plinsertpointerstobediscussedthere–referpalliproceedings)

DAY2ACTIVITIES

AGENDA10

INAUGURATIONS

| SR NO. | ASSETS/ACTIVITIES INAUGRATED | STATUSOFTHEASSET/AC- TIVITIES(NUMBER,OTHER DETAILS) | GEO-TAGGED PHOTOS |
| --- | --- | --- | --- |
|  | VILLAGEHAATunderJKSRLM (SUN- DAYMARKET) | 01 | Yes |
|  | PMAYhousesifanyreadyforinaugra- tion | 05 | Yes |
|  | Swachhgramprojects-segregation shedsetc | ____ | __ |
|  | Amritsarovars | 02 | YES |
|  | Sportskits | 01 ISSUED | Yes |
|  | Villageculturalevents | GOGRI SONG | ---------- |
|  | JJMassets/projects | ---------- | --------------- |
|  | Anyothertobeidentifiedatdistrict level | ______ | _______ |

FOLLOWUPOF(B2V1,B2V2&B2V3):

(Prefilledexcelsheet tobetakenfromdistrictlevel/andalsotobedownloaded

fromwww.jkpanchayat.in)

| S.NO. | Particulars | Actiontaken | Remarks# |
| --- | --- | --- | --- |
| I. UrgentPublicRequirements/Demands-B2V1 |  |  |  |
| 1 | BAD CONDATION OF ROAD | BLACK TOPPING |  |
| 2 | NON AVAILIBLITY OF WATER | STILL PENDING DUE TO NON AVAILABLITY OF Gi PIPES |  |
| 3 | POWER SUPPLY | DISCUSS &RESLOVED THE PROBLEM |  |
| 4 |  |  |  |
| 5 |  |  |  |
| 6 |  |  |  |
| 7 |  |  |  |
| II. UrgentPublicRequirements/Demands-B2V2 |  |  |  |
| 1 | NON AVAILIBLITY OF WATER | STILL PENDING DUE TO NON AVAILIBLITY OF Gi PIPES |  |
| 2 | IPOWER SUPPLY | DISCUSS & Resolved THE PROBLEM |  |
| 3 | SCHOOL BUILDING DAMAGE | PWD DEPT.HAS NOT TAKEN SERIOUSLY |  |
| 4 |  |  |  |
| 5 |  |  |  |
| 6 |  |  |  |
| 7 |  |  |  |
| S.NO. | Particulars | Actiontaken | Remarks# |
| III. MajorProblems–B2V1 |  |  |  |
| 1 | SAFE DRINKING WATER | NIL |  |
| 2 | CANNAL FOR IRRIGATION | NIL |  |
| 3 | ROAD CONNECTIVITY |  |  |

| 4 | HEALTH | NON AVAILIBLITY OF HEALTH CENTRE |  |
| --- | --- | --- | --- |
| 5 |  |  |  |
| IV. MajorProblems-B2V2 |  |  |  |
| 1 | BANK AND ATMS NEED | NIL |  |
| 2 | NEED OF WATER TANKS AND WATER SUPPLY | NIL |  |
| 3 | ELECTRIC POLES AND TRANSFORMER | NIL |  |
| 4 | LACK OF AWC IN WARD NO 1,2,11,8,9,& 5 |  |  |
| 5 |  |  |  |
| V. MajorProblems-B2V3 |  |  |  |
| 1 | BANK BRANCHES AND ATM | NIL |  |
| 2 | ANIMAL HUSBANDRY DISPENSARY | NIL |  |
| 3 | UOGRADATION OF M/S BOWLI | NIL |  |
| 4 | WATER PROBLEMS IN W/NO 1,2&3 |  |  |
| 5 | SHORTAGE OF ELECTRIC POLES & TRANSFORMER | NIL |  |
| VI. MajorComplaints-B2V1 |  |  |  |
| 1 | SAFE DRINKING WATER | NIL |  |
| 2 | Pdd poles and transformer | nil |  |
| 3 |  |  |  |
| VII. MajorComplaints-B2V2 |  |  |  |
| 1 | ROAD CONNECTIVITY IN 2,3,5,6 &8,WARDS | Few roads are stated but not completed |  |
| 2 | LACK OF AWC IN WARD NO 1,2,11,8,9,& 5 | NIL |  |
| 3 |  |  |  |
| VIII. MajorComplaints-B2V3 |  |  |  |
| 1 | BANK BRANCHES AND ATM | NIL |  |
| 2 | ANIMAL HUSBANDRY DISPENSARY | NIL |  |
| 3 | LACK OF AWC IN WARD NO 1,2,11,8,9,& 5 | NIL |  |
|  | WATER PROBLEMS IN ALL WARDS | NIL |  |
|  | SHORTAGE OF ELECTRIC POLES & TRANSFORMER | NIL |  |

OVERALLPERCEPTIONOFFUCNTIONING OF GOVERNMENTDEPARTMENTS

1.         BESTDEPARTMENT: RDD  PARTICULARLY MGNREGA STAFF

2.       LEASTRESPONSIVEDEPARTMENT: NIL

GENERALASSESSMENTOFTHEVISTINGOFFICER

| I | AnymajorcomplaintbroughttothenoticeoftheVisitingOfficer 1 damage of ms nari 2 deviancy of water supply 3 Heath centre 4 lack of awc in five wards 5 play ground 6 community hall 7 left out pmayg 8 Unsafe building of ms saral |
| --- | --- |
| II | Major/urgentpublicdemandsthatwas/werereflectedearlierbuthavenotbeenaddressedsofar : 1 SHORTAGE OF WATER SUPPLY 2 HEATH CENTRE 2ROAD OF WARD NO 1& 2. 3 GOVT MIDDLE SCHOOL SARAL UPGRADED TO HIGH SCHOOL BUT BUILDING SCHOOLIS NOT COMPLETED YET 4 ELECTRIC POLES.AND TRANSFORMER 5 NONAVIAVLABILITY OF ANIMAL HUSBANDRY 6 PLAY GROUND AT H/S SARAL 7 HAND PUMP IN EACH WARD 8 WATER TANK 9 PHE LEFT SCHAME 10 NON AVAILABILTY OF BANK BRANCHS AND ATMS 5 11 LACK OF AWC IN WARD NO 1,2,11,8,9,& 5. UPGRADATION OF T/ROAD MOH KHATANA 12 COMMAN BATH AT DIFFERENT GRAVEYARD . |
| III | Overallassessmentofthevisitandsuggestions: (Thevisitingofficertoensurethattheoverallassessmentisrecordedindetailsalongwithconcretesugges- tions) THE LARGE SCALE DEVELOPMENT HAS TAKEN PLACE IN THE PYT. UNDER MGNREGA AND PMAY SCHEME. 100 NOS OF ELECTRIC POLES BE PROVIDED IN PYT, ANIMAL HUSBANDRY DISPENSARY BE OPENED IN THE PYT, (DAILY WAGERS IN GOVT. DEPTT BE REGULARISED AS THEY ARE WORKING 24X7.) UNSAFE BUILDING OF MS SARAL |
| IV | OverallRatingofgovtfunctioningas givenbythePanchayat(Scaleof0to10) 10 |
| V | CertificatefromSarpanchthatthevisitingofficerhasstayedinthepanchayatfor2daysYES ATTACHED |

SignatureofSarpanch                                                                              SignatureoftheVisitingOfficer

Name………………………                                                                               Name… ……………………

DepartmentofRuralDevelompentandPanchayatiRaj

GovernmentofJammu &Kashmir