4

15TH OCTto3RD NOV,2022

KEYFEATURES

•     DeputyCommissionerstoleadtheinitiative

•    RuraldevelopmentDepartmenttobethenodaldepartment

•	PlanningDevelopment&MonitoringdepartmentandITtobethesupport departments

ACTIONSANDTIMELINES

| ACTION | RESPONSIBILITY | LATESTBY | REMARKS |
| --- | --- | --- | --- |
| Janabhiyan | Alldepartments | Oct15-26th | Goingon |
| DeputationofSecttstaff/ HoDs | GAD | Oct14 | Done |
| DeploymentofStaffto Panchayatsandservingof ordersondeployedofficers | DCs | Oct25 | DCswilldeployseniorlevelstaff fromthedistricts.Strictactionto betakenagainstabstentions.No exemptionstobegiven |
| TrainingofdistricttrainorsonB2V4 | RDD | Oct26 |  |
| Trainingofvisitingofficers | DCs | Oct27 |  |
| FieldVisitstobecompleted by | VisitingOfficers | Nov3 | DCstosuperviseandensurethat eachPanchayatisvisitedwithin theperiodspecified |
| DataofB2V4tobe uploadedby | VisitingOfficers | Nov10 | DCstosuperviseandensurethat dataofallPanchayatsisuploadedbythevisitingofficerwithin theperiodspecified |

INSTRUCTIONSFORTHEVISITINGOFFICER(DAYWISE)

| DATE | INSTRUCTIONS | ACTIONPOINTS |
| --- | --- | --- |
| Day0 | Meetingwithdeputycommissionerandhis/her team | a. TakeprintoutsoffilledbookletsofB2V1,B2V2andB2V3from www.jkpanchayat.in b.Alsotakeprintoutsofthesummarizedexcelsheetsofthepreviousphasesfromwww.jkpanchayat.in c. CollectATRsonissuesraisedduringprevious3phasesfromthe officeofDeputyCommissioner(Planningdeptt) d.Takeprintsofblank 2bookletsofB2V4fromwww.jkpanchayat.ine.Takeplansfor2previousyearsandATRsfromtheplanningdeptt f. CompletetrainingsondifferentcomponentsofB2V4being organizedbyrespectiveDeputyCommissioners g.CollectListofnewworksstarted/ongoing/completedduringthepreviousandcurrentFinancialyearunderthefollowingheads: • PRIgrants • DistrictPlan • UTplan • MGNREGA • Otherschemesofotherdepartments • Anyotherwork h. Plans/beneficiarylists: • MGNREGAdraftplandocumentfortheyear2022-23. • ListofAwaas+beneficiariesalongwithIHHLConvergence • Listofpensionbeneficiaries. • ListofSHGs • Listofagricultureschemebeneficiaries i. Listsofbeneficiariesfor: • Variouscertificates/benefitstobedistributedbythevisitingofficer. • Anyotheractivitiesidentifiedbydifferentdepartments |

| Day1 | Reachthevillage | 1. | Ensurethatallfrontlineworkersofdifferentdepttsarepresent. |
| --- | --- | --- | --- |
|  |  | 2. | Ensureexhibitionbydifferentdepts.aboutindividualbeneficiaryschemes |
|  |  | 3. | InspectJKB/PSBcounters/outlets |
|  |  | 4. | Participate/ensureorganizationofsportsactivityinplayfield,talenthunt/culturalevent/youthactivity |
|  |  | 5. | GandhiKatha(suggesteddetailsuploadedonjkpanchayat.in) |
|  |  | 6. | Visitatleast2amritsarovarsandgetitsgeotaggedphotos |
|  |  | 7. | InspectKhidmat(CSC)CentresandcreateGenerateawarenesson 225schemesparticularlyG2CschemeslikeBEAMS,Janbhagidari, AapkiZaminAapkiNigrani,DigitalJ&K |
|  |  | 8. | Visitingofficershallalsoplanandconductpanchayatlevelconver- gencemeetingofalldepartments |
|  |  | 9. | CheckeffectivenessofCentrallysponsoredschemes |
|  |  | 10. | VisitandinspectallgovernmentestablishmentsincludingPHE, AWC,FPS,schools,etc |
|  |  | 11. | AttemptsaturationofdeliverablesoJanAbhiyanandwhereverdeficienciesfound,leadadrivetoachievealldeliverables |
|  |  | 12. | Assesseffectivenessofsanitationcampaigninthepanchayat |
|  |  | 13. | Ensureselfemploymentactivitiesfor15youthperpanchayat |
|  |  | 14. | Identify20potentialcandidatesperpanchayatforHIMAYATtraining alongwiththetradeonwhichtheywanttraining |
|  |  | 15. | Whereverpossible,distributeemploymentlettersforpeopleselect- edundervariousgovernmentemployments |
|  |  | 16. | Intheevening,holdnormalmeetingwithseniorcitizens,govtem- ployeesincludingretiredemployees,exservicemen,youthclub,andany citizens ofthevillagewhoareenrolledincollege/university |
|  |  | 17. | OpendiscussiononNashaMuktAbhiyan |

Day2            Haveameetingwithall stakeholders-depttofficialsandpanchayatmembers

1.       DiscussionontheandassesstheprogressofdifferentschemesrelatingtothelocalizedSDGsprioritizedforthatvillageaspertheresolutionpassedby thatGramPanchayaton21stApril22,onNationalPanchayti RajDay.

2.	SensitizevillageresidentsaboutmyScheme”portal(myscheme.in) whichincludesinformationaboutalltheschemesbeingrunbyCen- tral/State/UTgovtacrossthecountry

3.	Hold meeting of theBiodiversityManagementCommitteestodeliber- ateonissuespertainingtoconservationof biodiversityandsustaina- bleutilizationofbiologicalresources.

4.       PrepareVillagedevelopmentplan,inconsultancywithGrampanchayat, discussitingramsabhaandgetitapproved.

5.       EnsuresaturationofsoilhealthcardandgoldenhealthcardunderGold- enHealthCardunderAyushmanBharat,

6.       Ensuresaturation of OldAgePensionScheme

7.       EnsureDomicileSaturation.

8.       EnsureKCCSaturation

9.       Ensuresaturationoflandpassbooks

10.     Ensureregistrationofvillagevendorsneededforanyscheme,onGEM

portal

11.     Ensurepanchayatcontractorsregistration

12.     EncouragePanchayatmembersforimportanceofplantationdrivein

PanchayatunderHarGaonHariyali

13.     EnsurepaintingondigitalJ&Kinpanchayatghars

14.     EnsurepaintingonpanchayatactivitesandCSSinpanchayatghars

15.	Thevisitingofficeshallchecknoofkindergarten andplayfieldspresent inthepanchayatfor kidsandstudents,iftheinfrastructurepresent inthesearegoodenough.

16.     HoldmeetingwithpanchayatmemberstodiscussaboutcorruptionmenaceandstepsrequiredtomakeJ&Kcorruptionfree

17.     Obtainacandidassessmentaboutperformanceofvariousdepttsin- cludingfairfeedbackaboutdiscrepanciesinfunctioning

18.	Check thestatusofNashaMuktAbhiyanandreportingof drugad- dictstoDeputyCommissioner.

19.     IdentifyTouristDestinations,Circuits,ThemeTreks,IdentifyHomestays, providesupportfortourismactivitiesthroughVillageCooperative

20.     OrganizeTalentHuntatPanchayatLevel

21.     Conductsocialauditofatleast5worksunderfollowingschemes:

a.       MGNREGA

b.PMAY

c.        IHHLtoiletsandpaymentsd.CSCs

e.AMRITSAROVARS

22.     Holdamahilasabhaandabalsabhaandrecordproceedingsinthefor- matgiven

23.     InauguratevillagehaatunderJKSRLM

24.     Checkifyouthclubsareformedinthepanchayatandwhatactivitiestheyareengagedin

25.     Organizeavillagelevelculturaleventtoengagepanchayatmembers

26.     SensitizeGPaboutE-kitabkoshaninitiativeofJ&KGovtforempoweringyouthsthroughonlinedigitalliteracy

GENERALINSTRUCTIONS

1.	Thevisitingofficershallrefrainhimself/herselfgivingorofferinganycommitmentonbehalfofthe governmentandshalladoptanunbiasedattitudeinreportingissues.Asfaraspossible,his/her observation shouldbebasedonafairandanalyticalviewemergingfromhis/herinteractioninthevillage.

2.	Heisgoingtothevillageasplanningofficer,notforsanctioninganyworksorformakinganycom- mitments.

3.	Whilepreparingvillagedevelopmentplan,hehastoensurethat,demandsareprioritizedandre- flectedunderavailableschemes,wherevernecessarythelargerworksaretobereferredtoadminis- trativedepttunderCSS/UTplansunderintimationtoDCsandrestoftheworkstoDCsforreflecting itunderdistrict/CSS plans

4.    His workshallbehardcoreplanningandauditandisnotaPRexercise.

5.	EveryDeputyCommissionerhastoensurethatatleastoneRDDofficial(ideallyPanchayatSecre- tary)ispresent  ineverypanchayatwithrelevantpanchayatrecords,toensureconductofallactivi- tiesasplanned.Panchayatwiseorderneedstobeissuedinadvance.

6.	Visitingofficershouldideallycarryhis/herlaptoptocompletethereportsatthepanchayatlevel itselfanduploadthefinalreport,dulysignedbothbythesarpanchandbythevisitingofficeronwww.jkpanchayat.inportal,beforetheyleavepanchayat.

7.	Focus ofvisitareyouth,skills,self-employment,nashamukt,bhrashtracharmukt,Rozgaryukt J&K, besidestocarryforwardtheactivitiesduringJanAbhiyanandsaturatethem.

8.    Inadditionattentionmaybegiventothefollowingareasa.     MakefulluseofCentrallySponsoredSchemes

b.Saturationofindividualbeneficiaryschemesc.     Self-employmentschemes

d.Banklinkedschemes-includingdepartmentalsubsidyschemese.Empowermentandtransparencythroughdigitalinitiatives

f.       Effectivenessofgrassrootsmachinery–

i.       Patwari,VLWpresentandavailable

ii.      AvailablefundsutilizedinpublicinterestandasperGramSabharesolutions iii.   Fairness ingovernance

iv.    CSS/Individual beneficiaryschemesetcv.      BrashtacharMuktJ&K

vi.   BhaiMuktJ&K

vii.  NashaMuktJ&K

9.	ThePRImembers(Sarpanchs,Panchs,BDCChairperson)shallbeattheforefrontofallactivities and givendueimportanceandtheapproachshouldbetostrengthenthemandmakethemfeelem- powered.He/sheshallensurethattheBDCchairpersonandSarpanch/Pancharepresentatthetimeofinaugurationandceremonies.

10.	Visitingofficershallnotleavethedistrictwithoutuploadingthereport,duly signedonthewww. jkpanchayat.inportal.EveryDeputyCommissionerhastoensurethat.

A)   DetailsofReportingOfficer:

Name:   SaleemKasser

Designation:Deputy Director (P&S)

Department/placeof posting:Govt. Medical College Rajouri

MobileNo:9419102520

EmailID:meetkaiser@gmail.com

HomeDistrict:Rajouri

Datesof visit:28-10-2022 & 29-10-2022

B)	LocationaldetailsofPanchayat:(tobepre-filled,informationtobetakenfromtheprevious phasesbooklets/summarizedexcelsheetuploadedonjkpanchayat.in/b2v4.php)(tobevali- datedbythevisitingofficerandmissingdetailstobefilled)

NameofthePanchayat:Mandhar

LocalGovernmentDirectory(LGD)codeofthePanchayat:. 7498

NameofCDBlock:NSSB

NameofTehsil:Haveli

NameofDistrict:Poonch

C)     PanchayatProfile:

No.ofrevenuevillagesinthePanchayat:- 02,   1. Mandhar. 2.Kerni

No.ofhamletsinthePanchayat:. 363

No.ofhouseholdsinthePanchayat:634

Population(approx)of  thePanchayat:. 3723

Part-II:

(TobefilledupbytheVisitingOfficerduringhis/hertwodayvisittothePanchayat.AllFieldshavetobe

FilledbytheVisitingOfficerbeforethebookletishanded overtotheDC

FrontlineOfficers/OfficialswhowereassignedtothePanchayatfortheprogramme:

| Department | Name | Designation |
| --- | --- | --- |
| Agriculture Department | Sanjeev Sharma | Agriculture Extension Assistant |
| Food and Supplies Deptt. | Zulfikar Khan | Dealer |
| Jal Shakti Department | Anwar Khan &Kabir Khan | Lineman |
| Revenue Department | Randhir Singh | NaibTehsildar |
| PWD | Mukther Ahmed | MTS |
| Health | Atfram Bi | MPW |
| School Education | ShaziaBatool | Teacher ( Physical teacher) |
| School Education | Khusnood Ahmad | Teacher |
| RDD | Amit Kumar | Account Assistant Panchayat |
| ICDS | Rukshena | worker |
| ICDS | Shookera | Worker |
| Health | Muneera Bi | ASHA |
| Social Welfare | Noor Ahmed Shah | Senior Assistant |
| RDD | Azad Mehmood Dar | NYC |
| RDD | Jagmeet Singh | Junior Engineer |

Detailsofabsentemployeesvis-à-vislistfurnishedbytheDCoffice:

| Department | Name | Designation |
| --- | --- | --- |
| Agriculture | Mohinder Singh | JAA |
| Jal Shakti | Shahid Iqbal | JE |
| Horticulture | Abdul Hamid | Tech. H. |
| CDPO | Taj-un-nisa | Supervisor |
| CDPO | PsrmeeksKour | MO |
| JK Bank Chandak | SachinTandon |  |
|  | Shekeel Ahmed | VLE |

DAY1-ACTIVITIES

AGENDA1:PANCHAYATASSETREGISTER

Infrastructure:

1.		PanchayatGharInfrastructure a.  Govtbuilding/private

b.  New/needingrepairs

2.       Furniture(Y/N)

3.       Computer/printer(Y/N) – procured  but has not been installed in Panchayat Ghar

4.       Internet(Y/N)

5.       Telephone(Y/N)

6.       Toilet(CSC/partofpanchayatghar)(Y/N)

7.       Water(Y/N)

8.       Electricity(Y/N)

9.       Bankbranch(Y/N)

10.     CSC(Y/N)

11.     Patwarkhana(Y/N)

12.     Villagehaat(Y/N) – Temporarily arranged in private shops

13.     Playground(Y/N)

14.     School-

a.        Kindergarten(Y/N)

b.Primary(Y/N)

c.         Secondary(Y/N)

d.College (Y/N)

e.University(Y/N)

15.     AnganwadiCentre(Y/N) - 07( 02 in Govt. building & 05in private building)

a.        (govt/private)

b.Totalchildrenenrolled -179

15.     AmritSarovars–details,location,condition- NA

16.     Governmentoffices-details,whetherfunctionalornot – Pyt. Ghar&Pyt. Secy. Office

17.     Rationshop(Y/N)

18.      Placesoftourismimportance–names,littledetailsonhistorical/culturalimportance-. Ziaratsainmera baba

19.      Villageheritagesites/treks-names,littledetailson historical/culturalimportance

20.     VLWOffice (Y/N)

21.     PrimaryHealthcareCentre(Y/N),

22.     ListofIncompleteBuildings-names,yearofconstruction – PatwarKhana(2012)

23.     ListofUnderutilizedBuildings-names

DAY1-ACTIVITIES

AGENDA2:

DIFFERENTINSTITUTIONS/INFRASTRUCTUREPROJECTSTOBEVISITED

| AMRITSAROVARS | Visit,verify | COMMENTS |
| --- | --- | --- |
| KhidmatCentres | Create/Generateawarenesson225schemes particularlyG2CschemsAapkiZaminAapkiNigrani, Beams,Janbhagidari,DigitalJ&K | Not Available, member of the Panchayat requested for immediate sanctioning of Khidmat Centre |
| JKB/PSBcounters/outlets | a)Statusofcounterb)Numberofvisitors | Not Available |
| Incompletebuildings/pro- jects | Verify whetheridentificationandredistributiondone | Patwarkhana, presently the work is being conducted out in Bandichechian (N T Office) |
| PDS | Visit,evaluate,onlinestatus | Not Available |
| PHC | Visit-evaluate,statusofstaff,equipmentandquality | Not Available |
| Youthclubs | Meet,interact,seeksuggestions | Sports kit distributed earlier, requested for playground at central place of Pyt. |
| SHG | Meet,identifyproblems,seeksuggestions | Not Available |
| PMAY | Inspect,Inaugurate | Houses under the scheme built requires soil/clay ( to avoid the damages during cross border shelling |
| Myschool,myprideprogress;schools-water, toilets,staff | Visit,checkforwater,electricity,sanitation,meetstudentsandstaff | Two School Requires Water &Electricity Connection |
| SwachhSBM | Evaluate | Money allocated per structure be increased to Rs. 25000/- |
| Panchayatplayground, SportskitsdistributionVillagegames | Ensure,verify.Participateinatleastonegameintheplayground |  |
| HarGaonHariyali, Planta- tiondrive | Evaluatestatus,feedback | Need One or Two plantation drive |
| Villageculturalevent Dangal/Haat/Mela | Participatein;ensurethatitisheld | Temporarily managed in private shops |
| Exhibitionofschemes | EnsurethateverydepartmentparticipatesandthatitcontinuesfortheentiredurationofB2V | Yes |
| JalJeewanMissionverifica- tion- WSS/JSD Electricitysupply | Verify | Poles installed, Transformer installed, requirement of nine poles |

DAY1-ACTIVITIES

AGENDA3:SATURATEJANBHIYAN

DELIVERABLESANDRECORDDEFICIENCIESIFANY(INSERTDELIVERABLESLISTHEREASPERGADFORMAT

DAY1-ACTIVITIES

AGENDA4:

SELFEMPLOYMENTACTIVITIES

EnsureSelfemploymentactivitiesforyouth,distributeemploymentlettersforpeopleselectedundervarioussocialschemes(15ISTHETARGETPERPANCHAYAT): Under integrated Dairy Dev. Scheme &MadhuKranti 03 units were started creating employment opportunities to around 07 people.

Numberofcasesindifferentcategoriessanctioned: Detailsofthebanksanctioningit:

Totalamountinvolved:

DAY1ACTIVITIES

AGENDA5

Intheevening,holdinformalmeetingswithseniorcitizens,govtemployees,retdemployees,youthclubandothercitizenswhoareenrolledoncollege/universityandhavediscussiononGandhiKatha,Nasha MuktAbhiyan,corruptionfreegovernance,doublingfarmersincomeandrecordtheproceedings

DAY2

- NoofIndividualCompostPitsconstructed-52

- NoofIndividualSoakPitsconstructed-290

V.          No.ofBiodiversitymanagementcommitteemeetingsheld:01/02 training held

VI.         IsthenameofSarpanchdisplayedoncitizeninformationboardsofallRD&PRschemes:Yes/No

VII.       AreSarpanchsbeinginvolvedinstart/inaugurationofactivities:Yes/No

VIII.      WhethersubjectshavebeenassignedbytheSarpanchtothePanchs:Yes/No

IX.        Whethergrievancesredressalboxisinstalled:Yes/No

X.         NoofgrievancesreceivedpertainingtoPanchayatlevel: XI.       NoofgrievancesdisposedofatPanchayatlevel:Alldispute resolved at local level

XII.       WhethertheSarpanch/PanchayatSecretaryhavedigitalsignatures:Yes/No

XIII.      WhetherallMGNREGA/14thFCpayments arebeingmadebySarpanchthroughDigitalSignature

Certificate(DSC):Yes/No

HUMAN RESOURCEAVAILABLEATTHEPANCHAYAT LEVEL:

| SRNO. | DEPARTMENTWISESTAFF | NUMBERS |  | NAMES |
| --- | --- | --- | --- | --- |
|  |  | SANCTIONED | ACTUAL |  |
|  | Ruraldevelopmentdepartment: BDO JE GRS TA |  |  | Aijaz Ahmed Bhatt Ayaz mehmood |
|  | SCHOOLEDUCATION: TEACHER HEADMASTER ANYOTHER | 33 | 29 | Khusnood Ahmed SheriaBatool |
|  | JAL JEEVAN: |  | 09 | Kabir Din Anwar Khan |
|  | PDD: LINEMAN JE ANYOTHER |  | 03 | Jagmeet Singh MohdZamen Farooq Ahmed |
|  | FOOD&CIVILSUPPLIES |  | 01 | Zulfiqar |
|  | AGRICULTURE&ANIMALHUS- BANDARY |  | 01 | Sanjeev Sharma |
|  | SOCIALWELFARE | 04 | 04 | Noor Ahmed Shah |
|  | HEALTH: ASHA ANM AYUSHDOCTOR ALLOPATHICDOCTOR | 04 03 | 06 | Lakshmi Devi Afreen Bi Jyoti Sharma Muneera Bi Shereenakouser |
|  | ANYOTHERDEPARTMENT (Soil Conservation) |  | 01 | Rashid |

DAY2-ACTIVITIES

AGENDANO.1

DiscussionontheandassesstheprogressofdifferentschemesrelatingtothelocalizedSDGsprior-itizedforthatvillageaspertheresolutionpassedbythatGramPanchayaton21stApril22,onNational PanchayatiRajDay(Copyoftheresolutiontobetakenfromwww.jkpanchayat.inportalunderthelinkof GramSwarajMonth)

1.       SDGs AGREED FORTHATVILLAGE,TOBEIMPLEMENTED BYMARCH2024:

2.       STATUSOFWORKSUNDERTHEFOLLOWINGSCHEMES:

1      Cleanandgreenvillage

i.InitiativestakenbythePanchayatformanagingSolidandLiquidWasteNot sufficient

ii.     InitiativestakenbythePanchayatforusinggreensourcesoffuellikesolar,biogas

iii.  Hasmappingoflanduse,waterbodies,forest,slopes,wetlands,degradedforestwithintheGram

Panchayatbeendone?Yes/No.IfNo,reason,thereof

iv.    HastheClimateResiliencePlanbeendevelopedfortheGP?Yes/No

v.     StepstakenbytheGramSabhaabouttheclimatechangemitigationfactorslikereducingenergy consumption,usageoffossilfuels,plastics,non-renewablebuildingmaterialsandalsotopromote measureslikeplantingoftrees,conservingforests,usageofgoodagriculturalpracticeslikedrip irrigation,waterconservationmeasuresandconservationofwetlands.- plantation drive are being done periodically

vi.  Whetherschoolshavestartedsegregatingwaste- Nil

vii. Whetherschoolshavetheirowncompost/soakagepitsforsolid/liquidwastemanagement Not seen

2     Healthyvillage

i)    AremeetingsrelatedtoVillageHealthandSanitationCommitteebeingheldregularly?-Yes

ii)   DoalltheeligibleindividualsbeenprovidedtheGoldenCard?-Maximumdone around 85% saturation

iii)  ArealltheChildrenbeingimmunizedaspertheSchedulerecommendedbyGovt.ofIndia?-Yes

iv)  ArealltheeligibleindividualsbeenvaccinatedagainstCOVID-19?-Yes

v)   DoesGramPanchayatensurethatallpregnantwomenaregettingnecessaryprenatalcheckups?--Yes

vi)  WhetherallthedeliverieswereInstitutionalizedorconductedbytrainedMidwives?-Institutionalized

3     Watersufficientvillage

i)    DoalltheIHHsintheGramPanchayathavewaterpipelineconnections?-No

ii)   WhetherGramPanchayathastakenstepsforgreywatermanagement.IfYespleasespecify iii)  DoalltheIHHsintheGramPanchayathavetoilets?-Not 97% (Saturation)

iv)  ArealltheIHHstoiletsfunctionalornot?

v)   DoalltheSchools/Anganwadicentershaveatoiletfacilityornot?-Not

vi)  Areallthetoiletsintheschools/Aaganwadifunctionalornot?-Not

vii) WhetherGramPachachayatBhawanhasseparatetoiletsforwomenornot?-Not

-

4      ChildFriendlyvillage

i)	Doallthechildrenundertheageof0-6yearsbeenenrolledintheAnganwadicentersforpre- schooling?Yes/NO –(Further efforts are required to achieve the result)

ii)    HowmanyBalSabha’swereorganizedintheGramPanchayat. -. 02

iii)  WhethertheissuesraisedbyBalSabhaareaddressedduringtheGramSabha. Yes/NO

iv)	WhetherGramPanchayatistrackingthedatarelatedtodropoutchildrenandchildrenwithirregular attendance?Yes/NO.

v)   DoalltheschoolsundertheGramPanchayathaveseparatetoiletsforgirlsandboys?Yes/No

5      Villagewithgoodgovernance

i)    IsCSClocatedintheGramPanchayatBhawanornot?- Not

ii)	IsthelistofbeneficiariesrelatedtotheSchemes/ProgramsdisplayedontheGrampanchayatwallor not? - Yes

iii)  DoestheGramPanchayathasitsbuildingornot? - Yes

iv)  IstheGramPanchayatofficefunctionalornot?-. Yes

v)   Aretheactivities approved undertheHalqaPanchayatDevelopmentPlandisplayedontheGram

Panchayatwallornot?- Yes

vi)  IsSocialAuditofearlierSchemes/Programscarriedoutornot?- Yes

6      Povertyfreeandenhancedlivelihoodvillage

i)    HasGramPanchayatdevelopedanycriteriafortheidentificationofthepoor?Yes/Noifyesspecify ii)   HavealltheeligiblehouseholdsregisteredinPDSornot?- Yes

iii)	HasGramPanchayatprovidedspaceforSelf-helpGroupsinPanchyatGharforholdingmeetings  or not?- No

iv)  HavealltheeligiblehouseholdsbeenregisteredforPensionornot?-Yes

v)   HasGramPanchayatfacilitatedYouthforSkillEnhancementCoursesandPlacement? - NA

vi)  HasJobCardsbeendistributedtoalltheeligibleindividualsunderMGNREGA?-. Yes

vii) HasGramPanchayatfacilitatedSHGsforBankAccountLinkages?

7     Sociallysecuredvillage

i)    WhetherGramPanchayatismaintainingdatarelatedtoDifferentlyAbledPeople? – yes,presentlyaround 10 people are differently abled.

ii)   IsGramPanchayatOfficeDisabledFriendlyornot?

iii)	Areprovisionsfora separate BudgetundertheResourceEnvelopeforWomenandChildrenmadeornot?- NA

iv)	DoalltheSchools intheGramPanchayathavefacilitiesforDifferentlyAbledChildrenliketoilets, barrier-freeaccess,etc.,ornot?- Not

v)   Arealltheeligibleindividualsaregettingpensions,likeoldagepension,widowpension,etc? - Yes

vi)  ArealltheeligiblehouseholdsgettingbenefitsfromIAYornot?

-Yes

8      EngenderedDevelopmentinVillage

i)    HowmanyMahilaSabha’swereorganizedintheGramPanchayat-Not sufficient information available

ii)	WhetherSHGsfederationshavebeenprovidedspaceformeetingsinthePanchayatBhawan(Yes/ No)

iii)  WhetherGPshavetakenstepsforincreasingwomen’sparticipationinGramSabha(Yes/No)

iv)  NumberofwomenbeneficiariesheadedhouseholdscoveredunderPDS

system - 25

v)   Numberofbeneficiaries(outoftotaleligiblepopulation)receivingsocialprotectionbenefitsunder

PradhanMantriMatritvaVandanaYojana………………….

9    Self-sufficientinfrastructureinthevillage

i.	WhetherGPhasaCommunityHallwithaccesstoelectricity,furniture,watersupply, toilet NA

ii.     WhethertheDisastermanagementplanisavailableattheGPLevel(Yes/No)

iii.  Whetherchild-friendlyparkwithrequiredfacilitiesisavailableinGP(Yes/No)

iv.    WhethertheGPhaseasyaccesstoGodownforstorage(Yes/No)

v.     Whetherstreetlightsareprovidedinpublicplacesforensuringsafety(Yes/No)

DAY2ACTIVITIES

AGENDANO.2

SensitizevillageresidentsaboutmyScheme”portal(myscheme.in)whichincludesinformationaboutall theschemesbeingrunbyCentral/State/UT govtacrossthecountry

(SchemeMaterialavailablefromhttps://jkpanchayat.in/b2v4.php)

DAY2ACTIVITIES

AGENDANO.3

HoldmeetingoftheBiodiversityManagementCommitteestodeliberate on issues pertaining to conserva- tion of biodiversity and sustainable utilization of biological resources. He should check People Biodiversity register(PBR)ofthatpanchayatandreviewifBiodiversityManagementCommittee constituted for that panchayat is holding minimum 4 meetings in a year and meeting once in every 3 months (RoleofBMCavailableathttps://jkpanchayat.in/b2v4.php)

COMMITTEEMEMBERS PRESENT

BIODIVERSITYREGISTERPHOTOS

PAST 4MEETINGDETAILS-DATES,MINUTESPHOTOS

DAY2ACTIVITIES

AGENDA4

Visitingofficershallalsoplanandconductpanchayatlevelconvergencemeeting  ofalldepartmentsandprepareVillagedevelopmentplanforvillage,inconsultancywithGrampanchayat,discussitingram sabhaandgetitapproved.

(GPDPformatavailableonhttps://jkpanchayat.in/b2v4.php)

InadditionGPDPplanshallalsoinclude:

           Touristplaceswhichneedtobedeveloped

           Specificproductwhichneedstobedeveloped

           Tourism-homestays

	20candidatesfortrainingunderHimayatschemealongwithtradeinwhich trainingistobegiven

DAY2ACTIVITIES

AGENDA5

Ensuresaturationoffollowingschemesandgivestatus:

| NAMEOFTHESCHEME | TOTALELIGIBLE BENEFICIARIESIN THE VILLAGE | TOTALBENEFICIARIESWHO AVAILEDTHEBENEFITSOFTHESCHEME | REASONSFOR PENDENCY |
| --- | --- | --- | --- |
| GoldenHealthCardunder AyushmanBharat | 2243 | 2193 | Aadhar card not available for children |
| Jananisurakshayojana |  |  |  |
| OLDAGEpension |  | 36 | Almost saturated |
| Widowpension |  | 27 | Almost saturated |
| Disabilitypension |  | 06 | Almost saturated |
| Domicilecertificate |  |  | Almost saturated (95%) |
| Kisancreditcard |  |  |  |
| PMkisansammannidhi | 263 |  | All those who applied for the scheme for the benefit |

| Landpassbook | 680( Household) | 08 | 08 No. Of land passbook issued during the programme |
| --- | --- | --- | --- |
| Registrationofvillageven- dorsonGEMportal |  |  |  |
| Registrationofvillagecon- tractorsonjktendersportal |  |  |  |
| Registrationofvillagecon- tractorsonPWDportal |  |  |  |
| Incompletebuildings/pro- jects |  |  | Patwarkhana P/s kandranw.no. 09 Anganwadiward no. 03 |

DAY2ACTIVITIES

AGENDA6

NASHAMUKTABHIYAN

1.       Whethergramsabharesolutionpassed  - Yes

2.       Detailsofactivitiesconducted

3.       WhetherallactivitiesandGSresolutionuploadedonjkpanchayats.inportal

4.       Howmanydrugaddictsinthevillage-. 00

5.       WhetherreportedtotheDeputyCommissioner

6.       Howmanyregisteredforrehabilitationundergovernmentprogramme

DAY2ACTIVITIES

AGENDA7

SOCIALAUDIT

Conductsocialauditofatleast5workseachunderfollowingschemes:

| NAMEOFTHE SCHEME | DETAILSOFTHE WORKS | YEAROFWORK APPROVAL | AMOUNT APPROVED FORTHEWORK | WHETHER WORKEXECUTED SATISFACTORILY | GEO- TAGGED PHOTOS | ANY GRIEVANCE RECORDED RELATINGTOTHAT WORK |
| --- | --- | --- | --- | --- | --- | --- |
| MGNREGA | Land leveling G.yard | 2021-22 | 1.80 lacs | Satisfactorily |  |  |
| PMAY | Lal din id- JK1072408 | 2020-21 | 1.30 lacs | Satisfactorily |  |  |
| IHHL UNDERSBM-G | Razia Begum id- 2002277114 | 2022-23 | 0.12 lacs | Satisfactorily |  |  |
| CSCUNDER SBMG |  |  |  |  |  |  |
| AMRIT SAROVARS |  |  |  |  |  |  |

DAY2ACTIVITIES

AGENDA8

MAHILASABHA

Totalwomeninthevillageabovetheageof18- 631

Totalattended- 08

Proceedings:

(Plinsertpointerstobediscussedthere–referpalliproceedings)

DAY2ACTIVITIES

AGENDA9

BALSABHA

Holdabalsabhaandrecordproceedings

Totalchildreninthevillageabovetheageof….. Totalattended

Proceedings:

(Plinsertpointerstobediscussedthere–referpalliproceedings)

DAY2ACTIVITIES

AGENDA10

INAUGURATIONS

| SR NO. | ASSETS/ACTIVITIES INAUGRATED | STATUSOFTHEASSET/AC- TIVITIES(NUMBER,OTHER DETAILS) | GEO-TAGGED PHOTOS |
| --- | --- | --- | --- |
|  | VILLAGEHAATunderJKSRLM(SUN- DAYMARKET) | Village Haat is being managed in rented shops |  |
|  | PMAYhousesifanyreadyforinaugra- tion | Inauguration done, progress satisfactory |  |
|  | Swachhgramprojects-segregation shedsetc |  |  |
|  | Amritsarovars |  |  |
|  | Sportskits | Distributed among members of Youth Club |  |
|  | Villageculturalevents |  |  |
|  | JJMassets/projects |  |  |
|  | Anyothertobeidentifiedatdistrictlevel |  |  |

FOLLOWUPOF(B2V1,B2V2&B2V3):

(Prefilledexcelsheettobetakenfromdistrictlevel/andalsotobedownloaded

fromwww.jkpanchayat.in)

| S.NO. | Particulars | Actiontaken | Remarks# |
| --- | --- | --- | --- |
| I. UrgentPublicRequirements/Demands-B2V1 |  |  |  |
| 1 |  |  |  |
| 2 |  |  |  |
| 3 |  |  |  |
| 4 |  |  |  |
| 5 |  |  |  |
| 6 |  |  |  |
| 7 |  |  |  |
| II. UrgentPublicRequirements/Demands-B2V2 |  |  |  |
| 1 |  |  |  |
| 2 |  |  |  |
| 3 |  |  |  |
| 4 |  |  |  |
| 5 |  |  |  |
| 6 |  |  |  |
| 7 |  |  |  |
| S.NO. | Particulars | Actiontaken | Remarks# |
| III. MajorProblems–B2V1 |  |  |  |
| 1 | Problem of border fencing area of one Pyt. Divided into two parts | No action taken yet |  |
| 2 | Slow progress on water scheme | No action taken yet |  |
| 3 |  |  |  |

| 4 |  |  |  |
| --- | --- | --- | --- |
| 5 |  |  |  |
| IV. MajorProblems-B2V2 |  |  |  |
| 1 | Work done liability under MGNREGA | No action taken yet |  |
| 2 | Road from Qasba to Mandhar | Action taken in this regard |  |
| 3 | Compensation of road from Qasba to Mandhar | Action taken in this regard |  |
| 4 |  |  |  |
| 5 |  |  |  |
| V. MajorProblems-B2V3 |  |  |  |
| 1 |  |  |  |
| 2 |  |  |  |
| 3 |  |  |  |
| 4 |  |  |  |
| 5 |  |  |  |
| VI. MajorComplaints-B2V1 |  |  |  |
| 1 | No problem was reported during the phase 1st |  |  |
| 2 |  |  |  |
| 3 |  |  |  |
| VII. MajorComplaints-B2V2 |  |  |  |
| 1 | Work done liability of MGNREGA | No action taken in this regard | Still the people facing the same problem |
| 2 |  |  |  |
| 3 |  |  |  |
| VIII. MajorComplaints-B2V3 |  |  |  |
| 1 | Pending liability under Bunker construction | No action taken |  |
| 2 | Restoration of canal Land sliding near Ziarat | No action taken No action taken |  |
| 3 |  |  |  |

DepartmentofRuralDevelompentandPanchayatiRaj

GovernmentofJammu&Kashmir