**BACK TO VILLAGE- PHASE IV (15TH OCTOBER TO 3RD NOVEMBER )**

**KEY FEATURES**

* Deputy Commissioners to lead the initiative
* Rural development Department to be the nodal department
* Planning Development & Monitoring department and IT to be the support departments

**ACTIONS AND TIMELINES**

|  |  |  |  |
| --- | --- | --- | --- |
| **ACTION** | **RESPONSIBILITY** | **LATEST BY** | **REMARKS** |
| Jan abhiyan | All departments | Oct 15 -25th | Going on |
| Deputation of Sectt staff/HoDs | GAD | Oct 14 | Done |
| Deployment of Staff to Panchayats and serving of orders on deployed officers | DCs | Oct 25 | DCs will deploy senior level staff from the districts. Strict action to be taken against absentations. No exemptions to be given |
| Training of district trainors on B2V4 | RDD | Oct 26 |  |
| Training of visiting officers | DCs | Oct 27 |  |
| Field Visits to be completed by | Visiting Officers | Nov 3 | DCs to supervise and ensure that each Panchayat is visited within the period specified |
| Data of B2V4 to be uploaded by | Visiting Officers | Nov 10 | DCs to supervise and ensure that data of all Panchayats is uploaded by the visiting officer within the period specified |

**INSTRUCTIONS FOR THE VISITING OFFICER (DAY WISE)**

|  |  |  |
| --- | --- | --- |
| **DATE** | **INSTRUCTIONS** | **ACTION POINTS** |
| Day 0 | Meeting with deputy commissioner and his/her team | 1. Take print outs of filled booklets of B2V1, B2V2 and B2V3 from [www.jkpanchayat.in](http://www.jkpanchayat.in) 2. Also take print outs of the summarized excel sheets of the previous phases from [www.jkpanchayat.in](http://www.jkpanchayat.in) 3. Collect ATRs on issues raised during previous 3 phases from the office of Deputy Commissioner (Planning deptt) 4. Take prints of blank 2 booklets of B2V4 from [www.jkpanchayat.in](http://www.jkpanchayat.in) 5. Take plans for 2 previous years and ATRs from the planning deptt 6. Complete trainings on different components of B2V4 being organized by respective Deputy Commissioners 7. Collect List of new works started/ ongoing/ completed during the previous and current Financial year under the following heads:  * PRI grants * District Plan * UT plan * MGNREGA * Other schemes of other departments * Any other work  1. Plans/ beneficiary lists:  * MGNREGA draft plan document for the year 2022-23. * List of Awaas+ beneficiaries alongwith IHHL Convergence * List of pension beneficiaries. * List of SHGs * List of agriculture scheme beneficiaries  1. Lists of beneficiaries for:  * Various certificates/ benefits to be distributed by the visiting officer. * Any other activities identified by different departments |
| Day 1 | Reach the village | 1. Ensure that all front line workers of different deptts are present. 2. Ensure exhibition by different depts. about individual beneficiary schemes 3. Inspect JKB/PSB counters/outlets 4. Participate/ensure organization of sports activity in playfield, talent hunt/cultural event/youth activity 5. Visit atleast 2 amritsarovars and get its geo tagged photos 6. Inspect Khidmat (CSC) Centres and create Generate awareness on 225 schemes particularly G2C schemes like BEAMS, Janbhagidari, AapkiZaminAapkiNigrani, Digital J&K 7. Visiting officer shall also plan and conduct panchayat level convergence meeting of all departments 8. Check effectiveness of Centrally sponsored schemes 9. Visit and inspect all government establishments including PHE, AWC, FPS, schools, etc 10. Attempt saturation of deliverable so Janabhiyan and wherever deficiencies found, lead a drive to achieve all deliverables 11. Assess effectiveness of sanitation campaign in the panchayat 12. Ensure self employment activities for 15 youth per panchayat 13. Wherever possible, distribute employment letters for people selected under various government employments 14. In the evening, hold inormal meeting with senior citizens, govt employees including retired employees, ex servicemen, youth club, and any citizens of the village who are enrolled in college/university 15. Open discussion on Nasha Mukt Abhiyan |
| Day2 | Have a meeting with all stakeholders- deptt officials and panchayat members | 1. Discussion on the and assess the progress of different schemes relating to the localized SDGs prioritized for that village as per the resolution passed by that Gram Panchayat on 21st April 22, on National Panchayti Raj Day. 2. **Sensitize village residents about myScheme” portal (myscheme.in)** which includes information about all the schemes being run by Central/ State/ UT govt across the country 3. Hold meeting of the **Biodiversity Management Committees** to deliberate on issues pertaining to conservation of biodiversity and sustainable utilization of biological resources. 4. Prepare Village development plan, in consultancy with Gram panchayat, discuss it in gram sabha and get it approved. 5. Ensure saturation of soil health card and golden health card under **Golden Health Card under Ayushman Bharat**, 6. Ensure saturation of **Old Age Pension Scheme** 7. Ensure Domicile Saturation. 8. Ensure KCC Saturation 9. Ensure saturation of land pass books 10. Ensure registration of village vendors needed for any scheme, on GEM portal 11. Ensure panchayat contractors registration 12. Encourage Panchayat members for importance of plantation drive in Panchayat under Har Gaon Hariyali 13. Ensure painting on digital J&K in panchayat ghars 14. Ensure painting on panchayat activites and CSS in panchayat ghars 15. The visiting office shall check no of kindergarten and playfields present in the panchayat for kids and students, if the infrastructure present in these are good enough. 16. Hold meeting with panchayat members to discuss about corruption menace and steps required to make J&K corruption free 17. Obtain a candid assessment about performance of various deptts including fair feedback about discrepancies in functioning 18. Check the status of Nasha Mukt Abhiyan and reporting of drug addicts to Deputy Commissioner. 19. Identify Tourist Destinations, Circuits, Theme Treks, Identify Homestays, provide support for tourism activities through Village Cooperative 20. Organize Talent Hunt at Panchayat Level 21. Conduct social audit of atleast 5 works under following schemes:     1. MGNREGA     2. PMAY     3. IHHL toilets and payments     4. CSCs     5. AMRIT SAROVARS 22. Hold a mahilasabha and a balsabha and record proceedings in the format given 23. Inaugurate village haat under JKSRLM 24. Check if youth clubs are formed in the panchayat and what activities they are engaged in 25. Organize a village level cultural event to engage panchayat members 26. Sensitize GP about E-kitab kosh an initiative of J&K Govt for empowering youths through online digital literacy |

**GENERAL INSTRUUTIONS**

1. The visiting officer shall refrain himself/ herself giving or offering any commitment on behalf of the government and shall adopt an unbiased attitude in reporting issues. As far as possible, his/her observation should be based on a fair and analytical view emerging from his/her interaction in the village.
2. He is going to the village as planning officer, not for sanctioning any works or for making any commitments.
3. While preparing village development plan, he has to ensure that, demands are prioritized and reflected under available schemes, wherever necessary the larger works are to be referred to administrative deptt under CSS/UT plans under intimation to DCs and rest of the works to DCs for reflecting it under district/CSS plans
4. His work shall be hard core planning and audit and is not a PR exercise.
5. **Focus of visit are youth, skills, self-employment, nasha mukt, bhrashtrachar mukt, Rozgar yukt J&K, besides to carry forward the activities during Jan Abhiyan and saturate them.**
6. **In addition attention may be given to the following areas**
   1. Make full use of Centrally Sponsored Schemes
   2. Saturation of individual beneficiary schemes
   3. Self-employment schemes
   4. Bank linked schemes- including departmental subsidy schemes
   5. Empowerment and transparency through digital initiatives
   6. Effectiveness of grass roots machinery –
      1. Patwari, VLW present and available
      2. Available funds utilized in public interest and as per Gram Sabha resolutions
      3. Fairness in governance
      4. CSS/Individual beneficiary schemes etc
      5. BrashtacharMukt J&K
      6. Bhai Mukt J&K
      7. NashaMukt J&K
7. The PRI members (Sarpanchs, Panchs, BDC Chairperson) shall be kept at the forefront of all activities and given due importance and the approach should be to strengthen them and make them feel empowered. He/she shall ensure that the BDC chairperson and Sarpanch/Panch are present at the time of inauguration and ceremonies.
8. The visitingofficer shall ensure that COVID protocols are strictly followed during the visits.

**BACK TO VILLAGE- PHASE IV (28TH & 29TH OCTOBER 2022 AT PANCHAYAT HALQA SHANKERPORA )**

**A) Details of Reporting Officer:**

**Name: MOHD IRSHAD WANI**

Designation: ASSISTANT EXECUTIVE ENGINEER

Department: KASHMIR POWER DISTRIBUTION CORPORATION LIMITED

Place of posting: O&MDIVISION BIJBEHARA

Mobile No: 9419412225, 9541502477

Email ID: mirshadwani@gmail.com

Home District: ANANTNAG

Dates of visit: 28-10-2022 & 29-10-2022

**B)Locational details of Panchayat: (to be pre-filled, information to be taken from the previous phases booklets/summarized excel sheet uploaded on** [**jkpanchayat.in**](http://www.jkpanchayat.in)**/b2v4.php ) (to be validated by the visiting officer and missing details to be filled)**

**Name of the Panchayat: SHANKERPORA**

Local Government Directory(LGD) code of the Panchayat: 242704

Name of CD Block: SHAHABAD

Name of Tehsil: DORU

Name of District: ANANTNAG

**C) Panchayat Profile:**

No. of revenue villages in the Panchayat: 2

No. of hamlets in the Panchayat: 7

No. of households in the Panchayat: 365

Population (approx) of the Panchayat: 2556

**Part II : (To be filled up by the Visiting Officer during his/her two day visit to the Panchayat. All Fields have to be filled by the Visiting Officer before the booklet is handed over to the DC**

**Frontline Officers/Officials who were assigned to the Panchayat for the programme:**

|  |  |  |
| --- | --- | --- |
| **Department** | **Name** | **Designation** |
| RURAL DEVELOPMENT DEPARTMENT | MANZOOR AHMED ITOO | PANCHAYAT SECRETARY |
| EDUCATION | JAVED AHMED DAR | TEACHER |
| EDUCATION | SHARIFA AKHTER | HEADMASTER |
| HEALTH | UROOJ IQBAL | FMPHW |
| HEALTH | NAZRANA AKHTER | MLHP |
| HEALTH | NAZIR AHMED MIR | HDF |
| HEALTH | MUBEENA AKHTER | ASHA |
| HEALTH | SHAHZADA AKHTER | ASHA |
| KPDCL | NAZIR AHMED DAR | LINEMAN |
| KPDCL | SHABIR AHMED BHAT | PDL |
| KPDCL | SARTAJ AHMED RATHER | PDL |
| KPDCL | FAYAZ AHMED LONE | PDL |
| KPDCL | DILAWAR HUSSAIN KHANDAY | PDL |
| KPDCL | NAZIR AHMED LONE | MR |
| AGRICULTURE | GHULAM MURTAZA GANAI | AEA |
| CA & PD | JAVAID AHMED LONE | STORE KEEPER |
| SOCIAL FORESTRY | GULZAR AHMED MALIK | J. MALI |
| ICDS | SHAHZADA AKHTER | AWW |
| ICDS | FARIDA AKHTER | AWW |
| ICDS | MEEMA AKHTER | AWW |
| ICDS | NELOFER AKHTER | AWW |
| ICDS | HAFEEZA AKHTER | AWW |
| IRRIGATION & FLOOD CONTROL | MANZOOR AHMED LONE |  |
| HANDICRAFTS | NASEEMA AKHTER | SUPERVISOR |
| FOREST DEPARTMENT | MOHAMMAD ASHRAF WANI | ORDERLY |
| HORTICULTURE | MUDASIR AHMED BHAT | HIIV |
| JAL SHAKTI DEPARTMENT | SHAHNAWAZ BHAT | LINEMAN |
| JAL SHAKTI DEPARTMENT | ARSHAD MANZOOR | LINEMAN |
| PHE MECHANICAL | ABDUL RASHID DAR | CL |
| PHE MECHANICAL | ABDUL SALAM VEEDAY | HELPER |
| DIC ANANTNAG | MOHAMMAD HUSSAIN | MTS |

**Details of absent employees vis-à-vis list furnished by the DC office: NO NOTABLE ABSENTEES**

**DAY 1 ACTIVITIES**

**AGENDA 1: PANCHAYAT ASSET REGISTER**

**Infrastructure:**

1. Panchayat Ghar Infrastructure

Govt building/private : GOVT BUILDING

New/needing repairs : NEWLY CONSTRUCTED BUT NEEDS REPAIR

1. Furniture (Y/N) : YES, SOME FURNITURE NEEDSREPLACEMENT
2. Computer/printer (Y/N) : YES
3. Internet (Y/N) : NO
4. Telephone (Y/N) : NO
5. Toilet (CSC/part of panchayat ghar) (Y/N) : YES, NEEDS REPAI & RENOVATION
6. Water (Y/N) : NO
7. Electricity (Y/N) : NO
8. Bank branch (Y/N) : YES
9. CSC (Y/N) : YES
10. Patwarkhana (Y/N ) : YES
11. Village haat (Y/N) : NO
12. Playground (Y/N) : YES
13. School-
14. Kindergarten (Y/N) : NO
15. Primary (Y/N) : NO
16. Secondary (Y/N) : 01 NO HIGH SCHOOL & 02 NO MIDDLE SCHOOLS
17. College (Y/N) : NO
18. University (Y/N) : NO
19. Anganwadi Centre (Y/N)
    1. (govt/private) : YES. HOUSED IN PRIVATE HOME
    2. Total children enrolled : 168

15. Amrit Sarovars – details, location, condition : KULAM CHINAR . IT IS IN GOOD CONDITION .CAN BE BEAUTIFIED FURTHER.GREAT POTENTIAL FOR TOURIST ATTRACTION

16. Government offices- details, whether functional or not : HEALTH WELNESS CENTRE ( HOUSED IN PRIVATE ACCOMMODATION), JAMMU & KASHMIR BANK SEMI GOVT DEPTT, SSA BUILDING AT KULAM CHINAR (NOT IN USE )

17. Ration shop (Y/N) : YES

18. Places of tourism importance – names, little details on historical/cultural importance: KULAM CHINAR . LOCATED ON ANANTNAG –DORU ROAD.

19. Village heritage sites/ treks- names, little details on historical/cultural importance : NIL

20.VLW Office (Y/N) : YES

21. Primary Healthcare Centre (Y/N), : NO. 01 NO HEALTH WELNESS CENTRE AT SHANKERPORA

22. List of Incomplete Buildings- names, year of construction : NIL

23. List of Underutilized Buildings- names SSA BUILDING AT KULAM CHINAR

**DAY 1 ACTIVITIES**

**AGENDA 2: DIFFERENT INSTITUTIONS/INFRASTRUCTURE PROJECTS TO BE VISITED**

|  |  |
| --- | --- |
| **AMRIT SAROVARS** | KULAM CHINAR . IT IS IN GOOD CONDITION .CAN BE BEAUTIFIED FURTHER.GREAT POTENTIAL FOR TOURIST ATTRACTION |
| **Khidmat Centres and 4.** | Is functional. People were made aware about majority of the flagship schemes particularly G2C schemes Aap ki Zamin Aap ki Nigrani, janbhagidari, digital J&K , but a no of schemes are yet to come in public domain. The CSC needs to be more proactive and increase his availability to people |
| **CSC counters/JKB/PSB counters/outlets** | a) Status of counter : no counter exhibited  b) Number of visitors : NIL.  Not doing enough. Poor indicators as reported by people |
| **INCOMPLETE BUILDINGS/PROJECTS** | NIL |
| **PDS** | Online status is satisfactory. But physical record not maintained properly |
| **HEALTH WELLNESS CENTRE** | Housed in a rented room which is in a dilapidated condition. The staff has arranged the medicine & equipments meticulously and are doing a good job |
| **YOUTH CLUBS** | No formal youth club. Met some youth, interacted with them and sought suggestions |
| **SHG** | NIL |
| **PMAY** | Inspected 02 no installations under PMAY and found satisfactory |
| **MY SCHOOL, MY PRIDE PROGRESS; SCHOOLS- WATER, TOILETS, STAFF** | Water and electricity facility is good. Insufficient furniture and furnishings. Sanitation is good. Toilet condition can be improved. Met students and staff and had a good healthy discussion |
| **SWACHH GRAM SBM** | SATISFACTORY |
| **PANCHAYAT PLAY GROUND**  **SPORTS KITS DISTRIBUTION**  **VILLAGE GAMES** | Ensured that a volleyball and a cricket match is played. Partly participated in both. Playground is in good condition. Carom Board with coins distributed among students. |
| **HAR GAON HARIYALI , PLANTATION DRIVE** | Needs improvement. |
| **VILLAGE CULTURAL EVENT**  **DANGAL/HAAT/MELA** | Cultural event presented by GHS Shankerpora |
| **EXHIBITION OF SCHEMES** | No department had put any scheme on exhibition. |
| **JAL JIWAN MISSION VERIFICATION- WSS/JSD**  **ELECTRICITY SUPPLY** | Verification done. One water sample test done by Field Testing Kit provided by the staff. Found OK |

**DAY 1 ACTIVITIES**

**AGENDA 3: SATURATE JAN BHIYANDELIVERABLES AND RECORD DEFICIENCIES IF ANY**

|  |  |  |
| --- | --- | --- |
| **Developmental Deliverables to be achieved during Jan Abhiyan (Preparatory phase of B2V4) w.e.f 15th October 2022 in panchayat halqa Shankerpora** | | |
| **NAME OF DEPTT** | **WORK/ DELIVERABLE** | **REMARKS** |
|
| **RDD** | ALL B2V WORKS- Document, *Verify, Complete* | DONE |
| VILLAGE HAATS –*Establish NRLM* | NO |
| **IT/CSC** | 1) CSC CAMPS- ONE PER PANCHAYAT | NOT DONE |
| 2) ALL 225 ONLINE SERVICES- Popularise, Inform | PARTLY DONE |
| 3) Beams, *Jan Bhagidari*- Assist in Access, Demonstrate, Educate, Inform, | NOT DONE |
| 4) Hoardings, Wall Paintings in all Panchayats about Digital J&K and services | PARTLY DONE |
| 5) Assist in enrollment of user services- Golden Cards, Domiciles, UDID etc | DONE |
| **JK BANK/EDI/LABOUR** | 1) SELF EMPLOYMENT TO AT LEAST 15 PERSONS/Panchayat | NOT DONE |
| 2) All INDIVIDUAL SUBSIDY SCHEMES- *Counter to be set up by banks at Panchayat level to verify, Sanction, disburse cases and also accept fresh applications* | NOT DONE |
| 3) ADHAAR SEEDING OF ALL INDIVIDUAL BENEFICIARY SCHEMES | DONE |
| **REVENUE** | 1) APKI ZAMIN APKI NIGRANI- *Inform, popularise* | DONE |
| 2) PATWAR KHANA- *Verify, Establish, Paint information and timings* | PARTLY DONE |
| 3) INHERITANCE MUTATIONS-*Complete* | NOT DONE |
| 4) LAND PASSBOOKS-generate and Issue for undisputed entries | POOR PROGESS |
| **HEALTH** | 1)PMJAY GOLDEN CARDS- *Saturate* | DONE |
| 2) *Swachh* hospitals- *clean toilets, junk free premises* | NO HOSPITAL IN THE HALQA |
| **SOCIAL WELFARE** | 1) DIVYANG CAMPS- *Hold Camps, ensure fittings* |  |
| 2) DISABILITY CARDS (UDID) – *All existing 2.5 lakhs UDID Cards to be made digital* | 1 CASE DONE |
| NOAPS/ISSS PENSIONS- Audit, Saturation of wall paintings of pension beneficiaries | DONE |
| 4) POSHAN VATIKA-ensure 100% plantation | NOT DONE |
| 5) ANEMIA CHECK UP CAMP-Conduct | 2 CAMPS |
| 6) AADHAR SEEDING- Ladli Beti beneficiaries, Aanganwadi beneficiaries | DONE |
| 7) BBBP events, at least 5 in every district | NOT DONE |
| 8) Formation of Senior Citizens club in every Panchayat | NOT DONE |
| **FOREST** | 1) GREEN J&K CAMAPAIGN – Jan Abhiyan | DONE |
| a) One Village One Beat Guard | DONE |
| b) Forest for Fodder and livelihood | NA |
| **TOURISM** | 1) TOURIST DESTINATIONS/CIRCUITS/THEMES TREKS/- Identify, Delineate, Demarcate | NO BODY FROM TOURISM PRESENT |
| 2) HOMESTAYS- Identify |
| 3) VILLAGE COOPERATIVE- Provide Support for Tourism activities |
| **CULTURE** | 1) TALENT HUNT AT PANCHAYAT LEVEL ORGANISE | NOT DONE |
| **LABOUR** | 1) e- SHRAM- Saturate | DONE |
| **SCHOOL EDUCATION** | 1) Bringing back all out of school children | PARTLY SUCCESSFUL |
| 2) MY SCHOOL MY PRIDE- | DONE |
| 3) PARENT TEACHER MEETING | DONE |
| **YOUTH AFFAIRS** | 1) Games in every Panchayat- Organise | NOT DONE |
| **POWER** | 1)   DISTRIBUTION TRANSFORMERS- |  |
| *a) Unique no Checked,* | DONE |
| *b)*   DTS identified with low oil and top up, |
| *c)*   DTs identifiedwith load imbalance, |
| *d)   No. of standard fusesr eplaced with non standard fuses,* |
| *e)*   identify No. of DTs identified without earthing/ ensured proper earthing |
| *f)*    No of foliage around DTsremoved |
| 2)   No. of cases of electrical accident claims pending to be resolved/ disbursed | NIL |
| **CAPD** | 1) SHIFT TO RATION CARD MANGEMENT SYSTEM (RCMS) | DONE |
| 2) 100% GRIEVANCE REDRESSAL | DONE |
|  |  |  |
| **COOPERATIVES** | 1) 25000 COOPERATIVE MEMBERS TO BE TRAINED | NOT DONE |
| **SCIENCE & TECHNOLOGY** | 1) Reach out to 10000 farmers for PM KUSUM SCHEME | NOT DONE |
| **PWD** | 1) 100% ONLINE PAYMENTS WITH NO MANUAL INTERFACE-Implement | DONE |
| **ARI & TRAININGS** | 1) INSPECTION OF 100 OFFICES AT BLOCK LEVEL- Evaluate quality of work and grievance disposal, record keeping, inventory management |  |
| **JAL SHAKTI** | 1) ACTIVATE ALL PANI SAMITIS sensitise the local community/Gram Panchayats/Pani Samitis of their role and responsibilities in Planning, Implementation and Monitoring of JJM 2. 2) Awareness generation regarding mechanism for Water Quality and testing of Water quality using Field | 2 MEETINGS HELD |
| Testing Kits (FTKs) as per JJM guidelines | DONE |
|  |  |
| **AGRICULTURE & ALLIED SECTORS** | 1) Individual beneficiary schemes including bank loan schemes- Accelerate, Saturate | NOT DONE |
| 2) Soil Health Cards- Saturate | DONE |
| 3) 5 KISAN MELAS- Organise | NOT DONE IN THIS HALQA |
| **PUBLIC GRIEVANCE** | 1) PERCEPTION OF DEPARTMENTS AMONG PUBLIC- Assess | SATISFACTORY |
| 2) 50 KEY ISSUES OF CONCERN LEADING TO GRIEVANCES- IDENTIFY | PUBLIC GRIEVANCE MAINLY RELATED TO ROAD CONDITION , QUALITY AND SUPPLY OF WATER, POWER SUPPLY AND NARROW LINK ROADS |

**DAY 1 ACTIVITIES**

**AGENDA 4:**

**SELF EMPLOYMENT ACTIVITIES**

**Ensure Self-employment activities for youth, distribute employment letters for people selected under various social schemes:**

**Number of cases in different categories sanctioned :** Name of 12 youth proposed for enlistment for desired loan and Branch Manager JKB Shankerpora requested to facilitate the process.

**Details of the bank sanctioning it :** Jammu & Kashmir Bank Shankerpora.

**Total amount involved :** Will be conveyed post sanctioning of loan.

**DAY 1 ACTIVITIES**

**AGENDA 5**

* In the evening, hold informal meetings with senior citizens , govt employees, retd employees , youth club and other citizens who are enrolled on college/university and have discussion on Nasha Mukt Abhiyan, corruption free governance, doubling farmers income and record their suggestions : **DONE and suggestions/demands noted and prioritized.**

**DAY 2**

**Check functionality of panchayats (data filled in the excel sheet and B2V1-3 reports to be validated and gaps to be filled) insert the link**

1. Maintenance of records: Gram Sabha registers(7 registers)
2. Social Audit Committee details : No social audit committee
3. Swachta Status – Village is ODF or ODF + : ODF
4. *MGNREGA/SBM convergence*
   1. *No of Individual Compost Pits constructed :More than 115*
   2. *No of Individual Soak Pits constructed :09*
5. No. of Biodiversity management committee meetings held: 02
6. Is the name of Sarpanch displayed oncitizen information boards of all RD&PR schemes :No
7. Are Sarpanchs being involved in start/inauguration of activities:Yes
8. Whether subjects have been assigned by the Sarpanch to the Panchs: Yes
9. Whether grievances redressal box isinstalled:Yes
10. No of grievances received pertaining to Panchayat level:06
11. No of grievances disposed of at Panchayat level:06
12. Whether the Sarpanch/Panchayat Secretary have digital signatures: Yes
13. Whether all MGNREGA/ 14th FC payments are being made by Sarpanch through Digital Signature Certificate (DSC): Yes

**HUMAN RESOURCE AVAILABLE AT THE PANCHAYAT LEVEL:**

|  |  |  |  |  |
| --- | --- | --- | --- | --- |
| **SNO** | **DEPARTMENT WISE STAFF** | **NUMBERS** | | **NAMES** |
|  |  | **SANCTIONED** | **ACTUAL** |  |
| 1 | **Rural Development Department:**  **BDO**  **JE**  **GRS**  **TA** | 1  1  1  1 | 1  1  1  1 | MUZFAR AHMED MALIK  ABDUL REHMAN WANI  JAVED AHMED SHAH  ZAHID RASHID |
| 2 | **SCHOOL EDUCATION:**  **Teacher**  **Head master**  **Any other** | 8  1  0 | 8  1  0 | Mtr Sharifa Akhter , Mansoor Ahmed Itoo , Kulvir Singh , Shabnam Mehmood , Shabir Ahmed Urfan , Jan Irfit Javeed , Nisar Ahmed Lone , Javed ahmed Dar , Mehraj Ahmed Ganai |
| 3 | **JAL JEEVAN** | 2 | 2 | ABDUL RASHID DAR  ABDUL SALAM VEEDAY |
| 4 | **PDD:**  **LINEMAN**  **JE**  **Any other** | NA | NA | NAZIR AHMED DAR  SHABIR AHMED BHAT  SARTAJ AHMED RATHER  FAYAZ AHMED LONE MR |
| 5 | **FOOD & CIVIL SUPPLIES** | 1 | 1 | JAVED AHMED LONE |
| 6 | **AGRICULTURE & ANIMAL HUSBANDARY** | NA | NA | GHULAM MURTAZA GANAI |
| 7 | **SOCIAL WELFARE** | ---- | ----- | ----- |
| 8 | **HEALTH:**  **ASHA**  **ANM**  **AYUSH DOCTOR**  **ALLOPATHIC DOCTOR** | 0  0 | 0  0 | HAFEEZA AKHTER, MUBEENA AKHTER  NAZRANA AKHTER MLHP  UROOJ IQBAL FMPHW |
| 9 | **ICDS** | NA | NA | SHAHZADA AKHTER, FARIDA AKHTER ,NELOFAR AKHTER , MEEMA AKHTER |

**DAY 2 ACTIVITIES**

**AGENDA NO.1** Discussion on the and assess the progress of different schemes relating to the localized SDGs prioritized for that village as per the resolution passed by that Gram Panchayat on 21st April 22, on National PanchayatiRaj Day **(Copy of the resolution to be taken from** [**www.jkpanchayat.in**](http://www.jkpanchayat.in) **portal under the link of Gram Swaraj Month)**

1. SDGs AGREED FOR THAT VILLAGE, TO BE IMPLEMENTED BY MARCH2024: -----
2. STATUS OF WORKS UNDER THE FOLLOWING SCHEMES:

1 **Clean and green village**

1. Initiatives taken by the Panchayat for managing Solid and Liquid Waste : PITS CONSTRUCTED FOR LIQUID WASTE MANAGEMENT.
2. Initiatives taken by the Panchayat for using green sources of fuel like solar, biogas NO MAJOR BREAKTHROUGH. A LOT NEEDS TO BE DONE.
3. Has mapping of land use, water bodies, forest, slopes, wet lands, degraded forest within the Gram Panchayat been done? Yes/No. If No, reason, thereof : NO
4. Has the Climate Resilience Plan been developed for the GP? No
5. Steps taken by the Gram Sabha about the climate change mitigation factors like reducing energy consumption, usage of fossil fuels, plastics, non-renewable building materials and also to promote measures like planting of trees, conserving forests, usage of good agricultural practices like drip irrigation, water conservation measures and conservation of wetlands : NIL
6. Whether schools have started segregating waste : YES
7. Whether schools have their own compost/soakage pits for solid/liquid waste management : YES
8. **Healthy village**
9. Are meetings related to Village Health and Sanitation Committee being held regularly? YES , MONTHLY
10. Do all the eligible individuals been provided the Golden Card? YES
11. Are all the Children being immunized as per the Schedule recommended by Govt. of India? YES
12. Are all the eligible individuals been vaccinated against COVID-19? YES
13. Does Gram Panchayat ensure that all pregnant women are getting necessary prenatal checkups? YES
14. Whether all the deliveries were Institutionalized or conducted by trained Midwives? YES . ALL DELIVERIES ARE INSTITUTIONALISED.

**3 Water sufficient village**

1. Do all the IHHs in the Gram Panchayat have water pipeline connections? ALMOST HALF THE HOUSEHOLDS
2. Whether Gram Panchayat has taken steps for grey water management. PARTLY. THROUGH SOAK PITS
3. Do all the IHHs in the Gram Panchayat have toilets? ALMOST ALL HAVE THEM INSIDE AND SOME HAVE THEM OITSIDE.
4. Are all the IHHs toilets functional or not? YES
5. Do all the Schools/Anganwadi centers have a toilet facility or not? YES
6. Are all the toilets in the schools/Aaganwadi functional or not? FUNCTIONAL BUT NEED REPAIR
7. Whether Gram Pachachayat Bhawan has separate toilets for women or not? NO

**4 Child Friendly village**

1. Do all the children under the age of 0-6 years been enrolled in the Anganwadi centers for pre-schooling? Yes
2. How many Bal Sabha’s were organized in the Gram Panchayat: 01 ORGANISED TODAY
3. Whether the issues raised by Bal Sabha are addressed during the Gram Sabha. WILL BE ENSURED
4. Whether Gram Panchayat is tracking the data related to dropout children and children with irregular attendance? Yes/NO.
5. Do all the schools under the Gram Panchayat have separate toilets for girls and boys? Yes/No

**5 Village with good governance**

1. Is CSC located in the Gram Panchayat Bhawan or not? YES
2. Is the list of beneficiaries related to the Schemes/Programs displayed on the Gram panchayat wall or not? NO. PIB INSTALLED
3. Does the Gram Panchayat has its building or not? YES. OWN BUILDING
4. Is the Gram Panchayat office functional or not? YES
5. Are the activities approved under the Halqa Panchayat Development Plan displayed on the Gram Panchayat wall or not? YES
6. Is Social Audit of earlier Schemes/Programs carried out or not? NO

**6 Poverty free and enhanced livelihood village**

1. Has Gram Panchayat developed any criteria for the identification of the poor? No
2. Have all the eligible households registered in PDS or not? YES . REGISTERED
3. Has Gram Panchayat provided space for Self-help Groups in Panchyat Ghar for holding meetings or not? NO SELF HELP GROUP HAS COME FORWARD SO FAR. AS & WHEN THEY COME FORWARD SPACE WILL BE PROVIDED TO THEM.
4. Have all the eligible households been registered for Pension or not? 100%
5. Has Gram Panchayat facilitated Youth for Skill Enhancement Courses and Placement? NO
6. Has Job Cards been distributed to all the eligible individuals under MGNREGA? YES
7. Has Gram Panchayat facilitated SHGs for Bank Account Linkages? NO SELF HELP GROUP REGISTERED

**7 Socially secured village**

1. Whether Gram Panchayat is maintaining data related to Differently Abled People? YES. 09 N0
2. Is Gram Panchayat Office Disabled Friendly or not? NOT DISABLE FRIENDLY.
3. Are provisions for a separate Budget under the Resource Envelope for Women and Children made or not? NO KNOWLEDGE
4. Do all the Schools in the Gram Panchayat have facilities for Differently Abled Children like toilets, barrier-free access, etc., or not? NO
5. Are all the eligible individuals are getting pensions, like old age pension, widow pension, etc? YES
6. Are all the eligible households getting benefits from IAY or not? N0

**8 Engendered Development in Village**

* + 1. How many Mahila Sabha’s were organized in the Gram Panchayat : 02 NO.ONE HELD TODAY
    2. ii) Whether SHGs federations have been provided space for meetings in the Panchayat Bhawan : presently no Self Help Group . As & when a group is formed , they shall be provided space for holding meetings.
    3. iii) Whether GPs have taken steps for increasing women’s participation in Gram Sabha: Yes

iv) Number of women beneficiaries headed households covered under PDS system : About 20

v) Number of beneficiaries (out of total eligible population) receiving social protection benefits under Pradhan Mantri Matritva Vandana Yojana : Concerned employees had no knowledge about it

**9 Self-sufficient infrastructure in the village**

i. Whether GP has a Community Hall with access to electricity, furniture, water supply,

toilet: NO

ii. Whether the Disaster management plan is available at the GP Level (Yes/No) : NO

iii. Whether child-friendly park with required facilities is available in GP (Yes/No) :NO

iv. Whether the GP has easy access to Godown for storage (Yes/No) : NO

v. Whether street lights are provided in public places for ensuring safety (Yes/No) YES. However no of street lights to be increased

**DAY 2 ACTIVITIES**

**AGENDA NO.2**

**Sensitize village residents about myScheme” portal (myscheme.in) which includes information about all the schemes being run by Central/ State/ UT govt across the country**

**(Scheme Material available from** [**https://jkpanchayat.in/b2v4.php**](https://jkpanchayat.in/b2v4.php)**) : DONE**

**DAY 2 ACTIVITIES**

**AGENDA NO.3**

**Hold meeting of the Biodiversity Management Committees to deliberate on issues pertaining to conservation of biodiversity and sustainable utilization of biological resources. He should check People Biodiversity register (PBR) of that panchayat and review if Biodiversity Management Committee constituted for that panchayat is holding minimum 4 meetings in a year and meeting once in every 3 months(Role of BMC available at https://jkpanchayat.in/b2v4.php)**

COMMITTEE MEMBERS : **ONE MEETING HELD ON 17-05-2022. HOWEVER THAT WAS AN INTRODUCTORY MEETING.NO PHOTOS AVAILABLE AS PER THE STATEMENT OF THE CONCERNED**

PRESENT

BIODIVERSITY REGISTER PHOTOS

PAST 4 MEETING DETAILS- DATES, MINUTES PHOTOS

**DAY 2 ACTIVITIES**

**AGENDA 4**

**Visiting officer shall also plan and conduct panchayat level convergence meeting of all departments and prepare Village development plan for village, in consultancy with Gram panchayat, discuss it in gram sabha and get it approved. DONE**

**(GPDP format available on** <https://jkpanchayat.in/b2v4.php>)

In addition GPDP plan shall also include : WILL BE INCLUDED

* Tourist places which need to be developed : KULAM CHINAR
* Specific product which needs to be developed : FISH HATCHERY, SHEEP FARMING
* Tourism- home stays : NIL

**DAY 2 ACTIVITIES**

**AGENDA 5**

**Ensure saturation of following schemes and give status:**

|  |  |  |  |
| --- | --- | --- | --- |
| **NAME OF THE SCHEME** | **TOTAL ELIGIBLE BENEFICIARIES** | **BENEFICIARIES WHO AVAILED** | **REASONS FOR PENDENCY** |
| Golden Health Card under Ayushman Bharat | 1575 | 1575 | NA |
| Janani suraksha yojana | 13 | 11 | 01 DELIVERED IN PRIVATE INSTITUTION |
| OLD AGE pension | 49 | 49 |  |
| Widow pension | 26 | 26 |  |
| Disability pension | 15 | 15 |  |
| Domicile certificate | 2820 | 500 | POOR RESPONSE OF PEOPLE |
| Kisan credit card | 348 | 348 |  |
| PM kisan sammannidhi | 273 | 273 |  |
| SOIL HEALTH CARD | 348 | 348 |  |
| Land pass book | 540 | 31 | 1 MALFUNCTIONING OF WEBSITE  2, NON AVAILABILITY OF FUNDS FOR PRINTING PASSBOOKS  3, POOR RESPONSE OF PEOPLE. |
| Registration of village vendors on GEM portal | NIL | NIL |  |
| Registration of village contractors on jktenders portal | --- | --- |  |
| Registration of village contractors on PWD portal | 2 | 2 |  |
| Incomplete buildings/projects | --- | --- |  |

**DAY 2 ACTIVITIES**

**AGENDA 6**

**NASHA MUKT ABHIYAN**

1. Whether gram sabha resolution passed : YES
2. Details of activities conducted : Meeting with students, Mahila Sabha & teachers on the causes , symptoms and remedies were discussed threadbare.
3. Whether all activities and GS resolution uploaded on jkpanchayats.in portal : YES
4. How many drug addicts in the village : NIL
5. Whether reported to the Deputy Commissioner: NA
6. How many registered for rehabilitation under government programme : NONE

**DAY 2 ACTIVITIES AGENDA 7**

**SOCIAL AUDIT**

Conduct social audit of at least 5 works under following schemes:

|  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- |
| **NAME OF THE SCHEME** | **DETAILS OF THE WORKS** | **YEAR OF WORK APPROVAL** | **AMOUNT APPROVED( Rs)** | **WHETHER WORK EXECUTED SATISFACTORILY** | **GEO-TAGGED PHOTOS** | **ANY GRIEVANCE RECORDED RELATING TO THAT WORK** |
| MGNREGA | Bodhy Ladh from Diversion to onwards | 2020-21 | 199935 | YES | Done | NIL |
| PMAY |  |  |  |  |  |  |
| IHHL UNDER SBM-G | Nazir Ahmed Mir S/O Assad-ullah . Shankerpora | 2021-22 | 12000 | YES | Done | NIL |
| CSC UNDER SBMG | CSC Near Jamia Masjid Shareef | 2019-20 | 200,000 | YES | Done | NIL |
| AMRIT SAROVARS | Desilting/Extraction of Kulam Chinar Spring | 2020-21 | 100,000 | YES | Done | Needs further Desilting |

**DAY 2 ACTIVITIES**

**AGENDA 8**

**MAHILA SABHA**

Total women in the village above the age of 18 : 579

Total attended : 16

Proceedings: **Noted Below:**

**Mahila Sabha**

Today on 29-10-2022, Saturday a Mahila Sabha was held at Shankerpora Panchayat under the Chairman Ship of Visiting Officer Mohammad Irshad Wani.

The agenda of the meeting was to conduct Mahila Sabha at Panchayat Level to aware the women of Panchayat Shankerpora about various flagship beneficial schemes of the Govt particularly Golden Health Card, Janani Suraksha Yojna, Old Age Pension, Widow pension, Disability Pension, Kisan Credit Card, Land Pass book, Rural Livelihood Mission etc. They were apprised about keeping the environment clean and the ways to make the Swachh Bharat mission a success. They were made to understand the importance of creating self help groups and to encourage local handicrafts and how to purchase/sell their products on bigger platform.

They were made aware about their role in making better families and society. They were also educated about the importance of Girl child and to bring her at par with the male child. They were told to be more proactive and be part of the governance by carrying physical verification of the works going on in the panchayat and inform about any deviation. They were told to keep an eye on the Mid-day Meal being implemented in the schools .

The meeting ended on a positive note with Mr Manzoor Ahmed Itoo Panchayat Secretary presenting the vote of Thanks

----Sd----

Visiting officer

Panchayat Shankerpora

**DAY 2 ACTIVITIES**

**AGENDA 9**

**BAL SABHA**

Hold a balsabha and record proceedings :

Total children in the village above the age of 08 years : More than 200

Total attended : 12

Proceedings: Noted Below :

**Bal Sabha**

Today on 29-10-22, Bal Sabha Meeting was held at Panchayat Shankerpora Block Shahabad

The agenda of the Bal Sabha was to create awareness among the children of Panchayat Shankerpora for ensuring good education and to motivate them to play games. Children suggested that for development of the Panchayat good roads, hospital facility, good schools, Exercise facility, playground, and a resourceful library catering to the needs of the young and small children was imperative. Visiting Officer also made the children aware about Swachh Bharat, Gram Sabha, On line facilities, Various Scholarship schemes, Easy Loan Schemes , drug abuse, and importance of maintaining good surroundings and environment. The children were also educated about the overuse of social media and gaming application and how to focus to make a good carrier and be a sincere & dutiful citizen.

----Sd---- Visiting Officer

Shankerpora Panchayat

**DAY 2 ACTIVITIES**

**AGENDA 10**

**INAUGRATIONS**

|  |  |  |  |
| --- | --- | --- | --- |
| **SR NO.** | **ASSETS /ACTIVITIES INAUGRATED** | **STATUS OF THE ASSET/ACTIVITIES (NUMBER, OTHER DETAILS)** | **GEO-TAGGED PHOTOS** |
|  | VILLAGE HAAT under JKSRLM (SUNDAY MARKET) |  |  |
|  | PMAY houses if any ready for inaugration |  |  |
|  | Swachh gram projects- segregation sheds etc |  |  |
|  | Amrit sarovars |  |  |
|  | Sports kits | One No Carom board with coins provided to students of GHS Shankerpora | Done |
|  | Village cultural events |  |  |
|  | JJM assets/projects |  |  |
|  | Any other to be identified at district level |  |  |

**FOLLOW UP OF (B2V1, B2V2 & B2V3):(Pre filled excel sheet to be taken from district level/ and also to be downloaded from www.jkpanchayat.in)**

|  |  |  |  |
| --- | --- | --- | --- |
| **S.NO.** | **Particulars** | **Action taken** | **Remarks #** |
| 1. **Urgent Public Requirements/ Demands- B2V1** | | | |
| 1 | Construction of flood protection bund on Nallah Sandran from Shankarpora to Shiv pora | No action. | No action. |
| 2 | Improvements of dilapidated link roads in Shankerpora, Joibal & KulamChinar | No action. | No action. |
| 3 | Replacement of wooden/unauthorized poles & conductor | About 10% done |  |
| 4 | Providing of Filtration Plant for PHE | No action. | Urgent requirement |
| 5 | Construction of drains in the halaqa | Partly done | All drains to be constructed |
| 6 | Upgradation of DOT Centre to PHC | Upgraded to Health wellness Centre | Can be upgraded to PHC |
| 1. **Urgent Public Requirements/ Demands- B2V2** | | | |
| 1 | Completion of balance work of protection wall of GHS Shankerpora | No action. |  |
| 2 | Macadamisation of Shankerpora – Wanpora road & bridge completion. | Done. Minimum work pending | Stabilisation and widening needed at few spots. |
| 3 | Old wooden/unauthorized poles & conductor need replacement | Not much done | May be taken up in RDSS |
| 4 | Construction of drains, tile path & review of PMAY & SBB,playground under Khelo India | Partly Done |  |
| 5 | Construction of link road from ADV road to Shangran . | No action |  |
| 6 | Establishment of Skill Development Centre, CSC,& NRLM Self Help group for women empowerment. | CSC established |  |
| 7 | Upgradation of DOT Centre to PHC | Upgraded to Health wellness Centre | Can be upgraded to PHC |
| **S.NO** | **Particulars** | **Action taken** | **Remarks** |
| 1. **Major Problems – B2V1** | | | |
| 1 | Floods due to non-availability of protection bund on Sandran Nallah |  |  |
| 2 | Condition of Main road & Link roads not good. |  |  |
| 3 | Unauthorized/unregulated extraction of bajri from Sandran Nallah | There is visible improvement | More needs to be done |
| 4 | Electric poles & wires not in good condition | Not much done | Will be taken up in RDSS |
| 5 | Link roads need widening & stabilisation | Not much done | Needs to be done. |
| 1. **Major Problems- B2V2** | | | |
| 1 | Poor power supply, wooden poles & upgradation of transformers | Some improvement. |  |
| 2 | Illegal extraction of bajri from Sandran Nallah | Partly regulated |  |
| 3 | Damage to fruit bearing trees due to snowfall | Taken up with the concerned |  |
| 4 | Non-availability of timber | Taken up with the concerned |  |
| 5 | Social Welfare Schemes are not being provided to needy and marginalized people | Taken up with the concerned |  |
| 1. **Major Problems- B2V3** | | | |
| 1 | Construction & widening of road from ADV Road to Shankerpora Village | Widening not done | Should be prioritised |
| 2 | Water shortage for irrigation purposes | Not much done |  |
| 1. **Major Complaints- B2V1** | | | |
| 1 | Encroachments & unauthorized/unregulated extraction of bajri from Sandran Nallah from Kulam Chinar to Shankerpora at various spots | Partly regulated | More needs to be done |
| 1. **Major Complaints- B2V2** | | | |
| 1 | Enrolment in Govt Schools is poor. | Improvement is there |  |
| 2 | Works of RDD not satisfactory | Works are now being monitored in a better way |  |
| 3 | Health care not catering to the people | Sufficient improvement |  |
| 1. **Major Complaints- B2V3** | | | |
| 1 | Construction & widening of road from ADV Road to Shankerpora Village | Widening not done | Should be prioritised |

**OVERALL PERCEPTION OF FUCNTIONING OF GOVERNMENT DEPARTMENTS**

BEST DEPARTMENT: HEALTH DEPARTMENT

LEAST RESPONSIVE: JAMMU & KASHMIR BANK LTD SHANKERPORA

**GENERAL ASSESSMENT OF THE VISTING OFFICER**

|  |  |
| --- | --- |
| I | Any major complaint brought to the notice of the Visiting Officer: |
|  | NON-FULFILMENT OF DEMANDS PROJECTED IN PREVIOUS Back to Village Programs |
| II | Major/ urgent public demandS that was/were reflected earlier but have not been addressed so far: |
|  | **Stabilisation, widening & macadamisation of road from Shankerpora bridge to ADV Road** . |
| III | **Overall assessment of the visit and suggestions: SATIFACTORY**  The B2V4 programme was conducted in Shankerpora village on the specified dates in a cordial & peaceful manner. The demands of the people and complaints were noted and shall be reflected in the GPDP of the Panchyat. The major demand of the people in all the previous and this Back to Village programme has been Stabilisation, widening & macadamisation of road from Shankerpora bridge to ADV Road .  There is a potential in the village for sheep farming and this needs to be encouraged and suitable plans made to augument the related Govt facilities.  ASHA workers & their AWW counterparts in ICDS complained of non payment of their genuine dues for which they have been waiting for months.  It is suggested that this programme should be held in summer to make more time available to the team for assessing the works and interaction with people. The no of key items need to be substantially reduced as I felt that 02 days are insufficient to cover all the paramaters related to a department.  People also complained of non fulfillment of demands of previous Back to Village Programs  And are not positive about any change in the resolution of their demands. |
| IV | Overall Rating of govt functioning as given by the Panchayat (Scale of 0 to 10) : **7** |
| V | Certificate from Sarpanch that the visiting officer has stayed in the panchayat for 2 days |

------Sd-------

Signature of Sarpanch Signature of the Visiting Officer

Name Sarpanch not Present Name : Mohammad Irshad Wani

Assistant Executive Engineer

O&M Division KPDCL Bijbehara

**GOVERNMENT OF JAMMU & KASHMIR**

**OFFICE OF THE BLOCK DEVELOPMENT OFFICER SHAHABAD**

CERTIFIED THAT I MOHAMMAD IRSHAD WANI CONDUCTED THE B2V4 PROGRAMME IN PANCHAYAT HALQA SHANKARPORA ON THE 28 TH AND 29TH OF OCTOBER 2022. I HAVE UPLOADED THE B2V4 BOOKLET ON THE JKPANCHAYAT PORTAL TODAY ON 02-11-2022.

**PANCHAYAT HALQA : SHANKERPORA**

**BLOCK : SHAHABAD ------ Sd -----**

MOHAMMAD IRSHAD WANI

ASSISTANT EXECUTIVE ENGINEER KPDCL

O&M DIVISION BIJBEHARA

|  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| **Gram Panchayat Development Plan of Panchayat SHANKARPORA (Mere Sapno ki Panchayat)** | | | | | |
| **Name of the concerned Department** | **Scheme** |  | **Name of the proposed work** | **Ward.no** | **TENTATIVE Cost** |
|  |
| **Department of Rural Department** | MGNREGA | 1 | Construction of Culvert on Dangje Nallah near Sikhdas Joibal |  |  |
| 2 | Construction of Retaining Waall for Bordee Lad at different spots in Kulam Chinar |  |  |
| 3 | Construction of Retaining Waall for Bote Lad from the house of Gull Mohd Ganai to Ab Rashid Ganai |  |  |
| 4 | Protection Bund for the Agricultural land of Gh Qadir Lone, Ab Gani Lone Gh Ahmed lone & shabir Ahmed Lone |  |  |
| 5 | Chain Link Fencing and tiled path for Jamia Masjid ward 1 Muqdampora Shankerpora |  |  |
| 6 | Tiled Path from the house of Parvez Ahmed Dar to Masjid Sharif at Joibal |  |  |
| 7 | Flood Protection Bund from Middle School Joibal to the house of Zahoor ahmed Dar and onwards |  |  |
| 8 | Footpath from Masjid Sharif to house of Farooq Ah Dar and others at Kulam Chinar |  |  |
| 9 | Providing of footpath and park inside Hugh school Shankerpora |  |  |
| JKRLM (UMEED) | 1 |  |  |  |
| PMAY-G (10 beneficiaries to be identified) | 1 |  |  |  |
| HIMAYAT (DDU-GKY) (20 candidates to be identified per panchayat) | 1 |  |  |  |
| SWACHH BHARAT MISSION (GRAMEEN ) | 1 |  |  |  |
| Saansad Adarsh Gram Yojana (SAGY) | 1 |  |  |  |
| **Department of Agriculture,  Cooperation & Farmers Welfare  (DAC&FW)** | Pradhan Mantri Kisan Samman Nidhi Yojana(PM-KISAN) | 1 | Rs. 2000 in three equal instalments for 273 eligible beneficieries |  | 16.38 lacs |
| Pradhan Mantri Kisan Maan Dhan Yojana(PM-KMY) | 1 | Pensionery Benefit Scheme depends upon the age of farmer (Eligibility from 18 years to 40 years of age) |  |  |
| Pradhan Mantri Annadata Aay Sanrakshan Abhiyan (PM-AASHA) |  |  |  |  |
| Pradhan Mantri Fasal BimaYojana (PMFBY) | 1 | Fasal Bhima Youjna for Oilseed @ 1.5% to be borne by Farmer |  | 6.740 |
| 2 | Fasal Bhima Youjna for Oilseed @ 1.5% to be borne by Farmer |  | 1.550 |
| Pradhan Mantri Krishi Sinchayee Yojana (PMKSY) | 1 | Bore Well on 50% subsidy Max. to Rs. 2.00 Lakh per unit (2 No.) |  | 4.00 |
| 2 | water harvesting Tank subsidy upto 1 lakh(2nos) |  | 2.00 |
| National Food Security Mission (NFSM) | 1 | irrigation pumpset 3 Nos @0.15 lakh per |  | 0.45 |
| 2 | Seed Storage Godown on 50% subsidy (2 No's.) |  | 3.00 |
| 3 | Power Sprayer on 50% subsidy (2 No.) |  | 0.48 |
| Mission for Integrated Development of Horticulture (MIDH) | 1 | Polygreen House on 75% Subsidy (3 No's.) |  | 0.54 |
| 2 | Vermicompost Unit on 50% subsidy (2 No's.) |  | 1.00 |
| 3 | Vermi Beds on 100% subsidy (10 No's) |  | 0.50 |
| Rashtriya Krishi Vikas Yojana | 1 | Power Weeder on 50% subsidy (3 No's.) |  | 1.50 |
| 2 | Brush Cutter on 50% subsidy (2 No's.) |  | 0.30 |
| 3 | Tool kit on 75% subsidy (10 No's.) |  | 0.30 |
| 4 | Tractors on 50% subsidy (02 No's) |  | 4.00 |
| Paramparag at Krishi Vikas Yojana (PKVY) | 1 |  |  |  |
| **Department of Elementary  Education** | Samagra Shiksha | 1 | Maintenance Grant for classrooms & Corridors |  | 1.0 Lakh |
| 2 | Maintenance of Toilet/Washroom points |  | 1.10 Lakh |
| 3 | Special Library grant |  | 0.5 Lakh |
| National Program for Education of Girls at Elementary Education ( NPEGEL) | 1 | Vocational Training Grant |  | 0.4 Lakh |
| 2 | Community Mobilization grant |  | 0.3 Lakh |
| 3 | Special girls toilet cum washroom block |  | 3.0 Lakh |
| Mid-day Meal Scheme | 1 | MDM utensils grant |  | 0.4 Lakh |
| 2 | Maintenance of School Kitchen Shed |  | 1.10 Lakh |
| 3 | Cooking gas connection (Cylinder & Stoves) |  | 0.10 Lakh |
| National Means-cum-Merit Scholarship Scheme (NMMSS) | 1 | Up to J&K BOSE |  | 0 |
| National Scheme of Incentive to Girls for Secondary  Education(NSIGSE) | 1 | Special grant for Exposure visits |  | 0.5 Lakh |
| 2 | Health & Hygiene grant |  | 0.6 Lakh |
| 3 | Exclusive Scholarship grant for BPL girls |  | 0.8 Lakh |
| **Deptt of social welfare** | Integrated Child Development Services (ICDS) | 1 |  |  |  |
| National Social Assistance Programme (NSAP) | 1 |  |  |  |
| POSHAN Abhiyan | 1 |  |  |  |
| **Department of Health and  Family Welfare** | Ayushman Bharat - Health and Wellness Centres (AB-HWCs) | 1 |  |  |  |
| Janani Suraksha Yojana (JSY) | 1 | Enhancement of cash benefit of the scheme from 1400 per head to Rs 2000 per head |  | 0.24 |
| Janani Shishu Suraksha Karyakram (JSSK) | 1 |  |  |  |
| Universal Immunization Programme (UIP) | 1 |  |  |  |
| Home Based Care of Newborn and Young Children | 1 | Providing of First Aid Kits to Newborn & Young Choildren |  | 0.06 |
| (HBNC/HBYC) Rashtriya Bal Swasthya Karyakram (RBSK) | 1 |  |  |  |
| National Ambulance Service (NAS) | 1 |  |  |  |
| Disease Control Programs | 1 | Extension of National Vector Borne Disease Control Programe |  |  |
| **National Disaster  Management Authority (NDMA)** | National Cyclone Risk Mitigation Project | 1 |  |  |  |
| **Department of Drinking water  and Sanitation** | Jal Jeevan Mission | 1 | Augumentation of water reservoir capacity of the existing water supply scheme located at Kulam Chinar from 38000 Gallons to 50000 Gallons |  |  |
| 2 | Construction of Water Filtration Plant for the existing water supply Scheme |  |  |
| 3 | Upgradation of the water supply pipes feeding village Joibal |  |  |
| **Department of Animal  Husbandry and Dairying** | Rashtriya Gokul Mission | 1 |  |  |  |
| National Dairy Plan-II | 1 | IDDS (Integrated Dairy Development Scheme )units at least 10 units |  |  |
| Dairy Processing and Infrastructure Development Fund | 1 |  |  |  |
| Supporting Dairy Cooperatives and Farmer Producer | 1 |  |  |  |
| National Livestock Mission | 1 | LIVESTOCK INSURANCE SCHEME WITH FREE OF COST PROVISION FOR BPL FAMILIES. |  |  |
| 2 | BACKYARD POULTRY UNITS AT LEAST 20 BENEFICIARIES |  |  |
| Livestock Census and Integrated Sample Survey | 1 |  |  |  |
| **Food  Processing Industries** | Pradhan Pantri Kisan SamapdaYojana (PMKSY) | 1 |  |  |  |
| **Skill  Development and Entrepreneurship** | Pradhan Mantri Kaushal Vikas Yojana (PMKVY) | 1 |  |  |  |
| National Apprenticeship Promotion Scheme (NAPS) | 1 |  |  |  |
| Jan Shikshan Sansthan | 1 |  |  |  |
| Skills Acquisition and Knowledge Awareness for Livelihood  Promotion (SANKALP) | 1 |  |  |  |
| Mahatma Gandhi National Fellowship (MGNF) | 1 |  |  |  |
| **Tribal Affairs** | Inclusive and sustainable growth of tribal population | 1 |  |  |  |
| **Capex Plan** | UT Capex | 1 | Widening , stabilisation and macadamisation of the road from Shankerpora Village to ADV road |  |  |
| 2 | Dedicated Govt Building for Health Wellness Centre at Shankerpora |  |  |
| 3 | construction of at least 02 no major Bore wells for irrigation Purposes |  |  |
| 4 | Providing of Sheep/Animal Husbandry Sub Centre at the Panchayat Halqa.Vacant SSA building constructed near Kulam Chinar can be used for the purpose |  |  |
| 5 | Widening , stabilisation , macadamisation and completion of balance work of the road connecting Shankerpora Village with Kulam Chinarpassing along the boundry wall of the High School |  |  |
| 6 | Removal of Encroachments on the 03 branches of Gam Kul |  |  |
| 7 | Replacement of old /deteriorated/unauthorised poles and worn out conductor at different locations in the viilage |  |  |
| 8 | Creation of 63 KVA Substation at New colony Joibal |  |  |
| 9 | Augumentation of 63 KVA Substation at Kulam chinar Spring to 100 KVA |  |  |
| District Capex | 1 | Establishment of ICT/Computer lab in the high School |  |  |
| 2 | Construction of 05 NO additional classrooms for Middle School Joibal |  |  |
| 3 | Improvement to Sandran Nallah downstream shankarpora bridge to Vessu |  |  |
| 4 | Construction of Community Hall/ Marriage hall at Shankerpora and Joibal |  |  |
| 5 | Construction of Public Park alongwith Passenger Shed at Main Stop Shankerpora on the ADV Road |  |  |
| 6 | Construction of Protection bund for RMSA Building |  |  |
|  | 7 | Completion of balance work of Basketball court |  |  |
|  | 8 | Construction of Net Practice facility inside Playfield |  |  |
|  | 9 | Construction of Link road from the house of Ab rehman lone to ab ahad Bhat at shankerpora with drain, edge wall including providing of 1.5 ft Dia 20 no Pipes |  |  |
|  | 10 | Extension of Lad from the house of Mohd Ramzan Darto Manzoor Ahmed Lone |  |  |
|  | 11 | Construction of Macro Washroom Block At High School Shankerpora |  |  |
|  | 12 | Providing of Badminton and Cricket kit to schools in the panchayat halqa |  |  |
|  |  | 13 | Widening and stabilisation of the road from Deva Mohalla to Mochi Mohalla |  |  |
|  |  | 14 | Widening and stabilisation of the road from Herpora to Goripora |  |  |
|  |  | 15 | Widening and stabilisation of the road from Kulam Chinar Main to interior of the village |  |  |
|  |  | 16 | Widening and stabilisation of the road at Wanipora |  |  |
| **PMGSY** | Road connectivity projects | 1 | Widening , stabilisation and macadamisation of the road from Shankerpora Village to Shangran via Joibal |  |  |
| **GENERAL** | | 1 | Providing of Timber Depo at Shankerpora |  |  |
| 2 | Providing of Night Chowkidar for the High School Shankerpora |  |  |

|  |  |
| --- | --- |
| **MAJOR DEMANDS OF THE PEOPLE OF PANCHAYAT HALQA SHANKARPORA BLOCK SHAHABAD** | |
|  | **Name of the proposed work** |
| **1** | Widening , stabilisation and macadamisation of the road from Shankerpora Village(Bridge) to ADV road |
| **2** | Widening , stabilisation , macadamisation and completion of balance work of the road connecting Shankerpora Village with Kulam Chinarpassing along the boundry wall of the High School |
| **3** | Dedicated Govt Building for Health Wellness Centre at Shankerpora |
| **4** | Providing of Sheep/Animal Husbandry Sub Centre at the Panchayat Halqa.Vacant SSA building constructed near Kulam Chinar can be used for the purpose |
| **5** | construction of at least 02 no major Bore wells for irrigation Purposes |
| **6** | Augumentation of water reservoir capacity of the existing water supply scheme located at Kulam Chinar from 38000 Gallons to 50000 Gallons |
| **7** | Removal of Encroachments on the 03 branches of Gam Kul |
| **8** | Construction of Water Filtration Plant for the existing water supply Scheme |
| **9** | Upgradation of the water supply pipes feeding village Joibal |
| **10** | Providing of Night Chowkidar for the High School Shankerpora |
| **11** | Replacement of old /deteriorated/unauthorised poles and worn out conductor at different locations in the panchayat |
| **12** | Establishment of ICT/Computer lab in the high School |
| **13** | Widening , stabilisation and macadamisation of the road from Shankerpora Village to Shangran via Joibal |
| **14** | Creation of 63 KVA Substation at New colony Joibal |
| **15** | Construction of 05 NO additional classrooms for Middle School Joibal |
| **16** | Construction of Community Hall/ Marriage hall at Shankerpora and Joibal |
| **17** | Maintenance of School Kitchen Shed |
| **18** | Augumentation of 63 KVA Substation at Kulam chinar Spring to 100 KVA |
| **19** | Construction of Public Park alongwith Passenger Shed at Main Stop Shankerpora on the ADV Road |
| **20** | Improvement to Sandran Nallah downstream shankarpora bridge to Vessu |
| **21** | Providing of Timber Depo at Shankerpora |
| **22** | Widening and stabilisation of the road from Deva Mohalla to Mochi Mohalla |
| **23** | Widening and stabilisation of the road from Herpora to Goripora |
| **24** | Widening and stabilisation of the road from Kulam Chinar Main to interior of the village |
| **25** | Widening and stabilisation of the road at Wanipora |
| **26** | Construction of Protection bund for RMSA Building |
| **27** | Completion of balance work of Basketball court |
| **28** | Construction of Net Practice facility inside Playfield |
| **29** | Construction of Link road from the house of Ab rehman lone to ab ahad Bhat at shankerpora with drain, edge wall including providing of 1.5 ft Dia 20 no Pipes |
| **30** | Extension of Lad from the house of Mohd Ramzan Darto Manzoor Ahmed Lone |
| **31** | Construction of Macro Washroom Block At High School Shankerpora |
| **32** | Construction of Culvert on Dangje Nallah near Sikhdas Joibal |
| **33** | Construction of Retaining Waall for Bordee Lad at different spots in Kulam Chinar |
| **34** | Construction of Retaining Waall for Bote Lad from the house of Gull Mohd Ganai to Ab Rashid Ganai |
| **35** | Protection Bund for the Agricultural land of Gh Qadir Lone, Ab Gani Lone Gh Ahmed lone & shabir Ahmed Lone |
| **36** | Chain Link Fencing and tiled path for Jamia Masjid ward 1 Muqdampora Shankerpora |
| **37** | Tiled Path from the house of Parvez Ahmed Dar to Masjid Sharif at Joibal |
| **38** | Flood Protection Bund from Middle School Joibal to the house of Zahoor ahmed Dar and onwards |
| **39** | Footpath from Masjid Sharif to house of Farooq Ah Dar and others at Kulam Chinar |
| **40** | Providing of footpath and park inside Hugh school Shankerpora |
| **41** | Providing of Badminton and Cricket kit to schools in the panchayat halqa |
|  | **MAJOR GRIEVANCE : UNAUTHORISED & UNREGULATED EXTRACTION OF THE BAJRI/SAND/STONES FROM THE SANDRAN NALLAH** |