4

15TH OCTto3RD NOV,2022

KEYFEATURES

•     DeputyCommissionerstoleadtheinitiative

•    RuraldevelopmentDepartmenttobethenodaldepartment

•	PlanningDevelopment&MonitoringdepartmentandITtobethesupport departments

ACTIONSANDTIMELINES

| ACTION | RESPONSIBILITY | LATESTBY | REMARKS |
| --- | --- | --- | --- |
| Janabhiyan | Alldepartments | Oct15-26th | Goingon |
| DeputationofSecttstaff/ HoDs | GAD | Oct14 | Done |
| DeploymentofStaffto Panchayatsandservingof ordersondeployedofficers | DCs | Oct25 | DCswilldeployseniorlevelstaff fromthedistricts.Strictactionto betakenagainstabstentions.No exemptionstobegiven |
| TrainingofdistricttrainorsonB2V4 | RDD | Oct26 |  |
| Trainingofvisitingofficers | DCs | Oct27 |  |
| FieldVisitstobecompleted by | VisitingOfficers | Nov3 | DCstosuperviseandensurethat eachPanchayatisvisitedwithin theperiodspecified |
| DataofB2V4tobe uploadedby | VisitingOfficers | Nov10 | DCstosuperviseandensurethat dataofallPanchayatsisuploadedbythevisitingofficerwithin theperiodspecified |

INSTRUCTIONSFORTHEVISITINGOFFICER(DAYWISE)

| DATE | INSTRUCTIONS | ACTIONPOINTS |
| --- | --- | --- |
| Day0 | Meetingwithdeputycommissionerandhis/her team | a. TakeprintoutsoffilledbookletsofB2V1,B2V2andB2V3from www.jkpanchayat.in b.Alsotakeprintoutsofthesummarizedexcelsheetsofthepreviousphasesfromwww.jkpanchayat.in c. CollectATRsonissuesraisedduringprevious3phasesfromthe officeofDeputyCommissioner(Planningdeptt) d.Takeprintsofblank 2bookletsofB2V4fromwww.jkpanchayat.ine.Takeplansfor2previousyearsandATRsfromtheplanningdeptt f. CompletetrainingsondifferentcomponentsofB2V4being organizedbyrespectiveDeputyCommissioners g.CollectListofnewworksstarted/ongoing/completedduringthepreviousandcurrentFinancialyearunderthefollowingheads: • PRIgrants • DistrictPlan • UTplan • MGNREGA • Otherschemesofotherdepartments • Anyotherwork h. Plans/beneficiarylists: • MGNREGAdraftplandocumentfortheyear2022-23. • ListofAwaas+beneficiariesalongwithIHHLConvergence • Listofpensionbeneficiaries. • ListofSHGs • Listofagricultureschemebeneficiaries i. Listsofbeneficiariesfor: • Variouscertificates/benefitstobedistributedbythevisitingofficer. • Anyotheractivitiesidentifiedbydifferentdepartments |

| Day1 | Reachthevillage | 1. | Ensurethatallfrontlineworkersofdifferentdepttsarepresent. |
| --- | --- | --- | --- |
|  |  | 2. | Ensureexhibitionbydifferentdepts.aboutindividualbeneficiaryschemes |
|  |  | 3. | InspectJKB/PSBcounters/outlets |
|  |  | 4. | Participate/ensureorganizationofsportsactivityinplayfield,talenthunt/culturalevent/youthactivity |
|  |  | 5. | GandhiKatha(suggesteddetailsuploadedonjkpanchayat.in) |
|  |  | 6. | Visitatleast2amritsarovarsandgetitsgeotaggedphotos |
|  |  | 7. | InspectKhidmat(CSC)CentresandcreateGenerateawarenesson 225schemesparticularlyG2CschemeslikeBEAMS,Janbhagidari, AapkiZaminAapkiNigrani,DigitalJ&K |
|  |  | 8. | Visitingofficershallalsoplanandconductpanchayatlevelconver- gencemeetingofalldepartments |
|  |  | 9. | CheckeffectivenessofCentrallysponsoredschemes |
|  |  | 10. | VisitandinspectallgovernmentestablishmentsincludingPHE, AWC,FPS,schools,etc |
|  |  | 11. | AttemptsaturationofdeliverablesoJanAbhiyanandwhereverdeficienciesfound,leadadrivetoachievealldeliverables |
|  |  | 12. | Assesseffectivenessofsanitationcampaigninthepanchayat |
|  |  | 13. | Ensureselfemploymentactivitiesfor15youthperpanchayat |
|  |  | 14. | Identify20potentialcandidatesperpanchayatforHIMAYATtraining alongwiththetradeonwhichtheywanttraining |
|  |  | 15. | Whereverpossible,distributeemploymentlettersforpeopleselect- edundervariousgovernmentemployments |
|  |  | 16. | Intheevening,holdnormalmeetingwithseniorcitizens,govtem- ployeesincludingretiredemployees,exservicemen,youthclub,andany citizens ofthevillagewhoareenrolledincollege/university |
|  |  | 17. | OpendiscussiononNashaMuktAbhiyan |

Day2            Haveameetingwithall stakeholders-depttofficialsandpanchayatmembers

1.       DiscussionontheandassesstheprogressofdifferentschemesrelatingtothelocalizedSDGsprioritizedforthatvillageaspertheresolutionpassedby thatGramPanchayaton21stApril22,onNationalPanchayti RajDay.

2.	SensitizevillageresidentsaboutmyScheme”portal(myscheme.in) whichincludesinformationaboutalltheschemesbeingrunbyCen- tral/State/UTgovtacrossthecountry

3.	Hold meeting of theBiodiversityManagementCommitteestodeliber- ateonissuespertainingtoconservationof biodiversityandsustaina- bleutilizationofbiologicalresources.

4.       PrepareVillagedevelopmentplan,inconsultancywithGrampanchayat, discussitingramsabhaandgetitapproved.

5.       EnsuresaturationofsoilhealthcardandgoldenhealthcardunderGold- enHealthCardunderAyushmanBharat,

6.       Ensuresaturation of OldAgePensionScheme

7.       EnsureDomicileSaturation.

8.       EnsureKCCSaturation

9.       Ensuresaturationoflandpassbooks

10.     Ensureregistrationofvillagevendorsneededforanyscheme,onGEM

portal

11.     Ensurepanchayatcontractorsregistration

12.     EncouragePanchayatmembersforimportanceofplantationdrivein

PanchayatunderHarGaonHariyali

13.     EnsurepaintingondigitalJ&Kinpanchayatghars

14.     EnsurepaintingonpanchayatactivitesandCSSinpanchayatghars

15.	Thevisitingofficeshallchecknoofkindergarten andplayfieldspresent inthepanchayatfor kidsandstudents,iftheinfrastructurepresent inthesearegoodenough.

16.     HoldmeetingwithpanchayatmemberstodiscussaboutcorruptionmenaceandstepsrequiredtomakeJ&Kcorruptionfree

17.     Obtainacandidassessmentaboutperformanceofvariousdepttsin- cludingfairfeedbackaboutdiscrepanciesinfunctioning

18.	Check thestatusofNashaMuktAbhiyanandreportingof drugad- dictstoDeputyCommissioner.

19.     IdentifyTouristDestinations,Circuits,ThemeTreks,IdentifyHomestays, providesupportfortourismactivitiesthroughVillageCooperative

20.     OrganizeTalentHuntatPanchayatLevel

21.     Conductsocialauditofatleast5worksunderfollowingschemes:

a.       MGNREGA

b.PMAY

c.        IHHLtoiletsandpaymentsd.CSCs

e.AMRITSAROVARS

22.     Holdamahilasabhaandabalsabhaandrecordproceedingsinthefor- matgiven

23.     InauguratevillagehaatunderJKSRLM

24.     Checkifyouthclubsareformedinthepanchayatandwhatactivitiestheyareengagedin

25.     Organizeavillagelevelculturaleventtoengagepanchayatmembers

26.     SensitizeGPaboutE-kitabkoshaninitiativeofJ&KGovtforempoweringyouthsthroughonlinedigitalliteracy

GENERALINSTRUCTIONS

1.	Thevisitingofficershallrefrainhimself/herselfgivingorofferinganycommitmentonbehalfofthe governmentandshalladoptanunbiasedattitudeinreportingissues.Asfaraspossible,his/her observation shouldbebasedonafairandanalyticalviewemergingfromhis/herinteractioninthevillage.

2.	Heisgoingtothevillageasplanningofficer,notforsanctioninganyworksorformakinganycom- mitments.

3.	Whilepreparingvillagedevelopmentplan,hehastoensurethat,demandsareprioritizedandre- flectedunderavailableschemes,wherevernecessarythelargerworksaretobereferredtoadminis- trativedepttunderCSS/UTplansunderintimationtoDCsandrestoftheworkstoDCsforreflecting itunderdistrict/CSS plans

4.    His workshallbehardcoreplanningandauditandisnotaPRexercise.

5.	EveryDeputyCommissionerhastoensurethatatleastoneRDDofficial(ideallyPanchayatSecre- tary)ispresent  ineverypanchayatwithrelevantpanchayatrecords,toensureconductofallactivi- tiesasplanned.Panchayatwiseorderneedstobeissuedinadvance.

6.	Visitingofficershouldideallycarryhis/herlaptoptocompletethereportsatthepanchayatlevel itselfanduploadthefinalreport,dulysignedbothbythesarpanchandbythevisitingofficeronwww.jkpanchayat.inportal,beforetheyleavepanchayat.

7.	Focus ofvisitareyouth,skills,self-employment,nashamukt,bhrashtracharmukt,Rozgaryukt J&K, besidestocarryforwardtheactivitiesduringJanAbhiyanandsaturatethem.

8.    Inadditionattentionmaybegiventothefollowingareasa.     MakefulluseofCentrallySponsoredSchemes

b.Saturationofindividualbeneficiaryschemesc.     Self-employmentschemes

d.Banklinkedschemes-includingdepartmentalsubsidyschemese.Empowermentandtransparencythroughdigitalinitiatives

f.       Effectivenessofgrassrootsmachinery–

i.       Patwari,VLWpresentandavailable

ii.      AvailablefundsutilizedinpublicinterestandasperGramSabharesolutions iii.   Fairness ingovernance

iv.    CSS/Individual beneficiaryschemesetcv.      BrashtacharMuktJ&K

vi.   BhaiMuktJ&K

vii.  NashaMuktJ&K

9.	ThePRImembers(Sarpanchs,Panchs,BDCChairperson)shallbeattheforefrontofallactivities and givendueimportanceandtheapproachshouldbetostrengthenthemandmakethemfeelem- powered.He/sheshallensurethattheBDCchairpersonandSarpanch/Pancharepresentatthetimeofinaugurationandceremonies.

10.	Visitingofficershallnotleavethedistrictwithoutuploadingthereport,duly signedonthewww. jkpanchayat.inportal.EveryDeputyCommissionerhastoensurethat.

A)   DetailsofReportingOfficer:

Name:   shanaz Ahmed Khan

Designation:Sr. Lecturer

Department/placeof posting:Education ( GHSS Boys Surankote)

MobileNo.:- 7889621400

EmailID:Khanshanaz09@gmail.com

HomeDistrict:Poonch

Datesof visit: 28-10-2022 & 29-10-2022

B)	LocationaldetailsofPanchayat:(tobepre-filled,informationtobetakenfromtheprevious phasesbooklets/summarizedexcelsheetuploadedonjkpanchayat.in/b2v4.php)(tobevali- datedbythevisitingofficerandmissingdetailstobefilled)

NameofthePanchayat:Islamqbad

LocalGovernmentDirectory(LGD)codeofthePanchayat:.

NameofCDBlock:NSSB

NameofTehsil:Haveli

NameofDistrict:Poonch

C)     PanchayatProfile:

No.ofrevenuevillagesinthePanchayat:. 01

No.ofhamletsinthePanchayat:.07

No.ofhouseholdsinthePanchayat:378

Population(approx)of  thePanchayat:. 2870

Part-II:

(TobefilledupbytheVisitingOfficerduringhis/hertwodayvisittothePanchayat.AllFieldshavetobe

FilledbytheVisitingOfficerbeforethebookletishanded overtotheDC

FrontlineOfficers/OfficialswhowereassignedtothePanchayatfortheprogramme:

| Department | Name | Designation |
| --- | --- | --- |
| Panchayati Raj | Sajad Ahmed | Panchayat secretary |
| Education. | ShajaqitH. shah | Teacher |
| Agriculture | Sanjeev Sharma | Agr. Asstt. |
| Animal Husbandry | Abdul Qayoom | Daily Wager |
| PHE | MohdRaiz | Daily Wager |
| Social Forestry | MohdShabir | guard |
| Food Supply | Shabir Ahmed Rathoor | StoreKeepeer er |
| Health | Sunil Shabir | Medical Astt. |
| Health | Dr. Asghar Ali | M.O. |
| Social welfare | Parveez Ahmed | Supervisior ICDS |
| PWD and R&B | Mukhterahmed |  |
| PDD | Jasmeet Singh | J.E. |
| PDD | Manzoor H. Shah | Meter reader |

Detailsofabsentemployeesvis-à-vislistfurnishedbytheDCoffice:

| Department | Name | Designation |
| --- | --- | --- |

DAY1-ACTIVITIES

AGENDA1:PANCHAYATASSETREGISTER

Infrastructure:

1.		PanchayatGharInfrastructure a.  Govtbuilding/private

b.  New/needingrepairs

2.       Furniture(Y/N)-Y

3.       Computer/printer(Y/N)- N

4.       Internet(Y/N)- N

5.       Telephone(Y/N)- N

6.       Toilet(CSC/partofpanchayatghar)(Y/N)- Y

7.       Water(Y/N)- Y

8.       Electricity(Y/N)- Y

9.       Bankbranch(Y/N)-N

10.     CSC(Y/N)- N

11.     Patwarkhana(Y/N)- N

12.     Villagehaat(Y/N) – N

13.     Playground(Y/N)- N

14.     School-

a.        Kindergarten(Y/N)-N

b.Primary(Y/N)-Y

c.         Secondary(Y/N)-Y

d.College (Y/N)- N

e.University(Y/N)- N

15.     AnganwadiCentre(Y/N) - Y

a.        (govt/private)

b.Totalchildrenenrolled

15.     AmritSarovars–details,location,condition - NIL

16.     Governmentoffices-details,whetherfunctionalornot –Functional

17.     Rationshop(Y/N)- Y

18.      Placesoftourismimportance–names,littledetailsonhistorical/culturalimportance- NIL

19.      Villageheritagesites/treks-names,littledetailson historical/culturalimportance

20.     VLWOffice (Y/N)

21.     PrimaryHealthcareCentre(Y/N)- N

22.     ListofIncompleteBuildings-names,yearofconstruction

23.     ListofUnderutilizedBuildings-names

DAY1-ACTIVITIES

AGENDA2:

DIFFERENTINSTITUTIONS/INFRASTRUCTUREPROJECTSTOBEVISITED

| AMRITSAROVARS | Visit,verify | COMMENTS |
| --- | --- | --- |
| KhidmatCentres | Create/Generateawarenesson225schemes particularlyG2CschemsAapkiZaminAapkiNigrani, Beams,Janbhagidari,DigitalJ&K | Not Khidmat Centre |
| JKB/PSBcounters/outlets | a)Statusofcounterb)Numberofvisitors | Not Bank Outlet |
| Incompletebuildings/pro- jects | Verify whetheridentificationandredistributiondone | NIL |
| PDS | Visit,evaluate,onlinestatus | PDS shop is fully functional |
| PHC | Visit-evaluate,statusofstaff,equipmentandquality | No PHC in the Panchayat |
| Youthclubs | Meet,interact,seeksuggestions | No Youth Clubs. |
| SHG | Meet,identifyproblems,seeksuggestions | Not Available |
| PMAY | Inspect,Inaugurate | PMAY Scheme is fully functional |
| Myschool,myprideprogress;schools-water, toilets,staff | Visit,checkforwater,electricity,sanitation,meetstudentsandstaff | Nil |
| SwachhSBM | Evaluate | Very effective |
| Panchayatplayground, SportskitsdistributionVillagegames | Ensure,verify.Participateinatleastonegameintheplayground | No playground available in panchayat |
| HarGaonHariyali, Planta- tiondrive | Evaluatestatus,feedback | Scheme is not fully functional |
| Villageculturalevent Dangal/Haat/Mela | Participatein;ensurethatitisheld | Nil |
| Exhibitionofschemes | EnsurethateverydepartmentparticipatesandthatitcontinuesfortheentiredurationofB2V | Done |
| JalJeewanMissionverifica- tion- WSS/JSD Electricitysupply | Verify | Survey of the Panchayat under progress |

DAY1-ACTIVITIES

AGENDA3:SATURATEJANBHIYAN

DELIVERABLESANDRECORDDEFICIENCIESIFANY(INSERTDELIVERABLESLISTHEREASPERGADFORMAT

DAY1-ACTIVITIES

AGENDA4:

SELFEMPLOYMENTACTIVITIES

EnsureSelf-employmentactivitiesforyouth,distributeemploymentlettersforpeopleselectedundervarioussocialschemes(15ISTHETARGETPERPANCHAYAT)

Numberofcasesindifferentcategoriessanctioned:Nil

Detailsofthebanksanctioningit: Nil

Totalamountinvolved: Nil

DAY1ACTIVITIES

AGENDA5

Intheevening,holdinformalmeetingswithseniorcitizens,govtemployees,retdemployees,youthclubandothercitizenswhoareenrolledoncollege/universityandhavediscussiononGandhiKatha,Nasha MuktAbhiyan,corruptionfreegovernance,doublingfarmersincomeandrecordtheproceedings

DAY2

- NoofIndividualCompostPitsconstructed 08

b     NoofIndividualSoakPitsconstructed-185

V.          No.ofBiodiversitymanagementcommitteemeetingsheld:06

VI.         IsthenameofSarpanchdisplayedoncitizeninformationboardsofallRD&PRschemes:Yes/No

VII.       AreSarpanchsbeinginvolvedinstart/inaugurationofactivities:Yes/No

VIII.      WhethersubjectshavebeenassignedbytheSarpanchtothePanchs:Yes/No

IX.        Whethergrievancesredressalboxisinstalled:Yes/No

X.         NoofgrievancesreceivedpertainingtoPanchayatlevel:Nil

XI.        NoofgrievancesdisposedofatPanchayatlevel:Nil

XII.       WhethertheSarpanch/PanchayatSecretaryhavedigitalsignatures:Yes/No

XIII.      WhetherallMGNREGA/14thFCpayments arebeingmadebySarpanchthroughDigitalSignature

Certificate(DSC):Yes/No

HUMAN RESOURCEAVAILABLEATTHEPANCHAYAT LEVEL:

| SRNO. | DEPARTMENTWISESTAFF | NUMBERS |  | NAMES |
| --- | --- | --- | --- | --- |
|  |  | SANCTIONED | ACTUAL |  |
|  | Ruraldevelopmentdepartment: BDO JE GRS TA | 01 01 01 01 | 01 01 01 01 | Aijaz Ahmed Bhat Bashir Anjum LalHusssain Rahim Ullah Khan |
|  | SCHOOLEDUCATION: TEACHER HEADMASTER ANYOTHER | 67 | 45 |  |
|  | JAL JEEVAN: | 01 | 01 | Mohd Bashir |
|  | PDD: LINEMAN JE ANYOTHER | 02 01 01 | 02 01 01 | Jagmeet Singh Manzoor H. shah |
|  | FOOD&CIVILSUPPLIES |  |  |  |
|  | AGRICULTURE&ANIMALHUS- BANDARY | AH-01 AGR- 01 | 01 01 | Abdul Qayoom(VP) Sanjeev Sharma (AA) |
|  | SOCIALWELFARE | 01 | 01 | Noor Ahmed Shah |
|  | HEALTH: ASHA ANM AYUSHDOCTOR ALLOPATHICDOCTOR | 03 02 01 01 | 03 02 01 Nil |  |
|  | ANYOTHERDEPARTMENT (Social Forestry) | 01 | 01 |  |

DAY2-ACTIVITIES

AGENDANO.1

DiscussionontheandassesstheprogressofdifferentschemesrelatingtothelocalizedSDGsprior-itizedforthatvillageaspertheresolutionpassedbythatGramPanchayaton21stApril22,onNational PanchayatiRajDay(Copyoftheresolutiontobetakenfromwww.jkpanchayat.inportalunderthelinkof GramSwarajMonth)

1.       SDGs AGREED FORTHATVILLAGE,TOBEIMPLEMENTED BYMARCH2024:

2.       STATUSOFWORKSUNDERTHEFOLLOWINGSCHEMES:

1      Cleanandgreenvillage

i.InitiativestakenbythePanchayatformanagingSolidandLiquidWasteSoak pits, Composit pits

ii.     InitiativestakenbythePanchayatforusinggreensourcesoffuellikesolar,biogas

NIL

iii.  Hasmappingoflanduse,waterbodies,forest,slopes,wetlands,degradedforestwithintheGram

Panchayatbeendone?Yes/No.IfNo,reason,thereof

iv.    HastheClimateResiliencePlanbeendevelopedfortheGP?Yes/No

v.     StepstakenbytheGramSabhaabouttheclimatechangemitigationfactorslikereducingenergy consumption,usageoffossilfuels,plastics,non-renewablebuildingmaterialsandalsotopromote measureslikeplantingoftrees,conservingforests,usageofgoodagriculturalpracticeslikedrip irrigation,waterconservationmeasuresandconservationofwetlands.

vi.  Whetherschoolshavestartedsegregatingwaste-Yes

vii. Whetherschoolshavetheirowncompost/soakagepitsforsolid/liquidwastemanagement

2     Healthyvillage

i)    AremeetingsrelatedtoVillageHealthandSanitationCommitteebeingheldregularly?-No

ii)   DoalltheeligibleindividualsbeenprovidedtheGoldenCard?-No

iii)  ArealltheChildrenbeingimmunizedaspertheSchedulerecommendedbyGovt.ofIndia?-Yes

iv)  ArealltheeligibleindividualsbeenvaccinatedagainstCOVID-19?-Yes

v)   DoesGramPanchayatensurethatallpregnantwomenaregettingnecessaryprenatalcheckups?--Yes

vi)  WhetherallthedeliverieswereInstitutionalizedorconductedbytrainedMidwives?-Yes

3     Watersufficientvillage

i)    DoalltheIHHsintheGramPanchayathavewaterpipelineconnections?-No

ii)   WhetherGramPanchayathastakenstepsforgreywatermanagement.IfYespleasespecify

iii)  DoalltheIHHsintheGramPanchayathavetoilets?-No

iv)  ArealltheIHHstoiletsfunctionalornot?- No

v)   DoalltheSchools/Anganwadicentershaveatoiletfacilityornot?-Yes

vi)  Areallthetoiletsintheschools/Aaganwadifunctionalornot?-Yes

vii) WhetherGramPachachayatBhawanhasseparatetoiletsforwomenornot?-No

-

4      ChildFriendlyvillage

i)	Doallthechildrenundertheageof0-6yearsbeenenrolledintheAnganwadicentersforpre- schooling?Yes/NO- Yes

ii)    HowmanyBalSabha’swereorganizedintheGramPanchayat. -. Nil

iii)  WhethertheissuesraisedbyBalSabhaareaddressedduringtheGramSabha. No

iv)	WhetherGramPanchayatistrackingthedatarelatedtodropoutchildrenandchildrenwithirregular attendance?- No

v)   DoalltheschoolsundertheGramPanchayathaveseparatetoiletsforgirlsandboys?Yes/No

5      Villagewithgoodgovernance

i)    IsCSClocatedintheGramPanchayatBhawanornot?- No

ii)	IsthelistofbeneficiariesrelatedtotheSchemes/ProgramsdisplayedontheGrampanchayatwallor not? - No

iii)  DoestheGramPanchayathasitsbuildingornot? - Yes

iv)  IstheGramPanchayatofficefunctionalornot?-. Yes

v)   Aretheactivities approved undertheHalqaPanchayatDevelopmentPlandisplayedontheGram

Panchayatwallornot?-No

vi)  IsSocialAuditofearlierSchemes/Programscarriedoutornot?- No

6      Povertyfreeandenhancedlivelihoodvillage

i)    HasGramPanchayatdevelopedanycriteriafortheidentificationofthepoor?Yes/Noifyesspecify ii)   HavealltheeligiblehouseholdsregisteredinPDSornot?- Yes

iii)	HasGramPanchayatprovidedspaceforSelf-helpGroupsinPanchyatGharforholdingmeetings  or not?-Yes

iv)  HavealltheeligiblehouseholdsbeenregisteredforPensionornot?-No

v)   HasGramPanchayatfacilitatedYouthforSkillEnhancementCoursesandPlacement? - No

vi)  HasJobCardsbeendistributedtoalltheeligibleindividualsunderMGNREGA?-. Yes

vii) HasGramPanchayatfacilitatedSHGsforBankAccountLinkages? - No

7     Sociallysecuredvillage

i)    WhetherGramPanchayatismaintainingdatarelatedtoDifferentlyAbledPeople? – No.

ii)   IsGramPanchayatOfficeDisabledFriendlyornot?- Yes

iii)	Areprovisionsfora separate BudgetundertheResourceEnvelopeforWomenandChildrenmadeornot?- No

iv)	DoalltheSchools intheGramPanchayathavefacilitiesforDifferentlyAbledChildrenliketoilets, barrier-freeaccess,etc.,ornot?- No

v)   Arealltheeligibleindividualsaregettingpensions,likeoldagepension,widowpension,etc? - Yes

vi)  ArealltheeligiblehouseholdsgettingbenefitsfromIAYornot?

-Yes

8      EngenderedDevelopmentinVillage

i)    HowmanyMahilaSabha’swereorganizedintheGramPanchayat-Nil

ii)	WhetherSHGsfederationshavebeenprovidedspaceformeetingsinthePanchayatBhawan(Yes/ No)

iii)  WhetherGPshavetakenstepsforincreasingwomen’sparticipationinGramSabha(Yes/No)

iv)  NumberofwomenbeneficiariesheadedhouseholdscoveredunderPDS

system - 17

v)   Numberofbeneficiaries(outoftotaleligiblepopulation)receivingsocialprotectionbenefitsunder

PradhanMantriMatritvaVandanaYojana………Nil………….

9    Self-sufficientinfrastructureinthevillage

i.	WhetherGPhasaCommunityHallwithaccesstoelectricity,furniture,watersupply, toilet No

ii.     WhethertheDisastermanagementplanisavailableattheGPLevel(Yes/No)

iii.  Whetherchild-friendlyparkwithrequiredfacilitiesisavailableinGP(Yes/No)

iv.    WhethertheGPhaseasyaccesstoGodownforstorage(Yes/No)

v.     Whetherstreetlightsareprovidedinpublicplacesforensuringsafety(Yes/No)

DAY2ACTIVITIES

AGENDANO.2

SensitizevillageresidentsaboutmyScheme”portal(myscheme.in)whichincludesinformationaboutall theschemesbeingrunbyCentral/State/UT govtacrossthecountry

(SchemeMaterialavailablefromhttps://jkpanchayat.in/b2v4.php)

DAY2ACTIVITIES

AGENDANO.3

HoldmeetingoftheBiodiversityManagementCommitteestodeliberateonissues pertainingtoconserva- tionofbiodiversityandsustainableutilizationofbiologicalresources.HeshouldcheckPeopleBiodiversity register(PBR)ofthatpanchayatandreviewifBiodiversityManagementCommittee constitutedforthatpanchayatis holdingminimum4meetings inayearandmeeting onceinevery3months (RoleofBMCavailableathttps://jkpanchayat.in/b2v4.php)

COMMITTEEMEMBERS. 05

PRESENT :05

BIODIVERSITYREGISTERPHOTOS : Nil

PAST 4 MEETINGDETAILS-DATES,MINUTESPHOTOS

: No meeting held

DAY2ACTIVITIES

AGENDA4

Visitingofficershallalsoplanandconductpanchayatlevelconvergencemeeting  ofalldepartmentsandprepareVillagedevelopmentplanforvillage,inconsultancywithGrampanchayat,discussitingram sabhaandgetitapproved.

(GPDPformatavailableonhttps://jkpanchayat.in/b2v4.php)

InadditionGPDPplanshallalsoinclude:

           Touristplaceswhichneedtobedeveloped

           Specificproductwhichneedstobedeveloped

           Tourism-homestays

	20candidatesfortrainingunderHimayatschemealongwithtradeinwhich trainingistobegiven

DAY2ACTIVITIES

AGENDA5

Ensuresaturationoffollowingschemesandgivestatus:

| NAMEOFTHESCHEME | TOTALELIGIBLE BENEFICIARIESIN THE VILLAGE | TOTALBENEFICIARIESWHO AVAILEDTHEBENEFITSOFTHESCHEME | REASONSFOR PENDENCY |
| --- | --- | --- | --- |
| GoldenHealthCardunder AyushmanBharat | 2870 | 1993 | Migration to foreign and to the local towns |
| Jananisurakshayojana | 45 | 35 | Not yet delivered |
| OLDAGEpension | 23 | 23 |  |
| Widowpension | 24 | 24 |  |
| Disabilitypension | 30 | 23 |  |
| Domicilecertificate | 2870 | 975 | DC issued by RD in progress |
| Kisancreditcard | 378 | 42 | KCC files under progress |
| PMkisansammannidhi UDID | 18 | 18 |  |

| Landpassbook |  |  |  |
| --- | --- | --- | --- |
| Registrationofvillageven- dorsonGEMportal | 19 | 19 |  |
| Registrationofvillagecon- tractorsonjktendersportal | 07 | 07 |  |
| Registrationofvillagecon- tractorsonPWDportal | 12 | 12 |  |
| Incompletebuildings/pro- jects | Nil | Nil | Nil |

DAY2ACTIVITIES

AGENDA6

NASHAMUKTABHIYAN

1.       Whethergramsabharesolutionpassed  - Yes

2.       Detailsofactivitiesconducted- Awareness camps in Panchayat Schools

3.       WhetherallactivitiesandGSresolutionuploadedonjkpanchayats.inportal- Yes

4.       Howmanydrugaddictsinthevillage-. Nil

5.       WhetherreportedtotheDeputyCommissioner - Nil

6.       Howmanyregisteredforrehabilitationundergovernmentprogramme-Nil

Nil

DAY2ACTIVITIES

AGENDA7

SOCIALAUDIT

Conductsocialauditofatleast5workseachunderfollowingschemes:

| NAMEOFTHE SCHEME | DETAILSOFTHE WORKS | YEAROFWORK APPROVAL | AMOUNT APPROVED FORTHEWORK | WHETHER WORKEXECUTED SATISFACTORILY | GEO- TAGGED PHOTOS | ANY GRIEVANCE RECORDED RELATINGTOTHAT WORK |
| --- | --- | --- | --- | --- | --- | --- |
| MGNREGA | Water tank near w.no. 05 | 2021-22 | 1.00 lacs | Up to mark | Yes | No |
| PMAY | Rehmatjaan Mukhtar Ah. | 2021-22 2020-21 | 1.30 lacs 1.30 lacs | Yes | Yes | No |
| IHHL UNDERSBM-G | Unit near H/o Shokatali | 2019-20 | 0.12 lacs | Yes | Yes | No |
| CSCUNDER SBMG | Nil | Nil | Nil | Nil | Nil | Nil |
| AMRIT SAROVARS | Near Me Islamabad | 2022-23 | 4.00 lac | Satisfactory | Yes | No |

DAY2ACTIVITIES

AGENDA8

MAHILASABHA

Totalwomeninthevillageabovetheageof18- 650

Totalattended- 95

Proceedings: Discuss on various issues of the Panchayat

(Plinsertpointerstobediscussedthere–referpalliproceedings)

DAY2ACTIVITIES

AGENDA9

BALSABHA

Holdabalsabhaandrecordproceedings

Totalchildreninthevillageabovetheage of 6yr.-320

Totalattended- 35

Proceedings:Opendiscussion with the children regarding various public institutions in the Panchayat and the problem faced by children community

(Plinsertpointerstobediscussedthere–referpalliproceedings)

DAY2ACTIVITIES

AGENDA10

INAUGURATIONS

| SR NO. | ASSETS/ACTIVITIES INAUGRATED | STATUSOFTHEASSET/AC- TIVITIES(NUMBER,OTHER DETAILS) | GEO-TAGGED PHOTOS |
| --- | --- | --- | --- |
|  | VILLAGEHAATunderJKSRLM(SUN- DAYMARKET) | Nil | Nil |
|  | PMAYhousesifanyreadyforinaugra- tion | 87 PMAY houses completed | Photos Geo-tagged on the portal |
|  | Swachhgramprojects-segregation shedsetc | Nil | Nil |
|  | Amritsarovars | 02 – One completed - One under construction | One (AS) Geo-tagged |
|  | Sportskits | Already distributed |  |
|  | Villageculturalevents | NashaMukt Bharat |  |
|  | JJMassets/projects | Nil | Nil |
|  | Anyothertobeidentifiedatdistrictlevel |  |  |

FOLLOWUPOF(B2V1,B2V2&B2V3):

(Prefilledexcelsheettobetakenfromdistrictlevel/andalsotobedownloaded

fromwww.jkpanchayat.in)

| S.NO. | Particulars | Actiontaken | Remarks# |
| --- | --- | --- | --- |
| I. UrgentPublicRequirements/Demands-B2V1 |  |  |  |
| 1 |  |  |  |
| 2 | Data regarding B2V1 not available |  |  |
| 3 |  |  |  |
| 4 |  |  |  |
| 5 |  |  |  |
| 6 |  |  |  |
| 7 |  |  |  |
| II. UrgentPublicRequirements/Demands-B2V2 |  |  |  |
| 1 | Banking facility/ATM | No action taken |  |
| 2 | Road connectivity to peripheral wards of Panchayat | No action taken |  |
| 3 | Demand of PHC in the Panchayat | No action taken |  |
| 4 | Clean drinking water facility | Not yet fulfilled |  |
| 5 |  |  |  |
| 6 |  |  |  |
| 7 |  |  |  |
| S.NO. | Particulars | Actiontaken | Remarks# |
| III. MajorProblems–B2V1 |  |  |  |
| 1 | Data regarding B2V1 is not available |  |  |
| 2 |  |  |  |
| 3 |  |  |  |

| 4 |  |  |  |
| --- | --- | --- | --- |
| 5 |  |  |  |
| IV. MajorProblems-B2V2 |  |  |  |
| 1 |  |  |  |
| 2 | Same as mentioned under demand B2V2 |  |  |
| 3 |  |  |  |
| 4 |  |  |  |
| 5 |  |  |  |
| V. MajorProblems-B2V3 |  |  |  |
| 1 | Road connectivity to the peripheral area of Panchayat | Project started not yet completed |  |
| 2 | Non-availability of the Bank/ATM | No action taken Work under progress |  |
| 3 | Non-availability of clean drinking water | Work under progress |  |
| 4 |  |  |  |
| 5 |  |  |  |
| VI. MajorComplaints-B2V1 |  |  |  |
| 1 | Data regarding B2V1 not available |  |  |
| 2 |  |  |  |
| 3 |  |  |  |
| VII. MajorComplaints-B2V2 |  |  |  |
| 1 | Same as mentioned under demands(B2V2) |  | Still the people facing the same problem |
| 2 |  |  |  |
| 3 |  |  |  |
| VIII. MajorComplaints-B2V3 |  |  |  |
| 1 | Use of wooden poles instead of Iron pole by PDas | PDD replaced wooden poles with iron poles |  |
| 2 | Non-availability Animal ahusbandry/centrein the Panchayat | No action taken |  |
| 3 |  |  |  |