4

15TH OCTto3RD NOV,2022

# KEYFEATURES

- DeputyCommissionerstoleadtheinitiative

- RuraldevelopmentDepartmenttobethenodaldepartment

- PlanningDevelopment&MonitoringdepartmentandITtobethesupport departments

# ACTIONSANDTIMELINES

| ACTION | RESPONSIBILITY | LATESTBY | REMARKS |
| --- | --- | --- | --- |
| Janabhiyan | Alldepartments | Oct15-26th | Goingon |
| DeputationofSecttstaff/ HoDs | GAD | Oct14 | Done |
| DeploymentofStaffto Panchayatsandservingof ordersondeployedofficers | DCs | Oct25 | DCswilldeployseniorlevelstaff fromthedistricts.Strictactionto betakenagainstabstentions.No exemptionstobegiven |
| Trainingofdistricttrainors onB2V4 | RDD | Oct26 |  |
| Trainingofvisitingofficers | DCs | Oct27 |  |
| FieldVisitstobecompleted by | VisitingOfficers | Nov3 | DCstosuperviseandensurethat eachPanchayatisvisitedwithin theperiodspecified |
| DataofB2V4tobe uploadedby | VisitingOfficers | Nov10 | DCstosuperviseandensurethat dataofallPanchayatsisupload- edbythevisitingofficerwithin theperiodspecified |

INSTRUCTIONSFORTHEVISITINGOFFICER(DAYWISE)

| DATE | INSTRUCTIONS | ACTIONPOINTS |
| --- | --- | --- |
| Day0 | Meetingwithdeputy commissionerandhis/her team | - TakeprintoutsoffilledbookletsofB2V1,B2V2andB2V3from www.jkpanchayat.in - Alsotakeprintoutsofthesummarizedexcelsheetsofthe previousphasesfromwww.jkpanchayat.in - CollectATRsonissuesraisedduringprevious3phasesfromthe officeofDeputyCommissioner(Planningdeptt) - Takeprintsofblank 2bookletsofB2V4fromwww.jkpanchayat.ine.Takeplansfor2previousyear sandATRsfromtheplanningdeptt f. CompletetrainingsondifferentcomponentsofB2V4being organizedbyrespectiveDeputyCommissioners g.CollectListofnewworksstarted/ongoing/completedduringthe previousandcurrentFinancialyearunderthefollowingheads: - PRIgrants - DistrictPlan - UTplan - MGNREGA - Otherschemesofotherdepartments - Anyotherwork - Plans/beneficiarylists: - MGNREGAdraftplandocumentfortheyear2022-23. - ListofAwaas+beneficiariesalongwithIHHL Convergence - Listofpensionbeneficiaries. - ListofSHGs - Listofagricultureschemebeneficiaries - Listsofbeneficiariesfor: - Variouscertificates/benefitstobedistributedbythe visitingofficer. - Anyotheractivitiesidentifiedbydifferentdepartments |

| Day1 | Reachthevillage | 1. | Ensurethatallfrontlineworkersofdifferentdepttsarepresent. |
| --- | --- | --- | --- |
|  |  | 2. | Ensureexhibitionbydifferentdepts.aboutindividualbeneficiary schemes |
|  |  | 3. | InspectJKB/PSBcounters/outlets |
|  |  | 4. | Participate/ensureorganizationofsportsactivityinplayfield,talent hunt/culturalevent/youthactivity |
|  |  | 5. | GandhiKatha(suggesteddetailsuploadedonjkpanchayat.in) |
|  |  | 6. | Visitatleast2amritsarovarsandgetitsgeotaggedphotos |
|  |  | 7. | InspectKhidmat(CSC)CentresandcreateGenerateawarenesson 225schemesparticularlyG2CschemeslikeBEAMS,Janbhagidari, AapkiZaminAapkiNigrani,DigitalJ&K |
|  |  | 8. | Visitingofficershallalsoplanandconductpanchayatlevelconver- gencemeetingofalldepartments |
|  |  | 9. | CheckeffectivenessofCentrallysponsoredschemes |
|  |  | 10. | VisitandinspectallgovernmentestablishmentsincludingPHE, AWC,FPS,schools,etc |
|  |  | 11. | Attemptsaturationofdeliverableso JanAbhiyanandwherever deficienciesfound,leadadrivetoachievealldeliverables |
|  |  | 12. | Assesseffectivenessofsanitationcampaigninthepanchayat |
|  |  | 13. | Ensureselfemploymentactivitiesfor15youthperpanchayat |
|  |  | 14. | Identify20potentialcandidatesperpanchayatforHIMAYATtraining alongwiththetradeonwhichtheywanttraining |
|  |  | 15. | Whereverpossible,distributeemploymentlettersforpeopleselect- edundervariousgovernmentemployments |
|  |  | 16. | Intheevening,holdnormalmeetingwith seniorcitizens,govtem- ployeesincludingretiredemployees,exservicemen,youthclub,and any citizens ofthevillagewhoareenrolledincollege/university |
|  |  | 17. | OpendiscussiononNashaMuktAbhiyan |

| Day2 | Haveameetingwithall stakeholders-depttofficials andpanchayatmembers | - Discussionontheandassesstheprogressofdifferentschemesrelating tothelocalizedSDGsprioritizedforthatvillageaspertheresolution passedby thatGramPanchayaton21st April22,onNationalPanchayti RajDay. - Sensitizevillage residentsaboutmyScheme”portal(myscheme.in) whichincludesinformationaboutalltheschemesbeingrunbyCen- tral/State/UTgovtacrossthecountry - Hold meeting of theBiodiversityManagementCommitteestodeliber- ateonissuespertaining toconservation of biodiversityandsustaina- bleutilizationof biologicalresources. - PrepareVillagedevelopmentplan,inconsultancywithGrampanchayat, discussitingramsabhaandgetitapproved. - Ensure saturationofsoilhealthcardandgoldenhealthcardunderGold- enHealthCardunderAyushmanBharat, - Ensuresaturation of OldAge PensionScheme - EnsureDomicileSaturation. - EnsureKCCSaturation - Ensure saturationoflandpassbooks - Ensureregistrationofvillagevendorsneededforanyscheme,onGEM portal - Ensurepanchayatcontractors registration - EncouragePanchayatmembers forimportanceofplantationdrivein PanchayatunderHarGaonHariyali - Ensure paintingondigitalJ&Kinpanchayatghars - Ensure paintingonpanchayatactivitesandCSSinpanchayatghars - Thevisiting officeshallchecknoof kindergarten andplayfields present inthepanchayat for kidsandstudents,iftheinfrastructure present inthesearegoodenough. - Holdmeeting withpanchayatmembers todiscussaboutcorruption menaceandstepsrequiredtomakeJ&Kcorruptionfree - Obtaina candidassessmentaboutperformanceofvariousdeptts in- cludingfairfeedbackaboutdiscrepanciesinfunctioning - Check thestatusof NashaMuktAbhiyanandreporting of drugad- dictstoDeputyCommissioner. - IdentifyTouristDestinations,Circuits,ThemeTreks,IdentifyHomestays, providesupportfortourismactivities throughVillageCooperative - OrganizeTalentHuntatPanchayatLevel - Conductsocialauditofatleast5worksunderfollowingschemes: - MGNREGA b.PMAY c. IHHLtoiletsandpayments d.CSCs e.AMRITSAROVARS - Holda mahilasabha anda balsabhaandrecordproceedingsinthefor- matgiven - InauguratevillagehaatunderJKSRLM - Checkifyouthclubsareformedinthepanchayatandwhatactivities theyareengagedin - Organizea villagelevelculturaleventtoengagepanchayatmembers - SensitizeGPaboutE-kitabkoshaninitiativeofJ&KGovtforempowering youthsthrough onlinedigitalliteracy |
| --- | --- | --- |

# GENERALINSTRUCTIONS

- Thevisitingofficershallrefrainhimself/herselfgivingorofferinganycommitmentonbehalfofthe governmentandshalladoptanunbiasedattitudeinreportingissues.As faraspossible,his/her observation shouldbebasedona fairandanalytical viewemergingfromhis/herinteractioninthe village.

- Heisgoingtothevillageasplanningofficer,notforsanctioninganyworksorformakinganycom- mitments.

- Whilepreparingvillagedevelopmentplan,hehastoensurethat,demandsareprioritizedandre- flectedunderavailableschemes,wherevernecessarythelargerworksaretobereferredtoadminis- trativedepttunderCSS/UTplansunderintimationtoDCsandrestoftheworkstoDCsforreflecting itunderdistrict/CSS plans

- His workshallbehardcoreplanningandauditandisnota PRexercise.

- EveryDeputyCommissionerhastoensurethatatleastoneRDDofficial(ideallyPanchayatSecre- tary)ispresent ineverypanchayatwithrelevantpanchayatrecords,toensureconductofallactivi- tiesasplanned.Panchayatwiseorderneedstobeissuedinadvance.

- Visitingofficershouldideallycarryhis/herlaptoptocompletethereportsatthepanchayatlevel itselfanduploadthefinalreport,duly	signedbothbythesarpanchandbythevisitingofficeron www.jkpanchayat.inportal,beforetheyleavepanchayat.

- Focus ofvisitareyouth,skills,self-employment,nashamukt,bhrashtracharmukt,Rozgaryukt J&K, besidestocarryforwardtheactivities duringJanAbhiyanandsaturatethem.

- Inadditionattentionmaybegiventothefollowingareas a. MakefulluseofCentrallySponsoredSchemes b.Saturationofindividualbeneficiaryschemes c.

Self-employmentschemes

d.Banklinkedschemes-includingdepartmentalsubsidyschemes e.Empowermentandtransparencythrough digitalinitiatives

- Effectivenessofgrassrootsmachinery–

  - Patwari,VLWpresent andavailable

  - AvailablefundsutilizedinpublicinterestandasperGramSabharesolutions iii.

Fairness ingovernance

iv.	CSS/Individual beneficiaryschemesetc v.

BrashtacharMuktJ&K

- BhaiMuktJ&K

- NashaMuktJ&K

- ThePRImembers (Sarpanchs,Panchs,BDCChairperson)shallbeattheforefrontofallactivities and givendueimportanceandtheapproach shouldbetostrengthenthemandmakethemfeelem- powered.He/sheshallensurethattheBDCchairpersonandSarpanch/Panch arepresent atthetime ofinaugurationandceremonies.

- Visitingofficershallnotleavethedistrictwithoutuploadingthereport,duly signedonthewww. jkpanchayat.inportal.EveryDeputyCommissionerhastoensurethat.

## DetailsofReportingOfficer:

Name: Syed Shahnawaz Bukhari

Designation: Assistant Commissioner

Department/placeof posting: StateTaxes Enforcement, North Kashmir

MobileNo:9906546991

EmailID: essenbukhari@gmail.com

HomeDistrict:Baramulla

Datesof visit: 28th & 29th October 2022

## LocationaldetailsofPanchayat:(tobepre-filled,informationtobetakenfromtheprevious phasesbooklets/summarizedexcelsheetuploadedonjkpanchayat.in/b2v4.php)(tobevali- datedbythevisitingofficerandmissingdetailstobefilled)

Name of the Panchayat: TAKIYASULTAN (DRANGBAL)

Local Government Directory (LGD) code of the Panchayat: 241190

Name of CD Block: Baramulla

Name of Tehsil: Baramulla

Name of District: Baramulla

## PanchayatProfile:

No.of revenue villages in the Panchayat: 2

No. of hamlets in the Panchayat: 2

No.of households in the Panchayat: 586

Population (approx) of the Panchayat: 4800

# Part-II:

(TobefilledupbytheVisitingOfficerduringhis/hertwodayvisittothePanchayat.AllFieldshavetobe filledbytheVisitingOfficerbeforethebookletishandedovertotheDC

## FrontlineOfficers/OfficialswhowereassignedtothePanchayatfortheprogramme:

| Department | Name | Designation |
| --- | --- | --- |
| Agriculture | Rizwana Khalid | AEO |
| Social Welfare | Mariya Hanief | Outreach Worker (ORW) |
| Horticulture | Javid Ahmad | I/C HDO |
| School Education | Khan Mohd Ishaq | Headmaster |
| Health Department | Dr Sheikh Nazir | BMO |
| CAPD | Syed Mohammad Ashraf | FPS |
| Forest Department | Ab Qayoom Malla | Range Officer |
| Social Forestry | Jan Mohammad Yaseen | Forest Guard |
| Sheep & Animal Husbandary | Fayaz ahmad Dar | ASM |
| Anganwadi | Syed Zaheena | Anganwadi Worker |
| Fisheries Department | Altaf Ahmad | Fisheries Guard |
| PDD | Ab Hamid Malla | AEE |
| J&K Grameen Bank | Syed Fayaz | Branch Clerk |

Detailsofabsentemployeesvis-à-vislistfurnishedbytheDCoffice:

| Department | Name | Designation |
| --- | --- | --- |
| Flood Control | Absent |  |
| J&K Bank | Absent |  |

# DAY1-ACTIVITIES

## AGENDA1:PANCHAYATASSETREGISTER

Infrastructure:

  - Panchayat Ghar Infrastructure

    - Govt building/private: Panchayat Ghar Not constructed so far

    - New/needing repairs	NA

  - Furniture(Y/N)	            N

  - Computer/printer(Y/N)	Y

  - Internet(Y/N)	N

  - Telephone(Y/N)	N

  - Toilet(CSC/part of panchayat Ghar )(Y/N)	N

  - Water(Y/N)	N

  - Electricity(Y/N)	            N

  - Bankbranch(Y/N)	N

  - CSC(Y/N)	Y

  - Patwarkhana (Y/N)	N

  - Village haat(Y/N)	N

  - Playground(Y/N)	N

  - School-

    - Kindergarten(Y/N)	Y

b. Primary/Middle(Y/N)         Y

c. Secondary(Y/N)	Y

d. College (Y/N)		N e. University(Y/N)	            N

  - Anganwadi Centre(Y/N)	Y

    - (Govt/private)	Private b.Total children enrolled		171

- AmriT Sarovars –details, location, condition	Nil

- Government offices-details, whether functional or not

- Ration shop(Y/N)	Y

- Placesoftourismimportance–names,littledetailsonhistorical/culturalimportance: BOSIAN, GABBWAR

- Village heritage sites/treks-names, little details on historical/cultural importance	: BARAMULLA-HAJIBAL-BOSIAN-GABBWAR

- VLW Office (Y/N)	       N

- Primary Health care Centre (Y/N):	Y

- List of Incomplete Buildings-names, year of construction: SCHOOL BUILDING AT HAJIBAL

- List of Underutilized Buildings-names: NA

# DAY1-ACTIVITIES

AGENDA2: DIFFERENTINSTITUTIONS/INFRASTRUCTUREPROJECTSTOBEVISITED

| AMRITSAROVARS | Visit,verify | COMMENTS |
| --- | --- | --- |
| KhidmatCentres | Create/Generate awareness on 225 schemes particularly G2C schemes Aapki Zamin Aapki Nigrani, Beams, Janbhagidari, Digital J&K | CSC Centre available in only one village of Panchayat |
| JKB/PSBcounters/outlets | a)Status of counter b)Number of visitors | NONE |
| Incomplete buildings/projects | Verify whether identification and redistribution done | School Building comprising Of 4 rooms |
| PDS | Visit, evaluate, online status | Visited, in good condition |
| PHC | Visit-evaluate, status of staff, equipment and quality | NONE |
| Youth clubs | Meet, interact, seek suggestions | NONE |
| SHG | Meet, identify problems, seek suggestions | Yes, No major Problem |
| PMAY | Inspect, Inaugurate | NONE |
| My school, my pride progress; schools-water, toilets, staff | Visit, check for water, electricity, sanitation ,meet students and staff | All In Place |
| Swachh SBM | Evaluate | Good |
| Panchayat playground, Sports kits distribution Village games | Ensure, verify. Participation at least one game in the playground | Conducted |

| 4 |  |  |
| --- | --- | --- |
| HarGaon Hariyali, Plantation drive | Evaluate status, feedback | Plantation Drive conducted |
| Village cultural event Dangal/Haat/Mela | Participation; ensure that it is held | Participated in Cultural Event |
| Exhibition of schemes | Ensure that every department participates and that it continues for the entire duration of B2V | All Major Departments participated |
| Jal Jeewan Mission Verification - WSS/JSD Electricity supply | Verify | Verified |

# DAY1-ACTIVITIES

AGENDA3:SATURATE JAN ABHIYAN DELIVERABLESANDRECORDDEFICIENCIESIFANY(INSERTDELI VERABLESLISTHEREASPERGADFORMAT

4

DAY1-ACTIVITIES

## AGENDA4:

SELFEMPLOYMENTACTIVITIES

Ensure Self-employment activities for youth, distribute employment letters for people selected under various social schemes (15 is THE TARGET PER PANCHAYAT)

Number of cases in different categories sanctioned: 2Detailsofthebanksanctioningit:

Total amount involved:

# DAY1ACTIVITIES

## AGENDA5

In the evening, hold informal meetings with senior citizens, govt employees, retd employees, youth club and other citizens who are enrolled on college/university and have discussion on Gandhi Katha, Nasha Mukt Abhiyan, corruption free governance, doubling farmers in come and record the proceedings: Done

## DAY2

- No of Individual Compost pits constructed: Nil, Estimation in process

- No of Individual Soak Pits constructed	102

- No. of Biodiversity management committee meetings held:	1

- Is the name of Sarpanch displayed on citizen information boards of all RD &PR schemes :Yes/No	 Yes

- Are Sarpanchs being involved instart /inauguration of activities :Yes/No	Yes

- Whether subjects have been assigned by the Sarpanch to the Panchs :Yes/No	Yes

- Whether grievances redressal box is installed :Yes/No	No

- No of grievance received pertaining to Panchayat level:	8

- No of grievances disposed of at Panchayat level:	            8

- WhethertheSarpanch/PanchayatSecretaryhavedigitalsignatures:Yes/No	Yes

- Whether all MGNREGA/14thFCpayments are being made by Sarpanch through Digital Signature Certificate(DSC):Yes/No	Yes

# HUMAN RESOURCEAVAILABLEATTHEPANCHAYAT LEVEL:

| SRNO. | DEPARTMENTWISESTAFF | NUMBERS |  | NAMES |
| --- | --- | --- | --- | --- |
|  |  | SANCTIONED | ACTUAL | Fayaz Ahmad Mir (KAS) Showkat Ahmad Mudasir Ahmad Irfan Ahmad Teachers Khan Mohd Ishaq Non Teaching Staff Assistant Lineman (6) I/C Filter (2) Mohd Saleem (PDC) Manzoor Ahmad -do- Shabir Ahmad –do- Gh Mohd Shah Ubaid Ashraf (store keeper) Syed Mohd Ashraf –do- Salma Firdous (JAEO) Showket ahmad (Sr.Vet Fayaz ah dar (Asst. Stock) |
|  | Rural Development department: | 1 1 1 1 | 1 1 1 1 |  |
|  | BDO |  |  |  |
|  | JE |  |  |  |
|  | GRS |  |  |  |
|  | TA |  |  |  |
|  | SCHOOLEDUCATION: 6 No. |  |  |  |
|  | TEACHER | 21 | 15 |  |
|  | HEADMASTER/Principal ANYOTHER | 2 6 | 1 0 |  |
|  | JAL JEEVAN: | 8 | 8 |  |
|  | PDD: LINEMAN JE ANYOTHER: I/C MR | 3 1 1 | 3 1 1 |  |
|  | FOOD&CIVILSUPPLIES | 2 | 2 |  |
|  | AGRICULTURE & ANIMAL Husbandary | 1 1 1 | 1 1 1 |  |

| 4 |  |  |  |  |
| --- | --- | --- | --- | --- |
|  | SOCIALWELFARE | 1 | 1 | Mariya Hanief (ORW) |
|  | HEALTH: ASHA ANM AYUSHDOCTOR ALLOPATHICDOCTOR | 3 3 0 0 | 3 3 0 0 | Hanifa (ASHA) Rifat (ASHA) |
|  | ANYOTHERDEPARTMENT Social Forestry | 1 | 1 | Jan Mohd Yaseen (I/C Forest Guard) |

DAY2-ACTIVITIES

## AGENDANO.1

DiscussionontheandassesstheprogressofdifferentschemesrelatingtothelocalizedSDGsprior- itizedforthatvillageaspertheresolutionpassedbythatGramPanchayaton21stApril22, on National Panchayati Raj Day(Copyoftheresolutiontobetakenfromwww.jkpanchayat.inportalunderthelinkof  Gram Swaraj Month)

  - SDGs AGREED FORTHATVILLAGE,TOBEIMPLEMENTED BY MARCH2024: Yes

  - STATUSOFWORKSUNDERTHEFOLLOWINGSCHEMES:	Plan Submitted

## Clean and green village

- InitiativestakenbythePanchayatformanagingSolidandLiquidWastePlan Yes

- InitiativestakenbythePanchayatforusinggreensourcesoffuellikesolar,biogasPlan

Yes

- Hasmappingoflanduse,waterbodies,forest,slopes,wetlands,degradedforestwithintheGram Panchayatbeendone?Yes/No.IfNo,reason,thereof:: NO

- HastheClimateResiliencePlanbeendevelopedfortheGP?Yes/No	Yes

- StepstakenbytheGramSabhaabouttheclimatechangemitigationfactorslikereducingenergy consumption, usage of fossilfuels,plastics,non-renewablebuildingmaterialsandalsotopromote measureslikeplantingoftrees,conservingforests,usageofgoodagriculturalpracticeslikedrip irrigation,waterconservationmeasuresandconservationofwetlands.	Yes

- Whetherschoolshavestartedsegregatingwaste No

- Whetherschools have their own compost/ soakage pits for solid/ liquid waste management: NO

## Healthy village

- Aremeetings relatedtoVillageHealthandSanitationCommitteebeingheldregularly? Yes

- DoalltheeligibleindividualsbeenprovidedtheGoldenCard?	NO

- ArealltheChildrenbeingimmunizedaspertheSchedulerecommendedbyGovt.ofIndia?	YES

- ArealltheeligibleindividualsbeenvaccinatedagainstCOVID-19                         NO

- DoesGramPanchayatensurethatallpregnantwomenaregettingnecessaryprenatalcheckups?	YES

- WhetherallthedeliverieswereInstitutionalizedorconductedbytrainedMidwives?        Institutional

## Water sufficient village

- Do all the IHHs in the Gram Panchayat have water pipeline connections?	Yes

- WhetherGramPanchayathastakenstepsforgreywatermanagement.IfYespleasespecif.	NO

- Do all the IHHs in the Gram Panchayat have toilets?	NO

- ArealltheIHHstoiletsfunctionalornot?	YES

- DoalltheSchools/Anganwadicentershavea toiletfacilityornot?	YES

- Areallthetoiletsintheschools/Aaganwadifunctionalornot?	YES

- WhetherGramPachachayatBhawanhasseparate toiletsforwomenornot?           NO

## Child Friendly village

- Doallthechildrenundertheageof0-6yearsbeenenrolledintheAnganwadicentersforpre- schooling?Yes/NO	YES

- HowmanyBalSabha’swereorganizedintheGramPanchayat     Twice a month

- WhethertheissuesraisedbyBalSabhaareaddressedduringtheGramSabha.  Yes

- WhetherGramPanchayatistrackingthedatarelatedtodropoutchildrenandchildrenwithirregular attendance?Yes/NO.	YES

- DoalltheschoolsundertheGramPanchayathaveseparate toiletsforgirlsandboys?Yes/No Yes

## Village with good governance

- IsCSClocatedintheGramPanchayatBhawanornot?	NO

- IsthelistofbeneficiariesrelatedtotheSchemes/ProgramsdisplayedontheGrampanchayatwallor not? NO

- DoestheGramPanchayathasitsbuildingornot?	NO

- IstheGramPanchayatofficefunctionalornot?	-----

- Aretheactivities approved undertheHalqaPanchayatDevelopmentPlandisplayedontheGram Panchayatwallornot? NO

- IsSocialAuditofearlierSchemes/Programscarriedoutornot?	YES

## Poverty free and enhanced livelihood village

- HasGramPanchayatdevelopedanycriteria fortheidentificationofthepoor?Yes/Noifyesspecify YES & other

- ii)   HavealltheeligiblehouseholdsregisteredinPDSornot?	YES

- HasGramPanchayatprovidedspaceforSelf-helpGroupsinPanchyatGharforholdingmeetings or not? NO Pyt Ghar In Halqa

- HavealltheeligiblehouseholdsbeenregisteredforPensionornot?	Yes

- HasGramPanchayatfacilitatedYouthforSkillEnhancementCoursesandPlacement?	NO

- HasJobCardsbeendistributedtoalltheeligibleindividualsunderMGNREGA?	YES

- HasGramPanchayatfacilitatedSHGsforBankAccountLinkages?	YES

## Sociallysecuredvillage

- WhetherGramPanchayatismaintainingdatarelatedtoDifferentlyAbledPeople?	YES

- IsGramPanchayatOffice DisabledFriendlyornot?  Building not Available

- Areprovisionsfora separate BudgetundertheResourceEnvelopeforWomenandChildrenmadeor not? ----------

- DoalltheSchools intheGramPanchayathavefacilitiesforDifferentlyAbledChildrenliketoilets, barrier- freeaccess,etc.,ornot?	Yes

- Arealltheeligibleindividualsaregettingpensions,likeoldagepension,widowpension,etc?  Yes

- ArealltheeligiblehouseholdsgettingbenefitsfromIAYornot?                                  YES

## Engendered Development in Village

- HowmanyMahilaSabha’swereorganizedintheGramPanchayat 12 sabhas Yearly

- WhetherSHGsfederationshavebeenprovidedspaceformeetings inthePanchayatBhawan(Yes/ No)   No Pyt Ghar In Halqa

- WhetherGPshavetakenstepsforincreasingwomen’sparticipationinGramSabha(Yes/No)  YES

- NumberofwomenbeneficiariesheadedhouseholdscoveredunderPDS system ---

- Numberofbeneficiaries(outoftotaleligiblepopulation)receivingsocialprotectionbenefitsunder PradhanMantriMatritvaVandanaYojana  127

- Self-sufficient infrastructure in the village

- Whether GP has a CommunityHallwithaccesstoelectricity,furniture,watersupply, toilet No

- WhethertheDisastermanagementplanisavailableattheGPLevel(Yes/No)  NO

- Whetherchild-friendlyparkwithrequiredfacilitiesisavailableinGP(Yes/No) No

- WhethertheGPhaseasyaccesstoGodownforstorage(Yes/No) NO

- Whetherstreetlightsareprovidedinpublicplacesforensuringsafety(Yes/No) No

# DAY2ACTIVITIES

## AGENDANO.2

SensitizevillageresidentsaboutmyScheme”portal(myscheme.in)whichincludesinformationaboutall theschemesbeingrunbyCentral/State/UT govtacrossthecountry (SchemeMaterialavailablefromhttps://jkpanchayat.in/b2v4.php)  Yes Done

# DAY2ACTIVITIES

## AGENDANO.3

HoldmeetingoftheBiodiversityManagementCommitteestodeliberateonissues	pertainingtoconserva- tionofbiodiversityandsustainableutilizationofbiologicalresources.HeshouldcheckPeopleBiodiversity register(PBR)ofthatpanchayatandreviewifBiodiversityManagementCommittee		constitutedforthat panchayatis	holdingminimum4meetings	inayearandmeeting	onceinevery3months	(RoleofBMC availableathttps://jkpanchayat.in/b2v4.php)

COMMITTEE MEMBERS: Sarpanch, Chairperson, Pyt secretary, School Headmaster, Panchs, forest Guards.

PRESENT	ALL

BIODIVERSITYREGISTERPHOTOS

PAST 4 MEETINGDETAILS-DATES,MINUTESPHOTOS

# DAY2ACTIVITIES

## AGENDA4

Visitingofficershallalsoplanandconductpanchayatlevelconvergencemeeting ofalldepartmentsand prepareVillagedevelopmentplanforvillage,inconsultancywithGrampanchayat,discussitingram sabhaandgetitapproved.

(GPDPformatavailableonhttps://jkpanchayat.in/b2v4.php) Done, Conducted

InadditionGPDPplanshallalsoinclude: Touristplaceswhichneedtobedeveloped: Bosian, Gabbewar, Hajibal

Specificproductwhichneedstobedeveloped :

Home Stays, ECO-Tourism, Trekking

Tourism-homestays

20candidatesfortrainingunderHimayatschemealongwithtradeinwhich trainingistobegiven List Enclosed

# DAY2ACTIVITIES

## AGENDA5

Ensuresaturationoffollowingschemesandgivestatus:

| NAMEOFTHESCHEME | TOTALELIGIBLE BENEFICIARIESIN THE VILLAGE | TOTALBENEFICIARIESWHO AVAILEDTHEBENEFITSOFT HESCHEME | REASONSFOR PENDENCY |
| --- | --- | --- | --- |
| GoldenHealthCardunder AyushmanBharat | 3385 | 2991 | Unavailability of AADHAR Cards |
| Jananisurakshayojana | 81 | 45 | Non Availibility of funds |
| OLDAGEpension | 186 | 186 | Nil |
| Widowpension | 10 | 10 | Nil |
| Disabilitypension | 46 | 46 | Nil |
| Domicilecertificate |  |  |  |
| Kisancreditcard | 159 | 159 | Nil |
| PMkisanSammannidhi | 202 | 202 | Nil |

| Landpassbook | Nil | Nil | Nil |
| --- | --- | --- | --- |
| Registrationofvillageven- dorsonGEMportal | No | No |  |
|  | No | No |  |
| Registrationofvillagecon- tractorsonjktendersportal |  |  |  |
|  | No | No |  |
| Registrationofvillagecon- tractorsonPWDportal |  |  |  |
| Incompletebuildings/pro- jects | Schol Building at Hajibal |  |  |

# DAY2ACTIVITIES

## AGENDA6 NASHAMUKTABHIYAN

  - Whethergramsabharesolutionpassed	YES

  - Detailsofactivities conducted: Sports, Cultural, Plantation drive, Gram Sabha

  - Whetherallactivities andGSresolutionuploadedonjkpanchayats.inportal: YES

  - Howmanydrugaddictsinthevillage	NIL

  - WhetherreportedtotheDeputyCommissioner	NA

  - Howmanyregisteredforrehabilitationundergovernmentprogram NIL

# DAY2ACTIVITIES

## AGENDA7 SOCIALAUDIT

Conductsocialauditofatleast5workseachunderfollowingschemes:

| NAMEOFTHE SCHEME | DETAILSOFTHE WORKS | YEAROFWORK APPROVAL | AMOUNT APPROVED FORTHEWORK | WHETHER WORKEXECUTED SATISFACTORILY | GEO- TAGGED PHOTOS | ANY GRIEVANCE RECORDED RELATINGTOTHAT WORK |
| --- | --- | --- | --- | --- | --- | --- |
| MGNREGA | No Ongoing Work |  |  |  |  |  |
| PMAY | Only 2 Cases executed in last financialy works going on |  |  |  |  |  |
| IHHL UNDERSBM-G | No Case Executed |  |  |  |  |  |
| CSCUNDER SBMG | NIL | NIL | NIL | NIL | NIL | NIL |
| AMRIT SAROVARS | 5 springs at Hajibal & 3 Springs At Drangbal being taken in current plan |  |  |  |  |  |

# DAY2ACTIVITIES

## AGENDA8 MAHILASABHA

Totalwomeninthevillageabovetheageof18	1007

Totalattended	89

Proceedings: Requested for additional Anganwadi centers because of distance to existing ones.

(Plinsertpointerstobediscussedthere–referpalliproceedings)

# DAY2ACTIVITIES

## AGENDA9 BALSABHA

Holda balsabhaandrecordproceedings

Totalchildreninthevillageabovetheageof10:460Total attended	67

Proceedings: Demand fencing of playground and small changing room (kept in plan)

(Plinsertpointerstobediscussedthere–referpalliproceedings)

# DAY2ACTIVITIES

AGENDA10 INAUGURATIONS

| SR NO. | ASSETS/ACTIVITIES INAUGRATED | STATUSOFTHEASSET/AC- TIVITIES(NUMBER,OTHER DETAILS) | GEO-TAGGED PHOTOS |
| --- | --- | --- | --- |
|  | VILLAGEHAATunderJKSRLM (SUN- DAYMARKET) | None | None |
|  | PMAYhousesifanyreadyforinaugration | Under construction |  |
|  | Swachhgramprojects-segregation shedsetc | One estimation complete |  |
|  | Amritsarovars | 5 springs at Hajibal need development |  |
|  | Sportskits | Carrom and Chess Boards distributed |  |
|  | Villageculturalevents | RUFF and Sufi Music |  |
|  | JJMassets/projects | --- | --- |
|  | Anyothertobeidentifiedatdistrict level | ---- | ---- |

# FOLLOWUPOF(B2V1,B2V2&B2V3):

(Prefilledexcelsheet tobetakenfromdistrictlevel/andalsotobedownloaded fromwww.jkpanchayat.in)

| S.NO. | Particulars | Actiontaken | Remarks# |
| --- | --- | --- | --- |
| I. Urgent Public Requirements/Demands-B2V1 |  |  |  |
| 1 | Inner Links at Drangbal | Work Completed |  |
| 2 | C/o P Bund at Hajibal | Estimate Submitted |  |
| 3 | Food store at Drangbal | Estimate not submitted |  |
| 4 | C/O P Bund at different spots at ward 2 Drangbal | -do- |  |
| 5 | C/O passenger shed ward 6 Drangbal | -do- |  |
| 6 | C/O Road from PMGSY onwards | -do- |  |
| 7 |  |  |  |
| II. Urgent Public Requirements/Demands-B2V2 |  |  |  |
| 1 | PP at Drangbal |  |  |
| 2 | Installation of Transformers |  |  |
| 3 | Blacktopping of Inner Links |  |  |
| 4 | Fencing of playground at Drangbal |  |  |
| 5 |  |  |  |
| 6 |  |  |  |
| 7 |  |  |  |
| S.NO. | Particulars | Actiontaken | Remarks# |
| III. Major Problems–B2V1 |  |  |  |
| 1 2 | Macdamization of Inner Links Non availability of public transport for Hajibal | Not taken up -do- |  |
| BACKTOVILLAGEPHASE- | IV (15THOCTTO3RDNOV) | ¦ 25 |  |

| 3 | Installation of Electric poles | -do- |  |
| --- | --- | --- | --- |
| 5 |  |  |  |
| IV. MajorProblems-B2V2 |  |  |  |
| 1 | Macdamization of Inner Links | Not Taken Up |  |
| 2 | Installation of Transformer & Electric poles | Not Taken Up |  |
| 3 | Inner Drainage system | Not Taken Up |  |
| 4 |  |  |  |
| 5 |  |  |  |
| V. MajorProblems-B2V3 |  |  |  |
| 1 | Macdamization of Inner Links | Not Taken Up |  |
| 2 | Issues Related to stone mining at Drangbal | Not Taken Up |  |
| 3 | Non Availability of Pyt Ghar | Not Taken Up |  |
| 4 | Non Availability of public transport for Hajibal | Not Taken Up |  |
| 5 |  |  |  |
| VI. MajorComplaints-B2V1 |  |  |  |
| 1 | Street Lights at Drangbal | Work not taken up |  |
| 2 | Animal Husbandry Centre | Work not taken up |  |
| 3 |  |  |  |
| VII. MajorComplaints-B2V2 |  |  |  |
| 1 | Non Availability of public transport for Hajibal | No Action |  |
| 2 |  |  |  |
| 3 | Illegal Stone mining at Drangbal | No Action |  |

BACKTOVILLAGEPHASE-IV (15THOCTTO3RDNOV)

| 25