4

15TH OCTto3RD NOV,2022

KEYFEATURES

•     DeputyCommissionerstoleadtheinitiative

•    RuraldevelopmentDepartmenttobethenodaldepartment

•	PlanningDevelopment&MonitoringdepartmentandITtobethesupport departments

ACTIONSANDTIMELINES

| ACTION | RESPONSIBILITY | LATESTBY | REMARKS |
| --- | --- | --- | --- |
| Janabhiyan | Alldepartments | Oct15-26th | Goingon |
| DeputationofSecttstaff/ HoDs | GAD | Oct14 | Done |
| DeploymentofStaffto Panchayatsandservingof ordersondeployedofficers | DCs | Oct25 | DCswilldeployseniorlevelstaff fromthedistricts.Strictactionto betakenagainstabstentions.No exemptionstobegiven |
| Trainingofdistricttrainors onB2V4 | RDD | Oct26 |  |
| Trainingofvisitingofficers | DCs | Oct27 |  |
| FieldVisitstobecompleted by | VisitingOfficers | Nov3 | DCstosuperviseandensurethat eachPanchayatisvisitedwithin theperiodspecified |
| DataofB2V4tobe uploadedby | VisitingOfficers | Nov10 | DCstosuperviseandensurethat dataofallPanchayatsisupload- edbythevisitingofficerwithin theperiodspecified |

INSTRUCTIONSFORTHEVISITINGOFFICER(DAYWISE)

| DATE | INSTRUCTIONS | ACTIONPOINTS |
| --- | --- | --- |
| Day0 | Meetingwithdeputy commissionerandhis/her team | a. TakeprintoutsoffilledbookletsofB2V1,B2V2andB2V3from www.jkpanchayat.in b.Alsotakeprintoutsofthesummarizedexcelsheetsofthe previousphasesfromwww.jkpanchayat.in c. CollectATRsonissuesraisedduringprevious3phasesfromthe officeofDeputyCommissioner(Planningdeptt) d.Takeprintsofblank 2bookletsofB2V4fromwww.jkpanchayat.ine.Takeplansfor2previousyearsandATRsfromtheplanningdeptt f. CompletetrainingsondifferentcomponentsofB2V4being organizedbyrespectiveDeputyCommissioners g.CollectListofnewworksstarted/ongoing/completedduringthe previousandcurrentFinancialyearunderthefollowingheads: • PRIgrants • DistrictPlan • UTplan • MGNREGA • Otherschemesofotherdepartments • Anyotherwork h. Plans/beneficiarylists: • MGNREGAdraftplandocumentfortheyear2022-23. • ListofAwaas+beneficiariesalongwithIHHL Convergence • Listofpensionbeneficiaries. • ListofSHGs • Listofagricultureschemebeneficiaries i. Listsofbeneficiariesfor: • Variouscertificates/benefitstobedistributedbythe visitingofficer. • Anyotheractivitiesidentifiedbydifferentdepartments |

| Day1 | Reachthevillage | 1. | Ensurethatallfrontlineworkersofdifferentdepttsarepresent. |
| --- | --- | --- | --- |
|  |  | 2. | Ensureexhibitionbydifferentdepts.aboutindividualbeneficiary schemes |
|  |  | 3. | InspectJKB/PSBcounters/outlets |
|  |  | 4. | Participate/ensureorganizationofsportsactivityinplayfield,talent hunt/culturalevent/youthactivity |
|  |  | 5. | GandhiKatha(suggesteddetailsuploadedonjkpanchayat.in) |
|  |  | 6. | Visitatleast2amritsarovarsandgetitsgeotaggedphotos |
|  |  | 7. | InspectKhidmat(CSC)CentresandcreateGenerateawarenesson 225schemesparticularlyG2CschemeslikeBEAMS,Janbhagidari, AapkiZaminAapkiNigrani,DigitalJ&K |
|  |  | 8. | Visitingofficershallalsoplanandconductpanchayatlevelconver- gencemeetingofalldepartments |
|  |  | 9. | CheckeffectivenessofCentrallysponsoredschemes |
|  |  | 10. | VisitandinspectallgovernmentestablishmentsincludingPHE, AWC,FPS,schools,etc |
|  |  | 11. | Attemptsaturationofdeliverableso JanAbhiyanandwherever deficienciesfound,leadadrivetoachievealldeliverables |
|  |  | 12. | Assesseffectivenessofsanitationcampaigninthepanchayat |
|  |  | 13. | Ensureselfemploymentactivitiesfor15youthperpanchayat |
|  |  | 14. | Identify20potentialcandidatesperpanchayatforHIMAYATtraining alongwiththetradeonwhichtheywanttraining |
|  |  | 15. | Whereverpossible,distributeemploymentlettersforpeopleselect- edundervariousgovernmentemployments |
|  |  | 16. | Intheevening,holdnormalmeetingwith seniorcitizens,govtem- ployeesincludingretiredemployees,exservicemen,youthclub,and any citizens ofthevillagewhoareenrolledincollege/university |
|  |  | 17. | OpendiscussiononNashaMuktAbhiyan |

Day2            Haveameetingwithall stakeholders-depttofficials andpanchayatmembers

1.       Discussionontheandassesstheprogressofdifferentschemesrelating tothelocalizedSDGsprioritizedforthatvillageaspertheresolution passedby thatGramPanchayaton21st April22,onNationalPanchayti RajDay.

2.	Sensitizevillage residentsaboutmyScheme”portal(myscheme.in) whichincludesinformationaboutalltheschemesbeingrunbyCen- tral/State/UTgovtacrossthecountry

3.	Hold meeting of theBiodiversityManagementCommitteestodeliber- ateonissuespertaining toconservation of biodiversityandsustaina- bleutilizationof biologicalresources.

4.       PrepareVillagedevelopmentplan,inconsultancywithGrampanchayat, discussitingramsabhaandgetitapproved.

5.       Ensure saturationofsoilhealthcardandgoldenhealthcardunderGold- enHealthCardunderAyushmanBharat,

6.       Ensuresaturation  of OldAge PensionScheme

7.       EnsureDomicileSaturation.

8.       EnsureKCCSaturation

9.       Ensure saturationoflandpassbooks

10.     Ensureregistrationofvillagevendorsneededforanyscheme,onGEM

portal

11.     Ensurepanchayatcontractors registration

12.     EncouragePanchayatmembers forimportanceofplantationdrivein

PanchayatunderHarGaonHariyali

13.     Ensure paintingondigitalJ&Kinpanchayatghars

14.     Ensure paintingonpanchayatactivitesandCSSinpanchayatghars

15.	Thevisiting officeshallchecknoof kindergarten andplayfields present inthepanchayat for kidsandstudents,iftheinfrastructure present inthesearegoodenough.

16.     Holdmeeting withpanchayatmembers todiscussaboutcorruption menaceandstepsrequiredtomakeJ&Kcorruptionfree

17.     Obtaina candidassessmentaboutperformanceofvariousdeptts in- cludingfairfeedbackaboutdiscrepanciesinfunctioning

18.	Check thestatusof NashaMuktAbhiyanandreporting of drugad- dictstoDeputyCommissioner.

19.     IdentifyTouristDestinations,Circuits,ThemeTreks,IdentifyHomestays, providesupportfortourismactivities throughVillageCooperative

20.     OrganizeTalentHuntatPanchayatLevel

21.     Conductsocialauditofatleast5worksunderfollowingschemes:

a.       MGNREGA

b.PMAY

c.        IHHLtoiletsandpayments d.CSCs

e.AMRITSAROVARS

22.     Holda mahilasabha anda balsabhaandrecordproceedingsinthefor- matgiven

23.     InauguratevillagehaatunderJKSRLM

24.     Checkifyouthclubsareformedinthepanchayatandwhatactivities theyareengagedin

25.     Organizea villagelevelculturaleventtoengagepanchayatmembers

26.     SensitizeGPaboutE-kitabkoshaninitiativeofJ&KGovtforempowering youthsthrough onlinedigitalliteracy

GENERALINSTRUCTIONS

1.	Thevisitingofficershallrefrainhimself/herselfgivingorofferinganycommitmentonbehalfofthe governmentandshalladoptanunbiasedattitudeinreportingissues.As faraspossible,his/her observation shouldbebasedona fairandanalytical viewemergingfromhis/herinteractioninthe village.

2.	Heisgoingtothevillageasplanningofficer,notforsanctioninganyworksorformakinganycom- mitments.

3.	Whilepreparingvillagedevelopmentplan,hehastoensurethat,demandsareprioritizedandre- flectedunderavailableschemes,wherevernecessarythelargerworksaretobereferredtoadminis- trativedepttunderCSS/UTplansunderintimationtoDCsandrestoftheworkstoDCsforreflecting itunderdistrict/CSS plans

4.    His workshallbehardcoreplanningandauditandisnota PRexercise.

5.	EveryDeputyCommissionerhastoensurethatatleastoneRDDofficial(ideallyPanchayatSecre- tary)ispresent  ineverypanchayatwithrelevantpanchayatrecords,toensureconductofallactivi- tiesasplanned.Panchayatwiseorderneedstobeissuedinadvance.

6.	Visitingofficershouldideallycarryhis/herlaptoptocompletethereportsatthepanchayatlevel itselfanduploadthefinalreport,duly signedbothbythesarpanchandbythevisitingofficeron www.jkpanchayat.inportal,beforetheyleavepanchayat.

7.	Focus ofvisitareyouth,skills,self-employment,nashamukt,bhrashtracharmukt,Rozgaryukt J&K, besidestocarryforwardtheactivities duringJanAbhiyanandsaturatethem.

8.    Inadditionattentionmaybegiventothefollowingareas a.     MakefulluseofCentrallySponsoredSchemes

b.Saturationofindividualbeneficiaryschemes c.     Self-employmentschemes

d.Banklinkedschemes-includingdepartmentalsubsidyschemes e.Empowermentandtransparencythrough digitalinitiatives

f.       Effectivenessofgrassrootsmachinery–

i.       Patwari,VLWpresent  andavailable

ii.      AvailablefundsutilizedinpublicinterestandasperGramSabharesolutions iii.   Fairness ingovernance

iv.    CSS/Individual beneficiaryschemesetc v.      BrashtacharMuktJ&K

vi.   BhaiMuktJ&K

vii.  NashaMuktJ&K

9.	ThePRImembers (Sarpanchs,Panchs,BDCChairperson)shallbeattheforefrontofallactivities and givendueimportanceandtheapproach shouldbetostrengthenthemandmakethemfeelem- powered.He/sheshallensurethattheBDCchairpersonandSarpanch/Panch arepresent  atthetime ofinaugurationandceremonies.

10.	Visitingofficershallnotleavethedistrictwithoutuploadingthereport,duly signedonthewww. jkpanchayat.inportal.EveryDeputyCommissionerhastoensurethat.

A)   DetailsofReportingOfficer:

Name: Altaf Ahmad Nath

Designation: Senior Lecturer

Department/placeof  posting: School Education / HSS Koil

Mobile No: 9906957270

EmailID:altafahmad2225@gmail.com

Home District: Pulwama

Dates of  visit: 28-10-2022 to 29-10-2022

B)	LocationaldetailsofPanchayat:(tobepre-filled,informationtobetakenfromtheprevious phasesbooklets/summarizedexcelsheetuploadedonjkpanchayat.in/b2v4.php)(tobevali- datedbythevisitingofficerandmissingdetailstobefilled)

Name of the Panchayat:- Rajpora Ullar

Local Government Directory(LGD )codeof  thePanchayat:-242838

Name of  CD Block:- Awantipora

Name of Tehsil:- Awantipora

Nameof    District:- Pulwama

C)     PanchayatProfile:

No.ofrevenuevillagesinthePanchayat: 02

No.ofhamletsinthePanchayat:- 04

No.ofhouseholdsinthePanchayat: 334

Population(approx)of  thePanchayat:-2928

Part-II:

(TobefilledupbytheVisitingOfficerduringhis/hertwodayvisittothePanchayat.AllFieldshavetobe

filledbytheVisitingOfficerbeforethebookletishandedovertotheDC

FrontlineOfficers/OfficialswhowereassignedtothePanchayatfortheprogramme:

| Department | Name | Designation |
| --- | --- | --- |
| RDD | Naseema Akhter | V.L.W |
| RDD | Tawseef Ahmad | P.A.A |
| REVENUE | Abdul Hamid Reshi | Patwari |
| SOCIAL FORESTRY | Abdul Ahad Dar | Junior Mali |
| SHEEP | Nazir Ahmad Khan | ASM |
| ANIMAL HUSBANDRY | Khurshid Ahmad | SVP |
| PHE | Abdul Rashid Malik | Lineman |
| PDD | Farooq Ahmad Malik | Lineman |
| HORTICULTURE | Mushtaq Ahmad Mir | H.I.G.III |
| YOUTH SERVICE & SPORTS | Rafeeqa Bano | P.E.M |
| R & B | Shahid ul Islam | Orderly |
| PDD | Bittu Singh | Tech III |
| AGRICULTURE | Sarwa Akhter | G.C.O |

Detailsofabsentemployeesvis-à-vislistfurnishedbytheDCoffice:

| Department | Name | Designation |
| --- | --- | --- |

DAY1-ACTIVITIES

AGENDA1:PANCHAYATASSETREGISTER

Infrastructure:

1.		Panchayat Ghar Infrastructure yes

a. Govt building/private

b.  New/needingrepairs         Government Building ,needs repairs

2.       Furniture(Y/N)                          No

3.       Computer/printer(Y/N)            No

4.       Internet(Y/N)                            No

5.       Telephone(Y/N)                        No

6.       Toilet(CSC/partofpanchayatghar)(Y/N)                 No

7.       Water(Y/N)                               No

8.       Electricity(Y/N)                         No

9.       Bankbranch(Y/N)                      No

10.     CSC(Y/N)                                   Yes

11.     Patwarkhana(Y/N)                     Yes

12.     Villagehaat(Y/N)                        Yes

13.     Playground(Y/N)                        Yes

14.     School-                                      Yes

a.        Kindergarten(Y/N)       No

b.Primary(Y/N)                        Yes

c.         Secondary(Y/N)             No

d. College (Y/N)                       Yes

e.University(Y/N)                     No

15.     AnganwadiCentre(Y/N)              Yes

a.        (govt/private)             Private Building

b.Totalchildrenenrolled         (216)     (8 Centres)

15.     AmritSarovars–details,location,condition   2 Rajpora Condition Miserable

16.     Governmentoffices-details,whetherfunctionalornot    Functional

17.     Rationshop(Y/N)                           Yes

18.      Placesoftourismimportance–names,littledetailsonhistorical/culturalimportance      Nil

19.      Villageheritagesites/treks-names,littledetailson historical/culturalimportance      Nil

20.     VLWOffice (Y/N)                          Yes

21.     PrimaryHealthcareCentre(Y/N),   Yes

22.     ListofIncompleteBuildings-names,yearofconstruction    College under construction

23.     ListofUnderutilizedBuildings-names     Nil

DAY1-ACTIVITIES

AGENDA2:

DIFFERENTINSTITUTIONS/INFRASTRUCTUREPROJECTSTOBEVISITED

| AMRITSAROVARS | Visit,verify | COMMENTS |
| --- | --- | --- |
| KhidmatCentres | Create/Generateawarenesson225schemes particularlyG2CschemsAapkiZaminAapkiNigrani, Beams,Janbhagidari,DigitalJ&K | Provides Services to the People |
| JKB/PSBcounters/outlets | a)Statusofcounter b)Numberofvisitors | Not available |
| Incompletebuildings/pro- jects | Verify whetheridentificationandredistribution done | College under construction |
| PDS | Visit,evaluate,onlinestatus | Available and functional |
| PHC | Visit-evaluate,statusofstaff,equipmentand quality | Functional but needs infrastructural development |
| Youthclubs | Meet,interact,seeksuggestions | Interacted and found aspirational |
| SHG | Meet,identifyproblems,seeksuggestions | Yes need economic assistance |
| PMAY | Inspect,Inaugurate | Yes |
| Myschool,mypride progress;schools-water, toilets,staff | Visit,checkforwater,electricity,sanitation,meet studentsandstaff | Scarcity of water in UPS Rajpora |
| SwachhSBM | Evaluate | Yes |
| Panchayatplayground, Sportskitsdistribution Villagegames | Ensure,verify.Participateinatleastonegamein theplayground | Yes having a big sports ground which needs renovation |
| HarGaonHariyali, Planta- tiondrive | Evaluatestatus,feedback | It is being carried out by social forestry Department |
| Villageculturalevent Dangal/Haat/Mela | Participatein;ensurethatitisheld | Yes performed by ICDS workers |
| Exhibitionofschemes | Ensurethateverydepartmentparticipatesand thatitcontinuesfortheentiredurationofB2V | CSC operater ,discussed them threadbare |
| JalJeewanMission verifica- tion- WSS/JSD Electricitysupply | Verify | Tap water facility not provided to all households. Electricity not provided to all households . |

DAY1-ACTIVITIES

AGENDA3:SATURATEJANBHIYAN

DELIVERABLESANDRECORDDEFICIENCIESIFANY(INSERTDELIVERABLESLISTHEREASPERGADFORMAT

- Development of Watseer road and all other interior roads of the village.

- Earth filling and lying of concrete at Shamshan Ghat” Cremation centre” .

- Up gradation of health sub centre to PHC.

- Provision of Tap water to be ensured to all house holds.

- Opening of Veterinary as the cattle grazers are in huge number.

- Ensuring drinking water facility to all schools in the village.

- Making provisions for transportation like Bus/Sumo service from Rajpora to Tral and Rajpora to Awantipora.

- Repairment/ Renovation of Multipurpose public park/ Janaz Gah.

- Installation of solar street lights throughout the village.

- Construction of Ring Wall at many places in the village like Gurduwara, approach road from Kanji Nag etc

- Making provision of irrigation facility to horticulture land.

List of deliverables

| S.No. | Deliverable | Department | Issued/Workdone |
| --- | --- | --- | --- |
| 1. | Golden Health card | Health | 2773 |
| 2. | Amrit Sarovar | RDD | 2 |
| 3. | CSC | IT | 2 |
| 4. | Pani Samiti meeting | Jal Shakti | 2 meetings |
| 5. | Painting of Digital J&K in panchayat | RDD | Done |
| 6. | Kissan Credit card | Agriculture | 134 |
| 7. | Domicile certificates | Revenue | 1500 |

DAY1-ACTIVITIES

AGENDA4:

SELFEMPLOYMENTACTIVITIES

EnsureSelf-employmentactivities foryouth,distributeemploymentlettersforpeopleselectedunder varioussocialschemes(15ISTHETARGETPERPANCHAYAT)

Numberofcasesindifferentcategoriessanctioned: Detailsofthebanksanctioningit:

Totalamountinvolved:                              (NIL)

DAY1ACTIVITIES

AGENDA5

Intheevening,holdinformalmeetings  withseniorcitizens,govtemployees,retdemployees,youthclub andothercitizenswhoareenrolledoncollege/universityandhavediscussiononGandhiKatha,Nasha MuktAbhiyan,corruptionfreegovernance,doublingfarmersincomeandrecordtheproceedings

(A deliberate meeting was held with all the concerned)

DAY2

a.       NoofIndividualCompostPitsconstructed Nil    b       .NoofIndividualSoakPitsconstructed       23

V.          No.ofBiodiversitymanagementcommitteemeetingsheld: 03

VI.         IsthenameofSarpanchdisplayedoncitizeninformationboardsofallRD&PRschemes: Yes

VII.       AreSarpanchsbeinginvolvedinstart/inaugurationofactivities  :Yes

VIII.      WhethersubjectshavebeenassignedbytheSarpanchtothePanchs:  No

IX.        Whethergrievancesredressalboxisinstalled:   Yes

X.         NoofgrievancesreceivedpertainingtoPanchayatlevel:4 XI.        NoofgrievancesdisposedofatPanchayatlevel:4

XII.       WhethertheSarpanch/PanchayatSecretaryhavedigitalsignatures:Yes

XIII.      WhetherallMGNREGA/14thFCpayments arebeingmadebySarpanchthrough DigitalSignature

Certificate(DSC):No

HUMAN RESOURCEAVAILABLEATTHEPANCHAYAT LEVEL:

| SRNO. | DEPARTMENTWISESTAFF | NUMBERS |  | NAMES |
| --- | --- | --- | --- | --- |
|  |  | SANCTIONED | ACTUAL | VLW :Naseema Akhter JE: Nighatji |
|  | Rural development department: BDO JE GRS TA | 5 | 5 | GRS: Irshad Ahmad TA : Shabir Ahmad PAA : Tawseef Ahmad |
|  | SCHOOLEDUCATION: TEACHER HEADMASTER ANYOTHER | Headmaster (2) Teacher (14) Others (4) | 2 14 4 | H/M Abdul Qayoom Bhat H/M Mohammad Amin |
|  | JAL JEEVAN: | 5 | 5 | Manzoor Ahmad (Helper) and others . |
|  | PDD: LINEMAN JE ANYOTHER | 10 | 10 | Farooq Ahmad Malik and others |
|  | FOOD&CIVILSUPPLIES | 2 | 1 | Nisar Ahmad( Store Keeper) |
|  | AGRICULTURE&ANIMALHUS- BANDARY | 0 | 0 | Nil |
|  | SOCIALWELFARE | 1 | 1 | Rozy Akhter |
|  | HEALTH: ASHA ANM AYUSHDOCTOR ALLOPATHICDOCTOR | 5 | 4 | Shameema ji Mahmooda Banoo and others |
|  | ANYOTHERDEPARTMENT |  |  |  |

DAY2-ACTIVITIES

AGENDANO.1

DiscussionontheandassesstheprogressofdifferentschemesrelatingtothelocalizedSDGsprior-itizedforthatvillageaspertheresolutionpassedbythatGramPanchayaton21stApril22,onNational PanchayatiRajDay(Copyoftheresolutiontobetakenfromwww.jkpanchayat.inportalunderthelinkof GramSwarajMonth)

1.       SDGs AGREED FORTHATVILLAGE,TOBEIMPLEMENTED BYMARCH2024:

2.       STATUSOFWORKSUNDERTHEFOLLOWINGSCHEMES:

1      Cleanandgreenvillage

i.InitiativestakenbythePanchayatformanagingSolidandLiquidWaste Nil

ii.     InitiativestakenbythePanchayatforusinggreensourcesoffuellikesolar,biogas

Nil

iii.  Hasmappingoflanduse,waterbodies,forest,slopes,wetlands,degradedforestwithintheGram

Panchayatbeendone?Yes/No.IfNo,reason,thereof  Nil

iv.    HastheClimateResiliencePlanbeendevelopedfortheGP  No

v.     StepstakenbytheGramSabhaabouttheclimatechangemitigationfactorslikereducingenergy consumption,usageoffossilfuels,plastics,non-renewablebuildingmaterialsandalsotopromote measureslikeplantingoftrees,conservingforests,usageofgoodagriculturalpracticeslikedrip irrigation,waterconservationmeasuresandconservationofwetlands.   Nil

vi.  Whetherschoolshavestartedsegregatingwaste   Yes

vii. Whetherschoolshavetheirowncompost/soakagepitsforsolid/liquidwastemanagement   Yes

2     Healthyvillage

i)    Aremeetings  relatedtoVillageHealthandSanitationCommitteebeingheldregularly?  Yes

ii)   DoalltheeligibleindividualsbeenprovidedtheGoldenCard?   Yes

iii)  ArealltheChildrenbeingimmunizedaspertheSchedulerecommendedbyGovt.ofIndia?    Yes

iv)  ArealltheeligibleindividualsbeenvaccinatedagainstCOVID-19?   Yes

v)   DoesGramPanchayatensurethatallpregnantwomenaregettingnecessaryprenatalcheckups?   Yes

vi)  WhetherallthedeliverieswereInstitutionalizedorconductedbytrainedMidwives?   Institutionalised

3     Watersufficientvillage

i)    DoalltheIHHsintheGramPanchayathavewaterpipelineconnections? NO

ii)   WhetherGramPanchayathastakenstepsforgreywatermanagement.IfYespleasespecify  No                iii)  DoalltheIHHsintheGramPanchayathavetoilets?   Yes

iv)  ArealltheIHHstoiletsfunctionalornot?   Functional

v)   DoalltheSchools/Anganwadicentershavea toiletfacilityornot? Yes

vi)  Areallthetoiletsintheschools/Aaganwadifunctionalornot?   Functional

vii) WhetherGramPachachayatBhawanhasseparate toiletsforwomenornot?No

4      ChildFriendlyvillage

i)	Doallthechildrenundertheageof0-6yearsbeenenrolledintheAnganwadicentersforpre- schooling?Yes

ii)    HowmanyBalSabha’swereorganizedintheGramPanchayat---4----------------

iii)  WhethertheissuesraisedbyBalSabhaareaddressedduringtheGramSabha. Yes

iv)	WhetherGramPanchayatistrackingthedatarelatedtodropoutchildrenandchildrenwithirregular attendance?Yes

v)   DoalltheschoolsundertheGramPanchayathaveseparate toiletsforgirlsandboys?No

5      Villagewithgoodgovernance

i)    IsCSClocatedintheGramPanchayatBhawanornot? Yes operational

ii)	IsthelistofbeneficiariesrelatedtotheSchemes/ProgramsdisplayedontheGrampanchayatwallor not? Yes

iii)  DoestheGramPanchayathasitsbuildingornot? Yes

iv)  IstheGramPanchayatofficefunctionalornot?No

v)   Aretheactivities approved undertheHalqaPanchayatDevelopmentPlandisplayedontheGram

Panchayatwallornot yes

vi)  IsSocialAuditofearlierSchemes/Programscarriedoutornot? Yes

6      Povertyfreeandenhancedlivelihoodvillage

- HasGramPanchayatdevelopedanycriteria fortheidentificationofthepoor?Yes

HavealltheeligiblehouseholdsregisteredinPDSornot? yes

iii)	HasGramPanchayatprovidedspaceforSelf-helpGroupsinPanchyatGharforholdingmeetings  or not? yes

iv)  HavealltheeligiblehouseholdsbeenregisteredforPensionornot?yes

v)   HasGramPanchayatfacilitatedYouthforSkillEnhancementCoursesandPlacement?yes

vi)  HasJobCardsbeendistributedtoalltheeligibleindividualsunderMGNREGA?yes

vii) HasGramPanchayatfacilitatedSHGsforBankAccountLinkages?No

7     Sociallysecuredvillage

i)    WhetherGramPanchayatismaintainingdatarelatedtoDifferentlyAbledPeople?yes

ii)   IsGramPanchayatOffice DisabledFriendlyornot?yes

iii)	Areprovisionsfora separate BudgetundertheResourceEnvelopeforWomenandChildrenmadeor not?No

iv)	DoalltheSchools intheGramPanchayathavefacilitiesforDifferentlyAbledChildrenliketoilets, barrier-freeaccess,etc.,ornot?yes

v)   Arealltheeligibleindividualsaregettingpensions,likeoldagepension,widowpension,etc?yes

vi)  ArealltheeligiblehouseholdsgettingbenefitsfromIAYornot.yes

8      EngenderedDevelopmentinVillage

i)    HowmanyMahilaSabha’swereorganizedintheGramPanchayat-------4------------

ii)	WhetherSHGsfederationshavebeenprovidedspaceformeetings  inthePanchayatBhawan(Yes)

iii)  WhetherGPshavetakenstepsforincreasingwomen’sparticipationinGramSabha(Yes)

iv)  NumberofwomenbeneficiariesheadedhouseholdscoveredunderPDS

system……13…………………

v)   Numberofbeneficiaries(outoftotaleligiblepopulation)receivingsocialprotectionbenefitsunder

PradhanMantriMatritvaVandanaYojana………17………….

9    Self-sufficientinfrastructureinthevillage

i.	WhetherGPhasa CommunityHallwithaccesstoelectricity,furniture,watersupply,       toilet ……no…………….

ii.     WhethertheDisastermanagementplanisavailableattheGPLevel(No)

iii.  Whetherchild-friendlyparkwithrequiredfacilitiesisavailableinGP(No)

iv.    WhethertheGPhaseasyaccesstoGodownforstorage(No)

v.     Whetherstreetlightsareprovidedinpublicplacesforensuringsafety(Yes)

DAY2ACTIVITIES

AGENDANO.2

SensitizevillageresidentsaboutmyScheme”portal(myscheme.in)whichincludesinformationaboutall theschemesbeingrunbyCentral/State/UT govtacrossthecountry  Sensitised by CSC

(SchemeMaterialavailablefromhttps://jkpanchayat.in/b2v4.php)

DAY2ACTIVITIES

AGENDANO.3

HoldmeetingoftheBiodiversityManagementCommitteestodeliberateonissuespertainingtoconserva- tionofbiodiversityandsustainableutilizationofbiologicalresources.HeshouldcheckPeopleBiodiversity register(PBR)ofthatpanchayatandreviewifBiodiversityManagementCommittee constitutedforthat panchayatis holdingminimum4meetings inayearandmeeting onceinevery3months (RoleofBMC availableathttps://jkpanchayat.in/b2v4.php)     Not Constituted

COMMITTEEMEMBERS PRESENT

BIODIVERSITYREGISTERPHOTOS

PAST 4MEETINGDETAILS-DATES,MINUTESPHOTOS

DAY2ACTIVITIES

AGENDA4

Visitingofficershallalsoplanandconductpanchayatlevelconvergencemeeting  ofalldepartmentsand prepareVillagedevelopmentplanforvillage,inconsultancywithGrampanchayat,discussitingram sabhaandgetitapproved.

(GPDPformatavailableonhttps://jkpanchayat.in/b2v4.php)

InadditionGPDPplanshallalsoinclude:

           Touristplaceswhichneedtobedeveloped

           Specificproductwhichneedstobedeveloped

           Tourism-homestays

	20candidatesfortrainingunderHimayatschemealongwithtradeinwhich trainingistobegiven

DAY2ACTIVITIES

AGENDA5

Ensuresaturationoffollowingschemesandgivestatus:

| NAMEOFTHESCHEME | TOTALELIGIBLE BENEFICIARIESIN THE VILLAGE | TOTALBENEFICIARIESWHO AVAILEDTHEBENEFITSOFTHESCHEME | REASONSFOR PENDENCY |
| --- | --- | --- | --- |
| GoldenHealthCardunder AyushmanBharat | 2928 | 2773 | Due to biometric and NFSA error |
| Jananisurakshayojana | 80 | 80 | nil |
| OLDAGEpension | 111 | 111 | No Pendency 0 |
| Widowpension | 24 24 | 24 | nil |
| Disabilitypension | 24 | 24 | nil |
| Domicilecertificate | 2878 | 1500 | Under process |
| Kisancreditcard | 134 | 134 | nil |
| PMkisansammannidhi | 134 | 120 | 4 deaths and mutation is pending for the rest |

| Landpassbook | 420 | nil | Digitalisqation of land records is under Process |
| --- | --- | --- | --- |
| Registrationofvillageven- dorsonGEMportal | 244 | nil | Not applied |
| Registrationofvillagecon- tractorsonjktendersportal | 5 | 5 | nil |
| Registrationofvillagecon- tractorsonPWDportal | 0 | 0 | Not applied |
| Incompletebuildings/pro- jects | 1 | 1 | Under construction |

DAY2ACTIVITIES

AGENDA6

NASHAMUKTABHIYAN

1.       Whethergramsabharesolutionpassed yes

2.       Detailsofactivities conducted (Developmental activities and to tackle the menace of drugs)

3.       Whetherallactivities andGSresolutionuploadedonjkpanchayats.inportal yes

4.       Howmanydrugaddictsinthevillage  Zero

5.       WhetherreportedtotheDeputyCommissioner nil

6.       Howmanyregisteredforrehabilitationundergovernmentprogrammde nil

DAY2ACTIVITIES

AGENDA7

SOCIALAUDIT

Conductsocialauditofatleast5workseachunderfollowingschemes:

| NAMEOFTHE SCHEME | DETAILSOFTHE WORKS | YEAROFWORK APPROVAL | AMOUNT APPROVED FORTHEWORK | WHETHER WORKEXECUTED SATISFACTORILY | GEO- TAGGED PHOTOS | ANY GRIEVANCE RECORDED RELATINGTOTHAT WORK |
| --- | --- | --- | --- | --- | --- | --- |
| MGNREGA | Const of road | 2020-21 | 4.30 lac | yes | Yes | No |
| PMAY | 3beneficiaries | 2020-21 | 4.80 lac | Yes | Yes | No |
| IHHL UNDERSBM-G | 100 benefici. | 2018 till date | 0.12 lac per | Yes | Yes | No |
| CSCUNDER SBMG | 2 | 2021-22 | 5.98 | Yes | Yes | No |
| AMRIT SAROVARS | 1 | 2022-23 | 2.00lac | Yes | Yes | No |

DAY2ACTIVITIES

AGENDA8

MAHILASABHA

Totalwomeninthevillageabovetheageof18=  812

Totalattended =  55

Proceedings:  Discussed issues faced by women

(Plinsertpointerstobediscussedthere–referpalliproceedings)

DAY2ACTIVITIES

AGENDA9

BALSABHA

Holda balsabhaandrecordproceedings

Totalchildreninthevillageabovetheageo 3-14= 250 Totalattended=20

Proceedings: Strongly demanded sports ground renovation

(Plinsertpointerstobediscussedthere–referpalliproceedings)

DAY2ACTIVITIES

AGENDA10

INAUGURATIONS

| SR NO. | ASSETS/ACTIVITIES INAUGRATED | STATUSOFTHEASSET/AC- TIVITIES(NUMBER,OTHER DETAILS) | GEO-TAGGED PHOTOS |
| --- | --- | --- | --- |
|  | VILLAGEHAATunderJKSRLM (SUN- DAYMARKET) | 01= Carried only by ICDS workers | Yes |
|  | PMAYhousesifanyreadyforinaugra- tion | 1 | yes |
|  | Swachhgramprojects-segregation shedsetc | zero | nil |
|  | Amritsarovars | 2 | Yes |
|  | Sportskits | Distributed sports kits as per the modalities | yes |
|  | Villageculturalevents | 1, performed by school children | nil |
|  | JJMassets/projects | 1 | Yes |
|  | Anyothertobeidentifiedatdistrict level |  |  |

FOLLOWUPOF(B2V1,B2V2&B2V3):

(Prefilledexcelsheet tobetakenfromdistrictlevel/andalsotobedownloaded

fromwww.jkpanchayat.in)

| S.NO. | Particulars |  |  |  |  | Actiontaken | Remarks# |
| --- | --- | --- | --- | --- | --- | --- | --- |
| I. UrgentPublicRequirements/Demands-B2V1 |  |  |  |  |  |  |  |
| 1. Upgradation of infrastructure through out Panchayat the panchyat |  |  |  |  |  |  |  |
| 2.Upgradation of Health Sub centre to PHC |  |  |  |  |  |  |  |
| 3.Development of Watseer road. |  |  |  |  |  |  |  |
| 4.Provision of Tap water to entire village. |  |  |  |  |  |  |  |
| 5. |  |  |  |  |  |  |  |
| 6 |  |  |  |  |  |  |  |
| 7 |  |  |  |  |  |  |  |
| II. UrgentPublicRequirements/Demands-B2V2 |  |  |  |  |  |  |  |
| - Provision of Harvesting tanks for horticulture purpose. |  |  |  |  |  |  |  |
| - Provision of vetanary as good number of people are rearing Cattles |  |  |  |  |  |  |  |
| 4 |  |  |  |  |  |  |  |
| 5 |  |  |  |  |  |  |  |
| 6 |  |  |  |  |  |  |  |
| 7 |  |  |  |  |  |  |  |
| S.NO. |  |  |  | Particulars |  | Actiontaken | Remarks# |
| III. MajorProblems–B2V1 |  |  |  |  |  |  |  |
| - Making arrangements for the development of Watseer road. |  |  |  |  |  |  |  |
| 2 |  |  |  |  |  |  |  |
| 3 |  |  |  |  |  |  |  |

| 4 |  |  |  |
| --- | --- | --- | --- |
| 5 |  |  |  |
| IV. MajorProblems-B2V2 |  |  |  |
| - Making provisions for Tap water to every House hold and development of interior roads throughout the village. |  |  |  |
| 2 |  |  |  |
| 3 |  |  |  |
| 4 |  |  |  |
| 5 |  |  |  |
| V. MajorProblems-B2V3 |  |  |  |
| - Raising and filling of Shamshaan Ghat “ Cremation site” |  |  |  |
| 2 |  |  |  |
| 3 |  |  |  |
| 4 |  |  |  |
| 5 |  |  |  |
| VI. MajorComplaints-B2V1 |  |  |  |
| - Nil |  |  |  |
| 2 |  |  |  |
| 3 |  |  |  |
| VII. MajorComplaints-B2V2 |  |  |  |
| - Nil |  |  |  |
| 2 |  |  |  |
| 3 |  |  |  |
| VIII. MajorComplaints-B2V3 |  |  |  |
| - Nil |  |  |  |
| 2 |  |  |  |
| 3 |  |  |  |

OVERALLPERCEPTIONOFFUCNTIONING OF GOVERNMENTDEPARTMENTS

1.         BESTDEPARTMENT:

2.       LEASTRESPONSIVEDEPARTMENT:

GENERALASSESSMENTOFTHEVISTINGOFFICER

| I | AnymajorcomplaintbroughttothenoticeoftheVisitingOfficer: Nil |
| --- | --- |
| II | Major/urgentpublicdemandsthatwas/werereflectedearlierbuthavenotbeenaddressedsofar: Al ready reflected in the report. |
| III | Overallassessmentofthevisitandsuggestions: (Thevisitingofficertoensurethattheoverallassessmentisrecordedindetailsalongwithconcretesugges- tions). B2V4; A good initiative, needs practicle implementation |
| IV | OverallRatingofgovtfunctioningas givenbythePanchayat(Scaleof0to10): 8 |
| V | CertificatefromSarpanchthatthevisitingofficerhasstayedinthepanchayatfor2days |

Signature of Sarpanch                                                                              Signature of theVisiting Officer

Name………………………                                                                               Name………………………

DepartmentofRuralDevelompentandPanchayatiRaj

GovernmentofJammu &Kashmir