4

15TH OCTto3RD NOV,2022

KEYFEATURES

•     DeputyCommissionerstoleadtheinitiative

•    RuraldevelopmentDepartmenttobethenodaldepartment

•	PlanningDevelopment&MonitoringdepartmentandITtobethesupport departments

ACTIONSANDTIMELINES

| ACTION | RESPONSIBILITY | LATESTBY | REMARKS |
| --- | --- | --- | --- |
| Janabhiyan | Alldepartments | Oct15-26th | Goingon |
| DeputationofSecttstaff/ HoDs | GAD | Oct14 | Done |
| DeploymentofStaffto Panchayatsandservingof ordersondeployedofficers | DCs | Oct25 | DCswilldeployseniorlevelstaff fromthedistricts.Strictactionto betakenagainstabstentions.No exemptionstobegiven |
| Trainingofdistricttrainors onB2V4 | RDD | Oct26 |  |
| Trainingofvisitingofficers | DCs | Oct27 |  |
| FieldVisitstobecompleted by | VisitingOfficers | Nov3 | DCstosuperviseandensurethat eachPanchayatisvisitedwithin theperiodspecified |
| DataofB2V4tobe uploadedby | VisitingOfficers | Nov10 | DCstosuperviseandensurethat dataofallPanchayatsisupload- edbythevisitingofficerwithin theperiodspecified |

INSTRUCTIONSFORTHEVISITINGOFFICER(DAYWISE)

| DATE | INSTRUCTIONS | ACTIONPOINTS |
| --- | --- | --- |
| Day0 | Meetingwithdeputy commissionerandhis/her team | a. TakeprintoutsoffilledbookletsofB2V1,B2V2andB2V3from www.jkpanchayat.in b.Alsotakeprintoutsofthesummarizedexcelsheetsofthe previousphasesfromwww.jkpanchayat.in c. CollectATRsonissuesraisedduringprevious3phasesfromthe officeofDeputyCommissioner(Planningdeptt) d.Takeprintsofblank 2bookletsofB2V4fromwww.jkpanchayat.ine.Takeplansfor2previousyearsandATRsfromtheplanningdeptt f. CompletetrainingsondifferentcomponentsofB2V4being organizedbyrespectiveDeputyCommissioners g.CollectListofnewworksstarted/ongoing/completedduringthe previousandcurrentFinancialyearunderthefollowingheads: • PRIgrants • DistrictPlan • UTplan • MGNREGA • Otherschemesofotherdepartments • Anyotherwork h. Plans/beneficiarylists: • MGNREGAdraftplandocumentfortheyear2022-23. • ListofAwaas+beneficiariesalongwithIHHL Convergence • Listofpensionbeneficiaries. • ListofSHGs • Listofagricultureschemebeneficiaries i. Listsofbeneficiariesfor: • Variouscertificates/benefitstobedistributedbythe visitingofficer. • Anyotheractivitiesidentifiedbydifferentdepartments |

| Day1 | Reachthevillage | 1. | Ensurethatallfrontlineworkersofdifferentdepttsarepresent. |
| --- | --- | --- | --- |
|  |  | 2. | Ensureexhibitionbydifferentdepts.aboutindividualbeneficiary schemes |
|  |  | 3. | InspectJKB/PSBcounters/outlets |
|  |  | 4. | Participate/ensureorganizationofsportsactivityinplayfield,talent hunt/culturalevent/youthactivity |
|  |  | 5. | GandhiKatha(suggesteddetailsuploadedonjkpanchayat.in) |
|  |  | 6. | Visitatleast2amritsarovarsandgetitsgeotaggedphotos |
|  |  | 7. | InspectKhidmat(CSC)CentresandcreateGenerateawarenesson 225schemesparticularlyG2CschemeslikeBEAMS,Janbhagidari, AapkiZaminAapkiNigrani,DigitalJ&K |
|  |  | 8. | Visitingofficershallalsoplanandconductpanchayatlevelconver- gencemeetingofalldepartments |
|  |  | 9. | CheckeffectivenessofCentrallysponsoredschemes |
|  |  | 10. | VisitandinspectallgovernmentestablishmentsincludingPHE, AWC,FPS,schools,etc |
|  |  | 11. | Attemptsaturationofdeliverableso JanAbhiyanandwherever deficienciesfound,leadadrivetoachievealldeliverables |
|  |  | 12. | Assesseffectivenessofsanitationcampaigninthepanchayat |
|  |  | 13. | Ensureselfemploymentactivitiesfor15youthperpanchayat |
|  |  | 14. | Identify20potentialcandidatesperpanchayatforHIMAYATtraining alongwiththetradeonwhichtheywanttraining |
|  |  | 15. | Whereverpossible,distributeemploymentlettersforpeopleselect- edundervariousgovernmentemployments |
|  |  | 16. | Intheevening,holdnormalmeetingwith seniorcitizens,govtem- ployeesincludingretiredemployees,exservicemen,youthclub,and any citizens ofthevillagewhoareenrolledincollege/university |
|  |  | 17. | OpendiscussiononNashaMuktAbhiyan |

Day2            Haveameetingwithall stakeholders-depttofficials andpanchayatmembers

1.       Discussionontheandassesstheprogressofdifferentschemesrelating tothelocalizedSDGsprioritizedforthatvillageaspertheresolution passedby thatGramPanchayaton21st April22,onNationalPanchayti RajDay.

2.	Sensitizevillage residentsaboutmyScheme”portal(myscheme.in) whichincludesinformationaboutalltheschemesbeingrunbyCen- tral/State/UTgovtacrossthecountry

3.	Hold meeting of theBiodiversityManagementCommitteestodeliber- ateonissuespertaining toconservation of biodiversityandsustaina- bleutilizationof biologicalresources.

4.       PrepareVillagedevelopmentplan,inconsultancywithGrampanchayat, discussitingramsabhaandgetitapproved.

5.       Ensure saturationofsoilhealthcardandgoldenhealthcardunderGold- enHealthCardunderAyushmanBharat,

6.       Ensuresaturation  of OldAge PensionScheme

7.       EnsureDomicileSaturation.

8.       EnsureKCCSaturation

9.       Ensure saturationoflandpassbooks

10.     Ensureregistrationofvillagevendorsneededforanyscheme,onGEM

portal

11.     Ensurepanchayatcontractors registration

12.     EncouragePanchayatmembers forimportanceofplantationdrivein

PanchayatunderHarGaonHariyali

13.     Ensure paintingondigitalJ&Kinpanchayatghars

14.     Ensure paintingonpanchayatactivitesandCSSinpanchayatghars

15.	Thevisiting officeshallchecknoof kindergarten andplayfields present inthepanchayat for kidsandstudents,iftheinfrastructure present inthesearegoodenough.

16.     Holdmeeting withpanchayatmembers todiscussaboutcorruption menaceandstepsrequiredtomakeJ&Kcorruptionfree

17.     Obtaina candidassessmentaboutperformanceofvariousdeptts in- cludingfairfeedbackaboutdiscrepanciesinfunctioning

18.	Check thestatusof NashaMuktAbhiyanandreporting of drugad- dictstoDeputyCommissioner.

19.     IdentifyTouristDestinations,Circuits,ThemeTreks,IdentifyHomestays, providesupportfortourismactivities throughVillageCooperative

20.     OrganizeTalentHuntatPanchayatLevel

21.     Conductsocialauditofatleast5worksunderfollowingschemes:

a.       MGNREGA

b.PMAY

c.        IHHLtoiletsandpayments d.CSCs

e.AMRITSAROVARS

22.     Holda mahilasabha anda balsabhaandrecordproceedingsinthefor- matgiven

23.     InauguratevillagehaatunderJKSRLM

24.     Checkifyouthclubsareformedinthepanchayatandwhatactivities theyareengagedin

25.     Organizea villagelevelculturaleventtoengagepanchayatmembers

26.     SensitizeGPaboutE-kitabkoshaninitiativeofJ&KGovtforempowering youthsthrough onlinedigitalliteracy

GENERALINSTRUCTIONS

1.	Thevisitingofficershallrefrainhimself/herselfgivingorofferinganycommitmentonbehalfofthe governmentandshalladoptanunbiasedattitudeinreportingissues.As faraspossible,his/her observation shouldbebasedona fairandanalytical viewemergingfromhis/herinteractioninthe village.

2.	Heisgoingtothevillageasplanningofficer,notforsanctioninganyworksorformakinganycom- mitments.

3.	Whilepreparingvillagedevelopmentplan,hehastoensurethat,demandsareprioritizedandre- flectedunderavailableschemes,wherevernecessarythelargerworksaretobereferredtoadminis- trativedepttunderCSS/UTplansunderintimationtoDCsandrestoftheworkstoDCsforreflecting itunderdistrict/CSS plans

4.    His workshallbehardcoreplanningandauditandisnota PRexercise.

5.	EveryDeputyCommissionerhastoensurethatatleastoneRDDofficial(ideallyPanchayatSecre- tary)ispresent  ineverypanchayatwithrelevantpanchayatrecords,toensureconductofallactivi- tiesasplanned.Panchayatwiseorderneedstobeissuedinadvance.

6.	Visitingofficershouldideallycarryhis/herlaptoptocompletethereportsatthepanchayatlevel itselfanduploadthefinalreport,duly signedbothbythesarpanchandbythevisitingofficeron www.jkpanchayat.inportal,beforetheyleavepanchayat.

7.	Focus ofvisitareyouth,skills,self-employment,nashamukt,bhrashtracharmukt,Rozgaryukt J&K, besidestocarryforwardtheactivities duringJanAbhiyanandsaturatethem.

8.    Inadditionattentionmaybegiventothefollowingareas a.     MakefulluseofCentrallySponsoredSchemes

b.Saturationofindividualbeneficiaryschemes c.     Self-employmentschemes

d.Banklinkedschemes-includingdepartmentalsubsidyschemes e.Empowermentandtransparencythrough digitalinitiatives

f.       Effectivenessofgrassrootsmachinery–

i.       Patwari,VLWpresent  andavailable

ii.      AvailablefundsutilizedinpublicinterestandasperGramSabharesolutions iii.   Fairness ingovernance

iv.    CSS/Individual beneficiaryschemesetc v.      BrashtacharMuktJ&K

vi.   BhaiMuktJ&K

vii.  NashaMuktJ&K

9.	ThePRImembers (Sarpanchs,Panchs,BDCChairperson)shallbeattheforefrontofallactivities and givendueimportanceandtheapproach shouldbetostrengthenthemandmakethemfeelem- powered.He/sheshallensurethattheBDCchairpersonandSarpanch/Panch arepresent  atthetime ofinaugurationandceremonies.

10.	Visitingofficershallnotleavethedistrictwithoutuploadingthereport,duly signedonthewww. jkpanchayat.inportal.EveryDeputyCommissionerhastoensurethat.

A)   DetailsofReportingOfficer:

Name:    Mohd Shafi Dar

Designation:Agriculture Extension Officer

Department/place of  posting: Department of Agriculture/ Sub Division Kakapora

MobileNo: 7006287763

EmailID: mohdshafishafi05@gmail.com

Home District: Pulwama

Datesof  visit: 28-10-2022 to 29-10-2022

B)	Locational details of Panchayat:(tobepre-filled,informationtobetakenfromtheprevious phasesbooklets/summarizedexcelsheetuploadedonjkpanchayat.in/b2v4.php)(tobevali- datedbythevisitingofficerandmissingdetailstobefilled)

NameofthePanchayat: Amlar

LocalGovernmentDirectory(LGD)codeof  thePanchayat:242889

Nameof  CD Block: Dadsara

NameofTehsil: Tral

Nameof    District: Pulwama

C)     Panchayat Profile:

No.of revenue villages in the Panchayat: 01

No. of hamlets in the Panchayat: 02

No.of households in the Panchayat: 613

Population(approx)of  the Panchayat: 3255

Part-II:

(TobefilledupbytheVisitingOfficerduringhis/hertwodayvisittothePanchayat.AllFieldshavetobe

Filled by the Visiting Officer before the booklet is handed over to the DC

FrontlineOfficers/OfficialswhowereassignedtothePanchayatfortheprogramme:

| Department | Name | Designation |
| --- | --- | --- |
| Rural Dev Department | Ali Mohd Wani | VLW |
| PDD | Mushtaq Ahmad | Sec Incharge |
| Agriculture | Bilal Ahmad Bhat | AEA |
| Forest | Manzoor Ahmad | Forester |
| Horticulture | Mohd Ashraf Reshi | HTG II |
| Irrigation | Shabir Ahmad | EG |
| Social Forestry | Farooq Ahmad | Jr Malli |
| Health | Rayeesa Bano | FMPHW/ANM |
| Youth Services and Sports | Mir Raies Ahmad | Phy Education teacher |
| Food and Civil Supplies | Wakeel Ahmad Dar | Store Keeper |
| Sheep Husbandry | Rukaya Rafiq | Assistant Stockman |
| PHE | Rafiq Ahmad | Helper |
| Revenue | Bashir Ah Dar | Patwari |

Details of absent employees vis-à-vis list furnished by the DC office:

| Department | Name | Designation |
| --- | --- | --- |
| Bank |  |  |

DAY1-ACTIVITIES

AGENDA1:PANCHAYATASSETREGISTER

Infrastructure:

1.		Panchayat Ghar Infrastructure a.  Govtbuilding/private

b.  New/needingrepairs… New

2.       Furniture(Y/N)--- Y

3.       Computer/printer(Y/N)--- N

4.       Internet(Y/N)--- N

5.       Telephone(Y/N)--- N

6.       Toilet(CSC/partofpanchayatghar)(Y/N)--- Y

7.       Water(Y/N)--- Y

8.       Electricity(Y/N)--Y

9.       Bankbranch(Y/N)--- N

10.     CSC(Y/N)--- Y

11.     Patwarkhana(Y/N)--- Y

12.     Village haat(Y/N)--- N

13.     Playground(Y/N)--- N

14.     School-

a.        Kindergarten(Y/N)-- N

b.Primary(Y/N)-- Y

c.         Secondary(Y/N)--- Y

d. College (Y/N)-- N

e.University(Y/N)--- N

15.     Anganwadi Centre(Y/N)-- Y

a.        (govt/private)--- Private rented

b. Total children enrolled--- 217

15.     Amrit Sarovars–details,location,condition… Reshi Mohalla (Good condition)

16.     Governmentoffices-details,whetherfunctionalornot---- Nil

17.     Rationshop(Y/N)--- Y

18.      Placesoftourismimportance–names,littledetailsonhistorical/culturalimportance--- Not available

19.      Village heritage sites/treks-names ,little details on historical/cultural importance--- Not available

20.     VLWOffice (Y/N)-- Y

21.     Primary Health care Centre(Y/N)-- Y

22.     List of Incomplete Buildings-names, year of construction—Health Centre and Middle School

23.     List of Underutilized Buildings-names--- Not available

DAY1-ACTIVITIES

AGENDA2:

DIFFERENTINSTITUTIONS/INFRASTRUCTUREPROJECTSTOBEVISITED

| AMRITSAROVARS | Visit,verify | COMMENTS |
| --- | --- | --- |
| KhidmatCentres | Create/Generateawarenesson225schemes particularlyG2CschemsAapkiZaminAapkiNigrani, Beams,Janbhagidari,DigitalJ&K | CSC centre at Amlar. All services being provided |
| JKB/PSBcounters/outlets | a)Statusofcounter b)Numberofvisitors | No branch at GP |
| Incompletebuildings/pro- jects | Verify whetheridentificationandredistribution done | School and Health Centre |
| PDS | Visit,evaluate,onlinestatus | Visited and found satisfactory |
| PHC | Visit-evaluate,statusofstaff,equipmentand quality | Satisfactory |
| Youthclubs | Meet,interact,seeksuggestions | Did not participate |
| SHG | Meet,identifyproblems,seeksuggestions | Met SHGs. Lack of awareness |
| PMAY | Inspect,Inaugurate | Inaugurated |
| Myschool,mypride progress;schools-water, toilets,staff | Visit,checkforwater,electricity,sanitation,meet studentsandstaff | Facility wise found satisfactory but staff dearth noticed |
| Swachh SBM | Evaluate | Evaluated |
| Panchayatplayground, Sportskitsdistribution Villagegames | Ensure,verify.Participateinatleastonegamein theplayground | Play ground Not available. Sports kits distributed among old age club |
| HarGaonHariyali, Planta- tiondrive | Evaluatestatus,feedback | Plantation drive inaugurated |
| Village cultural event Dangal/Haat/Mela | Participatein;ensurethatitisheld | Held |
| Exhibitionofschemes | Ensurethateverydepartmentparticipatesand thatitcontinuesfortheentiredurationofB2V | Done by all Departments |
| JalJeewanMission verifica- tion- WSS/JSD Electricitysupply | Verify | Verified JJM. Electricity Supply satisfactory |

DAY1-ACTIVITIES

AGENDA3: SATURATE JAN BHIYAN

DELIVERABLES AND RECORD DEFICIENCIES IF ANY (INSERT DELIVERABLES LIST HEREAS PER GAD FORMAT

All the frontline departments assured that the Jan Abhiyan deliverables have been achieved to a considerable extent. However, the achievements are not 100% due to poor public participation and interest. Saturation of PMKISAN and PMKMY schemes have been achieved to a great extent by Deptt of Agriculture

DAY1-ACTIVITIES

AGENDA4:

SELFEMPLOYMENTACTIVITIES--- No official from any bank was present to provide the data.

Ensure Self-employment activities for youth, distribute employment letters for peoples elected under various social schemes(15ISTHETARGETPERPANCHAYAT)

Number of cases in different categories sanctioned: Details of the bank sanctioning it:

Total amount involved:

DAY1ACTIVITIES

AGENDA5

Intheevening,holdinformalmeetings  withseniorcitizens,govtemployees,retdemployees,youthclub andothercitizenswhoareenrolledoncollege/universityandhavediscussiononGandhiKatha,Nasha MuktAbhiyan,corruptionfreegovernance,doublingfarmersincomeandrecordtheproceedings

DAY2

a.       No of Individual Compost Pits constructed--- Under process

-b.No of Individual Soak Pits constructed--- 25

V.          No. of Biodiversity management committee meetings held: 01

VI.         Is the name of Sarpanch displayed on citizen information boards of all RD&PR schemes:Yes/No-- No

VII.       Are Sarpanchs being involved in start/inauguration of activities: Yes/No--- No

VIII.      Whether subjects have been assigned by the Sarpanch to the Panchs: Yes/No--- No

IX.        Whether grievances redressal box is installed: Yes/N--- Yes

X.         NoofgrievancesreceivedpertainingtoPanchayatlevel:   Nil

XI.        NoofgrievancesdisposedofatPanchayatlevel:   Nil

XII.       WhethertheSarpanch/PanchayatSecretaryhavedigitalsignatures:Yes/No--- Yes

XIII.      WhetherallMGNREGA/14thFCpayments arebeingmadebySarpanchthrough DigitalSignature

Certificate(DSC):Yes/No--- No Sarpanch exists in the Panchayat

.

HUMAN RESOURCEAVAILABLEATTHEPANCHAYAT LEVEL:

| SRNO. | DEPARTMENTWISESTAFF | NUMBERS |  | NAMES |
| --- | --- | --- | --- | --- |
|  |  | SANCTIONED | ACTUAL |  |
|  | Rural development department: BDO JE GRS TA | 01 01 01 01 | 01 01 01 01 | Shafiq Ahmad Wani Mohd Shafi Wani Nisar Ah Tantray Farhat Agha |
|  | SCHOOLEDUCATION: (high/middle/pry schools TEACHER HEADMASTER ANYOTHER | 31 03 | 22 03 | Nazir Khanday, Farooq Parray |
|  | JAL JEEVAN: Helper Casual Labour | 02 01 | 02 01 | Rafiq Ah Mir, Mohd Maqbool Javaid Ah Sheikh |
|  | PDD: LINEMAN JE ANYOTHER | 01 01 01 | 01 01 01 | Mushtaq Ah Khanday Jalal udin Bhat Zahoor Ahmad |
|  | FOOD&CIVILSUPPLIES | 01 | 01 | Wakeel Ahmad Dar (SK) |
|  | AGRICULTURE&ANIMALHUS- BANDARY | 01 | 01 | Kauseena (JAEO Agriculture) Ab Rashid Larik (Animal Husbandry) |
|  | SOCIALWELFARE | 01 | 01 | Ishfaq Bashir |
|  | HEALTH: ASHA ANM AYUSHDOCTOR ALLOPATHICDOCTOR | 03 02 01 Nil | 03 02 01 - | Gulshana, Mehbooba, Fehmeeda Jitendar Kour, Raiesa Bano Sumaya Hassan |
|  | ANYOTHERDEPARTMENT Youth Services and Sports Revenue | 02 01 | 02 01 | Bilal Bhat, Shina Akhter Bashir Ah Dar |

DAY2-ACTIVITIES

AGENDANO.1

DiscussionontheandassesstheprogressofdifferentschemesrelatingtothelocalizedSDGsprior-itizedforthatvillageaspertheresolutionpassedbythatGramPanchayaton21stApril22,onNational PanchayatiRajDay(Copyoftheresolutiontobetakenfromwww.jkpanchayat.inportalunderthelinkof GramSwarajMonth)

1.       SDGs AGREED FORTHATVILLAGE,TO BE IMPLEMENTED BY MARCH 2024: Clean and Green Village

2.       STATUS OF WORKS UNDER THE FOLLOWING SCHEMES:

1      Cleanandgreenvillage

- Initiatives taken by the Panchayat for managing Solid and Liquid Waste--- Yes

- Initiatives taken by the Panchayat for using green sources of fuel like solar, biogas-- Nil

- Hasmappingoflanduse,waterbodies,forest,slopes,wetlands,degradedforestwithintheGram

- Panchayat been done? Yes/No. If No, reason,thereof--- yes

iv.    Has the Climate Resilience Plan been developed for the GP? Yes/No--- No

v.     StepstakenbytheGramSabhaabouttheclimatechangemitigationfactorslikereducingenergy consumption,usageoffossilfuels,plastics,non-renewablebuildingmaterialsandalsotopromote measureslikeplantingoftrees,conservingforests,usageofgoodagriculturalpracticeslikedrip irrigation, water conservation measures and conservation of wetlands.--- No

vi.  Whether schools have started segregating waste--- No

vii. Whetherschoolshavetheirowncompost/soakagepitsforsolid/liquidwastemanagement--- No

2     Healthyvillage

i)    Are meetings  related to Village Health and Sanitation Committee being held regularly?-- Yes

ii)   Do all the eligible individuals been provided the Golden Card?-- Yes

iii)  ArealltheChildrenbeingimmunizedaspertheSchedulerecommendedbyGovt.ofIndia?--- Yes

iv)  ArealltheeligibleindividualsbeenvaccinatedagainstCOVID-19?-- Yes

v)   DoesGramPanchayatensurethatallpregnantwomenaregettingnecessaryprenatalcheckups?-- Yes

vi)  WhetherallthedeliverieswereInstitutionalizedorconductedbytrainedMidwives?-- Yes

3     Watersufficientvillage

i)    Do all the IHHs in the GramPanchayat have water pipeline connections?-- No

ii)   WhetherGramPanchayathastakenstepsforgreywatermanagement.IfYespleasespecify--- Yes

iii)  DoalltheIHHsintheGramPanchayathavetoilets?—Yes

iv)  ArealltheIHHstoiletsfunctionalornot?--- Yes

v)   DoalltheSchools/Anganwadicentershavea toiletfacilityornot?--- Yes

vi)  Areallthetoiletsintheschools/Aaganwadifunctionalornot?--- Yes

vii) WhetherGramPachachayatBhawanhasseparate toiletsforwomenornot?-- No

4      ChildFriendlyvillage

i)	Doallthechildrenundertheageof0-6yearsbeenenrolledintheAnganwadicentersforpre- schooling?Yes/NO--- Yes

ii)    How many BalSabha’s were organized in the GramPanchayat-------------------01

iii)  Whether the issues raised by Bal Sabha are addressed during the GramSabha. Yes/NO-- Yes

iv)	WhetherGramPanchayatistrackingthedatarelatedtodropoutchildrenandchildrenwithirregular attendance? Yes/NO.--- Yes

v)   Do all the schools under the Gram Panchayat have separate toilets for girls and boys?Yes/No---- Yes

5      Villagewithgoodgovernance

i)    Is CSC located in the GramPanchayat Bhawan or not?-- Yes

ii)IsthelistofbeneficiariesrelatedtotheSchemes/ProgramsdisplayedontheGrampanchayatwallor not?-- Yes

iii)  Does the GramPanchayat has its building or not?-- Yes

iv)  IstheGramPanchayatofficefunctionalornot?-- No

v)   Aretheactivities approved undertheHalqaPanchayatDevelopmentPlandisplayedontheGram

Panchayatwallornot?-- Yes

vi)  IsSocialAuditofearlierSchemes/Programscarriedoutornot?-- Yes

6      Povertyfreeandenhancedlivelihoodvillage

- HasGramPanchayatdevelopedanycriteria fortheidentificationofthepoor?Yes/Noifyesspecify-- Yes

- HavealltheeligiblehouseholdsregisteredinPDSornot?-- Yes

iii)	HasGramPanchayatprovidedspaceforSelf-helpGroupsinPanchyatGharforholdingmeetings  or not?-- yes

iv)  HavealltheeligiblehouseholdsbeenregisteredforPensionornot?-- Yes

v)   HasGramPanchayatfacilitatedYouthforSkillEnhancementCoursesandPlacement?-- No

vi)  HasJobCardsbeendistributedtoalltheeligibleindividualsunderMGNREGA?-- Yes

vii) HasGramPanchayatfacilitatedSHGsforBankAccountLinkages?--- Yes

7     Sociallysecuredvillage

i)    WhetherGramPanchayatismaintainingdatarelatedtoDifferentlyAbledPeople?-- Yes

ii)   IsGramPanchayatOffice DisabledFriendlyornot?--- Yes

iii)	Areprovisionsfora separate BudgetundertheResourceEnvelopeforWomenandChildrenmadeor not?-- No

iv)	DoalltheSchools intheGramPanchayathavefacilitiesforDifferentlyAbledChildrenliketoilets, barrier-freeaccess,etc.,ornot?--- Yes

v)   Arealltheeligibleindividualsaregettingpensions,likeoldagepension,widowpension,etc?--- Yes

vi)  ArealltheeligiblehouseholdsgettingbenefitsfromIAYornot?--- Yes

8      EngenderedDevelopmentinVillage

i)    HowmanyMahilaSabha’swereorganizedintheGramPanchayat-------------------02

ii)	WhetherSHGsfederationshavebeenprovidedspaceformeetings  inthePanchayatBhawan(Yes/ No)-- Yes

iii)  WhetherGPshavetakenstepsforincreasingwomen’sparticipationinGramSabha(Yes/No)—Yes

iv) NumberofwomenbeneficiariesheadedhouseholdscoveredunderPDS system………………………15

v)   Numberofbeneficiaries(outoftotaleligiblepopulation)receivingsocialprotectionbenefitsunder

PradhanMantriMatritvaVandanaYojana………………….12

9    Self-sufficientinfrastructureinthevillage

i.	WhetherGPhasa CommunityHallwithaccesstoelectricity,furniture,watersupply, toilet………………………. No

ii.     WhethertheDisastermanagementplanisavailableattheGPLevel(Yes/No)--- Yes

iii.  Whetherchild-friendlyparkwithrequiredfacilitiesisavailableinGP(Yes/No) -- No

iv.    WhethertheGPhaseasyaccesstoGodownforstorage(Yes/No)-- No

v.     Whetherstreetlightsareprovidedinpublicplacesforensuringsafety(Yes/No)--- Yes

DAY2ACTIVITIES

AGENDANO.2

SensitizevillageresidentsaboutmyScheme”portal(myscheme.in)whichincludesinformationaboutall theschemesbeingrunbyCentral/State/UT govtacrossthecountry

(SchemeMaterialavailablefromhttps://jkpanchayat.in/b2v4.php)

DAY2ACTIVITIES

AGENDANO.3

HoldmeetingoftheBiodiversityManagementCommitteestodeliberateonissues pertaining to conserva- tionofbiodiversityandsustainableutilizationofbiologicalresources.HeshouldcheckPeopleBiodiversity register(PBR)ofthatpanchayatandreviewifBiodiversityManagementCommittee constitutedforthat panchayatis holdingminimum4meetings in a year and meeting onceinevery3months (RoleofBMC availableathttps://jkpanchayat.in/b2v4.php)

COMMITTEEMEMBERS—Farooq Ah Bhat (VLW), Jitendar Kaur (Health), Mehbooba (Asha)

PRESENT--- All the members were  not present except few

BIODIVERSITYREGISTERPHOTOS--- Not available

PAST 4MEETINGDETAILS-DATES,MINUTESPHOTOS---- 28.08.2020 and 29.10.2022

DAY2ACTIVITIES

AGENDA4

Visiting officer shall also plan and conduct panchayat level convergence meeting  of all departments and prepareVillagedevelopmentplanforvillage,inconsultancywithGrampanchayat,discussitingram sabha and get it approved.—Convergence meeting of all the departments held and GPDP prepared which was later passed under Gram Sabha (GPDP annexed at I)

(GPDPformatavailableonhttps://jkpanchayat.in/b2v4.php)

In addition GPDP plan shall also include:

           Tourist places which need to be developed

           Specific product which needs to be developed

           Tourism-homestays

	20candidatesfortrainingunderHimayatschemealongwithtradeinwhich training is to be given

DAY2ACTIVITIES

AGENDA5

Ensuresaturationoffollowingschemesandgivestatus:

| NAMEOFTHESCHEME | TOTALELIGIBLE BENEFICIARIESIN THE VILLAGE | TOTALBENEFICIARIESWHO AVAILEDTHEBENEFITSOFTHESCHEME | REASONSFOR PENDENCY |
| --- | --- | --- | --- |
| Golden Health Card under Ayushman Bharat | 2676 | 2599 | Correction in aadhar |
| Janani suraksha yojana | 15 111 | 15 | Nil |
| OLD AGE pension | 111 61 | 111 | Nil |
| Widow pension | 61 45 | 61 | Nil |
| Disability pension | 45 | 45 | Nil |
| Domicile certificate | 613 | 490 | Need based applications are received |
| Kisan credit card | 494 | 494 | Nil |
| PM kisan samman nidhi | 310 | 310 | Nil |

| Land passbook | 550 | 50 | Remaining are under process |
| --- | --- | --- | --- |
| Registration of village ven- dors on GEM portal | - | - | - |
| Registration of village con- tractors on jktenders portal | 08 | 06 | Under process |
| Registration of village con- tractors on PWD portal | 08 | 06 | Under process |
| Incomplete buildings/ projects | 02 | 02 | Health centre and School |

DAY2ACTIVITIES

AGENDA6

NASHAMUKTABHIYAN

1.       Whether gram sabha resolution passed--- Yes

2.       Details of activities conducted—Nasha Mukht related speeches delivered

3.       Whether all activities and GS resolution uploaded on jkpanchayats.in portal--- Yes

4.       How many drug addicts in the village--- Data Not available

5.       Whether reported to the Deputy Commissioner… No

6.       How many registered for rehabilitation under government programme-- Nil

DAY2ACTIVITIES

AGENDA7

SOCIALAUDIT

Conductsocialauditofatleast5workseachunderfollowingschemes:

| NAMEOFTHE SCHEME | DETAILSOFTHE WORKS | YEAROFWORK APPROVAL | AMOUNT APPROVED FORTHEWORK | WHETHER WORKEXECUTED SATISFACTORILY | GEO- TAGGED PHOTOS | ANY GRIEVANCE RECORDED RELATINGTOTHAT WORK |
| --- | --- | --- | --- | --- | --- | --- |
| MGNREGA | 1. C/O protection bund from H/O Gh Mohidin Sheikh at Nowpora Amlar 2. Development of grave yard and Pyt Ghar by way of earthfilling at Amlar 3. C/O drain/protection bund near L/O Habibullah Mir at Nowpora Amlar 4. C/O drain/bund from Badi Kull near foot bridge near L/O Altaf Ah Shah 5. C/O protection bund and desilting of badi kull from H/O Nazir Ah Ganie at Amlar | 2021-22 2021-22 2021-22 2021-22 2021-22 | 1.09 Lakhs 2.81 Lakhs 0.98 Lakhs 1.79 Lakhs 1.99 Lakhs | Yes Yes Yes Yes Yes | Yes Yes Yes Yes Yes | - |
| PMAY | 1.C/O house of Rouf Rashid Mir 2. C/O PMAY house of Mohd Amin Shah 3. C/O PMAY house of Mohd Ashraf Rather 4. C/O PMAY house of Javid Ah Khanday | 2021-22 2021-22 2021-22 2021-22 | 1.30 Lakhs 1.30 Lakhs 1.30 Lakhs 1.30 Lakhs | Yes Yes Yes Yes | Yes Yes Yes Yes |  |
| IHHL UNDERSBM-G | 1.Mohd Afzal Reshi 2. Mushtaq Ah Mir 3. Gh Mohd Mir 4. Maqsood Ah Khanday 5. Shabir Ah Ganie | 2021-22 2021-22 2021-22 2021-22 2021-22 | 0.12 Lakhs 0.12 Lakhs 0.12 Lakhs 0.12 Lakhs 0.12 Lakhs | Yes Yes Yes Yes Yes | Yes Yes Yes Yes Yes |  |
| CSCUNDER SBMG |  |  |  |  |  |  |
| AMRIT SAROVARS |  |  |  |  |  |  |

DAY2ACTIVITIES

AGENDA8

MAHILASABHA

Totalwomeninthevillageabovetheageof18--- 961

Total attended--- 09

Proceedings:

(Plinsertpointerstobediscussedthere–referpalliproceedings)

Women empowerment

Employment generation

Education

Save the girl child

DAY2ACTIVITIES

AGENDA9

BALSABHA

Hold a balsabha and record proceedings---

Total children in the village above the age of 06 years --- 217

Total attended--- 07

Proceedings:

Cleanliness, save environment, child education, avoid child labour, physical exercise ect.

(Plinsertpointerstobediscussedthere–referpalliproceedings)

DAY2ACTIVITIES

AGENDA10

INAUGURATIONS

| SR NO. | ASSETS/ACTIVITIES INAUGRATED | STATUSOFTHEASSET/AC- TIVITIES(NUMBER,OTHER DETAILS) | GEO-TAGGED PHOTOS |
| --- | --- | --- | --- |
|  | VILLAGE HAAT under JKSRLM (SUN- DAYMARKET) | Not available |  |
|  | PMAY houses if any ready for inaugra- tion | One house of M. Amin Shah at Kanli Mohala inaugurated | Yes uploaded on portal by Nodal Officer |
|  | Swachh gram projects-segregation sheds etc | - | - |
|  | Amrit sarovars | Reshi Mohalla Spring at Nowpora | Yes |
|  | Sports kits | 01 | Yes |
|  | Village cultural events |  |  |
|  | JJMassets/projects |  |  |
|  | Anyothertobeidentifiedatdistrict level |  |  |

FOLLOWUPOF(B2V1,B2V2&B2V3):

(Prefilledexcelsheet tobetakenfromdistrictlevel/andalsotobedownloaded

fromwww.jkpanchayat.in)

| S.NO. | Particulars | Action taken | Remarks# |  |
| --- | --- | --- | --- | --- |
| I. Urgent Public Requirements/Demands-B2V1 |  |  |  |  |
| 1 | C/O road from Amlar to Hari | Approved under B2V2 Pro |  | Under execution |
| 2 | Digging of borewell and water treatment with upgradation of existing reservoir Propo | Proposed under JJM WSS |  |  |
| 3 |  |  |  |  |
| 4 |  |  |  |  |
| 5 |  |  |  |  |
| 6 |  |  |  |  |
| 7 |  |  |  |  |
| II. UrgentPublicRequirements/Demands-B2V2 |  |  |  |  |
| 1 | C/O flood protection bund along the banks of flood channel | DPR stands submitted |  |  |
| 2 | C/O bathrooms at Masjid Ibrahim Nowpora | To be executed under SBM (G) during ( (G) |  |  |
| 3 |  |  |  |  |
| 4 |  |  |  |  |
| 5 |  |  |  |  |
| 6 |  |  |  |  |
| 7 |  |  |  |  |
| S.NO. | Particulars | Actiontaken |  | Remarks# |
| III. MajorProblems–B2V1 |  |  |  |  |
| 1 |  |  |  |  |
| 2 |  |  |  |  |
| 3 |  |  |  |  |

| 4 |  |  |  |
| --- | --- | --- | --- |
| 5 |  |  |  |
| IV. MajorProblems-B2V2 |  |  |  |
| 1 |  |  |  |
| 2 |  |  |  |
| 3 |  |  |  |
| 4 |  |  |  |
| 5 |  |  |  |
| V. MajorProblems-B2V3 |  |  |  |
| 1 |  |  |  |
| 2 |  |  |  |
| 3 |  |  |  |
| 4 |  |  |  |
| 5 |  |  |  |
| VI. MajorComplaints-B2V1 |  |  |  |
| 1 |  |  |  |
| 2 |  |  |  |
| 3 |  |  |  |
| VII. MajorComplaints-B2V2 |  |  |  |
| 1 |  |  |  |
| 2 |  |  |  |
| 3 |  |  |  |
| VIII. MajorComplaints-B2V3 |  |  |  |
| 1 |  |  |  |
| 2 |  |  |  |
| 3 |  |  |  |

OVERALLPERCEPTIONOFFUCNTIONING OF GOVERNMENTDEPARTMENTS

1.         BEST DEPARTMENT:   RDD

2.       LEAST RESPONSIVE DEPARTMENT: Bank

GENERALASSESSMENTOFTHEVISTINGOFFICER

| I | Any major complaint brought to the notice of the Visiting Officer: Old School Building at Amlar Tral is unsafe fro general public and school going children. It shall be dismantled at an earlies |
| --- | --- |
| II | Major/urgentpublicdemandsthatwas/werereflectedearlierbuthavenotbeenaddressedsofar: C/O link roads from Amlar to Hari via Sheikhpora Khodpora |
| III | Overall assessment of the visit and suggestions: (Thevisitingofficertoensurethattheoverallassessmentisrecordedindetailsalongwithconcretesugges- tions) Lack of awareness about different schemes of various Departments. All the frontline departments must conduct awareness camps in the GP |
| IV | Overall Rating of govt functioning as given by the Panchayat (Scale of 0 to10)--- 06 |
| V | Certificate from Sarpanch that the visiting officer has stayed in the panchayat for 2days |

SignatureofSarpanch                                                                              SignatureoftheVisitingOfficer

Name………………………                                                                               Name………………………

Department of Rural Development and Panchayati Raj

Government of Jammu & Kashmir