# 4

15THOCTto3RDNOV,2022

4

15THOCTto3RDNOV,2022

# KEYFEATURES

- DeputyCommissionerstoleadtheinitiative

- RuraldevelopmentDepartmenttobethenodaldepartment

- PlanningDevelopment&MonitoringdepartmentandITtobethesupportdepartments

# ACTIONSANDTIMELINES

| ACTION | RESPONSIBILITY | LATESTBY | REMARKS |
| --- | --- | --- | --- |
| Janabhiyan | Alldepartments | Oct15-26th | Goingon |
| DeputationofSecttstaff/HoDs | GAD | Oct14 | Done |
| Deployment of Staff toPanchayats and serving ofordersondeployedofficers | DCs | Oct25 | DCs will deploy senior level stafffromthedistricts.Strictactiontobe taken against abstentions. Noexemptionstobegiven |
| TrainingofdistricttrainorsonB2V4 | RDD | Oct26 |  |
| Trainingofvisitingofficers | DCs | Oct27 |  |
| FieldVisitstobecompletedby | VisitingOfficers | Nov3 | DCstosuperviseandensurethateach Panchayatis visitedwithintheperiodspecified |
| DataofB2V4tobeuploadedby | VisitingOfficers | Nov10 | DCstosuperviseandensurethatdata of all Panchayats is upload-ed by the visiting officer withintheperiodspecified |

INSTRUCTIONSFORTHEVISITINGOFFICER(DAYWISE)

| DATE | INSTRUCTIONS | ACTIONPOINTS |
| --- | --- | --- |
| Day0 | Meeting with deputycommissionerandhis/herteam | - TakeprintoutsoffilledbookletsofB2V1,B2V2andB2V3fromwww.jkpanchayat.in - Alsotakeprintoutsofthesummarizedexcelsheetsofthepreviousphasesfromwww.jkpanchayat.in - CollectATRsonissuesraisedduringprevious3phasesfromtheofficeofDeputyCommissioner(Planningdeptt) - Takeprintsofblank2bookletsofB2V4fromwww.jkpanchayat.in - Takeplansfor2previousyearsandATRsfromtheplanningdeptt - CompletetrainingsondifferentcomponentsofB2V4beingorganizedbyrespectiveDeputyCommissioners - CollectListofnewworksstarted/ongoing/completedduringthepreviousandcurrentFinancialyearunderthefollowingheads: - PRIgrants - DistrictPlan - UTplan - MGNREGA - Otherschemesofotherdepartments - Anyotherwork - Plans/beneficiarylists: - MGNREGAdraftplandocumentfortheyear2022-23. - ListofAwaas+beneficiariesalongwithIHHLConvergence - Listofpensionbeneficiaries. - List of SHGs - Listofagricultureschemebeneficiaries - Listsofbeneficiariesfor: - Various certificates/ benefits to be distributed by thevisitingofficer. - Anyotheractivitiesidentifiedbydifferentdepartments |

| Day1 | Reach thevillage | - Ensurethatallfrontlineworkersofdifferentdepttsarepresent. - Ensureexhibitionbydifferentdepts.aboutindividualbeneficiaryschemes - InspectJKB/PSBcounters/outlets - Participate/ensureorganizationofsportsactivityinplayfield,talenthunt/culturalevent/youthactivity - GandhiKatha(suggesteddetailsuploadedonjkpanchayat.in) - Visitatleast2amritsarovarsandgetitsgeotaggedphotos - InspectKhidmat(CSC)CentresandcreateGenerateawarenesson225schemesparticularlyG2CschemeslikeBEAMS,Janbhagidari,AapkiZaminAapkiNigrani,DigitalJ&K - Visitingofficershallalsoplanandconductpanchayatlevelconver-gencemeetingofalldepartments - CheckeffectivenessofCentrallysponsoredschemes - VisitandinspectallgovernmentestablishmentsincludingPHE,AWC,FPS,schools,etc - AttemptsaturationofdeliverablesoJanAbhiyanandwhereverdeficienciesfound,leadadrivetoachievealldeliverables - Assesseffectivenessofsanitationcampaigninthepanchayat - Ensureselfemploymentactivitiesfor15youthperpanchayat - Identify20potentialcandidatesperpanchayatforHIMAYATtrainingalongwiththetradeonwhichtheywanttraining - Whereverpossible,distributeemploymentlettersforpeopleselect-edundervariousgovernmentemployments - In the evening, hold normal meeting with senior citizens, govtem-ployeesincludingretiredemployees,exservicemen,youthclub,andanycitizensofthevillagewhoareenrolledincollege/university - OpendiscussiononNashaMuktAbhiyan |
| --- | --- | --- |

| Day2 | Have a meeting with allstakeholders- deptt officialsandpanchayatmembers | - Discussionontheandassesstheprogressofdifferentschemesrelatingto the localized SDGs prioritized for that village as per the resolutionpassedbythatGramPanchayaton21stApril22,onNationalPanchaytiRajDay. - SensitizevillageresidentsaboutmyScheme” portal(myscheme.in)whichincludesinformationaboutalltheschemesbeingrunbyCen-tral/State/UTgovtacrossthecountry - HoldmeetingoftheBiodiversityManagementCommitteestodeliber-ateonissuespertainingtoconservationofbiodiversityandsustaina-bleutilizationofbiologicalresources. - PrepareVillagedevelopmentplan,inconsultancywithGrampanchayat,discussitingramsabhaandgetitapproved. - EnsuresaturationofsoilhealthcardandgoldenhealthcardunderGold-enHealthCardunderAyushmanBharat, - EnsuresaturationofOldAgePensionScheme - EnsureDomicileSaturation. - EnsureKCCSaturation - Ensuresaturationoflandpassbooks - Ensureregistrationofvillagevendorsneededforanyscheme,onGEMportal - Ensurepanchayatcontractorsregistration - EncouragePanchayatmembersforimportanceofplantationdriveinPanchayatunderHarGaonHariyali - EnsurepaintingondigitalJ&Kinpanchayatghars - EnsurepaintingonpanchayatactivitesandCSSinpanchayatghars - The visiting office shall check no of kindergarten and playfieldspresentinthepanchayatforkidsandstudents,iftheinfrastructurepresentinthesearegoodenough. - HoldmeetingwithpanchayatmemberstodiscussaboutcorruptionmenaceandstepsrequiredtomakeJ&Kcorruptionfree - Obtainacandidassessmentaboutperformanceofvariousdepttsin-cludingfairfeedbackaboutdiscrepanciesinfunctioning - CheckthestatusofNashaMuktAbhiyanandreportingofdrugad-dictstoDeputyCommissioner. - Identify Tourist Destinations, Circuits, Theme Treks, Identify Homestays,providesupportfortourismactivitiesthroughVillageCooperative - OrganizeTalentHuntatPanchayatLevel - Conductsocialauditofatleast5worksunderfollowingschemes: - MGNREGA - PMAY - IHHLtoiletsandpayments - CSCs - AMRITSAROVARS - Holdamahilasabhaandabalsabhaandrecordproceedingsinthefor-matgiven - InauguratevillagehaatunderJKSRLM - Checkifyouthclubsareformedinthepanchayatandwhatactivitiestheyareengagedin - Organizeavillagelevelculturaleventtoengagepanchayatmembers - SensitizeGPaboutE-kitabkoshaninitiativeofJ&KGovtforempoweringyouthsthroughonlinedigitalliteracy |
| --- | --- | --- |

# GENERALINSTRUCTIONS

- Thevisitingofficershallrefrainhimself/herselfgivingorofferinganycommitmentonbehalfofthegovernmentandshalladoptanunbiasedattitudeinreportingissues.Asfaraspossible,his/herobservationshouldbebasedonafairandanalyticalviewemergingfromhis/herinteractioninthevillage.

- Heisgoingtothevillageasplanningofficer,notforsanctioninganyworksorformakinganycom-mitments.

- Whilepreparingvillagedevelopmentplan,hehastoensurethat,demandsareprioritizedandre-flectedunderavailableschemes,wherevernecessarythelargerworksaretobereferredtoadminis-trativedepttunderCSS/UTplansunderintimationtoDCsandrestoftheworkstoDCsforreflectingitunderdistrict/CSSplans

- HisworkshallbehardcoreplanningandauditandisnotaPRexercise.

- EveryDeputyCommissionerhastoensurethatatleastoneRDDofficial(ideallyPanchayatSecre-tary)ispresentineverypanchayatwithrelevantpanchayatrecords,toensureconductofallactivi-tiesasplanned.Panchayatwiseorderneedstobeissuedinadvance.

- Visiting officer should ideally carry his/her laptop to complete the reports at the panchayat levelitself and upload the final report, duly signed both by the sarpanch and by the visiting officer onwww.jkpanchayat.inportal,beforetheyleavepanchayat.

- Focus of visit are youth, skills, self-employment, nashamukt, bhrashtracharmukt, Rozgaryukt J&K,besidestocarryforwardtheactivitiesduringJanAbhiyanandsaturatethem.

- Inadditionattentionmaybegiventothefollowingareas

  - MakefulluseofCentrallySponsoredSchemes

  - Saturationofindividualbeneficiaryschemes

  - Self-employmentschemes

  - Banklinkedschemes-includingdepartmentalsubsidyschemes

  - Empowermentandtransparencythroughdigitalinitiatives

  - Effectivenessofgrassrootsmachinery–

    - Patwari,VLWpresentandavailable

    - AvailablefundsutilizedinpublicinterestandasperGramSabharesolutions

    - Fairnessingovernance

    - CSS/Individualbeneficiaryschemesetc

    - BrashtacharMuktJ&K

    - Bhai MuktJ&K

    - NashaMuktJ&K

- ThePRImembers(Sarpanchs,Panchs,BDCChairperson)shallbeattheforefrontofallactivitiesandgiven due importance and the approach should be to strengthen them and make them feel em-powered.He/sheshallensurethattheBDCchairpersonandSarpanch/Pancharepresentatthetimeofinaugurationandceremonies.

- Visitingofficershallnotleavethedistrictwithoutuploadingthereport,dulysignedonthewww.jkpanchayat.inportal.EveryDeputyCommissionerhastoensurethat.

## DetailsofReportingOfficer:

Name: Shabir Hussain

Designation: Lecturer

Department/placeofposting: Education, HSS bhata Dhurian

MobileNo: 9107251259

EmailID:shabirhussain_in@gmail.com	                                                                                                                        HomeDistrict:Poonch	                                                                                                               Datesofvisit:02-11-2022 to 03-11-2022

## LocationaldetailsofPanchayat:(tobepre-filled,informationtobetakenfromtheprevious

phasesbooklets/summarizedexcelsheetuploadedonjkpanchayat.in/b2v4.php)(tobevali-datedbythevisitingofficerandmissingdetailstobefilled)

NameofthePanchayat:Kaller Kattel Upper

LocalGovernmentDirectory (LGD)codeofthePanchayat:	 NameofCDBlock: Surankote	                                                                                                             NameofTehsil: Surankote	 Name  of  District: Poonch

## PanchayatProfile:

No.ofrevenuevillagesinthePanchayat:01	                                                                         No.ofhamletsinthePanchayat:07		                                                                                        No.ofhouseholdsinthePanchayat:590

Population(approx)ofthePanchayat:2600

# Part-II:

(TobefilledupbytheVisitingOfficerduringhis/hertwodayvisittothePanchayat.AllFieldshavetobefilledbytheVisitingOfficerbeforethebookletishandedovertotheDC

## FrontlineOfficers/OfficialswhowereassignedtothePanchayatfortheprogramme:

| Department | Name | Designation |
| --- | --- | --- |
| RDD | Mohd Sarab Khan | Secy Pyt |
| Social Welfare | Najaf Ali Shah | Class 4 |
| PDD | Imtyaz Ahmed | Lineman |
| Health | Abdul Salam | Pharmacist |
| Agriculture | Rakesh Kunar | AEA |
| Jal Javeen | Altaf Hussain | Daily Wager |
| Irrigation | Mohd Afzal | Class 4 |
| Social Forestry | Maqbool Hussain Shah | Jr. mali |
| Food and Supply | Nasir Ahmed | Dealer |
| Education | Mustafa Ahmed | REK |
| Revenue | Mujafer H Shah | Patwari |
| Sheep Husbandry | Mukhtar Liyquat | ASN |
| Soil Conservation | Abdul Rashid | Helber |

Detailsofabsentemployeesvis-à-vislistfurnishedbytheDCoffice:

| Department | Name | Designation |
| --- | --- | --- |
|  | NIL |  |

# DAY1-ACTIVITIES

## AGENDA1:PANCHAYATASSETREGISTER

Infrastructure:

  - PanchayatGharInfrastructure

    - Govtbuilding/private: Pvt. Building

    - New/needingrepairs:

  - Furniture(Y/N): Yes

  - Computer/printer(Y/N)Yes

  - Internet(Y/N)Yes

  - Telephone(Y/N)No

  - Toilet(CSC/partofpanchayatghar)(Y/N): yes

  - Water(Y/N): yes

  - Electricity(Y/N): Yes

  - Bank branch (Y/N): No

  - CSC(Y/N): Yes

  - Patwarkhana(Y/N)No

  - Villagehaat(Y/N): Yes

  - Playground(Y/N): No

  - School-

    - Kindergarten(Y/N):

    - Primary(Y/N)Yes

    - Secondary(Y/N)No

    - College(Y/N)No

    - University(Y/N)No

  - AnganwadiCentre(Y/N): Yes

    - (govt/private): Private

    - Totalchildrenenrolled: 100

- Amrit Sarovars–details,location,condition: Nil

- Governmentoffices-details,whetherfunctionalornot: No

- Rationshop(Y/N): Yes

- Placesoftourismimportance–names,littledetailsonhistorical/culturalimportance: No

- Villageheritagesites/treks-names,littledetailsonhistorical/culturalimportance: No

- VLWOffice(Y/N): Yes

- PrimaryHealthcareCentre(Y/N): No

- ListofIncompleteBuildings-names,yearofconstruction: CSC  session 2018-19

- ListofUnderutilizedBuildings-names: Nil

# DAY1-ACTIVITIES

## AGENDA2:

DIFFERENTINSTITUTIONS/INFRASTRUCTUREPROJECTSTOBEVISITED

| AMRITSAROVARS | Visit,verify | COMMENTS |
| --- | --- | --- |
| KhidmatCentres | Create /Generate awareness on 225 schemesparticularlyG2CschemsAapkiZaminAapkiNigrani,Beams,Janbhagidari,DigitalJ&K | No Khidmat center but scheme is implemented |
| JKB/PSBcounters/outlets | - Statusofcounter - Numberofvisitors | Nil |
| Incomplete buildings/pro-jects | Verifywhetheridentificationandredistributiondone | 01 CSC needs major completion |
| PDS | Visit,evaluate,onlinestatus | Yes but govt ration shop is not available |
| PHC | Visit-evaluate,statusofstaff,equipmentandquality | Not but required |
| Youthclubs | Meet,interact,seeksuggestions | Nil but demand for physical field |
| SHG | Meet,identifyproblems,seeksuggestions | No |
| PMAY | Inspect,Inaugurate | Yes Inaugtrated |
| My school, my prideprogress; schools- water,toilets,staff | Visit,checkforwater,electricity,sanitation,meetstudentsandstaff | Yes |
| SwachhSBM | Evaluate | Yes |
| Panchayatplayground,SportskitsdistributionVillagegames | Ensure,verify.Participateinatleastonegameintheplayground | Yes sports kit distributed but play ground is not available |
| HarGaonHariyali,Planta-tiondrive | Evaluatestatus,feedback | Yes |
| Village cultural eventDangal/Haat/Mela | Participatein;ensurethatitisheld | Yes but permanent place is required |
| Exhibitionofschemes | Ensurethateverydepartmentparticipatesandthatitcontinuesforthe entiredurationofB2V | Yes |
| Jal Jeewan Mission verifica-tion-WSS/JSD Electricitysupply | Verify | Yes |

# DAY1-ACTIVITIES

## AGENDA 3: SATURATE JAN BHIYANDELIVERABLESANDRECORDDEFICIENCIESIFANY

(INSERTDELIVERABLES LIST HEREAS PER GAD FORMAT

# DAY1-ACTIVITIES

## AGENDA4:

SELFEMPLOYMENTACTIVITIES

EnsureSelf-employmentactivitiesforyouth,distributeemploymentlettersforpeopleselectedundervarioussocialschemes(15ISTHETARGETPERPANCHAYAT)

## Numberofcasesindifferentcategoriessanctioned: Nil

Detailsofthebanksanctioningit: Nil

Totalamountinvolved:Nil

# DAY1ACTIVITIES

## AGENDA5

Intheevening,holdinformalmeetingswithseniorcitizens,govtemployees,retdemployees,youthclubandothercitizenswhoareenrolledoncollege/universityandhavediscussiononGandhiKatha,NashaMuktAbhiyan,corruptionfreegovernance,doublingfarmersincomeandrecordtheproceedings

## DAY2

- NoofIndividualCompostPitsconstructed: 60

- NoofIndividualSoakPitsconstructed: 110

- No.ofBiodiversitymanagementcommitteemeetingsheld:02

- IsthenameofSarpanchdisplayedoncitizeninformationboardsofallRD&PRschemes:Yes/No: Yes

- AreSarpanchsbeinginvolvedinstart/inaugurationofactivities:Yes/No: Yes

- WhethersubjectshavebeenassignedbytheSarpanchtothePanchs:Yes/No: Yes

- Whethergrievancesredressalboxisinstalled:Yes/No: No

- NoofgrievancesreceivedpertainingtoPanchayatlevel:Nil

- NoofgrievancesdisposedofatPanchayatlevel:Nil

- WhethertheSarpanch/PanchayatSecretaryhavedigitalsignatures:Yes/No: Yes

- WhetherallMGNREGA/14thFCpaymentsarebeingmadebySarpanchthroughDigitalSignatureCertificate(DSC):Yes/No: Yes

# HUMANRESOURCEAVAILABLEATTHEPANCHAYATLEVEL:

| SRNO. | DEPARTMENTWISESTAFF | NUMBERS |  | NAMES |
| --- | --- | --- | --- | --- |
|  |  | SANCTIONED | ACTUAL |  |
|  | Ruraldevelopmentdepartment:BDO/VLW JE GRS TA | 01 01 01 01 | 01 Nil 01 01 | Sarab Khan Nil Niaz Ahmed Ahjaz Ahmed Bhatti |
|  | SCHOOL EDUCATION:TEACHER HEADMASTER ANYOTHER | 17 01 | 17 01 |  |
|  | JALJEEVAN: | 02 | 02 |  |
|  | PDD: LINEEMAN JE ANYOTHER | 01 01 01 | 01 01 01 | \Imteyaz Ahmed Mohd Farooq Mohd Azam |
|  | FOOD&CIVILSUPPLIES | --- | ----- | ---- |
|  | AGRICULTURE&ANIMALHUS-BANDARY | ---- | ---- | ---- |
|  | SOCIALWELFARE | ---- | ---- | ---- |
|  | HEALTH: ASHAANM AYUSHDOCTOR ALLOPATHICDOCTOR | 04 02 01 Nil | 04 01 01 Nil |  |
|  | ANYOTHERDEPARTMENT Sheep husbandry Soil Conservation | 01 01 | 01 01 | Mohd Jamil Abdul Rashid |

DAY2-ACTIVITIES

## AGENDANO.1

DiscussionontheandassesstheprogressofdifferentschemesrelatingtothelocalizedSDGsprior-itizedforthatvillageaspertheresolutionpassedbythatGramPanchayaton21stApril22,onNationalPanchayatiRajDay(Copyoftheresolutiontobetakenfromjammuwww.jkpanchayat.inportalunderthelinkofGramSwarajMonth)

  - SDGsAGREEDFORTHATVILLAGE,TOBEIMPLEMENTEDBYMARCH2024:

  - STATUSOFWORKSUNDERTHEFOLLOWINGSCHEMES:

## Cleanandgreenvillage

- InitiativestakenbythePanchayatformanagingSolidandLiquidWaste Compost Pit and Soak Pit

- InitiativestakenbythePanchayatforusinggreensourcesoffuellikesolar,biogas: Nil

- Hasmappingoflanduse,waterbodies,forest,slopes,wetlands,degradedforestwithintheGramPanchayatbeendone?Yes/No.IfNo,reason,thereof Yes

- HastheClimateResiliencePlanbeendevelopedfortheGP?Yes/No: No

- StepstakenbytheGramSabhaabouttheclimatechangemitigationfactorslikereducingenergyconsumption,usageoffossilfuels,plastics,non-

renewablebuildingmaterialsandalsotopromotemeasureslikeplantingoftrees,conservingforests,usageof	goodagriculturalpracticeslikedripirrigation,waterconservationmeasuresandconservationofwetlands:

- Whetherschoolshavestartedsegregatingwaste: No

- Whetherschoolshavetheirowncompost/soakagepitsforsolid/liquidwastemanagement: Yes

## Healthyvillage

- Aremeetingsrelatedto VillageHealthandSanitationCommitteebeingheldregularly?: Yes

- DoalltheeligibleindividualsbeenprovidedtheGoldenCard?: Yes

- ArealltheChildrenbeingimmunizedaspertheSchedulerecommendedbyGovt.ofIndia?: Yes

- ArealltheeligibleindividualsbeenvaccinatedagainstCOVID-19?Yes

- DoesGramPanchayatensurethatallpregnantwomenaregettingnecessaryprenatalcheckups?Yes

- WhetherallthedeliverieswereInstitutionalizedorconductedbytrainedMidwives?Yes

## Watersufficientvillage

- DoalltheIHHsintheGramPanchayathavewaterpipelineconnections?No

- WhetherGramPanchayathastakenstepsforgreywatermanagement.IfYespleasespecify: Soak Pit

- DoalltheIHHsintheGramPanchayathavetoilets?No

- ArealltheIHHstoiletsfunctionalornot? No

- DoalltheSchools/Anganwadicentershaveatoiletfacilityornot? No

- Areallthetoiletsintheschools/Aaganwadifunctionalornot? No

- WhetherGramPachachayatBhawanhasseparatetoiletsforwomenornot?No

## ChildFriendlyvillage

- Doallthechildrenundertheageof0-6yearsbeenenrolledintheAnganwadicentersforpre-schooling?Yes/NO: Yes

- HowmanyBalSabha’swereorganizedintheGramPanchayat--------02-----------

- WhethertheissuesraisedbyBalSabhaareaddressedduringtheGramSabha.Yes/NO: Yes

- WhetherGramPanchayatistrackingthedatarelatedtodropoutchildrenandchildrenwithirregularattendance?Yes/NO: Yes

- DoalltheschoolsundertheGramPanchayathaveseparatetoiletsforgirlsandboys?Yes/No: Yes

## Villagewithgoodgovernance

- IsCSClocatedintheGramPanchayatBhawanornot?Yes

- IsthelistofbeneficiariesrelatedtotheSchemes/ProgramsdisplayedontheGrampanchayatwallornot?Yes

- DoestheGramPanchayathasitsbuildingornot?No

- IstheGramPanchayatofficefunctionalornot?Yes

- AretheactivitiesapprovedundertheHalqaPanchayatDevelopmentPlandisplayedontheGramPanchayatwallornot? Yes

- IsSocialAuditofearlierSchemes/Programscarriedoutornot?Yes

## Povertyfreeandenhancedlivelihoodvillage

- HasGramPanchayatdevelopedanycriteriafortheidentificationofthepoor?Yes/Noifyesspecify: Yes

- HavealltheeligiblehouseholdsregisteredinPDSornot?Yes

- HasGramPanchayatprovidedspaceforSelf-helpGroupsinPanchyatGharforholdingmeetingsornot?Yes

- HavealltheeligiblehouseholdsbeenregisteredforPensionornot?Yes

- HasGramPanchayatfacilitatedYouthforSkillEnhancementCoursesandPlacement?Yes

- HasJobCardsbeendistributedtoalltheeligibleindividualsunderMGNREGA?Yes

- HasGramPanchayatfacilitatedSHGsforBankAccountLinkages?Yes

## Sociallysecuredvillage

- WhetherGramPanchayatismaintainingdatarelatedtoDifferentlyAbledPeople? Yes

- IsGramPanchayatOfficeDisabledFriendlyornot?

- AreprovisionsforaseparateBudgetundertheResourceEnvelopeforWomenandChildrenmadeornot? No

- Do all the Schools in the Gram Panchayat have facilities for Differently Abled Children like toilets,barrier-freeaccess,etc.,ornot? No

- Arealltheeligibleindividualsaregettingpensions,likeoldagepension,widowpension,etc? Yes

- ArealltheeligiblehouseholdsgettingbenefitsfromIAYornot?Yes

## EngenderedDevelopmentinVillage

- HowmanyMahilaSabha’swereorganizedintheGramPanchayat------- No ------------

- WhetherSHGsfederationshavebeenprovidedspaceformeetingsinthePanchayatBhawan(Yes/No)No

- WhetherGPshavetakenstepsforincreasingwomen’sparticipationinGramSabha(Yes/No) No

- NumberofwomenbeneficiariesheadedhouseholdscoveredunderPDSsystem……………35…………

- Numberofbeneficiaries(outoftotaleligiblepopulation)receivingsocialprotectionbenefitsunderPradhanMantriMatritvaVandanaYojana………12………….

- Self-sufficientinfrastructureinthevillage

- Whether GP has a Community Hall with access to electricity, furniture, water supply,toilet…………No…………….

- WhethertheDisastermanagementplanisavailableattheGPLevel(Yes/No)Yes

- Whetherchild-friendlyparkwithrequiredfacilitiesisavailableinGP(Yes/No)No

- WhethertheGPhaseasyaccesstoGodownforstorage(Yes/No)No

- Whetherstreetlightsareprovidedinpublicplacesforensuringsafety(Yes/No)No

# DAY2ACTIVITIES

## AGENDANO.2

SensitizevillageresidentsaboutmyScheme”portal(myscheme.in)whichincludesinformationaboutalltheschemesbeingrunbyCentral/State/UTgovtacrossthecountry: Yes executed in convergence meeting, gram sabha etc.

(SchemeMaterialavailablefromhttps://jkpanchayat.in/b2v4.php)

# DAY2ACTIVITIES

## AGENDANO.3

HoldmeetingoftheBiodiversityManagementCommitteestodeliberateonissuespertainingtoconserva-tion of biodiversity and sustainable utilization of biological resources. He should check People Biodiversityregister(PBR)ofthatpanchayatandreviewifBiodiversityManagementCommitteeconstitutedforthatpanchayat is holding minimum 4 meetings in a year and meeting once in every 3 months (Role of BMCavailableathttps://jkpanchayat.in/b2v4.php)

COMMITTEE MEMBERS :06

PRESENT: 04

BIODIVERSITYREGISTERPHOTOS:Nil

PAST4MEETINGDETAILS-DATES,MINUTESPHOTOS:  Nil

# DAY2ACTIVITIES

## AGENDA4

VisitingofficershallalsoplanandconductpanchayatlevelconvergencemeetingofalldepartmentsandprepareVillagedevelopmentplanforvillage,inconsultancywithGrampanchayat,discussitingramsabhaandgetitapproved: Referred to general prioritize list of development projects.

(GPDPformatavailableonhttps://jkpanchayat.in/b2v4.php)

## InadditionGPDPplanshallalsoinclude:

Tourist places which need to be developed:Nil

Specificproductwhichneedstobe developed: Animal Husbandry, Horticulture, Health Centre Tourism-homestays: Required

20candidatesfortrainingunderHimayatschemealongwithtradeinwhich:trainingistobegiven:

# DAY2ACTIVITIES

## AGENDA5

Ensuresaturationoffollowingschemesandgivestatus:

| NAMEOFTHESCHEME | TOTAL ELIGIBLEBENEFICIARIESIN THEVILLAGE | TOTALBENEFICIARIESWHO AVAILED THE BENEFITS OFTHESCHEME | REASONSFORPENDENCY |
| --- | --- | --- | --- |
| GoldenHealthCardunderAyushmanBharat | 1900 | 1620 | Foreign and out of state |
| Jananisurakshayojana | 38 | 38 |  |
| OLDAGEpension | 20 | 20 |  |
| Widowpension | 01 | 01 |  |
| Disabilitypension | 14 | 14 |  |
| Domicilecertificate | 2500 | 2000 | Under process |
| Kisancreditcard | 148 | 148 |  |
| PMkisansammannidhi | 142 | 142 |  |

| Landpassbook | 600 | 400 | Under process |
| --- | --- | --- | --- |
| Registrationofvillageven-dorsonGEMportal | Nil | Nil |  |
| Registrationofvillagecon-tractorsonjktenders portal | 06 | 06 |  |
| Registrationofvillagecon-tractorsonPWDportal | 03 | 03 |  |
| Incomplete buildings/pro-jects | 1 | 1 | Shortage of funds |

# DAY2ACTIVITIES

## AGENDA6

NASHAMUKTABHIYAN

- Whethergramsabharesolutionpassed: Yes

- Detailsofactivitiesconducted: Pledge

- WhetherallactivitiesandGSresolutionuploadedonjkpanchayats.inportal: Yes

- Howmanydrugaddictsinthevillage: Nil

- WhetherreportedtotheDeputyCommissioner: Nil

- Howmanyregisteredforrehabilitationundergovernmentprogramme: No

# DAY2ACTIVITIES

## AGENDA 7SOCIALAUDIT

Conductsocialauditofatleast5workseachunderfollowingschemes:

| NAMEOFTHE SCHEME | DETAILSOFTHE WORKS | YEAROFWORK APPROVAL | AMOUNT APPROVEDFORTHEWORK | WHETHER WORK EXECUTEDSATISFACTORILY | GEO- TAGGEDPHOTOS | ANYGRIEVANCE RECORDEDRELATINGTOTHATWORK |
| --- | --- | --- | --- | --- | --- | --- |
| MGNREGA | 24 | 2022-23 | 17.94 lakh | Satisfactory | Yes | No |
| PMAY | 120 | 2022 to 2023 | ---- | --- | 40 GT |  |
| IHHL UNDERSBM-G | 41 | 2022 to 2023 | 4.92 lakh | Satisfactory | Nil | Nil |
| CSC UNDERSBMG | --- | --- | --- | --- | --- | --- |
| AMRITSAROVARS | --- | --- | --- | --- | --- | --- |

# DAY2ACTIVITIES

## AGENDA 8

## MAHILASABHA

Totalwomeninthevillageabovetheageof18: Nil

Totalattended :

Proceedings:

(Plinsertpointerstobediscussedthere–referpalliproceedings)

# DAY2ACTIVITIES

## AGENDA 9

## BALSABHA

Holdabalsabhaandrecordproceedings

Totalchildreninthevillageabovetheageof…6 to 12 years old..

Totalattended: 80

Proceedings: General awareness about quality education and co-curricular activities

(Plinsertpointerstobediscussedthere–referpalliproceedings)

# DAY2ACTIVITIES

AGENDA 10INAUGURATIONS

| SRNO. | ASSETS /ACTIVITIESINAUGRATED | STATUSOFTHEASSET/AC-TIVITIES (NUMBER, OTHERDETAILS) | GEO-TAGGEDPHOTOS |
| --- | --- | --- | --- |
|  | VILLAGEHAATunderJKSRLM(SUN-DAYMARKET) | No |  |
|  | PMAYhousesifanyreadyforinaugra-tion | 02 |  |
|  | Swachhgramprojects-segregationshedsetc | Nil |  |
|  | Amritsarovars | Nil |  |
|  | Sportskits | Yes |  |
|  | Villageculturalevents | Nil |  |
|  | JJMassets/projects | Nil |  |
|  | Any other to be identified at districtlevel | Nil |  |

# FOLLOWUPOF(B2V1,B2V2&B2V3):

(Prefilledexcelsheettobetakenfromdistrictlevel/andalsotobedownloadedfromwww.jkpanchayat.in)

| S.NO. | Particulars | Actiontaken | Remarks# |
| --- | --- | --- | --- |
| I. UrgentPublicRequirements/Demands-B2V1 |  |  |  |
| - Upgradation of PHE project |  | Under process |  |
| - Fund required 10 lakh per ward |  | Completed |  |
| - Opening of New PS in Mato Wali |  | Nil |  |
| - 1 gridding centre in GP Upper Kallar |  | Nil |  |
| - AWC ward no 2, 5, 6 |  | Nil |  |
| - Panchayat Ghar |  | Nil |  |
| - PHC building |  | Nil |  |
| II. UrgentPublicRequirements/Demands-B2V2 |  |  |  |
| - New pipeline in water tank |  | Under process |  |
| - Panchayat Ghar |  | Nil |  |
| - Hand Pumps 20 numbers |  | Nil |  |
| - Tractor road Hirawali to Jabran |  | Nil |  |
| - PHC |  | Nil |  |
| - Sheep and animal husbandry Centre |  | Nil |  |
| - Higher Secondary school |  | Nil |  |
| S.NO. | Particulars | Actiontaken | Remarks# |
| III. MajorProblems–B2V1 |  |  |  |
| Same as V2V1 |  |  |  |

| IV. MajorProblems-B2V2 |  |  |  |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Same as B2V2 |  |  |  |  |  |  |  |  |  |  |  |  |  |
| V. MajorProblems-B2V3 |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Not Available |  |  |  |  |  |  |  |  |  |  |  |  |  |
| VI. MajorComplaints-B2V1 |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Same as B2V1 |  |  |  |  |  |  |  |  |  |  |  |  |  |
| VII. MajorComplaints- |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Same as B2V2 |  |  |  |  |  |  |  |  |  |  |  |  |  |
| VIII. MajorComplaints-B2V3 |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Not Available |  |  |  |  |  |  |  |  |  |  |  |  |  |

DepartmentofRuralDevelompentandPanchayatiRajGovernmentofJammu&Kashmir