# 4

15THOCTto3RDNOV,2022

4

15THOCTto3RDNOV,2022

# KEYFEATURES

- DeputyCommissionerstoleadtheinitiative

- RuraldevelopmentDepartmenttobethenodaldepartment

- PlanningDevelopment&MonitoringdepartmentandITtobethesupportdepartments

# ACTIONSANDTIMELINES

| ACTION | RESPONSIBILITY | LATESTBY | REMARKS |
| --- | --- | --- | --- |
| Janabhiyan | Alldepartments | Oct15-26th | Goingon |
| DeputationofSecttstaff/HoDs | GAD | Oct14 | Done |
| Deployment of Staff toPanchayats and serving ofordersondeployedofficers | DCs | Oct25 | DCs will deploy senior level stafffromthedistricts.Strictactiontobe taken against abstentions. Noexemptionstobegiven |
| TrainingofdistricttrainorsonB2V4 | RDD | Oct26 |  |
| Trainingofvisitingofficers | DCs | Oct27 |  |
| FieldVisitstobecompletedby | VisitingOfficers | Nov3 | DCstosuperviseandensurethateach Panchayatis visitedwithintheperiodspecified |
| DataofB2V4tobeuploadedby | VisitingOfficers | Nov10 | DCstosuperviseandensurethatdata of all Panchayats is upload-ed by the visiting officer withintheperiodspecified |

INSTRUCTIONSFORTHEVISITINGOFFICER(DAYWISE)

| DATE | INSTRUCTIONS | ACTIONPOINTS |
| --- | --- | --- |
| Day0 | Meeting with deputycommissionerandhis/herteam | - TakeprintoutsoffilledbookletsofB2V1,B2V2andB2V3fromwww.jkpanchayat.in - Alsotakeprintoutsofthesummarizedexcelsheetsofthepreviousphasesfromwww.jkpanchayat.in - CollectATRsonissuesraisedduringprevious3phasesfromtheofficeofDeputyCommissioner(Planningdeptt) - Takeprintsofblank2bookletsofB2V4fromwww.jkpanchayat.in - Takeplansfor2previousyearsandATRsfromtheplanningdeptt - CompletetrainingsondifferentcomponentsofB2V4beingorganizedbyrespectiveDeputyCommissioners - CollectListofnewworksstarted/ongoing/completedduringthepreviousandcurrentFinancialyearunderthefollowingheads: - PRIgrants - DistrictPlan - UTplan - MGNREGA - Otherschemesofotherdepartments - Anyotherwork - Plans/beneficiarylists: - MGNREGAdraftplandocumentfortheyear2022-23. - ListofAwaas+beneficiariesalongwithIHHLConvergence - Listofpensionbeneficiaries. - List of SHGs - Listofagricultureschemebeneficiaries - Listsofbeneficiariesfor: - Various certificates/ benefits to be distributed by thevisitingofficer. - Anyotheractivitiesidentifiedbydifferentdepartments |

| Day1 | Reach thevillage | - Ensurethatallfrontlineworkersofdifferentdepttsarepresent. - Ensureexhibitionbydifferentdepts.aboutindividualbeneficiaryschemes - InspectJKB/PSBcounters/outlets - Participate/ensureorganizationofsportsactivityinplayfield,talenthunt/culturalevent/youthactivity - GandhiKatha(suggesteddetailsuploadedonjkpanchayat.in) - Visitatleast2amritsarovarsandgetitsgeotaggedphotos - InspectKhidmat(CSC)CentresandcreateGenerateawarenesson225schemesparticularlyG2CschemeslikeBEAMS,Janbhagidari,AapkiZaminAapkiNigrani,DigitalJ&K - Visitingofficershallalsoplanandconductpanchayatlevelconver-gencemeetingofalldepartments - CheckeffectivenessofCentrallysponsoredschemes - VisitandinspectallgovernmentestablishmentsincludingPHE,AWC,FPS,schools,etc - AttemptsaturationofdeliverablesoJanAbhiyanandwhereverdeficienciesfound,leadadrivetoachievealldeliverables - Assesseffectivenessofsanitationcampaigninthepanchayat - Ensureselfemploymentactivitiesfor15youthperpanchayat - Identify20potentialcandidatesperpanchayatforHIMAYATtrainingalongwiththetradeonwhichtheywanttraining - Whereverpossible,distributeemploymentlettersforpeopleselect-edundervariousgovernmentemployments - In the evening, hold normal meeting with senior citizens, govtem-ployeesincludingretiredemployees,exservicemen,youthclub,andanycitizensofthevillagewhoareenrolledincollege/university - OpendiscussiononNashaMuktAbhiyan |
| --- | --- | --- |

| Day2 | Have a meeting with allstakeholders- deptt officialsandpanchayatmembers | - Discussionontheandassesstheprogressofdifferentschemesrelatingto the localized SDGs prioritized for that village as per the resolutionpassedbythatGramPanchayaton21stApril22,onNationalPanchaytiRajDay. - SensitizevillageresidentsaboutmyScheme” portal(myscheme.in)whichincludesinformationaboutalltheschemesbeingrunbyCen-tral/State/UTgovtacrossthecountry - HoldmeetingoftheBiodiversityManagementCommitteestodeliber-ateonissuespertainingtoconservationofbiodiversityandsustaina-bleutilizationofbiologicalresources. - PrepareVillagedevelopmentplan,inconsultancywithGrampanchayat,discussitingramsabhaandgetitapproved. - EnsuresaturationofsoilhealthcardandgoldenhealthcardunderGold-enHealthCardunderAyushmanBharat, - EnsuresaturationofOldAgePensionScheme - EnsureDomicileSaturation. - EnsureKCCSaturation - Ensuresaturationoflandpassbooks - Ensureregistrationofvillagevendorsneededforanyscheme,onGEMportal - Ensurepanchayatcontractorsregistration - EncouragePanchayatmembersforimportanceofplantationdriveinPanchayatunderHarGaonHariyali - EnsurepaintingondigitalJ&Kinpanchayatghars - EnsurepaintingonpanchayatactivitesandCSSinpanchayatghars - The visiting office shall check no of kindergarten and playfieldspresentinthepanchayatforkidsandstudents,iftheinfrastructurepresentinthesearegoodenough. - HoldmeetingwithpanchayatmemberstodiscussaboutcorruptionmenaceandstepsrequiredtomakeJ&Kcorruptionfree - Obtainacandidassessmentaboutperformanceofvariousdepttsin-cludingfairfeedbackaboutdiscrepanciesinfunctioning - CheckthestatusofNashaMuktAbhiyanandreportingofdrugad-dictstoDeputyCommissioner. - Identify Tourist Destinations, Circuits, Theme Treks, Identify Homestays,providesupportfortourismactivitiesthroughVillageCooperative - OrganizeTalentHuntatPanchayatLevel - Conductsocialauditofatleast5worksunderfollowingschemes: - MGNREGA - PMAY - IHHLtoiletsandpayments - CSCs - AMRITSAROVARS - Holdamahilasabhaandabalsabhaandrecordproceedingsinthefor-matgiven - InauguratevillagehaatunderJKSRLM - Checkifyouthclubsareformedinthepanchayatandwhatactivitiestheyareengagedin - Organizeavillagelevelculturaleventtoengagepanchayatmembers - SensitizeGPaboutE-kitabkoshaninitiativeofJ&KGovtforempoweringyouthsthroughonlinedigitalliteracy |
| --- | --- | --- |

# GENERALINSTRUCTIONS

- Thevisitingofficershallrefrainhimself/herselfgivingorofferinganycommitmentonbehalfofthegovernmentandshalladoptanunbiasedattitudeinreportingissues.Asfaraspossible,his/herobservationshouldbebasedonafairandanalyticalviewemergingfromhis/herinteractioninthevillage.

- Heisgoingtothevillageasplanningofficer,notforsanctioninganyworksorformakinganycom-mitments.

- Whilepreparingvillagedevelopmentplan,hehastoensurethat,demandsareprioritizedandre-flectedunderavailableschemes,wherevernecessarythelargerworksaretobereferredtoadminis-trativedepttunderCSS/UTplansunderintimationtoDCsandrestoftheworkstoDCsforreflectingitunderdistrict/CSSplans

- HisworkshallbehardcoreplanningandauditandisnotaPRexercise.

- EveryDeputyCommissionerhastoensurethatatleastoneRDDofficial(ideallyPanchayatSecre-tary)ispresentineverypanchayatwithrelevantpanchayatrecords,toensureconductofallactivi-tiesasplanned.Panchayatwiseorderneedstobeissuedinadvance.

- Visiting officer should ideally carry his/her laptop to complete the reports at the panchayat levelitself and upload the final report, duly signed both by the sarpanch and by the visiting officer onwww.jkpanchayat.inportal,beforetheyleavepanchayat.

- Focus of visit are youth, skills, self-employment, nashamukt, bhrashtracharmukt, Rozgaryukt J&K,besidestocarryforwardtheactivitiesduringJanAbhiyanandsaturatethem.

- Inadditionattentionmaybegiventothefollowingareas

  - MakefulluseofCentrallySponsoredSchemes

  - Saturationofindividualbeneficiaryschemes

  - Self-employmentschemes

  - Banklinkedschemes-includingdepartmentalsubsidyschemes

  - Empowermentandtransparencythroughdigitalinitiatives

  - Effectivenessofgrassrootsmachinery–

    - Patwari,VLWpresentandavailable

    - AvailablefundsutilizedinpublicinterestandasperGramSabharesolutions

    - Fairnessingovernance

    - CSS/Individualbeneficiaryschemesetc

    - BrashtacharMuktJ&K

    - Bhai MuktJ&K

    - NashaMuktJ&K

- ThePRImembers(Sarpanchs,Panchs,BDCChairperson)shallbeattheforefrontofallactivitiesandgiven due importance and the approach should be to strengthen them and make them feel em-powered.He/sheshallensurethattheBDCchairpersonandSarpanch/Pancharepresentatthetimeofinaugurationandceremonies.

- Visitingofficershallnotleavethedistrictwithoutuploadingthereport,dulysignedonthewww.jkpanchayat.inportal.EveryDeputyCommissionerhastoensurethat.

## DetailsofReportingOfficer:

Name: Paramjeet Singh

Designation: Secretary

Department/placeofposting: GAD/ Social welfare Deptt./ S&E BCC

MobileNo: 9419261755

EmailID:pjsraina@gmail.com	                                                                                                                        HomeDistrict:JAMMU	                                                                                                               Datesofvisit:02-11-2022 to 03-11-2022

## LocationaldetailsofPanchayat:(tobepre-filled,informationtobetakenfromtheprevious

phasesbooklets/summarizedexcelsheetuploadedonjkpanchayat.in/b2v4.php)(tobevali-datedbythevisitingofficerandmissingdetailstobefilled)

NameofthePanchayat:Surankote Upper

LocalGovernmentDirectory (LGD)codeofthePanchayat:1256	 NameofCDBlock: Surankote	                                                                                                             NameofTehsil: Surankote	 Name  of  District: Poonch

## PanchayatProfile:

No.ofrevenuevillagesinthePanchayat:01	                                                                         No.ofhamletsinthePanchayat:09		                                                                                        No.ofhouseholdsinthePanchayat:702

Population(approx)ofthePanchayat:3065

# Part-II:

(TobefilledupbytheVisitingOfficerduringhis/hertwodayvisittothePanchayat.AllFieldshavetobefilledbytheVisitingOfficerbeforethebookletishandedovertotheDC

## FrontlineOfficers/OfficialswhowereassignedtothePanchayatfortheprogramme:

| Department | Name | Designation |
| --- | --- | --- |
| RDD | Tariq Hussain | GRS |
| Revenue | Vishav Karmal | Patwari |
| Education | Bilal Hussain | Teacher |
| PWD | Nusrat Jabeen | TSWO |
| PDD | Puneet Kumar | JE |
| PHE | Kiffaat Hussain | JE |
| PMGSY | Mohd Kabir | Frontline worker |
| Agriculture | Mohd Sameer | JAEO |
| AH | Dr. Syed Koser | AS |
| ICDS | Narseen Akhter | AW |
| Forest | Mohd Tazeen | Guard |
| Food and Supply | Badder Nissar | Dealer |

Detailsofabsentemployeesvis-à-vislistfurnishedbytheDCoffice:

| Department | Name | Designation |
| --- | --- | --- |
|  | NIL |  |

# DAY1-ACTIVITIES

## AGENDA1:PANCHAYATASSETREGISTER

Infrastructure:

  - PanchayatGharInfrastructure

    - Govtbuilding/private: Govt. Building

    - New/needingrepairs:

  - Furniture(Y/N): Yes

  - Computer/printer(Y/N)Yes

  - Internet(Y/N)Yes

  - Telephone(Y/N)No

  - Toilet(CSC/partofpanchayatghar)(Y/N): Yes

  - Water(Y/N): Yes

  - Electricity(Y/N): Yes

  - Bank branch (Y/N): No

  - CSC(Y/N): Yes

  - Patwarkhana(Y/N)No

  - Villagehaat(Y/N): No

  - Playground(Y/N): No

  - School-

    - Kindergarten(Y/N): Yes

    - Primary(Y/N)Yes

    - Secondary(Y/N)No

    - College(Y/N)No

    - University(Y/N)No

  - AnganwadiCentre(Y/N): Yes

    - (govt/private): private

    - Totalchildrenenrolled: 97

- Amrit Sarovars–details,location,condition: under construction

- Governmentoffices-details,whetherfunctionalornot: functional

- Rationshop(Y/N): No

- Placesoftourismimportance–names,littledetailsonhistorical/culturalimportance: Nil

- Villageheritagesites/treks-names,littledetailsonhistorical/culturalimportance: No

- VLWOffice(Y/N): Yes

- PrimaryHealthcareCentre(Y/N): No

- ListofIncompleteBuildings-names,yearofconstruction: Nil

- ListofUnderutilizedBuildings-names: Nil

# DAY1-ACTIVITIES

## AGENDA2:

DIFFERENTINSTITUTIONS/INFRASTRUCTUREPROJECTSTOBEVISITED

| AMRITSAROVARS | Visit,verify | COMMENTS |
| --- | --- | --- |
| KhidmatCentres | Create /Generate awareness on 225 schemesparticularlyG2CschemsAapkiZaminAapkiNigrani,Beams,Janbhagidari,DigitalJ&K | Public besides PRI’s were aware about all the schemes |
| JKB/PSBcounters/outlets | - Statusofcounter - Numberofvisitors | No counter was established however manager J&K Grameen Bank was called who make awareness about scheme |
| Incomplete buildings/pro-jects | Verifywhetheridentificationandredistributiondone | Nil |
| PDS | Visit,evaluate,onlinestatus | No center is available |
| PHC | Visit-evaluate,statusofstaff,equipmentandquality | No PHC is available |
| Youthclubs | Meet,interact,seeksuggestions | Youth club have been formed |
| SHG | Meet,identifyproblems,seeksuggestions | group was formed |
| PMAY | Inspect,Inaugurate | 02 x Iinaugurated |
| My school, my prideprogress; schools- water,toilets,staff | Visit,checkforwater,electricity,sanitation,meetstudentsandstaff | v. poor condition of all the schools, moreover majority of staff posted have stay of more than 10 years |
| SwachhSBM | Evaluate | 01 |
| Panchayatplayground,SportskitsdistributionVillagegames | Ensure,verify.Participateinatleastonegameintheplayground | Sports kit distributed tug of war game displayed |
| HarGaonHariyali,Planta-tiondrive | Evaluatestatus,feedback | Plantation drive conducted |
| Village cultural eventDangal/Haat/Mela | Participatein;ensurethatitisheld | Tug of war, bad mention match conducted |
| Exhibitionofschemes | Ensurethateverydepartmentparticipatesandthatitcontinuesforthe entiredurationofB2V | Ensured |
| Jal Jeewan Mission verifica-tion-WSS/JSD Electricitysupply | Verify | Schemes are under process |

# DAY1-ACTIVITIES

## AGENDA 3: SATURATE JAN BHIYANDELIVERABLESANDRECORDDEFICIENCIESIFANY

(INSERTDELIVERABLES LIST HEREAS PER GAD FORMAT

| S/No | Deliverables | Remarks |
| --- | --- | --- |
| 01 | Land Passbook | 25 No’s Distributed |
| 02 | Golden health cards | Already issued |
| 03 | Self-employed drive | 15 |
| 04 | Himayat scheme | 20 |
| 05 | Awareness on Jan Abhiyan | Undertaken |
| 06 | Nasha Mukth | Pledge taken |
| 07 | Sports kit to senior citizen | Distributed |
| 08 | Bal sabha + mahila sabha | Done |
| 09 | Sports event (tug of war) | Done |

| S/No | Deficiencies | Remarks |
| --- | --- | --- |
| 01 | PDS | Required |
| 02 | PHC’s | Required |
| 03 | Tap water to each household | Required |

# DAY1-ACTIVITIES

## AGENDA4:

SELFEMPLOYMENTACTIVITIES

EnsureSelf-employmentactivitiesforyouth,distributeemploymentlettersforpeopleselectedundervarioussocialschemes(15ISTHETARGETPERPANCHAYAT)

## Numberofcasesindifferentcategoriessanctioned:

Detailsofthebanksanctioningit:

Totalamountinvolved: No employment letter have been distributed, however 15 person have been motivated for the purpose.

# DAY1ACTIVITIES

## AGENDA5

Intheevening,holdinformalmeetingswithseniorcitizens,govtemployees,retdemployees,youthclubandothercitizenswhoareenrolledoncollege/universityandhavediscussiononGandhiKatha,NashaMuktAbhiyan,corruptionfreegovernance,doublingfarmersincomeandrecordtheproceedings

## DAY2

- NoofIndividualCompostPitsconstructed: 20

- NoofIndividualSoakPitsconstructed: 270

- No.ofBiodiversitymanagementcommitteemeetingsheld:05

- IsthenameofSarpanchdisplayedoncitizeninformationboardsofallRD&PRschemes:Yes/No: Yes

- AreSarpanchsbeinginvolvedinstart/inaugurationofactivities:Yes/No: Yes

- WhethersubjectshavebeenassignedbytheSarpanchtothePanchs:Yes/No: Yes

- Whethergrievancesredressalboxisinstalled:Yes/No: Yes

- NoofgrievancesreceivedpertainingtoPanchayatlevel:Nil

- NoofgrievancesdisposedofatPanchayatlevel:Nil

- WhethertheSarpanch/PanchayatSecretaryhavedigitalsignatures:Yes/No: Yes

- WhetherallMGNREGA/14thFCpaymentsarebeingmadebySarpanchthroughDigitalSignatureCertificate(DSC):Yes/No: Yes

# HUMANRESOURCEAVAILABLEATTHEPANCHAYATLEVEL:

| SRNO. | DEPARTMENTWISESTAFF | NUMBERS |  | NAMES |
| --- | --- | --- | --- | --- |
|  |  | SANCTIONED | ACTUAL |  |
|  | Ruraldevelopmentdepartment:BDO/BDO JE GRS TA | 0 01 01 01 | 0 Nil 01 01 | Tariq Hussain Showket Ali |
|  | SCHOOL EDUCATION:TEACHER HEADMASTER ANYOTHER | 16 01 | 15 Nil |  |
|  | JALJEEVAN: | 04 | 04 | Mohd Rashid, Mohd Iqhlaq, Mohd Yousef, Mohd Riaz |
|  | PDD: LINEMANJE ANYOTHER MeterReader | 02 01 01 | 02 01 01 | Zulifkar Ali, Khalil Amed Puneet Kumar Jaffar Iqbal |
|  | FOOD&CIVILSUPPLIES |  |  | No depot is available |
|  | AGRICULTURE&ANIMALHUS-BANDARY VS VP attendant | 01, 01,02 | 0,01,01 | Jameel Ahmed, Parveen Akhter |
|  | SOCIALWELFARE | Nil | Nil | Nil |
|  | HEALTH: ASHAANM AYUSHDOCTOR ALLOPATHICDOCTOR | 05 02 Nil Nil | 05 02 Nil Nil | Naseem Akhter, Saheen Akhter, Farmita Akhter, Khatoon Begum, Robina Akhter |
|  | ANYOTHERDEPARTMENT ICDS 4 AH 4 AW | 04 04 | 04 04 | Nasreen Akhter, Zarina Begum, Sahin Akhter, Begum Noor, Rakhmat Jaan, Shamin Akhter, zanit Bi, Sakina Begum |

DAY2-ACTIVITIES

## AGENDANO.1

DiscussionontheandassesstheprogressofdifferentschemesrelatingtothelocalizedSDGsprior-itizedforthatvillageaspertheresolutionpassedbythatGramPanchayaton21stApril22,onNationalPanchayatiRajDay(Copyoftheresolutiontobetakenfromjammuwww.jkpanchayat.inportalunderthelinkofGramSwarajMonth)

  - SDGsAGREEDFORTHATVILLAGE,TOBEIMPLEMENTEDBYMARCH2024:Clean and Green Village

  - STATUSOFWORKSUNDERTHEFOLLOWINGSCHEMES: Village with good governance

## Cleanandgreenvillage

- InitiativestakenbythePanchayatformanagingSolidandLiquidWaste Composit pit and soak Pit

- InitiativestakenbythePanchayatforusinggreensourcesoffuellikesolar,biogas: Nil

- Hasmappingoflanduse,waterbodies,forest,slopes,wetlands,degradedforestwithintheGramPanchayatbeendone?Yes/No.IfNo,reason,thereof No

- HastheClimateResiliencePlanbeendevelopedfortheGP?Yes/No:

- StepstakenbytheGramSabhaabouttheclimatechangemitigationfactorslikereducingenergyconsumption,usageoffossilfuels,plastics,non-

renewablebuildingmaterialsandalsotopromotemeasureslikeplantingoftrees,conservingforests,usageof	goodagriculturalpracticeslikedripirrigation,waterconservationmeasuresandconservationofwetlands:

- Whetherschoolshavestartedsegregatingwaste: Yes

- Whetherschoolshavetheirowncompost/soakagepitsforsolid/liquidwastemanagement: Yes

## Healthyvillage

- Aremeetingsrelatedto VillageHealthandSanitationCommitteebeingheldregularly?: Yes

- DoalltheeligibleindividualsbeenprovidedtheGoldenCard?: Yes

- ArealltheChildrenbeingimmunizedaspertheSchedulerecommendedbyGovt.ofIndia?: Yes

- ArealltheeligibleindividualsbeenvaccinatedagainstCOVID-19?No

- DoesGramPanchayatensurethatallpregnantwomenaregettingnecessaryprenatalcheckups?Yes

- WhetherallthedeliverieswereInstitutionalizedorconductedbytrainedMidwives?Yes

## Watersufficientvillage

- DoalltheIHHsintheGramPanchayathavewaterpipelineconnections?No

- WhetherGramPanchayathastakenstepsforgreywatermanagement.IfYespleasespecify: No

- DoalltheIHHsintheGramPanchayathavetoilets?No

- ArealltheIHHstoiletsfunctionalornot?No

- DoalltheSchools/Anganwadicentershaveatoiletfacilityornot?Yes

- Areallthetoiletsintheschools/Aaganwadifunctionalornot?Yes

- WhetherGramPachachayatBhawanhasseparatetoiletsforwomenornot?No

## ChildFriendlyvillage

- Doallthechildrenundertheageof0-6yearsbeenenrolledintheAnganwadicentersforpre-schooling?Yes/NO: Yes

- HowmanyBalSabha’swereorganizedintheGramPanchayat--------02-----------

- WhethertheissuesraisedbyBalSabhaareaddressedduringtheGramSabha.Yes/NO: No

- WhetherGramPanchayatistrackingthedatarelatedtodropoutchildrenandchildrenwithirregularattendance?Yes/NO: No

- DoalltheschoolsundertheGramPanchayathaveseparatetoiletsforgirlsandboys?Yes/No: No

## Villagewithgoodgovernance

- IsCSClocatedintheGramPanchayatBhawanornot? Yes

- IsthelistofbeneficiariesrelatedtotheSchemes/ProgramsdisplayedontheGrampanchayatwallornot? Yes

- DoestheGramPanchayathasitsbuildingornot? Yes

- IstheGramPanchayatofficefunctionalornot?Yes

- AretheactivitiesapprovedundertheHalqaPanchayatDevelopmentPlandisplayedontheGramPanchayatwallornot?No

- IsSocialAuditofearlierSchemes/Programscarriedoutornot?Yes

## Povertyfreeandenhancedlivelihoodvillage

- HasGramPanchayatdevelopedanycriteriafortheidentificationofthepoor?Yes/Noifyesspecify: No

- HavealltheeligiblehouseholdsregisteredinPDSornot?Yes

- HasGramPanchayatprovidedspaceforSelf-helpGroupsinPanchyatGharforholdingmeetingsornot? Yes

- HavealltheeligiblehouseholdsbeenregisteredforPensionornot?Yes

- HasGramPanchayatfacilitatedYouthforSkillEnhancementCoursesandPlacement? Yes

- HasJobCardsbeendistributedtoalltheeligibleindividualsunderMGNREGA?Yes

- HasGramPanchayatfacilitatedSHGsforBankAccountLinkages?Yes

## Sociallysecuredvillage

- WhetherGramPanchayatismaintainingdatarelatedtoDifferentlyAbledPeople? Yes

- IsGramPanchayatOfficeDisabledFriendlyornot?Yes

- AreprovisionsforaseparateBudgetundertheResourceEnvelopeforWomenandChildrenmadeornot? No

- Do all the Schools in the Gram Panchayat have facilities for Differently Abled Children like toilets,barrier-freeaccess,etc.,ornot? No

- Arealltheeligibleindividualsaregettingpensions,likeoldagepension,widowpension,etc? Yes

- ArealltheeligiblehouseholdsgettingbenefitsfromIAYornot?Yes

## EngenderedDevelopmentinVillage

- HowmanyMahilaSabha’swereorganizedintheGramPanchayat-------05------------

- WhetherSHGsfederationshavebeenprovidedspaceformeetingsinthePanchayatBhawan(Yes/No) Yes

- WhetherGPshavetakenstepsforincreasingwomen’sparticipationinGramSabha(Yes/No)No

- NumberofwomenbeneficiariesheadedhouseholdscoveredunderPDSsystem………………………

- Numberofbeneficiaries(outoftotaleligiblepopulation)receivingsocialprotectionbenefitsunderPradhanMantriMatritvaVandanaYojana………49………….

- Self-sufficientinfrastructureinthevillage

- Whether GP has a Community Hall with access to electricity, furniture, water supply,toilet…………No…………….

- WhethertheDisastermanagementplanisavailableattheGPLevel(Yes/No)Yes

- Whetherchild-friendlyparkwithrequiredfacilitiesisavailableinGP(Yes/No)No

- WhethertheGPhaseasyaccesstoGodownforstorage(Yes/No)No

- Whetherstreetlightsareprovidedinpublicplacesforensuringsafety(Yes/No)Yes

# DAY2ACTIVITIES

## AGENDANO.2

SensitizevillageresidentsaboutmyScheme”portal(myscheme.in)whichincludesinformationaboutalltheschemesbeingrunbyCentral/State/UTgovtacrossthecountry

(SchemeMaterialavailablefromhttps://jkpanchayat.in/b2v4.php)

# DAY2ACTIVITIES

## AGENDANO.3

HoldmeetingoftheBiodiversityManagementCommitteestodeliberateonissuespertainingtoconserva-tion of biodiversity and sustainable utilization of biological resources. He should check People Biodiversityregister(PBR)ofthatpanchayatandreviewifBiodiversityManagementCommitteeconstitutedforthatpanchayat is holding minimum 4 meetings in a year and meeting once in every 3 months (Role of BMCavailableathttps://jkpanchayat.in/b2v4.php)

COMMITTEEMEMBERS: 07

PRESENT:04

BIODIVERSITYREGISTERPHOTOS:

PAST4MEETINGDETAILS-DATES,MINUTESPHOTOS:

# DAY2ACTIVITIES

## AGENDA4

VisitingofficershallalsoplanandconductpanchayatlevelconvergencemeetingofalldepartmentsandprepareVillagedevelopmentplanforvillage,inconsultancywithGrampanchayat,discussitingramsabhaandgetitapproved.

(GPDPformatavailableonhttps://jkpanchayat.in/b2v4.php)

## InadditionGPDPplanshallalsoinclude:

Tourist places which need to be developed:Not Available

Specificproductwhichneedstobedeveloped:Walnut

Tourism-homestays:Nil

20candidatesfortrainingunderHimayatschemealongwithtradeinwhich:trainingistobegiven:Copy enclosed

# DAY2ACTIVITIES

## AGENDA5

Ensuresaturationoffollowingschemesandgivestatus:

| NAMEOFTHESCHEME | TOTAL ELIGIBLEBENEFICIARIESIN THEVILLAGE | TOTALBENEFICIARIESWHO AVAILED THE BENEFITS OFTHESCHEME | REASONSFORPENDENCY |
| --- | --- | --- | --- |
| GoldenHealthCardunderAyushmanBharat | 2289 | 1805 | under process |
| Jananisurakshayojana | 22 | 22 | - |
| OLDAGEpension | 190 | 179 | under process |
| Widowpension | 62 | 57 | Docu def |
| Disabilitypension | 105 | 102 | -do- |
| Domicilecertificate | 3065 | 2365 | On going process |
| Kisancreditcard | 220 | 215 | Under process |
| PMkisansammannidhi | 170 | 140 | Docu defi |

| Landpassbook | 504 | 200 | Under Process |
| --- | --- | --- | --- |
| Registrationofvillageven-dorsonGEMportal | Nil | Nil |  |
| Registrationofvillagecon-tractorsonjktenders portal | 05 | 05 |  |
| Registrationofvillagecon-tractorsonPWDportal | 03 | 03 |  |
| Incomplete buildings/pro-jects | - | - | - |

# DAY2ACTIVITIES

## AGENDA6

NASHAMUKTABHIYAN

- Whethergramsabharesolutionpassed: Yes resolution by the GP that there is no person with addiction in the village and whole village is nasha mukt

- Detailsofactivitiesconducted: -

- WhetherallactivitiesandGSresolutionuploadedonjkpanchayats.inportal: Yes

- Howmanydrugaddictsinthevillage:Not reported

- WhetherreportedtotheDeputyCommissioner: -

- Howmanyregisteredforrehabilitationundergovernmentprogramme: -

# DAY2ACTIVITIES

## AGENDA 7SOCIALAUDIT

Conductsocialauditofatleast5workseachunderfollowingschemes:

| NAMEOFTHE SCHEME | DETAILSOFTHE WORKS | YEAROFWORK APPROVAL | AMOUNT APPROVEDFORTHEWORK | WHETHER WORK EXECUTEDSATISFACTORILY | GEO- TAGGEDPHOTOS | ANYGRIEVANCE RECORDEDRELATINGTOTHATWORK |
| --- | --- | --- | --- | --- | --- | --- |
| MGNREGA | 03 | 2020-21 | 3.90 lakh | Yes | Yes | No |
| PMAY | 02 | 2019-20 | 2.6 lakh | Yes | Yes | No |
| IHHL UNDERSBM-G | 01 | 2020-21 | 0.12 lakh | Yes | Yes | No |
| CSC UNDERSBMG |  |  |  |  |  |  |
| AMRITSAROVARS | 01 |  |  |  |  | Under const |

# DAY2ACTIVITIES

## AGENDA 8

## MAHILASABHA

Totalwomeninthevillageabovetheageof18: 973

Totalattended :17

Proceedings:Awareness created about immunization health and hygiene anemia defi, discourage about marriage below 18 of female child and all scheme of Govt of india related to female and women.

(Plinsertpointerstobediscussedthere–referpalliproceedings)

# DAY2ACTIVITIES

## AGENDA 9

## BALSABHA

Holdabalsabhaandrecordproceedings

Totalchildreninthevillageabovetheageof…6 years and below 16 years.

Totalattended: 20

Proceedings:

(Plinsertpointerstobediscussedthere–referpalliproceedings)

# DAY2ACTIVITIES

AGENDA 10INAUGURATIONS

| SRNO. | ASSETS /ACTIVITIESINAUGRATED | STATUSOFTHEASSET/AC-TIVITIES (NUMBER, OTHERDETAILS) | GEO-TAGGEDPHOTOS |
| --- | --- | --- | --- |
|  | VILLAGEHAATunderJKSRLM(SUN-DAYMARKET) | No | No |
|  | PMAYhousesifanyreadyforinaugra-tion | 02 | Yes |
|  | Swachhgramprojects-segregationshedsetc | - | - |
|  | Amritsarovars | 01 | UNDER CONTT |
|  | Sportskits | 01 | Yes |
|  | Villageculturalevents | Yes | Yes |
|  | JJMassets/projects | - | - |
|  | Any other to be identified at districtlevel | - | - |

# FOLLOWUPOF(B2V1,B2V2&B2V3):

(Prefilledexcelsheettobetakenfromdistrictlevel/andalsotobedownloadedfromwww.jkpanchayat.in)

| S.NO. | Particulars | Actiontaken | Remarks# |
| --- | --- | --- | --- |
| I. UrgentPublicRequirements/Demands-B2V1 |  |  |  |
| - Link road to panchayat ghar and water taken |  |  | Nil |
| - Road from college to kamri wala and link road to each hamlet |  |  | Nil |
| - Upgradation of MS to HS basti dra |  |  | Nil |
| - Panchayat be promoted as model town |  |  | Nil |
| II. UrgentPublicRequirements/Demands-B2V2 |  |  |  |
| - Water supply system |  | Nil | However plan approved as stated by AEE, PHE |
| - Lack of Anganwari center |  | Nil |  |
| S.NO. | Particulars | Actiontaken | Remarks# |
| III. MajorProblems–B2V1 |  |  |  |
| - Drinking water supply |  | Nil |  |
| - Lack of health S.C |  | Nil |  |

| IV. MajorProblems-B2V2 |  |  |  |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| - Lack of Angadwari building |  |  |  |  |  | Nil |  |  |  |  |  |  |  |
| - Worst condition of road JWG to basti dra |  |  |  |  |  | Nil |  |  |  |  |  |  |  |
| V. MajorProblems-B2V3 |  |  |  |  |  |  |  |  |  |  |  |  |  |
| - Lack of water supply system in whole village |  |  |  |  | Nil |  | However plan approved as stated by AEE, PHE |  |  |  |  |  |  |
| VI. MajorComplaints-B2V1 |  |  |  |  |  |  |  |  |  |  |  |  |  |
| - Non-availability of Hr Sec School |  |  | Nil |  |  |  |  |  |  |  |  |  |  |
| - Road connectivity to hamlet |  |  | Nil |  |  |  |  |  |  |  |  |  |  |
| - Non availability of tab water |  |  | Nil |  |  |  |  |  |  |  |  |  |  |
| VII. MajorComplaints-B2V2 |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  | Nil |  |  |  |  |  |  |  |  |  |  |  |
|  |  | Nil |  |  |  |  |  |  |  |  |  |  |  |
| VIII. MajorComplaints-B2V3 |  |  |  |  |  |  |  |  |  |  |  |  |  |
| - Lack of water supply system in whole village | Nil |  |  |  |  |  |  |  |  |  |  |  | However plan approved as stated by AEE, PHE |
|  |  |  |  |  |  |  |  |  |  |  |  |  | - |

DepartmentofRuralDevelompentandPanchayatiRajGovernmentofJammu&Kashmir