4





**15TH OCTto3RD NOV,2022**

**KEYFEATURES**

• DeputyCommissionerstoleadtheinitiative

• RuraldevelopmentDepartmenttobethenodaldepartment

• PlanningDevelopment&MonitoringdepartmentandITtobethesupport departments

**ACTIONSANDTIMELINES**

|  |  |  |  |
| --- | --- | --- | --- |
| **ACTION** | **RESPONSIBILITY** | **LATESTBY** | **REMARKS** |
| **Janabhiyan** | Alldepartments | Oct15-26th | Goingon |
| **DeputationofSecttstaff/ HoDs** | GAD | Oct14 | Done |
| **DeploymentofStaffto Panchayatsandservingof ordersondeployedofficers** | DCs | Oct25 | DCswilldeployseniorlevelstaff fromthedistricts.Strictactionto betakenagainstabstentions.No exemptionstobegiven |
| **Trainingofdistricttrainors onB2V4** | RDD | Oct26 |  |
| **Trainingofvisitingofficers** | DCs | Oct27 |  |
| **FieldVisitstobecompleted by** | VisitingOfficers | Nov3 | DCstosuperviseandensurethat eachPanchayatisvisitedwithin theperiodspecified |
| **DataofB2V4tobe uploadedby** | VisitingOfficers | Nov10 | DCstosuperviseandensurethat dataofallPanchayatsisupload- edbythevisitingofficerwithin theperiodspecified |

**INSTRUCTIONSFORTHEVISITINGOFFICER(DAYWISE)**

|  |  |  |
| --- | --- | --- |
| **DATE** | **INSTRUCTIONS** | **ACTIONPOINTS** |
| **Day0** | Meetingwithdeputy commissionerandhis/her team | a. TakeprintoutsoffilledbookletsofB2V1,B2V2andB2V3from [www.jkpanchayat.in](http://www.jkpanchayat.in)b.Alsotakeprintoutsofthesummarizedexcelsheetsofthe previousphasesfrom[www.jkpanchayat.in](http://www.jkpanchayat.in)c. CollectATRsonissuesraisedduringprevious3phasesfromthe officeofDeputyCommissioner(Planningdeptt)d.Takeprintsofblank 2bookletsofB2V4from[www.jkpanchayat.in](http://www.jkpanchayat.in)e.Takeplansfor2previousyearsandATRsfromtheplanningdeptt f. CompletetrainingsondifferentcomponentsofB2V4beingorganizedbyrespectiveDeputyCommissionersg.CollectListofnewworksstarted/ongoing/completedduringthe previousandcurrentFinancialyearunderthefollowingheads:• PRIgrants• DistrictPlan• UTplan• MGNREGA• Otherschemesofotherdepartments• Anyotherworkh. Plans/beneficiarylists:• MGNREGAdraftplandocumentfortheyear2022-23.• ListofAwaas+beneficiariesalongwithIHHL Convergence• Listofpensionbeneficiaries.• ListofSHGs• Listofagricultureschemebeneficiariesi. Listsofbeneficiariesfor:• Variouscertificates/benefitstobedistributedbythe visitingofficer.• Anyotheractivitiesidentifiedbydifferentdepartments |

|  |  |  |  |
| --- | --- | --- | --- |
| **Day1** | Reachthevillage | 1. | Ensurethatallfrontlineworkersofdifferentdepttsarepresent. |
|  |  | 2. | Ensureexhibitionbydifferentdepts.aboutindividualbeneficiary schemes |
|  |  | 3. | InspectJKB/PSBcounters/outlets |
|  |  | 4. | Participate/ensureorganizationofsportsactivityinplayfield,talent hunt/culturalevent/youthactivity |
|  |  | 5. | GandhiKatha(suggesteddetailsuploadedonjkpanchayat.in) |
|  |  | 6. | Visitatleast2amritsarovarsandgetitsgeotaggedphotos |
|  |  | 7. | InspectKhidmat(CSC)CentresandcreateGenerateawarenesson225schemesparticularlyG2CschemeslikeBEAMS,Janbhagidari, AapkiZaminAapkiNigrani,DigitalJ&K |
|  |  | 8. | Visitingofficershallalsoplanandconductpanchayatlevelconver- gencemeetingofalldepartments |
|  |  | 9. | CheckeffectivenessofCentrallysponsoredschemes |
|  |  | 10. | VisitandinspectallgovernmentestablishmentsincludingPHE, AWC,FPS,schools,etc |
|  |  | 11. | Attemptsaturationofdeliverableso JanAbhiyanandwherever deficienciesfound,leadadrivetoachievealldeliverables |
|  |  | 12. | Assesseffectivenessofsanitationcampaigninthepanchayat |
|  |  | 13. | Ensureselfemploymentactivitiesfor15youthperpanchayat |
|  |  | 14. | Identify20potentialcandidatesperpanchayatforHIMAYATtraining alongwiththetradeonwhichtheywanttraining |
|  |  | 15. | Whereverpossible,distributeemploymentlettersforpeopleselect- edundervariousgovernmentemployments |
|  |  | 16. | Intheevening,holdnormalmeetingwith seniorcitizens,govtem- ployeesincludingretiredemployees,exservicemen,youthclub,and any citizens ofthevillagewhoareenrolledincollege/university |
|  |  | 17. | OpendiscussiononNashaMuktAbhiyan |

Day2 Haveameetingwithall stakeholders-depttofficials andpanchayatmembers

1. Discussionontheandassesstheprogressofdifferentschemesrelating tothelocalizedSDGsprioritizedforthatvillageaspertheresolution passedby thatGramPanchayaton21st April22,onNationalPanchayti RajDay.

2. Sensitizevillage residentsaboutmyScheme”portal(myscheme.in) whichincludesinformationaboutalltheschemesbeingrunbyCen- tral/State/UTgovtacrossthecountry

3. Hold meeting of theBiodiversityManagementCommitteestodeliber- ateonissuespertaining toconservation of biodiversityandsustaina- bleutilizationof biologicalresources.

4. PrepareVillagedevelopmentplan,inconsultancywithGrampanchayat, discussitingramsabhaandgetitapproved.

5. Ensure saturationofsoilhealthcardandgoldenhealthcardunderGold- enHealthCardunderAyushmanBharat,

6. Ensuresaturation of OldAge PensionScheme

7. EnsureDomicileSaturation.

8. EnsureKCCSaturation

9. Ensure saturationoflandpassbooks

10. Ensureregistrationofvillagevendorsneededforanyscheme,onGEM

portal

11. Ensurepanchayatcontractors registration

12. EncouragePanchayatmembers forimportanceofplantationdrivein

PanchayatunderHarGaonHariyali

13. Ensure paintingondigitalJ&Kinpanchayatghars

14. Ensure paintingonpanchayatactivitesandCSSinpanchayatghars

15. Thevisiting officeshallchecknoof kindergarten andplayfields present inthepanchayat for kidsandstudents,iftheinfrastructure present inthesearegoodenough.

16. Holdmeeting withpanchayatmembers todiscussaboutcorruption menaceandstepsrequiredtomakeJ&Kcorruptionfree

17. Obtaina candidassessmentaboutperformanceofvariousdeptts in- cludingfairfeedbackaboutdiscrepanciesinfunctioning

18. Check thestatusof NashaMuktAbhiyanandreporting of drugad- dictstoDeputyCommissioner.

19. IdentifyTouristDestinations,Circuits,ThemeTreks,IdentifyHomestays, providesupportfortourismactivities throughVillageCooperative

20. OrganizeTalentHuntatPanchayatLevel

21. Conductsocialauditofatleast5worksunderfollowingschemes:

a. MGNREGA

b.PMAY

c. IHHLtoiletsandpayments d.CSCs

e.AMRITSAROVARS

22. Holda mahilasabha anda balsabhaandrecordproceedingsinthefor- matgiven

23. InauguratevillagehaatunderJKSRLM

24. Checkifyouthclubsareformedinthepanchayatandwhatactivities theyareengagedin

25. Organizea villagelevelculturaleventtoengagepanchayatmembers

26. SensitizeGPaboutE-kitabkoshaninitiativeofJ&KGovtforempowering youthsthrough onlinedigitalliteracy

**GENERALINSTRUCTIONS**

1. Thevisitingofficershallrefrainhimself/herselfgivingorofferinganycommitmentonbehalfofthe governmentandshalladoptanunbiasedattitudeinreportingissues.As faraspossible,his/her observation shouldbebasedona fairandanalytical viewemergingfromhis/herinteractioninthe village.

2. Heisgoingtothevillageasplanningofficer,notforsanctioninganyworksorformakinganycom- mitments.

3. Whilepreparingvillagedevelopmentplan,hehastoensurethat,demandsareprioritizedandre- flectedunderavailableschemes,wherevernecessarythelargerworksaretobereferredtoadminis- trativedepttunderCSS/UTplansunderintimationtoDCsandrestoftheworkstoDCsforreflecting itunderdistrict/CSS plans

4. His workshallbehardcoreplanningandauditandisnota PRexercise.

5. EveryDeputyCommissionerhastoensurethatatleastoneRDDofficial(ideallyPanchayatSecre- tary)ispresent ineverypanchayatwithrelevantpanchayatrecords,toensureconductofallactivi- tiesasplanned.Panchayatwiseorderneedstobeissuedinadvance.

6. Visitingofficershouldideallycarryhis/herlaptoptocompletethereportsatthepanchayatlevel itselfanduploadthefinalreport,duly signedbothbythesarpanchandbythevisitingofficeron [www.jkpanchayat.in](http://www.jkpanchayat.in)portal,beforetheyleavepanchayat.

7. Focus ofvisitareyouth,skills,self-employment,nashamukt,bhrashtracharmukt,Rozgaryukt J&K, besidestocarryforwardtheactivities duringJanAbhiyanandsaturatethem.

8. Inadditionattentionmaybegiventothefollowingareas a. MakefulluseofCentrallySponsoredSchemes

b.Saturationofindividualbeneficiaryschemes c. Self-employmentschemes

d.Banklinkedschemes-includingdepartmentalsubsidyschemes e.Empowermentandtransparencythrough digitalinitiatives

f. Effectivenessofgrassrootsmachinery–

i. Patwari,VLWpresent andavailable

ii. AvailablefundsutilizedinpublicinterestandasperGramSabharesolutions iii. Fairness ingovernance

iv. CSS/Individual beneficiaryschemesetc v. BrashtacharMuktJ&K

vi. BhaiMuktJ&K

vii. NashaMuktJ&K

9. ThePRImembers (Sarpanchs,Panchs,BDCChairperson)shallbeattheforefrontofallactivities and givendueimportanceandtheapproach shouldbetostrengthenthemandmakethemfeelem- powered.He/sheshallensurethattheBDCchairpersonandSarpanch/Panch arepresent atthetime ofinaugurationandceremonies.

10. Visitingofficershallnotleavethedistrictwithoutuploadingthereport,duly signedonthe**www. jkpanchayat.in**portal.EveryDeputyCommissionerhastoensurethat.

**A) DetailsofReportingOfficer:**

Name: RESHI RASIQ RAFIQ

Designation: ASSISTANT ENGINEER

Department/placeof posting: Irrigation & Flood Control Department / Flood Control Division Kakapora

MobileNo:  **9797007956**

EmailID: **Rasiq.reshi871@gmail.com**

HomeDistrict: **Pulwama**

Datesof visit: **28/10/2022 & 29/10/2022**

**B) LocationaldetailsofPanchayat:(tobepre-filled,informationtobetakenfromtheprevious phasesbooklets/summarizedexcelsheetuploadedonjkpanchayat.in/b2v4.php)(tobevali- datedbythevisitingofficerandmissingdetailstobefilled)**

NameofthePanchayat: **Aglar A**

LocalGovernmentDirectory(LGD)codeof thePanchayat: **2455555**

Nameof CDBlock: **Achgooze (Keller)**

NameofTehsil:  **Rajpora**

Nameof District: **Pulwama**

**C) PanchayatProfile:**

No.ofrevenuevillagesinthePanchayat: **03**

No.ofhamletsinthePanchayat: **06**

No.ofhouseholdsinthePanchayat: **440**

Population(approx)of thePanchayat: **2665**

**Part-II:**

(TobefilledupbytheVisitingOfficerduringhis/hertwodayvisittothePanchayat.AllFieldshavetobe

filledbytheVisitingOfficerbeforethebookletishandedovertotheDC

**FrontlineOfficers/OfficialswhowereassignedtothePanchayatfortheprogramme:**

|  |  |  |
| --- | --- | --- |
| Department | Name | Designation |
|  PDD | Mohd Amin Rather |  I/c Sector |
| R&B |  Shameem Ahmad |  Works Supervisor |
| PMGSY | Zahoor Ahmad Thoker |  Junior Engineer |
| EDUCATION | Mohd Shafi Bhat |  Headmaster |
| SHEEP DEPARTMENT | Mohd Shafi Dar |  I/c Stock Assistant |
| HEALTH | Mir Masooda |  FMPHW |
| IRRIGATION | Mohd Azeem |  Orderly |
| ICDS | Zareefa Bano |  Supervisor |
| PHE (JAL SHAKTI)  |  Ab Hameed Wagay | Ast Lineman |
| AGRICULTURE | Bilal Ahmad Dar | Agriculture Overseer |
| REVENUE | Mohd Ashraf Yatoo |  Patwari |
| YOUTH SERVICES & SPORTS | Mukhtar Ahmad Dar |  PET |
| FOOD & CIVIL SUPPLIES | Ishfaq Ahmad Dar |  Store-Keeper |
| FOREST  | Gh Nabi Khan | B.O |

**Detailsofabsentemployeesvis-à-vislistfurnishedbytheDCoffice:**

|  |  |  |
| --- | --- | --- |
| Department | Name | Designation |
|  |  |  |
|  |  |  |
|  |  |  |
|  |  |  |
|  |  |  |
|  |  |  |
|  |  |  |
|  |  |  |
|  |  |  |
|  |  |  |
|  |  |  |
|  |  |  |
|  |  |  |
|  |  |  |
|  |  |  |

**DAY1-ACTIVITIES**

**AGENDA1:PANCHAYATASSETREGISTER**

**Infrastructure:**

1. PanchayatGharInfrastructure a. Govtbuilding/private Govt building

b. New/needingrepairs .. New

2. Furniture(Y/N) N

3. Computer/printer(Y/N) N

4. Internet(Y/N) N

5. Telephone(Y/N) N

6. Toilet(CSC/partofpanchayatghar)(Y/N) Y

7. Water(Y/N) Y

8. Electricity(Y/N) N

9. Bankbranch(Y/N)b N

10. CSC(Y/N) Y

11. Patwarkhana(Y/N) N

12. Villagehaat(Y/N) N

13. Playground(Y/N) Y

14. School-

a. Kindergarten(Y/N) N

b.Primary(Y/N) Y

c. Secondary(Y/N) Y

d. College (Y/N) N

e.University(Y/N) N

15. AnganwadiCentre(Y/N) Y

a. (govt/private) Private

b.Totalchildrenenrolled : 240

15. AmritSarovars–details,location,condition : 01 no ; Under Construction

16. Governmentoffices-details,whetherfunctionalornot : RDD, ICDS

17. Rationshop(Y/N) Y

18. Placesoftourismimportance–names,littledetailsonhistorical/culturalimportance NIL

19. Villageheritagesites/treks-names,littledetailson historical/culturalimportance NIL

20. VLWOffice (Y/N) Y

21. PrimaryHealthcareCentre(Y/N), N

22. ListofIncompleteBuildings-names,yearofconstruction: NIL

23. ListofUnderutilizedBuildings-names NIL

**DAY1-ACTIVITIES**

**AGENDA2:**

**DIFFERENTINSTITUTIONS/INFRASTRUCTUREPROJECTSTOBEVISITED**

|  |  |  |
| --- | --- | --- |
| **AMRITSAROVARS** | **Visit,verify** | **COMMENTS** |
| KhidmatCentres | Create/Generateawarenesson225schemes particularlyG2CschemsAapkiZaminAapkiNigrani, Beams,Janbhagidari,DigitalJ&K | Khidmat Centre is established, providing services to and creating awareness among the people regarding various G2C schemes.  |
| JKB/PSBcounters/outlets | a)Statusofcounter b)Numberofvisitors | Not Existing |
| Incompletebuildings/pro- jects | Verify whetheridentificationandredistribution done | High School Building and Water Supply Scheme- Karewa.  |
| PDS | Visit,evaluate,onlinestatus | Ration store is established.  |
| PHC | Visit-evaluate,statusofstaff,equipmentand quality | Not established yet. Even there is no Health sub-centre. People of the panchayat Halqa suffer a lot in absence of very basic health services.  |
| Youthclubs | Meet,interact,seeksuggestions | Interacted with the youth, listened to and noted their suggestions and demands.  |
| SHG | Meet,identifyproblems,seeksuggestions |  Not Existing |
| PMAY | Inspect,Inaugurate | Presently two no. houses under PMAY are under construction.  |
| Myschool,mypride progress;schools-water, toilets,staff |  Visit, check for water, electricity, sanitation, Satisfactory.  meet students and staff |
| SwachhSBM | Evaluate |   Satisfactory |
| Panchayatplayground, Sportskitsdistribution Villagegames | Ensure,verify.Participateinatleastonegamein theplayground | Panchayat Playground is under construction.Due to presence of few very low yielding Walnut trees in the middle of the playground, the levelling of the playground is yet to be done in order to make it functional. Sports event held in HS aglar Premises.  |
| HarGaonHariyali, Planta- tiondrive | Evaluatestatus,feedback | Satisfactory.Plantation drive was carried out in the premises of the High school Aglar in collaboration with the Forest Department.  |
| VillageculturaleventDangal/Haat/Mela | Participatein;ensurethatitisheld |  Event Held |
| Exhibitionofschemes | Ensurethateverydepartmentparticipatesand thatitcontinuesfortheentiredurationofB2 |  Every department participated for full duration.  |
| JalJeewanMission verifica- tion- WSS/JSDElectricitysupply | Verify |    WSS Functioning satisfactorily in Aglar Kandi belt. Kadipora area needs attention.  |

**DAY1-ACTIVITIES**

**AGENDA3:SATURATEJANBHIYAN**

**DELIVERABLESANDRECORDDEFICIENCIESIFANY(INSERTDELIVERABLESLISTHEREASPERGADFORMAT**

|  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| **S. No.** | **Deliverable** | **Department** | **Overall Target** | **Remarks** |  **Deficiencies** |
| 1 | Golden Health Cards | Health | 100,000 | Panchayat/District Targets to be fixed by the Department based on gap in figures of every Panchayat | 100 per cent saturation achieved |
| 2 | Land Passbooks | Revenue | 1,000,000 | Panchayat/District Targets to be fixed by the Department based on gap in figures of every Panchayat | Digitization Completed. Rectification under Process.Land Passbooks shall be issued soon after rectification process is completed |
| 3 | Inheritance Mutations | Revenue | 7,000 | Panchayat/District Targets to be fixed by the Department based on survey of every Panchayat by the Patwaries | 23 mutations done. In Progress |
| 4 | Self Employment Drive | J&K Bank & Industries | 65,000 | At least 15 persons per Panchayat | 10 cases involving an amount if 16.50 lacs sanctioned by JK Bank Drabgam. Self-employment enrollment not easily accessible to interested candidates. No effective awareness/ campaigning done by agencies such as EDI, DICC, KVIB, Handicrafts etc. |
| 5 | Identify candidates for skill training under HIMAYAT and other schemes | RDD | 100,000 | At least 20 per Panchayat | 10 candidates identified for training..Deficiencies in form of awareness and accessibility found. Capacity of training centers needs enhancement.  |
| 6 | CSC/IT Camps in every Panchayat | IT | 4290 | One per Panchayat | Held.Some Eshram Cards, UDID cards and Golden Cards processed during the B2V4 programme |
| 7 | Creating Awareness of Jan Bhagidari among PRIs and general public | IT | 100,000 | 25 additional hits/Panchayat | 20 hits approx achieved |
| 8 | Painting of Digital J&K in every Panchayat | RDD | 4290 | One per Panchayat | Displayed |
| 9 | *Pani Samitis* meetings to be held | Jal Shakti | 4290 | One per Panchayat | Satisfactorily Done |
| 10 | Field testing kits to be provided for all Panchayats and trainings given | Jal Shakti | 4290 | One per Panchayat | One kit given..Training is deficient |
| 11 | Certification of water sufficiency and quality of Panchayats  | Jal Shakti | 451 | As per list decided by Department | Achieved |
| 12 | Implement Swachh Gram Plans·       Door to door collection and disposal- ensure·       Management of grey water, black water and solid waste  | RDD | 6,870 | To be implemented in every Village | Door to Door Collection not done. Scientific disposal not done. Management of Grey Water Satisfactory.  |
| 13 | UDID Cards to be converted to Digital Format | Social Welfare | 250,000 | Panchayat/District Targets to be fixed by the Department based on existing cards | 30 ℅ progress achieved |
| 14 | E-shram Cards | Labour | 250,000 | Panchayat/District Targets to be fixed by the Department based on survey | 50℅ achieved |
| 15 | Inspect Playfields and ensure that at least one sports event is held | YSS | 4290 | At least one per Panchayat | Sports event held satisfactorily |
| 16 | Inspect office of Patwari, VLW and ensure that name and phone number of the Patwari/VLW is painted on the wall of the office | Revenue, RDD | 8580 | 2 per Panchayat ( 1 patwari office + 1 VLW office) | No Deficiencies |
| 17 | Amrit Sarovars- Inspect quality | RDD | 1,500 | 75 per District | Inspected. Found Under Constitution |
| 18 | Youth Clubs Interact | Youth Mission | 4290 | At least one per Panchayat | No presence from the department. However, interaction with the youth of the GP |
| 19 | Azadi Ka Amrit Mahotsav- Upload High Quality videos | Culture & DCs | 15,000 | At least 3 per Panchayat | Organised. No deficiencies |
| 20 | Hold Gram Sabha meetings and assess quality and effectiveness of service delivery, performance and ranking of departments and perception of corruption | All visiting Officers | 4,290 | Every Panchayat | No deficiencies |

**DAY1-ACTIVITIES**

**AGENDA4:**

**SELFEMPLOYMENTACTIVITIES**

EnsureSelf-employmentactivities foryouth,distributeemploymentlettersforpeopleselectedunder varioussocialschemes(15ISTHETARGETPERPANCHAYAT)

**Numberofcasesindifferentcategoriessanctioned: 10**

**Detailsofthebanksanctioningit: JK Bank Branch Drabgam**

**Totalamountinvolved: Rs 16.50 lacs**

**DAY1ACTIVITIES**

**AGENDA5**

Intheevening,holdinformalmeetings withseniorcitizens,govtemployees,retdemployees,youthclub andothercitizenswhoareenrolledoncollege/universityandhavediscussiononGandhiKatha,Nasha MuktAbhiyan,corruptionfreegovernance,doublingfarmersincomeandrecordtheproceedings

**DAY2**

a. NoofIndividualCompost pits constructed: NIL

b.NoofIndividualSoakPitsconstructed : 50

V. No.ofBiodiversitymanagementcommitteemeetingsheld: 02 including meeting held during B2V4.

VI. IsthenameofSarpanchdisplayedoncitizeninformationboardsofallRD&PRschemes:Yes/No NO

VII. AreSarpanchsbeinginvolvedinstart/inaugurationofactivities:Yes/No NO

VIII. WhethersubjectshavebeenassignedbytheSarpanchtothePanchs:Yes/No NO

IX. Whethergrievancesredressalboxisinstalled:Yes/No Y

X. No of grievancesreceivedpertainingtoPanchayatlevel : NIL

XI. NoofgrievancesdisposedofatPanchayatlevel: NIL

XII. WhethertheSarpanch/PanchayatSecretaryhavedigitalsignatures:Yes/No YES

XIII. WhetherallMGNREGA/14thFCpayments arebeingmadebySarpanchthrough DigitalSignature

Certificate(DSC):Yes/No : No elected Sarpanch.

**HUMAN RESOURCEAVAILABLEATTHEPANCHAYAT LEVEL:**

|  |  |  |  |
| --- | --- | --- | --- |
| **SRNO.** | **DEPARTMENTWISESTAFF** | **NUMBERS** | **NAMES** |
|  |  | SANCTIONED | ACTUAL |  |
|  | Ruraldevelopmentdepartment: BDOJE GRS TA |  01 01 01 01 |  01 01 01 01 |  Dr Towqeer Ahmad Er Gulzar Ahmad Bilal Ahmad Dar Bilal Ahmad Bandh.  |
|  | SCHOOLEDUCATION:HS AGLARTEACHERHEADMASTER ANYOTHER |   |  |  |
|  | JAL JEEVAN: |  |  |  |
|  | PDD: LINEMAN JEANYOTHER |  01 01 01 |   01 01 01 |  Hilal Ahmad Mir Er Bilal Ahmad Lone Mohd Amin Rather |
|  | FOOD&CIVILSUPPLIES |   01 |   01 |   Ishfaq Ahmad Dar |
|  | AGRICULTURE&ANIMALHUS- BANDARY |   03 |   03 |   Towseed Ahmad - JAEO Mohd Shadi Dar - I/c SA Towseef Ahmad - ASM |
|  | SOCIALWELFARE |  |  |  |
|  | HEALTH: ASHA ANMAYUSHDOCTOR ALLOPATHICDOCTOR |  03 |   03 |   Tahira ; Naseema and  |
|  | ANYOTHERDEPARTMENT |  01 |   01 |   Mohd Ashraf (Patwari)  |

**DAY2-ACTIVITIES**

**AGENDANO.1**

DiscussionontheandassesstheprogressofdifferentschemesrelatingtothelocalizedSDGsprior-itizedforthatvillageaspertheresolutionpassedbythatGramPanchayaton21stApril22,onNational PanchayatiRajDay(Copyoftheresolutiontobetakenfrom[www.jkpanchayat.in](http://www.jkpanchayat.in)portalunderthelinkof GramSwarajMonth)

1. SDGs AGREED FORTHATVILLAGE,TOBEIMPLEMENTED BYMARCH2024: 1). Clean and Green Village and 2) Water Sufficient Village

2. STATUSOFWORKSUNDERTHEFOLLOWINGSCHEMES:

**1 Cleanandgreenvillage**

i.InitiativestakenbythePanchayatformanagingSolidandLiquidWasteDoor to Door Collection for Solid wastes and soakage pits being provided for liquid wastes to every eligibile IHH.

ii. InitiativestakenbythePanchayatforusinggreensourcesoffuellikesolar,biogas : Solar lights installed at different locations across the panchayat Halqa. Viz. Aglar Kandi (02 no) ; Kadipora ( 02 no) and Gujjar basti (01 no)

iii. Hasmappingoflanduse,waterbodies,forest,slopes,wetlands,degradedforestwithintheGram

Panchayatbeendone?Yes/No.IfNo,reason,thereof: Not Yet; As reported by the Panchayat staff,ground work and data collection is being done and the mapping shall follow accordingly.

iv. HastheClimateResiliencePlanbeendevelopedfortheGP?Yes/No :: NO

v. StepstakenbytheGramSabhaabouttheclimatechangemitigationfactorslikereducingenergy consumption,usageoffossilfuels,plastics,non-renewablebuildingmaterialsandalsotopromote measureslikeplantingoftrees,conservingforests,usageofgoodagriculturalpracticeslikedrip irrigation,waterconservationmeasuresandconservationofwetlands. :: So far, the panchayat has taken the first step of creating awareness among and sensitising the people about these climatic mtigation factors.

vi. Whetherschoolshavestartedsegregatingwaste : Yes, partially.

vii. Whetherschoolshavetheirowncompost/soakagepitsforsolid/liquidwastemanagement: Not yet ; construction of sokage and compost pits stands approved and the work on them shall be taken up in the near future.

**2 Healthyvillage**

i) Aremeetings relatedtoVillageHealthandSanitationCommitteebeingheldregularly? Yes

ii) DoalltheeligibleindividualsbeenprovidedtheGoldenCard? Yes

iii) ArealltheChildrenbeingimmunizedaspertheSchedulerecommendedbyGovt.ofIndia? Yes

iv) ArealltheeligibleindividualsbeenvaccinatedagainstCOVID-19? Yes

v) DoesGramPanchayatensurethatallpregnantwomenaregettingnecessaryprenatalcheckups? Yes

vi) WhetherallthedeliverieswereInstitutionalizedorconductedbytrainedMidwives? NO

**3 Watersufficientvillage**

i) DoalltheIHHsintheGramPanchayathavewaterpipelineconnections? Yes.

ii) WhetherGramPanchayathastakenstepsforgreywatermanagement.IfYespleasespecify : Yes.. Soakage pits are being provided to every eligible IHH.

iii) DoalltheIHHsintheGramPanchayathavetoilets? Yes.

iv) ArealltheIHHstoiletsfunctionalornot? Yes.

v) DoalltheSchools/Anganwadicentershavea toiletfacilityornot? Yes.

vi) Areallthetoiletsintheschools/Aaganwadifunctionalornot? Yes,.. However need updation and separate toilets for girl students.

vii) WhetherGramPachachayatBhawanhasseparate toiletsforwomenornot? NO

n

**4 ChildFriendlyvillage**

i) Doallthechildrenundertheageof0-6yearsbeenenrolledintheAnganwadicentersforpre- schooling?Yes/NO Yes

ii) HowmanyBalSabha’swereorganizedintheGramPanchayat-----------01--------

iii) WhethertheissuesraisedbyBalSabhaareaddressedduringtheGramSabha. Yes/NO NO

iv) WhetherGramPanchayatistrackingthedatarelatedtodropoutchildrenandchildrenwithirregular attendance?Yes/NO. Yes

v) DoalltheschoolsundertheGramPanchayathaveseparate toiletsforgirlsandboys?Yes/No NO

**5 Villagewithgoodgovernance**

i) IsCSClocatedintheGramPanchayatBhawanornot? Yes

ii) IsthelistofbeneficiariesrelatedtotheSchemes/ProgramsdisplayedontheGrampanchayatwallor not? NO

iii) DoestheGramPanchayathasitsbuildingornot? Yes

iv) IstheGramPanchayatofficefunctionalornot? Yes

v) Aretheactivities approved undertheHalqaPanchayatDevelopmentPlandisplayedontheGram

Panchayatwallornot? NO

vi) IsSocialAuditofearlierSchemes/Programscarriedoutornot?Yes

**6 Povertyfreeandenhancedlivelihoodvillage**

i) HasGramPanchayatdevelopedanycriteria fortheidentificationofthepoor?Yes/Noifyesspecify NO

ii) HavealltheeligiblehouseholdsregisteredinPDSornot? Yes

iii) HasGramPanchayatprovidedspaceforSelf-helpGroupsinPanchyatGharforholdingmeetings or not? NO SHG EXIST

iv) HavealltheeligiblehouseholdsbeenregisteredforPensionornot? NO

v) HasGramPanchayatfacilitatedYouthforSkillEnhancementCoursesandPlacement? NO

vi) HasJobCardsbeendistributedtoalltheeligibleindividualsunderMGNREGA? YES

vii) HasGramPanchayatfacilitatedSHGsforBankAccountLinkages? NO SHG EXIST

**7 Sociallysecuredvillage**

i) WhetherGramPanchayatismaintainingdatarelatedtoDifferentlyAbledPeople? Yes

ii) IsGramPanchayatOffice DisabledFriendlyornot? Yes

iii) Areprovisionsfora separate BudgetundertheResourceEnvelopeforWomenandChildrenmadeor not? NO

iv) DoalltheSchools intheGramPanchayathavefacilitiesforDifferentlyAbledChildrenliketoilets, barrier-freeaccess,etc.,ornot? NO

v) Arealltheeligibleindividualsaregettingpensions,likeoldagepension,widowpension,etc? Yes

vi) ArealltheeligiblehouseholdsgettingbenefitsfromIAYornot? NO

**8 EngenderedDevelopmentinVillage**

i) HowmanyMahilaSabha’swereorganizedintheGramPanchayat------------01-----

ii) WhetherSHGsfederationshavebeenprovidedspaceformeetings inthePanchayatBhawan(Yes/ No) NO SHG EXIST

iii) WhetherGPshavetakenstepsforincreasingwomen’sparticipationinGramSabha(Yes/No) Yes

iv) NumberofwomenbeneficiariesheadedhouseholdscoveredunderPDS

system………………………

v) Numberofbeneficiaries(outoftotaleligiblepopulation)receivingsocialprotectionbenefitsunder

PradhanMantriMatritvaVandanaYojana………Nil………….

9 Self-sufficientinfrastructureinthevillage

i. WhetherGPhasa CommunityHallwithaccesstoelectricity,furniture,watersupply, toilet…………NO…………….

ii. WhethertheDisastermanagementplanisavailableattheGPLevel(Yes/No) NO

 iii. Whetherchild-friendlyparkwithrequiredfacilitiesisavailableinGP(Yes/No) NO

iv. WhethertheGPhaseasyaccesstoGodownforstorage(Yes/No) NO

v. Whetherstreetlightsareprovidedinpublicplacesforensuringsafety(Yes/No) Yes

**DAY2ACTIVITIES**

**AGENDANO.2**

SensitizevillageresidentsaboutmyScheme”portal(myscheme.in)whichincludesinformationaboutall theschemesbeingrunbyCentral/State/UT govtacrossthecountry

*(SchemeMaterialavailablefromhttps://jkpanchayat.in/b2v4.php)*

**DAY2ACTIVITIES**

**AGENDANO.3**

HoldmeetingoftheBiodiversityManagementCommitteestodeliberateonissues pertainingtoconserva- tionofbiodiversityandsustainableutilizationofbiologicalresources.HeshouldcheckPeopleBiodiversity register(PBR)ofthatpanchayatandreviewifBiodiversityManagementCommittee constitutedforthat panchayatis holdingminimum4meetings inayearandmeeting onceinevery3months *(RoleofBMC availableathttps://jkpanchayat.in/b2v4.php)*

COMMITTEE MEMBERS: 06

PRESENT: 04.

BIODIVERSITYREGISTERPHOTOS

PAST 4MEETINGDETAILS-DATES,MINUTESPHOTOS

One meeting held on 27 August 2020 with the main agenda points being : Awareness about various schemes viz Horticulture, PMAY, MGNREGA, etc. Members having resolved to show full committment to achieve the targets.

**DAY2ACTIVITIES**

**AGENDA4**

Visitingofficershallalsoplanandconductpanchayatlevelconvergencemeeting ofalldepartmentsand prepareVillagedevelopmentplanforvillage,inconsultancywithGrampanchayat,discussitingram sabhaandgetitapproved.

(GPDPformatavailableonhttps://jkpanchayat.in/b2v4.php)

**InadditionGPDPplanshallalsoinclude:**

 Touristplaceswhichneedtobedeveloped : **N/A**

 Specificproductwhichneedstobedeveloped : **N/A**

 Tourism-homestays : **N/A**

 20candidatesfortrainingunderHimayatschemealongwithtradeinwhich training is to be given. **BCC ( Basic Computer Course)**

**DAY2ACTIVITIES**

**AGENDA5**

Ensuresaturationoffollowingschemesandgivestatus:

|  |  |  |  |
| --- | --- | --- | --- |
| **NAMEOFTHESCHEME** | **TOTALELIGIBLE BENEFICIARIESIN THE VILLAGE** | **TOTALBENEFICIARIESWHO AVAILEDTHEBENEFITSOFTHESCHEME** | **REASONSFOR PENDENCY** |
| GoldenHealthCardunderAyushmanBharat |  2665 | 2665 |  Nil |
| Jananisurakshayojana | 23 |   11 | Out of 12 pending. 04 not eligible, rest under process |
| OLDAGEpension |  45 |  45 |  NIL |
| Widowpension |  17 |  17 |  NIL |
| Disabilitypension |  23 |  23 |  NIL |
| Domicilecertificate |  2665 |  1350 | 1315 pending. Lack of awareness among the people.Concerned Patwari as well as the locals present were sensitised to expedite the process and saturate the same.  |
| Kisancreditcard |  250 |  205 | Pending eligible beneficiaries are not interested.  |
| PMkisansammannidhi |  150 |   120 |  Forms of the pending eligible beneficiaries under process.  |

|  |  |  |  |
| --- | --- | --- | --- |
| Landpassbook |  395 |  Nil | Digitization has been completed. Rectification under progress.Land passbooks shall be issued after the rectification process is completed.  |
| Registrationofvillageven- dorsonGEMportal |  - |  - |  |
| Registrationofvillagecon- tractorsonjktendersportal |  01 |  01 |  |
| Registrationofvillagecon- tractorsonPWDportal |   01 | 01 |  |
| Incomplete Buildings/projects |  -  |

**DAY2ACTIVITIES**

**AGENDA6**

**NASHAMUKTABHIYAN**

1. Whethergramsabharesolutionpassed : **Yes**

2. Detailsofactivities conducted: **MGNREGA, SBM, PMAY**.

3. Whetherallactivities andGSresolutionuploadedonjkpanchayats.inportal : **Yes**

4. Howmanydrugaddictsinthevillage : **NIL**

5. WhetherreportedtotheDeputyCommissioner ---

6. Howmanyregisteredforrehabilitationundergovernmentprogramme

**DAY2ACTIVITIES**

**AGENDA7**

**SOCIALAUDIT**

Conductsocialauditofatleast5workseachunderfollowingschemes:

|  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- |
| NAMEOFTHE SCHEME | DETAILSOFTHE WORKS | YEAROFWORK APPROVAL | AMOUNT APPROVEDFORTHEWORK | WHETHERWORKEXECUTED SATISFACTORILY | GEO- TAGGED PHOTOS | ANY GRIEVANCE RECORDED RELATINGTOTHAT WORK |
| MGNREGA |  05 No |  2020 - 2021 2021 - 2022 |   21.26 Lacs   |  Yes |  Yes |  Nil |
| PMAY |  02 No |  2020-2021 |  3.00 Lacs |  Yes |  Yes |  Nil |
| IHHLUNDERSBM-G |   05 No |

|  |
| --- |
|  |

  |   0.60 Lacs |   Yes |   Yes |  Nil |
| CSCUNDER SBMG |   - |   - |  |  |  |   -- |
| AMRIT SAROVARS |  01 |   01 |    |  Yes.. Under Construction |  Yes |   Nil |

**DAY2ACTIVITIES**

**AGENDA 8**

**MAHILASABHA**

Totalwomeninthevillageabovetheageof18: 590

Totalattended : 10

Proceedings: Interacted with the attending members, and listened to and noted their concerns and demands. The main concerns that need to be adressed are :

1. Tailor and artisan centre for women of the halqa.

2. Health sub-centre be established. 𝙈𝙊𝙎𝙏 𝙐𝙍𝙂𝙀𝙉𝙏.

3. Aganwadi Centre be established at Kadipora and New Colony Aglar.

4. Counselling centre for women.

*(Plinsertpointerstobediscussedthere–referpalliproceedings)*

**DAY2ACTIVITIES**

**AGENDA9**

**BALSABHA**

Holda balsabhaandrecordproceedings

Totalchildreninthevillageabovetheageof 08 : …..

Totalattended : 22

Proceedings: Interacted with the students, Sensitized them about their role in the overall development of the society. listened to and noted their concerns:The main concerns of the children are :

1. Establishment of Computer lab in the High School aglar.

2.Smart Classrooms.

3. Seperate toilet facilities for girl students.

4.Uniform and Sports Kits.

5.Children Amusement Park in the halqa.

6. Playground in the halqa be made functional.

7. Health Sub -Centre be established.

*(Plinsertpointerstobediscussedthere–referpalliproceedings)*

**DAY2ACTIVITIES**

**AGENDA10**

**INAUGURATIONS**

|  |  |  |  |
| --- | --- | --- | --- |
| **SR NO.** | **ASSETS/ACTIVITIES INAUGRATED** | **STATUSOFTHEASSET/AC- TIVITIES(NUMBER,OTHER DETAILS)** | **GEO-TAGGED PHOTOS** |
|  | VILLAGEHAATunderJKSRLM (SUN- DAYMARKET) |  Not Established Yet |  -- |
|  | PMAYhousesifanyreadyforinaugra- tion |   -- |  -- |
|  | Swachhgramprojects-segregation shedsetc |  --.  |  -- |
|  | Amritsarovars |   01 no.  Under construction |  Attached |
|  | Sportskits |  -- |   -- |
|  | Villageculturalevents |  01..Wanwun performed bhi the girl students of HS Aglar |   Attached |
|  | JJMassets/projects |   --- |   --- |
|  | Anyothertobeidentifiedatdistrict level |   -- |    -- |

**FOLLOWUPOF(B2V1,B2V2&B2V3):**

*(Prefilledexcelsheet tobetakenfromdistrictlevel/andalsotobedownloaded*

*from[www.jkpanchayat.in)](http://www.jkpanchayat.in)*

|  |  |  |  |
| --- | --- | --- | --- |
| S.NO. | Particulars | Actiontaken | Remarks# |
| I. UrgentPublicRequirements/Demands-B2V1 |
| 1 |  Upgradation of HS Aglar to HSS at Aglar Kandi |  Not Feasible.. HSS Drabgam is at a distance of 03 kms.  |   |
| 2 | Setting up of PHC at Aglar Kandi Sub-Centre at Kadipora and Gujjar Basti.  | Not Feasible | Health Sub-centre be provided to the Panchayat, as this being the MOST IMPORTANT AND PRESSED DEMAND OF THE PEOPLE THERE.  |
| 3 | Upgradation of Filtration Plant and laying out of the Pipes in the Panchayat Halqa | Under Execution.  | Pipe laying for almost 3.5 km yet to be done due to non-availability of funds |
| 4 | requisition of HT poles transformer 3 nos  | 01 transformer each installed in Aglar Kandi and Gujjar Basti. | 01 more transformee each in Aglar Kandi and Kadipora will be installed within a month. LT Poles not installed yet.  |
| 5 | upgradation of interior link roads nin the halqa  | Completed |  -- |
| 6 | setting up ofsheep/animal husbandary sub centre in halqa  | not feasible | The halqa is very rich in Livelihood stock viz Cattle, Cows etc. First-Aid Sheep and Animal Husbandry unit be provided atleast.  |
| 7 | requirement improvement of koul from patharpora to kangan  | estimate of 6 lac prepared  |  -- |
| II. UrgentPublicRequirements/Demands-B2V2 |
| 1 |  Upgradation of electric infrastructure in GP. .  |  02 transformers installed in Aglar and Kadipora so far | 02 more transformers shall be installed within a month IN GP. LT ans HT poles yet to be installed.  |
| 2 | Power supply to whole area as per schedule  |  Provided |  |
|   3. | Upgradation of HS to HSS  | Not Feasible |  |
|   |
| 4. | Fencing of all the govt schools in GP. |  Approved under B2V1. Under tendering. | The present status is that the fencing of the various schools in the GP stands PARTIALLY done.Fencing of the remaining portions needs to be done at an earliest to ensure the safety of the school children. |
| 5. |  C/O Foot bridge over Nallah Romshi at Khudsa Gratta. |  Authorisation is awaited. |  |
| 6.7. |  Correction in the ration list of the PHH/AH. Laying of landlines/services from Drabgam to Kamrazipora via Aglar |  Rectification under process. Approved under B2V2 |  No Action taken.  |
| S.NO. | Particulars | Actiontaken | Remarks# |
| III. MajorProblems–B2V1 |
| 1 |  Upgradation of HS Aglar to HSS at Aglar Kandi |  Not Feasible.. HSS Drabgam is at a distance of 03 kms.  |   |
| 2 | Setting up of PHC at Aglar Kandi Sub-Centre at Kadipora and Gujjar Basti.  | Not Feasible | Health Sub-centre be provided to the Panchayat, as this being the MOST IMPORTANT AND PRESSED DEMAND OF THE PEOPLE THERE.  |
| 3 | Upgradation of Filtration Plant and laying out of the Pipes in the Panchayat Halqa | Under Execution.  | Pipe laying for almost 3.5 km yet to be done due to non-availability of funds. |
|  4. | requisition of HT poles transformer 3 nos  | 01 transformer each installed in Aglar Kandi and Gujjar Basti. | 01 more transformer each in Aglar Kandi and Kadipora will be installed within a month. LT Poles not installed yet.  |
|   5. | upgradation of interior link roads in the halqa  | Completed |  |

|  |  |  |  |
| --- | --- | --- | --- |
|  |  |  |  |
|  |  |  |  |
| IV. MajorProblems-B2V2 |
| 1 |  Upgradation of electric infrastructure. |  02 transformers installed in Aglar and Kadipora so far. |  02 more transformers shall be installed within a month IN GP. LT ans HT poles yet to be installed. |
| 2 |  C/O Foot bridge over Nallah Romshi at Khudsa Gratta |  Authorisation is awaited. |  |
| 3 |  Power Supply to the Panchayat as per Schedule. |  Power Supply provided as per Schedule. |  |
|  4 |  |  |  |
| 5 |  |  |  |
| V. MajorProblems-B2V3 |
| 1 |  Setting up of PHC at Aglar Kandi Sub-Centre at Kadipora and Gujjar Basti |  Not Feasible as per B2V1 and B2V2 reports. |  Health Sub-centre be provided to the Panchayat, as this being the MOST IMPORTANT AND PRESSED DEMAND OF THE PEOPLETHERE. |
|  2 | Upgradation of electric infrastructure in GP incl 03 no transformers for Aglar kandi, Gujjar basti and Kadipora. |  02 transformers installed in Aglar and Kadipora so far. |  02 more transformers shall be installed within a month IN GP. LT ans HT poles yet to be installed. |
| 3 |  Authorisation for C/O footbridge over Nallah Romshi at Khusda Gratta is awaited. |  Authorisation is awaited. |  |
| 4 |  Laying of 3 inch pipeline from chowan to Gujjar Basti and Mohandpora to Kadipora. |  Not Taken Up |  Needs to be taken up |
| 5 | Establishment of Agriculture and related centres including Patwari khana in the Halqa.  |  Not established yet. |  Needs Establishment.  |
| VI. MajorComplaints-B2V1 |
| 1 |  Low salary of ICDS Staff working in the field. |  NIL |  |
| 2 | Non availibilty of many departments |  NIL |  |
| 3 |  |  |  |
| VII. MajorComplaints-B2V2 |
| 1 | Indiscriminate curtailment of the power supply.  |  Electricity provided as per schedule. |  |
| 2 | Deployment of teachers to other schools. |  Most of the teachers posted back to the original place of posting.  |  |
| 3 |  |  |  |
| VIII. MajorComplaints-B2V3 |
| 1 |  Widening and macdamistion of the road from Drabgam to Pakherpora via Aglar. |  Not Taken Up |  Needs to be taken up |
| 2 | Construction of 07 borewells in panhayat Halqa. |  Not taken Up |  Atleast 02 bore wells yo ne provided |
| 3 | Inclusion of Chuntiwara and Gujjar Basti in backward area.  |  Not Taken Up |   Needs Consideration.  |

**OVERALLPERCEPTIONOFFUCNTIONING OF GOVERNMENTDEPARTMENTS**

1. **BESTDEPARTMENT: RURAL DEVELOPMENT DEPARTMENT**

**2. LEASTRESPONSIVEDEPARTMENT: All other Departments trying their level best as per the resources available at their disposal. Scope of improvement is always there.**

**GENERALASSESSMENTOFTHEVISTINGOFFICER**

|  |  |
| --- | --- |
| I | **AnymajorcomplaintbroughttothenoticeoftheVisitingOfficer**:1. Cutting of Walnut trees in the premises of the HS Aglar for the safety of the staff and the students. 2. Construction of the Side Drain through the HS Aglar. 3.C/O access road from the Main Road tobOrimary School Aglar via High School. 4.C/O Side drain along Aglar -Gujjar Basti Main Road from H/O Mukhtar Ah Dar to Feroz Ah Lone. 5.Completion of WSS -karewa. 6. Pipe Distribution Network in the GP to ensure hastle free Water Supply. 7.C/O bore well in New Colony Aglar and Reshiwaen Mohalla Aglar. 8. Shifting of Rohmu PHE line to upper Contours near HS Aglar. 9.Raising of Platforms of various Transformers in GP.  10.C/O protection bund along the Kralduj road at Vulnerable Spots. |
| II | **Major/urgentpublicdemandsthatwas/werereflectedearlierbuthavenotbeenaddressedsofar:**1. Setting up of Health Sub-centre in the Aglar Kandi village of Panchayat Halqa. **This is the Prime and the Most important demand of the GP.** **2. Setting up of Animal and Sheep Husbandry First-Aid Unit in the GP.** 3. Construction of Access road from Kanigam to Pakherpora Via Ani -e - lad. 4. Construction of Access road from Main Road to Orchards ( Tilwan-Khaer) of Kadipora. 5.Upgradation of School Infrastructure and leveling and Fencing of School Premises falling under GP. 6. Demarcation and removal of Encroachments and illegal occupation of State land in Village Kadipora. 7. Upgradation and widening of Drabgam-Pakherpora road via Aglar.  |
| III | **Overallassessmentofthevisitandsuggestions**:(Thevisitingofficertoensurethattheoverallassessmentisrecordedindetailsalongwithconcretesugges- tions)The Panchayat Halqa Lacks basic infrastructure vis-à-vis education , Banking, Medical, Livestock, and development of interior access roads, besides protection works at vulnerable streches within the Panchayat Halqa. The Demands put forth by the general public needs to be attended on priorty to improve the rating of Panchayat Halqa. |
| IV | **OverallRatingofgovtfunctioningas givenbythePanchayat(Scaleof0to10) : 05** |
| V | CertificatefromSarpanchthatthevisitingofficerhasstayedinthepanchayatfor2days:**Certified that the visiting officer stayed in the Panchayat halqa Aglar-A for 2 days during B2V4 program.**  |
|  | **Signature of Sarpanch Signature of the Visiting Officer Name……………………… Name………………………**  |
|  |  |
|  |  |



**DepartmentofRuralDevelompentandPanchayatiRaj**

**GovernmentofJammu &Kashmir**