4





**15TH OCTto3RD NOV,2022**

**KEYFEATURES**

• DeputyCommissionerstoleadtheinitiative

• RuraldevelopmentDepartmenttobethenodaldepartment

• PlanningDevelopment&MonitoringdepartmentandITtobethesupport departments

**ACTIONSANDTIMELINES**

|  |  |  |  |
| --- | --- | --- | --- |
| **ACTION** | **RESPONSIBILITY** | **LATESTBY** | **REMARKS** |
| **Janabhiyan** | Alldepartments | Oct15-26th | Goingon |
| **DeputationofSecttstaff/ HoDs** | GAD | Oct14 | Done |
| **DeploymentofStaffto Panchayatsandservingof ordersondeployedofficers** | DCs | Oct25 | DCswilldeployseniorlevelstaff fromthedistricts.Strictactionto betakenagainstabstentions.No exemptionstobegiven |
| **Trainingofdistricttrainors onB2V4** | RDD | Oct26 |  |
| **Trainingofvisitingofficers** | DCs | Oct27 |  |
| **FieldVisitstobecompleted by** | VisitingOfficers | Nov3 | DCstosuperviseandensurethat eachPanchayatisvisitedwithin theperiodspecified |
| **DataofB2V4tobe uploadedby** | VisitingOfficers | Nov10 | DCstosuperviseandensurethat dataofallPanchayatsisupload- edbythevisitingofficerwithin theperiodspecified |

**INSTRUCTIONSFORTHEVISITINGOFFICER(DAYWISE)**

|  |  |  |
| --- | --- | --- |
| **DATE** | **INSTRUCTIONS** | **ACTIONPOINTS** |
| **Day0** | Meetingwithdeputy commissionerandhis/her team | a. TakeprintoutsoffilledbookletsofB2V1,B2V2andB2V3from [www.jkpanchayat.in](http://www.jkpanchayat.in)  b.Alsotakeprintoutsofthesummarizedexcelsheetsofthe previousphasesfrom[www.jkpanchayat.in](http://www.jkpanchayat.in)  c. CollectATRsonissuesraisedduringprevious3phasesfromthe officeofDeputyCommissioner(Planningdeptt)  d.Takeprintsofblank 2bookletsofB2V4from[www.jkpanchayat.in](http://www.jkpanchayat.in)e.Takeplansfor2previousyearsandATRsfromtheplanningdeptt f. CompletetrainingsondifferentcomponentsofB2V4being  organizedbyrespectiveDeputyCommissioners  g.CollectListofnewworksstarted/ongoing/completedduringthe previousandcurrentFinancialyearunderthefollowingheads:  • PRIgrants  • DistrictPlan  • UTplan  • MGNREGA  • Otherschemesofotherdepartments  • Anyotherwork  h. Plans/beneficiarylists:  • MGNREGAdraftplandocumentfortheyear2022-23.  • ListofAwaas+beneficiariesalongwithIHHL Convergence  • Listofpensionbeneficiaries.  • ListofSHGs  • Listofagricultureschemebeneficiaries  i. Listsofbeneficiariesfor:  • Variouscertificates/benefitstobedistributedbythe visitingofficer.  • Anyotheractivitiesidentifiedbydifferentdepartments |

|  |  |  |  |
| --- | --- | --- | --- |
| **Day1** | Reachthevillage | 1. | Ensurethatallfrontlineworkersofdifferentdepttsarepresent. |
|  |  | 2. | Ensureexhibitionbydifferentdepts.aboutindividualbeneficiary schemes |
|  |  | 3. | InspectJKB/PSBcounters/outlets |
|  |  | 4. | Participate/ensureorganizationofsportsactivityinplayfield,talent hunt/culturalevent/youthactivity |
|  |  | 5. | GandhiKatha(suggesteddetailsuploadedonjkpanchayat.in) |
|  |  | 6. | Visitatleast2amritsarovarsandgetitsgeotaggedphotos |
|  |  | 7. | InspectKhidmat(CSC)CentresandcreateGenerateawarenesson  225schemesparticularlyG2CschemeslikeBEAMS,Janbhagidari, AapkiZaminAapkiNigrani,DigitalJ&K |
|  |  | 8. | Visitingofficershallalsoplanandconductpanchayatlevelconver- gencemeetingofalldepartments |
|  |  | 9. | CheckeffectivenessofCentrallysponsoredschemes |
|  |  | 10. | VisitandinspectallgovernmentestablishmentsincludingPHE, AWC,FPS,schools,etc |
|  |  | 11. | Attemptsaturationofdeliverableso JanAbhiyanandwherever deficienciesfound,leadadrivetoachievealldeliverables |
|  |  | 12. | Assesseffectivenessofsanitationcampaigninthepanchayat |
|  |  | 13. | Ensureselfemploymentactivitiesfor15youthperpanchayat |
|  |  | 14. | Identify20potentialcandidatesperpanchayatforHIMAYATtraining alongwiththetradeonwhichtheywanttraining |
|  |  | 15. | Whereverpossible,distributeemploymentlettersforpeopleselect- edundervariousgovernmentemployments |
|  |  | 16. | Intheevening,holdnormalmeetingwith seniorcitizens,govtem- ployeesincludingretiredemployees,exservicemen,youthclub,and any citizens ofthevillagewhoareenrolledincollege/university |
|  |  | 17. | OpendiscussiononNashaMuktAbhiyan |

Day2 Haveameetingwithall stakeholders-depttofficials andpanchayatmembers

1. Discussionontheandassesstheprogressofdifferentschemesrelating tothelocalizedSDGsprioritizedforthatvillageaspertheresolution passedby thatGramPanchayaton21st April22,onNationalPanchayti RajDay.

2. Sensitizevillage residentsaboutmyScheme”portal(myscheme.in) whichincludesinformationaboutalltheschemesbeingrunbyCen- tral/State/UTgovtacrossthecountry

3. Hold meeting of theBiodiversityManagementCommitteestodeliber- ateonissuespertaining toconservation of biodiversityandsustaina- bleutilizationof biologicalresources.

4. PrepareVillagedevelopmentplan,inconsultancywithGrampanchayat, discussitingramsabhaandgetitapproved.

5. Ensure saturationofsoilhealthcardandgoldenhealthcardunderGold- enHealthCardunderAyushmanBharat,

6. Ensuresaturation of OldAge PensionScheme

7. EnsureDomicileSaturation.

8. EnsureKCCSaturation

9. Ensure saturationoflandpassbooks

10. Ensureregistrationofvillagevendorsneededforanyscheme,onGEM

portal

11. Ensurepanchayatcontractors registration

12. EncouragePanchayatmembers forimportanceofplantationdrivein

PanchayatunderHarGaonHariyali

13. Ensure paintingondigitalJ&Kinpanchayatghars

14. Ensure paintingonpanchayatactivitesandCSSinpanchayatghars

15. Thevisiting officeshallchecknoof kindergarten andplayfields present inthepanchayat for kidsandstudents,iftheinfrastructure present inthesearegoodenough.

16. Holdmeeting withpanchayatmembers todiscussaboutcorruption menaceandstepsrequiredtomakeJ&Kcorruptionfree

17. Obtaina candidassessmentaboutperformanceofvariousdeptts in- cludingfairfeedbackaboutdiscrepanciesinfunctioning

18. Check thestatusof NashaMuktAbhiyanandreporting of drugad- dictstoDeputyCommissioner.

19. IdentifyTouristDestinations,Circuits,ThemeTreks,IdentifyHomestays, providesupportfortourismactivities throughVillageCooperative

20. OrganizeTalentHuntatPanchayatLevel

21. Conductsocialauditofatleast5worksunderfollowingschemes:

a. MGNREGA

b.PMAY

c. IHHLtoiletsandpayments d.CSCs

e.AMRITSAROVARS

22. Holda mahilasabha anda balsabhaandrecordproceedingsinthefor- matgiven

23. InauguratevillagehaatunderJKSRLM

24. Checkifyouthclubsareformedinthepanchayatandwhatactivities theyareengagedin

25. Organizea villagelevelculturaleventtoengagepanchayatmembers

26. SensitizeGPaboutE-kitabkoshaninitiativeofJ&KGovtforempowering youthsthrough onlinedigitalliteracy

**GENERALINSTRUCTIONS**

1. Thevisitingofficershallrefrainhimself/herselfgivingorofferinganycommitmentonbehalfofthe governmentandshalladoptanunbiasedattitudeinreportingissues.As faraspossible,his/her observation shouldbebasedona fairandanalytical viewemergingfromhis/herinteractioninthe village.

2. Heisgoingtothevillageasplanningofficer,notforsanctioninganyworksorformakinganycom- mitments.

3. Whilepreparingvillagedevelopmentplan,hehastoensurethat,demandsareprioritizedandre- flectedunderavailableschemes,wherevernecessarythelargerworksaretobereferredtoadminis- trativedepttunderCSS/UTplansunderintimationtoDCsandrestoftheworkstoDCsforreflecting itunderdistrict/CSS plans

4. His workshallbehardcoreplanningandauditandisnota PRexercise.

5. EveryDeputyCommissionerhastoensurethatatleastoneRDDofficial(ideallyPanchayatSecre- tary)ispresent ineverypanchayatwithrelevantpanchayatrecords,toensureconductofallactivi- tiesasplanned.Panchayatwiseorderneedstobeissuedinadvance.

6. Visitingofficershouldideallycarryhis/herlaptoptocompletethereportsatthepanchayatlevel itselfanduploadthefinalreport,duly signedbothbythesarpanchandbythevisitingofficeron [www.jkpanchayat.in](http://www.jkpanchayat.in)portal,beforetheyleavepanchayat.

7. Focus ofvisitareyouth,skills,self-employment,nashamukt,bhrashtracharmukt,Rozgaryukt J&K, besidestocarryforwardtheactivities duringJanAbhiyanandsaturatethem.

8. Inadditionattentionmaybegiventothefollowingareas a. MakefulluseofCentrallySponsoredSchemes

b.Saturationofindividualbeneficiaryschemes c. Self-employmentschemes

d.Banklinkedschemes-includingdepartmentalsubsidyschemes e.Empowermentandtransparencythrough digitalinitiatives

f. Effectivenessofgrassrootsmachinery–

i. Patwari,VLWpresent andavailable

ii. AvailablefundsutilizedinpublicinterestandasperGramSabharesolutions iii. Fairness ingovernance

iv. CSS/Individual beneficiaryschemesetc v. BrashtacharMuktJ&K

vi. BhaiMuktJ&K

vii. NashaMuktJ&K

9. ThePRImembers (Sarpanchs,Panchs,BDCChairperson)shallbeattheforefrontofallactivities and givendueimportanceandtheapproach shouldbetostrengthenthemandmakethemfeelem- powered.He/sheshallensurethattheBDCchairpersonandSarpanch/Panch arepresent atthetime ofinaugurationandceremonies.

10. Visitingofficershallnotleavethedistrictwithoutuploadingthereport,duly signedonthe**www. jkpanchayat.in**portal.EveryDeputyCommissionerhastoensurethat.

**A) Details of Reporting Officer:**

Name: Bashir Ahmad Wani

Designation: Lecturer

Department/place of posting: HSS RAHMOO

Mobile No:- 9906699874

EmailID:bashirahmadwani627@gmail.com

Home District:- pulwama

Dates of visit: 28/10/2022 to 29/10/2022

**B) LocationaldetailsofPanchayat:(tobepre-filled,informationtobetakenfromtheprevious phasesbooklets/summarizedexcelsheetuploadedonjkpanchayat.in/b2v4.php)(tobevali- datedbythevisitingofficerandmissingdetailstobefilled)**

Name of the Panchayat: Dadoora

Local Government Directory(LGD)code of the Panchayat: 242853

Name of CD Block: **Pulwama**

Name of Tehsil: **Pulwama**

Name of District: PULWAMA

**C) Panchayat Profile:**

No. of revenue villages in the Panchayat :\_\_\_\_\_\_\_\_\_03\_ Dadoora , Shangepoa and thumna .

No. of hamlets in the Panchayat \_\_\_\_\_\_03\_\_\_\_\_\_\_\_\_

No. of house holds in the Panchayat:\_\_\_\_\_\_\_\_\_\_375\_\_\_\_\_\_\_\_\_

Population(approx)of the Panchayat:\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_2163\_\_\_\_\_\_\_\_\_\_\_\_

**Part-II:**

(TobefilledupbytheVisitingOfficerduringhis/hertwodayvisittothePanchayat.AllFieldshavetobe

Filled by the Visiting Officer before the booklet is handed over to the DC

**FrontlineOfficers/OfficialswhowereassignedtothePanchayatfortheprogramme:**

|  |  |  |
| --- | --- | --- |
| Department | Name | Designation |
| RDD | Irfan Yousuf | VLW |
| RDD | Sartaj Ahmad Mir | MIRAB |
| RDD | Mahjbeena Ali | GRS |
| CAPD | Sajad Ahmad Bhat | Stor Keeper |
| Health | Altaf Hussain Bhat | Pharamacist |
| Sheep Husbandary | Gh Mohideen Shekih | ASM |
| Agriculture | Mushtaq Ahmad Dar | Lab Attendent |
| Horticulture | Wakeel Ahmad Bhat | Tech. IV |
| PWD ( PMGSY ) | Zahoor Ahmd Thoker | Jr. Er |
| PWD ( PMGSY ) | Zahid Ahmad Chat | Asst. Et |
| Fisheries | Tawseef Yousuf | F/G |
| Forest | Fayaz Ahmad Hajan | Chowkidar |
| Irrigation | Mohd Ayoub Malik | Works supervisor |
| Sports | Altaf Ahmad Bhat | PET |

**Details of absent employees vis-à-vis list furnished by the DC office:**

|  |  |  |
| --- | --- | --- |
| Department | Name | Designation |
|  |  |  |
|  |  |  |
|  |  |  |
|  |  |  |
|  |  |  |
|  |  |  |
|  |  |  |
|  |  |  |
|  |  |  |
|  |  |  |
|  |  |  |
|  |  |  |
|  |  |  |
|  |  |  |
|  |  |  |

**DAY1-ACTIVITIES**

**AGENDA1:PANCHAYATASSETREGISTER**

**Infrastructure:**

1. Panchayat Ghar Infrastructure a. Private

b. needing repairs

2. Furniture(N)

3. Computer/printer(N)

4. Internet(N)

5. Telephone(N)

6. Toilet(CSC/part of Panchayat ghar ) (N)

7. Water(N)

8. Electricity(N)

9. Bank branch(N)

10. CSC(N)

11. Patwar khana(N)

12. Village haat(Y)

13. Playground(N)

14. School-

a. Kindergarten(Y)

b. Primary (Y)

c. Secondary(N)

d. College (N)

e. University(N)

15. Anganwadi Centre(Y)

a. (private)

b.Total children enrolled ( 140 )

15. Amrit Sarovars–details, location, condition **NA .**

16. Government offices-details, whether functional or not **ONLY SCHOOL AND AWC**S

17. Ration shop (Y)

18. Placesoftourismimportance–names,littledetailsonhistorical/culturalimportance .( NA )

19. Village heritage sites/treks-names ,little details on historical/cultural importance. ( NA)

20. VLW Office (Y) **but in private room**

21. Primary Health care Centre (NA )

22. List of Incomplete Buildings-names, year of construction ( NA )

23. List of Underutilized Buildings-names NA

**DAY1-ACTIVITIES**

**AGENDA2:**

**DIFFERENTINSTITUTIONS/INFRASTRUCTUREPROJECTSTOBEVISITED**

|  |  |  |
| --- | --- | --- |
| **AMRITSAROVARS** | **Visit,verify** | **COMMENTS** |
| KhidmatCentres | Create/Generateawarenesson225schemes particularlyG2CschemsAapkiZaminAapkiNigrani, Beams,Janbhagidari,DigitalJ&K | There is only one KC for 06 villages . However the concerned scheme operate aware the general mass about different schemes like Aapki Zameen Aapki Nigreeni |
| JKB/PSBcounters/outlets | a)Statusofcounter 03Rajpora b)Number of visitors 1000 | Counters were not installed at GP Dadorah . |
| Incompletebuildings/pro- jects | Verify whetheridentificationandredistribution done | There is no incomplete building . |
| PDS | Visit,evaluate,onlinestatus | Visited and found satisfactory |
| PHC | Visit-evaluate,statusofstaff,equipmentand quality | Not Available in GP. |
| Youthclubs | Meet,interact,seeksuggestions | Demand of play ground |
| SHG | Meet,identifyproblems,seeksuggestions | SHG role is appreciable but need financial support from govt. |
| PMAY | Inspect,Inaugurate | Inspected and inaugurated |
| Myschool,mypride progress;schools-water, toilets,staff | Visit,checkforwater,electricity,sanitation,meet studentsandstaff | Basic needs like water ,electricity Sanitation available . |
| SwachhSBM | Evaluate | Inspected and found satisfactory |
| Panchayatplayground, Sportskitsdistribution Villagegames | Ensure,verify.Participateinatleastonegamein theplayground | Children participated in different games like chess , cricket, Carrom Kho Kho ,etc. |
| HarGaonHariyali, Planta- tiondrive | Evaluatestatus,feedback | Launched by visiting officer in school premises |
| Villageculturalevent  Dangal/Haat/Mela | Participatein;ensurethatitisheld | Stalls where installed by agriculture , horticulture, handicraft department |
| Exhibitionofschemes | Ensurethateverydepartmentparticipatesand thatitcontinuesfortheentiredurationofB2V | Every department participated during B2V4 from 28-29 oct 2022 |
| JalJeewanMission verifica- tion- WSS/JSD  Electricitysupply | Verify | In process as per reports ,  Electricity satisfactory |

**DAY1-ACTIVITIES**

**AGENDA3:SATURATEJANBHIYAN**

**DELIVERABLESANDRECORDDEFICIENCIESIFANY(INSERTDELIVERABLESLISTHEREASPERGADFORMAT**

1. **A bal sabah was organized under B2V4 Program at M.S Dadoora in which many activites like Essay writing , painting competation etc were organized.**
2. **A plantation drive under B2V4 program was also organized in which plants where planted in the said school ground.**
3. **Agenerally lecture to frent line workers of different dept. was given by visiting officer, stressing on duty with dedication and corruption free public deals in office and fields .**
4. **Different stalls were installed by different depts.. for public awearness how where appreacted their work.**
5. **A Gram Sabha was organized in GP to discuss the problems of the village and also to sortout their solutions .**
6. **A General visit to whole panchatat Halqa Dadora to lisen to public and also to see the different developments works and inaugurated the completed ones with Geo tagged photograes**

**DAY1-ACTIVITIES**

**AGENDA4:**

**SELFEMPLOYMENTACTIVITIES**

EnsureSelf-employmentactivities foryouth,distributeemploymentlettersforpeopleselectedunder varioussocialschemes(15ISTHETARGETPERPANCHAYAT)

**Numberofcasesindifferentcategoriessanctioned:**

**Detailsofthebanksanctioningit:**

**Totalamountinvolved:**

**DAY1ACTIVITIES**

**AGENDA5**

Intheevening,holdinformalmeetings withseniorcitizens,govtemployees,retdemployees,youthclub andothercitizenswhoareenrolledoncollege/universityandhavediscussiononGandhiKatha,Nasha MuktAbhiyan,corruptionfreegovernance,doublingfarmersincomeandrecordtheproceedings

**DAY2**

a. NoofIndividualCompostPitsconstructed **NIL**

b.NoofIndividualSoakPitsconstructed **12**

V. No.ofBiodiversitymanagementcommitteemeetingsheld:  **NIL**

VI. IsthenameofSarpanchdisplayedoncitizeninformationboardsofallRD&PRschemes: NA

VII. AreSarpanchsbeinginvolvedinstart/inaugurationofactivities: **( No )** **There is no punch and surpanch in the Halqa .**

VIII. WhethersubjectshavebeenassignedbytheSarpanchtothePanchs: P**anchayat body not existed in GP**

IX. Whethergrievancesredressalboxisinstalled: **No**

X. NoofgrievancesreceivedpertainingtoPanchayatlevel: **05**

XI. NoofgrievancesdisposedofatPanchayatlevel: **NIL**

XII. WhethertheSarpanch/PanchayatSecretaryhavedigitalsignatures: **YES for Panchayat Secretary.**

XIII. WhetherallMGNREGA/14thFCpayments arebeingmadebySarpanchthrough DigitalSignature

Certificate(DSC): **YES for Panchayat Secretary.**

**HUMAN RESOURCEAVAILABLEATTHEPANCHAYAT LEVEL:**

|  |  |  |  |  |
| --- | --- | --- | --- | --- |
| **SRNO.** | **DEPARTMENTWISESTAFF** | **NUMBERS** | | **NAMES** |
|  |  | SANCTIONED | ACTUAL |  |
|  | Ruraldevelopmentdepartment: BDO  JE GRS TA | 01  01  01  01 | 01  01  01  01 | Gulzar Bini Rahman  Nazir Ahmad Alie  Mahjabeena Ali  Farooq Ahmad |
|  | SCHOOLEDUCATION: TEACHER  HEADMASTER ANYOTHER | 18  02  REK,Cooks etc. | 16  17  01  03  0 | Gh mohideen HM, others |
|  | JAL JEEVAN: | 01 | 01 | Javid Ahmad Ganie |
|  | PDD: LINEMAN JE  ANYOTHER | 01  01  01 MR | 01  01 | Shabir Ahmad ,  Nazir Ahmad . |
|  | FOOD&CIVILSUPPLIES | 01 | 01 | Sajad Ahmad |
|  | AGRICULTURE&ANIMALHUS- BANDARY | 01 | 01 | Khalid Muzzafer( Agriculture) |
|  | SOCIALWELFARE | NIL | NIL | NIL |
|  | HEALTH: ASHA ANM  AYUSHDOCTOR ALLOPATHICDOCTOR | --  -01  --01  ---  ----- | 01  01 | Haseena Akther,  Tahirah Akther |
|  | ANYOTHERDEPARTMENT | NIL | NIL | NIL |

**DAY2-ACTIVITIES**

**AGENDANO.1**

DiscussionontheandassesstheprogressofdifferentschemesrelatingtothelocalizedSDGsprior-itizedforthatvillageaspertheresolutionpassedbythatGramPanchayaton21stApril22,onNational PanchayatiRajDay(Copyoftheresolutiontobetakenfrom[www.jkpanchayat.in](http://www.jkpanchayat.in)portalunderthelinkof GramSwarajMonth)

1. SDGs AGREED FORTHATVILLAGE,TOBEIMPLEMENTED BYMARCH2024: **YES**

2. STATUSOFWORKSUNDERTHEFOLLOWINGSCHEMES:

**1 Cleanandgreenvillage**

i.InitiativestakenbythePanchayatformanagingSolidandLiquidWaste Sites identified for solid and liquid waste management.(SLWM)

ii. InitiativestakenbythePanchayatforusinggreensourcesoffuellikesolar,biogas

**NIL**

iii. Hasmappingoflanduse,waterbodies,forest,slopes,wetlands,degradedforestwithintheGram

Panchayatbeendone?Yes/No.IfNo,reason,thereof **NO**

iv. HastheClimateResiliencePlanbeendevelopedfortheGP?**No**

v. StepstakenbytheGramSabhaabouttheclimatechangemitigationfactorslikereducingenergy consumption,usageoffossilfuels,plastics,non-renewablebuildingmaterialsandalsotopromote measureslikeplantingoftrees,conservingforests,usageofgoodagriculturalpracticeslikedrip irrigation,waterconservationmeasuresandconservationofwetlands. **NA**

vi. Whetherschoolshavestartedsegregatingwaste **YES**

vii. Whetherschoolshavetheirowncompost/soakagepitsforsolid/liquidwastemanagement **YES**

**2 Healthyvillage**

i) Aremeetings relatedtoVillageHealthandSanitationCommitteebeingheldregularly?**YES**

ii) DoalltheeligibleindividualsbeenprovidedtheGoldenCard?  **UNDER PROCESS**

iii) ArealltheChildrenbeingimmunizedaspertheSchedulerecommendedbyGovt.ofIndia?**YES**

iv) ArealltheeligibleindividualsbeenvaccinatedagainstCOVID-19? **YES**

v) DoesGramPanchayatensurethatallpregnantwomenaregettingnecessaryprenatalcheckups?**YES**

vi) WhetherallthedeliverieswereInstitutionalizedorconductedbytrainedMidwives?**YES**

**3 Watersufficientvillage**

i) DoalltheIHHsintheGramPanchayathavewaterpipelineconnections? **NO**

ii) WhetherGramPanchayathastakenstepsforgreywatermanagement.IfYespleasespecify **YES( Soak pits )**

iii) DoalltheIHHsintheGramPanchayathavetoilets? **yes**

iv) ArealltheIHHstoiletsfunctionalornot? **Functional**

v) DoalltheSchools/Anganwadicentershavea toiletfacilityornot? **YES**

vi) Areallthetoiletsintheschools/Aaganwadifunctionalornot? **YES**

vii) WhetherGramPachachayatBhawanhasseparate toiletsforwomenornot? **Gram Panchayat bhawn not available.**

**4 ChildFriendlyvillage**

i) Doallthechildrenundertheageof0-6yearsbeenenrolledintheAnganwadicentersforpre- schooling?**Yes**

ii) HowmanyBalSabha’swereorganizedintheGramPanchayat----------------02

iii) WhethertheissuesraisedbyBalSabhaareaddressedduringtheGramSabha. **Yes**

iv) WhetherGramPanchayatistrackingthedatarelatedtodropoutchildrenandchildrenwithirregular attendance**?Yes**

v) DoalltheschoolsundertheGramPanchayathaveseparate toiletsforgirlsandboys? **YES**

**5 Villagewithgoodgovernance**

i) IsCSClocatedintheGramPanchayatBhawanornot?  **NO**

ii) IsthelistofbeneficiariesrelatedtotheSchemes/ProgramsdisplayedontheGrampanchayatwallor not? **YES**

iii) DoestheGramPanchayathasitsbuildingornot? **NO**

iv) IstheGramPanchayatofficefunctionalornot? **YES But in private room**

v) Aretheactivities approved undertheHalqaPanchayatDevelopmentPlandisplayedontheGram

Panchayatwallornot **YES**

vi) IsSocialAuditofearlierSchemes/Programscarriedoutornot? **YES**

**6 Povertyfreeandenhancedlivelihoodvillage**

1. HasGramPanchayatdevelopedanycriteria fortheidentificationofthepoor?**NO**
2. ii) HavealltheeligiblehouseholdsregisteredinPDSornot?**YES**

iii) HasGramPanchayatprovidedspaceforSelf-helpGroupsinPanchyatGharforholdingmeetings or not? **The Self help holds meetings in a private room.**

iv) HavealltheeligiblehouseholdsbeenregisteredforPensionornot?**NO**

v) HasGramPanchayatfacilitatedYouthforSkillEnhancementCoursesandPlacement? **NO**

vi) HasJobCardsbeendistributedtoalltheeligibleindividualsunderMGNREGA?**YES**

vii) HasGramPanchayatfacilitatedSHGsforBankAccountLinkages?**YES**

**7 Sociallysecuredvillage**

i) WhetherGramPanchayatismaintainingdatarelatedtoDifferentlyAbledPeople?**YES**

ii) IsGramPanchayatOffice DisabledFriendlyornot? **Friendly**

iii) Areprovisionsfora separate BudgetundertheResourceEnvelopeforWomenandChildrenmadeor not?  **YES**

iv) DoalltheSchools intheGramPanchayathavefacilitiesforDifferentlyAbledChildrenliketoilets, barrier-freeaccess,etc.,ornot? **YES**

v) Arealltheeligibleindividualsaregettingpensions,likeoldagepension,widowpension,etc? **YES**

vi) ArealltheeligiblehouseholdsgettingbenefitsfromIAYornot?

**YES ,**

**8 EngenderedDevelopmentinVillage**

i) HowmanyMahilaSabha’swereorganizedintheGramPanchayat------------ **02**----

ii) WhetherSHGsfederationshavebeenprovidedspaceformeetings inthePanchayatBhawan **YES**

iii) WhetherGPshavetakenstepsforincreasingwomen’sparticipationinGramSabha(**YES )**

iv) NumberofwomenbeneficiariesheadedhouseholdscoveredunderPDS

system………**12**

v) Numberofbeneficiaries(outoftotaleligiblepopulation)receivingsocialprotectionbenefitsunder

PradhanMantriMatritvaVandanaYojana  **52**

9 Self-sufficientinfrastructureinthevillage

i. WhetherGPhasa CommunityHallwithaccesstoelectricity,furniture,watersupply, toilet… **NO**

ii. WhethertheDisastermanagementplanisavailableattheGPLevel(**No**)

iii. Whetherchild-friendlyparkwithrequiredfacilitiesisavailableinGP(**No**)

iv. WhethertheGPhaseasyaccesstoGodownforstorage(**No**)

v. Whetherstreetlightsareprovidedinpublicplacesforensuringsafety(**No**) ONLY FOR TWO MASJIDS PROVIDED BY RDD

**DAY2ACTIVITIES**

**AGENDANO.2**

SensitizevillageresidentsaboutmyScheme”portal(myscheme.in)whichincludesinformationaboutall theschemesbeingrunbyCentral/State/UT govtacrossthecountry **(NA )**

*(SchemeMaterialavailablefromhttps://jkpanchayat.in/b2v4.php)*

**DAY2ACTIVITIES**

**AGENDANO.3**

HoldmeetingoftheBiodiversityManagementCommitteestodeliberateonissues pertainingtoconserva- tionofbiodiversityandsustainableutilizationofbiologicalresources.HeshouldcheckPeopleBiodiversity register(PBR)ofthatpanchayatandreviewifBiodiversityManagementCommittee constitutedforthat panchayatis holdingminimum4meetings inayearandmeeting onceinevery3months *(RoleofBMC availableathttps://jkpanchayat.in/b2v4.php)*

COMMITTEEMEMBERS PRESENT

BIODIVERSITYREGISTERPHOTOS

PAST 4MEETINGDETAILS-DATES,MINUTESPHOTOS

**DAY2ACTIVITIES**

**AGENDA4**

Visitingofficershallalsoplanandconductpanchayatlevelconvergencemeeting ofalldepartmentsand prepareVillagedevelopmentplanforvillage,inconsultancywithGrampanchayat,discussitingram sabhaandgetitapproved.

(GPDPformatavailableonhttps://jkpanchayat.in/b2v4.php)

**InadditionGPDPplanshallalsoinclude:**

 Touristplaceswhichneedtobedeveloped  **NIL**

 Specificproductwhichneedstobedeveloped **Apple , walnut ,vegetable, fruit plant may be provide**

 Tourism-homestays**NIL**

 20candidatesfortrainingunderHimayatschemealongwithtradeinwhich trainingistobegiven  **20 List enclosed**

**DAY2ACTIVITIES**

**AGENDA5**

Ensuresaturationoffollowingschemesandgivestatus:

|  |  |  |  |
| --- | --- | --- | --- |
| **NAMEOFTHESCHEME** | **TOTALELIGIBLE BENEFICIARIESIN THE VILLAGE** | **TOTALBENEFICIARIESWHO AVAILEDTHEBENEFITSOFTHESCHEME** | **REASONSFOR PENDENCY** |
| GoldenHealthCardunder  AyushmanBharat | 1960 | 1570 | Lack of operate |
| Jananisurakshayojana | --- | ----- | ------ |
| OLDAGEpension | 81 | 81 | ---- |
| Widowpension | 31 | 31 | ------- |
| Disabilitypension | 24 | 24 | --------------- |
| Domicilecertificate | 2163 | 182 | -------------- |
| Kisancreditcard | 157 | 257 | -------------- |
| PMkisansammannidhi | 139 | 139 | ---------------------- |
|  |  |  |  |

|  |  |  |  |
| --- | --- | --- | --- |
| Landpassbook | 200 | 40 | ---------- |
| Registrationofvillageven- dorsonGEMportal | Nil | Nil | ------------- |
| Registrationofvillagecon- tractorsonjktendersportal | 01 | Rameez Ah Shah S/O Nazir Ah Shah | -------- |
| Registrationofvillagecon- tractorsonPWDportal | NIL | NIL | NIL |
| Incompletebuildings/pro- jects | NIL | NIL | NIL |
|  |  |  |  |

**DAY2ACTIVITIES**

**AGENDA6**

**NASHAMUKTABHIYAN**

1. Whethergramsabharesolutionpassed **YES**

2. Detailsofactivities conducted Awareness about **General Awarness given on cleanliness of surroundings , NASHA MUKTI and many problems of the village discussed**

3. Whetherallactivities andGSresolutionuploadedonjkpanchayats.inportal **YES**

4. Howmanydrugaddictsinthevillage **NIL**

5. WhetherreportedtotheDeputyCommissioner **NIL**

6. Howmanyregisteredforrehabilitationundergovernmentprogramme

**NIL**

**DAY2ACTIVITIES**

**AGENDA7**

**SOCIALAUDIT**

Conductsocialauditofatleast5workseachunderfollowingschemes:

|  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- |
| NAMEOFTHE SCHEME | DETAILSOFTHE WORKS | YEAROFWORK APPROVAL | AMOUNT APPROVED  FORTHEWORK | WHETHER  WORKEXECUTED SATISFACTORILY | GEO- TAGGED PHOTOS | ANY GRIEVANCE RECORDED RELATINGTOTHAT WORK |
| MGNREGA | Cont. of Road from house of ab Gani, Tiken Road | 2022-23 | 7.00lacs | Satisfactory | Yes | Nil |
| PMAY | Nazir Ah Bhat S/O Assadullah | 2021-22 | 1.50 Lacs | Satisfactory | Yes | NIL |
| IHHL  UNDERSBM-G | 10 | 2021-22 | 0.12 lacs | YES | YES | NIL |
| CSCUNDER SBMG | ------ | === | ------ | ----- | ---- | --- |
| AMRIT SAROVARS | ----- | ---- | ---- | ---- | --- | ---- |

**DAY2ACTIVITIES**

**AGENDA8**

**MAHILASABHA**

Totalwomeninthevillageabovetheageof18 **430**

Totalattended **22**

Proceedings: Women’s demanded for more empowerment , should be provided assessment and financial help to set their own business units to stand one their feet.

*(Plinsertpointerstobediscussedthere–referpalliproceedings)*

**DAY2ACTIVITIES**

**AGENDA9**

**BALSABHA**

Holda balsabhaandrecordproceedings **14-18 =480**

Totalchildreninthevillageabovetheageof…**..**

Totalattended **20**

Proceedings: the said Bal Balsabha was given education on unity , bad impacts of plastics and NASHA MUKTI. Moreover , the participants of Balsabha strongly demanded the provision of play ground in the village

*(Plinsertpointerstobediscussedthere–referpalliproceedings)*

**DAY2ACTIVITIES**

**AGENDA10**

**INAUGURATIONS**

|  |  |  |  |
| --- | --- | --- | --- |
| **SR NO.** | **ASSETS/ACTIVITIES INAUGRATED** | **STATUSOFTHEASSET/AC- TIVITIES(NUMBER,OTHER DETAILS)** | **GEO-TAGGED PHOTOS** |
|  | VILLAGEHAATunderJKSRLM (SUN- DAYMARKET) | **Stalls were installed by SHG’s under JKSRM ( in B2V4 )** | **YES** |
|  | PMAYhousesifanyreadyforinaugra- tion | **Completed upto Roof level** | **YES** |
|  | Swachhgramprojects-segregation shedsetc | **Sites identified and will be executed very soon** | **NA** |
|  | Amritsarovars | **-----** | **-----** |
|  | Sportskits | **------** | **------** |
|  | Villageculturalevents | **A Cultural event was organized at MS Dadoora** | **Yes** |
|  | JJMassets/projects | **The concerned dept. has not take any step** | **----** |
|  | Anyothertobeidentifiedatdistrict level | **------** | **----** |
|  |  |  |  |

**FOLLOWUPOF(B2V1,B2V2&B2V3):**

*(Prefilledexcelsheet tobetakenfromdistrictlevel/andalsotobedownloaded*

*from*[*www.jkpanchayat.in)*](http://www.jkpanchayat.in)

|  |  |  |  |
| --- | --- | --- | --- |
| S.NO. | Particulars | Actiontaken | Remarks# |
| I. UrgentPublicRequirements/Demands-B2V1 | | | |
| 1. The whole area ( GP) needs treated drinking water through Taps |  | No Action Taken | -------------- |
| 1. Animal Husbandry Center At dadoora |  | -NAT | NAT |
| 1. Requirement of sufficient funds for IAY sheds |  | The funds are to be allotted by central govt. | ------------ |
| 1. Improvement / providing of leans /drains in whole GP |  | The lanes /drains are executed under B2V1 and under 14th FCA | Satisfactory |
| 1. Improvement of HT , LT, System of PDD network |  | Action is already taken by depart. | Satisfactory as per public. |
|  |  | \ |  |
| 7 |  |  |  |
| II. UrgentPublicRequirements/Demands-B2V2 | | | |
| 1. Development of road from Masjid sharief Banpora Dadoora to House of Mohd akram Bhat . |  | Pending | Pending |
| 1. Macadamization of road from Doodrah to Babhara |  | In tendering process and Maccadamication will be started very soon (as per the representative of concerned depart. ) | ----- |
| 1. Creation of Patwari Halqa at Doodra |  | Pending | Pending |
| 1. Cont, of P/Bund from House of M Yousuf Sheikh to GMS Dadoora |  | Pending | Pending |
| 1. Cont. of sub. Station by PDD at new coloney Dadoora |  | NAT | NAT |
|  |  |  |  |
|  |  |  |  |
| S.NO. | Particulars | Actiontaken | Remarks# |
| III. MajorProblems–B2V1 | | | |
| 1.Drinking water problem in overall GP . The tobewells available at some sports at GP, but water quality is not good.water should be treated with necessary chemicals before in use to avoid intestinal and other infections on this part . |  | The concerned dept has not taken any step till date | Pending |
| 1. ------ | - | ---------- | --- |
| 1. ----------- |  | ---------- | ---- |
| 1. --------------- |  | --------------- | ------------------- |
| 1. ---------------- |  | -------------- | ----------------- |
|  |  |  |  |

|  |  |  |  |
| --- | --- | --- | --- |
|  |  |  |  |
|  |  |  |  |
| IV. MajorProblems-B2V2 | | | |
| 1. Construction of computer lab./ providing DG set for UPS Dadoorah |  | Demand fulfilled | Currently in function and found satisfactory |
| 1. Installation of Tarnsfermer for new coloney dadoora |  | Transformer installed resently by concerned dept | Found functional and satisfactory |
| ------ |  | -------- |  |
|  |  |  |  |
|  |  |  |  |
| V. MajorProblems-B2V3 | | | |
| 1.Drinking water facility at doodra |  | NAT |  |
| 1. Macdimacization of road from kangan to Shangerpora via doodra and Babhara |  | Already in tendering process ( as per officials) |  |
| ------ | ----------------- |  |  |
|  |  |  |  |
|  |  |  |  |
| VI. MajorComplaints-B2V1 | | | |
| 1. Poor people suffer allot on account of getting funds allotted for cont. of sheds under IAY Shehme |  | It is central scheme | Pending |
| -------- |  | ------------ | ---------- |
|  |  |  |  |
| VII. MajorComplaints-B2V2 | | | |
| 1. NIL |  | NIL |  |
|  |  |  |  |
| 3 |  |  |  |
| VIII. MajorComplaints-B2V3 | | | |
| Verification of BPL/AAY ration cards of village Dadoora . the said complaint was laughed by Wali Mohd Bhat Ro Dadoora |  | As per the CAPD dealer (namely Sajad Ahmad Bhat bearing mobile no 7006774605 ) of concerned dept, , the complaint logged by Wali Mohd Bhat R/o Dadrooh is base less and verification for BPL /AAY ration holders was done in transparent mode |  |
|  |  |  |  |
|  |  |  |  |

**OVERALLPERCEPTIONOFFUCNTIONING OF GOVERNMENTDEPARTMENTS**

1. **BESTDEPARTMENT: ICDS / Handicrafts**

**2. LEASTRESPONSIVEDEPARTMENT: Forestry**

**GENERALASSESSMENTOFTHEVISTINGOFFICER**

|  |  |
| --- | --- |
| I | AnymajorcomplaintbroughttothenoticeoftheVisitingOfficer: **P.T.O Over leaf** |
| II | Major/urgentpublicdemandsthatwas/werereflectedearlierbuthavenotbeenaddressedsofar: **P.T.O Over leaf** |
| III | Overallassessmentofthevisitandsuggestions:  (Thevisitingofficertoensurethattheoverallassessmentisrecordedindetailsalongwithconcretesugges- tions) **P.T.O Over leaf** |
| IV | OverallRatingofgovtfunctioningas givenbythePanchayat(Scaleof0to10) **0-6** |
| V | CertificatefromSarpanchthatthevisitingofficerhasstayedinthepanchayatfor2days  **Sarpanch not available hence nodal office to sign in place of Sarpanch** |

**SignatureofSarpanch SignatureoftheVisitingOfficer**

**Name……………………… Name………………………**

General Assessment of the visiting officer

**Any Major complaint brought to the notice of the visiting officer :-**

1. Macadamization of Road from kangan to Shangerpora via Dadoora and Dadoora to Babhar
2. The whole area is facing acute shortage of drinking water facility . The public seems very angry , and it is a long pending public demand and no steps has taken to fulfill the crises of drinking water in the area. Although , water reservoir lies at Shangerpora , but it is only the arrangement of pipes which the concerned department has make to overcome the shortage of drinking water in this village to make the public happy
3. Providing of medical aid health center at Dadoora
4. Providing of veterinary center at Dadoora
5. Providing of Patwari Khana at Dadoora
6. Installation of transformer at Bunpora, Dadoora to meet the low voltage crises.
7. Installation of street lights in the whole village including graveyard
8. Construction of remaining part of Boundary wall cum fencing of Graveyard near Govt. UPS Dadoora and a drain on inner side of the said boundary wall of the Graveyard for the irrigation of nearly orchard lands.
9. Construction of Boundary wall of Govt. UPS Dadoora and a path from Main Gate to Headmasters Office along with floor tiles as most of the Govt. /official programmes are organized at the said school.
10. Construction of additional classrooms at UPS shangerpora due to insufficient classrooms
11. Construction of Boundary Wall of Govt. Primary school Nadipora, Dadoora.
12. Construction of protection bund (P/Bund) near the land of Gh. Mohd and others at Tunmna for irrigation of their orchards.
13. Providing of Siphon at Satkharan ladi near near graveyard of Shangerpora for irrigation of orchards .
14. To provide siphon plus drain near the house of Ab Rahim Yatoo to irrigate near about 20 Kanals of orchard land
15. Installation of public Tube well at New Colony Dadoora ( Babahara Road) is also the need of the hour as the said Colony is also facing shortage of drinking water facility.
16. The young generation seems to be very angry with the government due to non availability of the play ground for conduction of different sports activities in the village is recommended on priority basis.
17. Construction of lanes /Drains and other demands were more in number so, the said demands are enclosed herewith this booklet of B2V4.

Sd/

Visiting officer

Bashir Ahmad Wani

Lect. HSS Rahmoo

Halqa Dadoora