4

15TH OCTto3RD NOV,2022

KEYFEATURES

•     DeputyCommissionerstoleadtheinitiative

•    RuraldevelopmentDepartmenttobethenodaldepartment

•	PlanningDevelopment&MonitoringdepartmentandITtobethesupportdepartments

ACTIONSANDTIMELINES

| ACTION | RESPONSIBILITY | LATESTBY | REMARKS |
| --- | --- | --- | --- |
| Janabhiyan | Alldepartments | Oct15-26th | Goingon |
| DeputationofSecttstaff/ HoDs | GAD | Oct14 | Done |
| DeploymentofStaffto Panchayatsandservingof ordersondeployedofficers | DCs | Oct25 | DCswilldeployseniorlevelstaff fromthedistricts.Strictactionto betakenagainstabstentions.No exemptionstobegiven |
| TrainingofdistricttrainorsonB2V4 | RDD | Oct26 |  |
| Trainingofvisitingofficers | DCs | Oct27 |  |
| FieldVisitstobecompletedby | VisitingOfficers | Nov3 | DCstosuperviseandensurethat eachPanchayatisvisitedwithin theperiodspecified |
| DataofB2V4tobe uploadedby | VisitingOfficers | Nov10 | DCstosuperviseandensurethat dataofallPanchayatsisupload- edbythevisitingofficerwithin theperiodspecified |

INSTRUCTIONSFORTHEVISITINGOFFICER(DAYWISE)

| DATE | INSTRUCTIONS | ACTIONPOINTS |
| --- | --- | --- |
| Day0 | Meetingwithdeputycommissionerandhis/her team | a. TakeprintoutsoffilledbookletsofB2V1,B2V2andB2V3from www.jkpanchayat.in b.Alsotakeprintoutsofthesummarizedexcelsheetsofthepreviousphasesfromwww.jkpanchayat.in c. CollectATRsonissuesraisedduringprevious3phasesfromthe officeofDeputyCommissioner(Planningdeptt) d.Takeprintsofblank 2bookletsofB2V4fromwww.jkpanchayat.ine.Takeplansfor2previousyearsandATRsfromtheplanningdeptt f. CompletetrainingsondifferentcomponentsofB2V4being organizedbyrespectiveDeputyCommissioners g.CollectListofnewworksstarted/ongoing/completedduringthepreviousandcurrentFinancialyearunderthefollowingheads: • PRIgrants • DistrictPlan • UTplan • MGNREGA • Otherschemesofotherdepartments • Anyotherwork h. Plans/beneficiarylists: • MGNREGAdraftplandocumentfortheyear2022-23. • ListofAwaas+beneficiariesalongwithIHHLConvergence • Listofpensionbeneficiaries. • ListofSHGs • Listofagricultureschemebeneficiaries i. Listsofbeneficiariesfor: • Variouscertificates/benefitstobedistributedbythevisitingofficer. • Anyotheractivitiesidentifiedbydifferentdepartments |

| Day1 | Reachthevillage | 1. | Ensurethatallfrontlineworkersofdifferentdepttsarepresent. |
| --- | --- | --- | --- |
|  |  | 2. | Ensureexhibitionbydifferentdepts.aboutindividualbeneficiaryschemes |
|  |  | 3. | InspectJKB/PSBcounters/outlets |
|  |  | 4. | Participate/ensureorganizationofsportsactivityinplayfield,talenthunt/culturalevent/youthactivity |
|  |  | 5. | GandhiKatha(suggesteddetailsuploadedonjkpanchayat.in) |
|  |  | 6. | Visitatleast2amritsarovarsandgetitsgeotaggedphotos |
|  |  | 7. | InspectKhidmat(CSC)CentresandcreateGenerateawarenesson 225schemesparticularlyG2CschemeslikeBEAMS,Janbhagidari, AapkiZaminAapkiNigrani,DigitalJ&K |
|  |  | 8. | Visitingofficershallalsoplanandconductpanchayatlevelconver- gencemeetingofalldepartments |
|  |  | 9. | CheckeffectivenessofCentrallysponsoredschemes |
|  |  | 10. | VisitandinspectallgovernmentestablishmentsincludingPHE, AWC,FPS,schools,etc |
|  |  | 11. | AttemptsaturationofdeliverablesoJanAbhiyanandwhereverdeficienciesfound,leadadrivetoachievealldeliverables |
|  |  | 12. | Assesseffectivenessofsanitationcampaigninthepanchayat |
|  |  | 13. | Ensureselfemploymentactivitiesfor15youthperpanchayat |
|  |  | 14. | Identify20potentialcandidatesperpanchayatforHIMAYATtraining alongwiththetradeonwhichtheywanttraining |
|  |  | 15. | Whereverpossible,distributeemploymentlettersforpeopleselect- edundervariousgovernmentemployments |
|  |  | 16. | Intheevening,holdnormalmeetingwithseniorcitizens,govtem- ployeesincludingretiredemployees,exservicemen,youthclub,andany citizens ofthevillagewhoareenrolledincollege/university |
|  |  | 17. | OpendiscussiononNashaMuktAbhiyan |

Day2            Haveameetingwithall stakeholders-depttofficialsandpanchayatmembers

1.       DiscussionontheandassesstheprogressofdifferentschemesrelatingtothelocalizedSDGsprioritizedforthatvillageaspertheresolutionpassedby thatGramPanchayaton21stApril22,onNationalPanchayti RajDay.

2.	SensitizevillageresidentsaboutmyScheme”portal(myscheme.in) whichincludesinformationaboutalltheschemesbeingrunbyCen- tral/State/UTgovtacrossthecountry

3.	Hold meeting of theBiodiversityManagementCommitteestodeliber- ateonissuespertainingtoconservationof biodiversityandsustaina- bleutilizationofbiologicalresources.

4.       PrepareVillagedevelopmentplan,inconsultancywithGrampanchayat, discussitingramsabhaandgetitapproved.

5.       EnsuresaturationofsoilhealthcardandgoldenhealthcardunderGold- enHealthCardunderAyushmanBharat,

6.       Ensuresaturation of OldAgePensionScheme

7.       EnsureDomicileSaturation.

8.       EnsureKCCSaturation

9.       Ensuresaturationoflandpassbooks

10.     Ensureregistrationofvillagevendorsneededforanyscheme,onGEM

portal

11.     Ensurepanchayatcontractorsregistration

12.     EncouragePanchayatmembersforimportanceofplantationdrivein

PanchayatunderHarGaonHariyali

13.     EnsurepaintingondigitalJ&Kinpanchayatghars

14.     EnsurepaintingonpanchayatactivitesandCSSinpanchayatghars

15.	Thevisitingofficeshallchecknoofkindergarten andplayfieldspresent inthepanchayatfor kidsandstudents,iftheinfrastructurepresent inthesearegoodenough.

16.     HoldmeetingwithpanchayatmemberstodiscussaboutcorruptionmenaceandstepsrequiredtomakeJ&Kcorruptionfree

17.     Obtainacandidassessmentaboutperformanceofvariousdepttsin- cludingfairfeedbackaboutdiscrepanciesinfunctioning

18.	Check thestatusofNashaMuktAbhiyanandreportingof drugad- dictstoDeputyCommissioner.

19.     IdentifyTouristDestinations,Circuits,ThemeTreks,IdentifyHomestays, providesupportfortourismactivitiesthroughVillageCooperative

20.     OrganizeTalentHuntatPanchayatLevel

21.     Conductsocialauditofatleast5worksunderfollowingschemes:

a.       MGNREGA

b.PMAY

c.        IHHLtoiletsandpaymentsd.CSCs

e.AMRITSAROVARS

22.     Holdamahilasabhaandabalsabhaandrecordproceedingsinthefor- matgiven

23.     InauguratevillagehaatunderJKSRLM

24.     Checkifyouthclubsareformedinthepanchayatandwhatactivitiestheyareengagedin

25.     Organizeavillagelevelculturaleventtoengagepanchayatmembers

26.     SensitizeGPaboutE-kitabkoshaninitiativeofJ&KGovtforempoweringyouthsthroughonlinedigitalliteracy

GENERALINSTRUCTIONS

1.	Thevisitingofficershallrefrainhimself/herselfgivingorofferinganycommitmentonbehalfofthe governmentandshalladoptanunbiasedattitudeinreportingissues.Asfaraspossible,his/her observation shouldbebasedonafairandanalyticalviewemergingfromhis/herinteractioninthevillage.

2.	Heisgoingtothevillageasplanningofficer,notforsanctioninganyworksorformakinganycom- mitments.

3.	Whilepreparingvillagedevelopmentplan,hehastoensurethat,demandsareprioritizedandre- flectedunderavailableschemes,wherevernecessarythelargerworksaretobereferredtoadminis- trativedepttunderCSS/UTplansunderintimationtoDCsandrestoftheworkstoDCsforreflecting itunderdistrict/CSS plans

4.    His workshallbehardcoreplanningandauditandisnotaPRexercise.

5.	EveryDeputyCommissionerhastoensurethatatleastoneRDDofficial(ideallyPanchayatSecre- tary)ispresent  ineverypanchayatwithrelevantpanchayatrecords,toensureconductofallactivi- tiesasplanned.Panchayatwiseorderneedstobeissuedinadvance.

6.	Visitingofficershouldideallycarryhis/herlaptoptocompletethereportsatthepanchayatlevel itselfanduploadthefinalreport,dulysignedbothbythesarpanchandbythevisitingofficeronwww.jkpanchayat.inportal,beforetheyleavepanchayat.

7.	Focus ofvisitareyouth,skills,self-employment,nashamukt,bhrashtracharmukt,Rozgaryukt J&K, besidestocarryforwardtheactivitiesduringJanAbhiyanandsaturatethem.

8.    Inadditionattentionmaybegiventothefollowingareasa.     MakefulluseofCentrallySponsoredSchemes

b.Saturationofindividualbeneficiaryschemesc.     Self-employmentschemes

d.Banklinkedschemes-includingdepartmentalsubsidyschemese.Empowermentandtransparencythroughdigitalinitiatives

f.       Effectivenessofgrassrootsmachinery–

i.       Patwari,VLWpresentandavailable

ii.      AvailablefundsutilizedinpublicinterestandasperGramSabharesolutions iii.   Fairness ingovernance

iv.    CSS/Individual beneficiaryschemesetcv.      BrashtacharMuktJ&K

vi.   BhaiMuktJ&K

vii.  NashaMuktJ&K

9.	ThePRImembers(Sarpanchs,Panchs,BDCChairperson)shallbeattheforefrontofallactivities and givendueimportanceandtheapproachshouldbetostrengthenthemandmakethemfeelem- powered.He/sheshallensurethattheBDCchairpersonandSarpanch/Pancharepresentatthetimeofinaugurationandceremonies.

10.	Visitingofficershallnotleavethedistrictwithoutuploadingthereport,duly signedonthewww. jkpanchayat.inportal.EveryDeputyCommissionerhastoensurethat.

A)   DetailsofReportingOfficer:

Name:   Er. Shahid UL  Bashir

Designation: Assistant Engineer

Department/placeof  posting:Jal Shakti PHE Division/Division Awantipora

MobileNo:- 9419587251

EmailID: shahiidmir@gmail.com

HomeDistrict:- pulwama

Datesof  visit: 28/10/2022 to 29/10/2022

B)	LocationaldetailsofPanchayat:(tobepre-filled,informationtobetakenfromtheprevious phasesbooklets/summarizedexcelsheetuploadedonjkpanchayat.in/b2v4.php)(tobevali- datedbythevisitingofficerandmissingdetailstobefilled)

NameofthePanchayat:Rajpora A

LocalGovernmentDirectory(LGD)codeof  thePanchayat:        245577

Nameof  CDBlock:Shadimarg

NameofTehsil:Rajpora

Nameof    District: PULWAMA

C)     PanchayatProfile:

No.ofrevenuevillagesinthePanchayat:_________01.

No.ofhamletsinthePanchayat    ______01_________

No.ofhouseholdsinthePanchayat:__________400__________

Population(approx)of  thePanchayat:_______________2579____________

Part-II:

(TobefilledupbytheVisitingOfficerduringhis/hertwodayvisit tothePanchayat.AllFieldshavetobe

FilledbytheVisitingOfficerbeforethebookletishanded over totheDC

FrontlineOfficers/OfficialswhowereassignedtothePanchayatfortheprogramme:

| Department | Name | Designation |
| --- | --- | --- |
| RDD | Abdul Hamid Mir | Panchayat Sectt |
| Education | Bashir Ahmed Wani | Master |
| PMGSY | Zahid Ahmed Chat | A.E |
| PMGSY | Zahoor Ahmed Thokker | J.E. |
| Jal Shakti | Fayaz Ah Mir | J.E |
| R&B | ShahidFarwe | R/W |
| HEALTH | Farida | Asha Worker |
| Social Welfare | Mehnwda | A.W.W. |
| FOOD Supply | ALI MOHD AHANGER | STOKEEPER |
| Sheep and animal husbandry | K Majeed | Lab Boy |
| Social Welfare | Syed Feliwada | Asha Worker |

Detailsofabsentemployeesvis-à-vislistfurnishedbytheDCoffice:

| Department | Name | Designation |
| --- | --- | --- |
| Nil | Nil | Nil |

DAY1-ACTIVITIES

AGENDA1:PANCHAYATASSETREGISTER

Infrastructure:

1.		PanchayatGharInfrastructure a.  Govtbuilding

b. New Building

2.       Furniture(No)

3.       Computer/printer(No)

4.       Internet(No)

5.       Telephone(No)

6.       Toilet(CSC/partofPanchayat ghar)(No)

7.       Water(No)

8.       Electricity(No)

9.       Bankbranch(Yes)

10.     CSC(Yes)

11.     Patwarkhana(No)

12.     Villagehaat(No)

13.     Playground(No)

14.     School-

a.        Kindergarten(No)

b.Primary(No)

c.         Secondary(Yes)

d. College (N)

e.University(N)

15.     AnganwadiCentre(Yes)  04  Nos

a.        (private Building)

b.Totalchildrenenrolled    (   292  )

15.     AmritSarovars–details,  02 Nos at location KuttMohalla, MandMohalla, little KKrimere, not in good condition .

16.     Governmentoffices-details,whether functionalornot;  Tehsil office, PDD, Post Office, all functional.

17.     Rationshop(Y)

18.      Placesoftourismimportance–names,littledetailsonhistorical/culturalimportance .( NIL )

19.      Villageheritagesites/treks-names,littledetailson historical/culturalimportance. ( NIL )

20.     VLWOffice (Yes )

21.     PrimaryHealthcareCentre(N )

22.     ListofIncompleteBuildings-names,yearofconstruction ( Nil )

23.     ListofUnderutilizedBuildings-names			NIL

DAY1-ACTIVITIES

AGENDA2:

DIFFERENTINSTITUTIONS/INFRASTRUCTUREPROJECTSTOBEVISITED

| AMRITSAROVARS | Visit,verify | COMMENTS |
| --- | --- | --- |
| KhidmatCentres | Create/Generateawarenesson225schemes particularlyG2CschemsAapkiZaminAapkiNigrani, Beams,Janbhagidari,DigitalJ&K | Kidmatcentres was visited and verified, services provided by the centre fond satisfactory. |
| JKB/PSBcounters/outlets | a)Statusofcounter Functionalb)Numberofvisitors800 plus visitors | Functional |
| Incompletebuildings/pro- jects | Verify whetheridentificationandredistribution done | NIL |
| PDS | Visit,evaluate,onlinestatus | 100% Saturation |
| PHC | Visit-evaluate,statusofstaff,equipmentand quality | Not Available in GP. |
| Youthclubs | Meet,interact,seeksuggestions | NA |
| SHG | Meet,identifyproblems,seeksuggestions | NA |
| PMAY | Inspect,Inaugurate | 2 under construction 1 inagrated |
| Myschool,myprideprogress;schools-water, toilets,staff | Visit,checkforwater,electricity,sanitation,meet studentsandstaff | All basic facilities available. |
| SwachhSBM | Evaluate | Satisfactory |
| Panchayatplayground, Sportskitsdistribution Villagegames | Ensure,verify.Participateinatleastonegamein theplayground | N.A |
| HarGaonHariyali, Planta- tiondrive | Evaluatestatus,feedback | Plantation driver was done at GHR sec Rajpora |
| Villageculturalevent Dangal/Haat/Mela | Participatein;ensurethatitisheld | NIL |
| Exhibitionofschemes | Ensurethateverydepartmentparticipatesand thatitcontinuesfortheentiredurationofB2V | Ensured |
| JalJeewanMission verifica- tion- WSS/JSD Electricitysupply | Verify | No scheme under JJM |

DAY1-ACTIVITIES

AGENDA3:SATURATEJANBHIYAN

DELIVERABLESANDRECORDDEFICIENCIESIFANY(INSERTDELIVERABLESLISTHEREASPERGADFORMAT

DAY1-ACTIVITIES

AGENDA4:

SELFEMPLOYMENTACTIVITIES

EnsureSelf-employmentactivities foryouth,distributeemploymentlettersforpeopleselectedunder varioussocialschemes(15ISTHETARGETPERPANCHAYAT)

Numberofcasesindifferentcategoriessanctioned:16

Detailsofthebanksanctioning it:    Bank Ltd

Totalamountinvolved: RS 60 Lakh

DAY1ACTIVITIES

AGENDA5

Intheevening,holdinformalmeetings  withseniorcitizens,govtemployees,retdemployees,youthclub andothercitizenswhoareenrolledoncollege/universityandhavediscussiononGandhiKatha,NashaMuktAbhiyan,corruptionfreegovernance,doublingfarmersincomeandrecordtheproceedings

DAY2

- No. ofIndividualCompostPitsconstructed- Nil

- NoofIndividualSoakPitsconstructed- 20

V.          No.ofBiodiversitymanagementcommitteemeetingsheld:		NIL

VI.         IsthenameofSarpanchdisplayedoncitizeninformationboardsofallRD&PRschemes:No

VII.       AreSarpanchsbeinginvolvedinstart/inaugurationofactivities:  ( No )  There is no punch and surpanch in the Halqa .

VIII.      WhethersubjectshavebeenassignedbytheSarpanch tothePanchs:No

IX.        Whethergrievancesredressalboxisinstalled:Yes

X.       NoofgrievancesreceivedpertainingtoPanchayatlevel:0

XI.        NoofgrievancesdisposedofatPanchayatlevel:0

XII.       WhethertheSarpanch/PanchayatSecretaryhavedigitalsignatures:Yes

XIII.      WhetherallMGNREGA/14thFCpayments arebeingmadebySarpanchthrough DigitalSignature

Certificate(DSC):No

HUMAN RESOURCEAVAILABLEATTHEPANCHAYAT LEVEL:

| SRNO. | DEPARTMENTWISESTAFF | NUMBERS |  | NAMES |
| --- | --- | --- | --- | --- |
|  |  | SANCTIONED | ACTUAL |  |
|  | RuralDev department: BDO JEGRS TA | 0 01 01 01 | 0 01 01 01 | Bashir Ahmad Sheikh Bilal Ahmed Qadri Ghulam Jeelani |
|  | SCHOOLEDUCATION:TEACHER HEADMASTER ANYOTHER | 26 01 12 REK,Cooks etc. | 23 01 12 03 0 |  |
|  | JAL JEEVAN: | ---- | 03 |  |
|  | PDD:LINEMAN JE ANYOTHER | 01 MR | 01 01 06 |  |
|  | FOOD&CIVILSUPPLIES | 02 | 02 | Ali MohdAhenger Farooq Ah Khan |
|  | AGRICULTURE&ANIMALHUS- BANDARY | NotExisting in the Halqa | NIL | NIL |
|  | SOCIALWELFARE | 4 | 4 | Mehmuda Syed Fehmeeda |
|  | HEALTH: ASHA ANM AYUSHDOCTOR ALLOPATHICDOCTOR | 02 | 02 0 0 0 | Fasida , Haseena |
|  | ANYOTHERDEPARTMENT | NIL | NIL | NIL |

DAY2-ACTIVITIES

AGENDANO.1

DiscussionontheandassesstheprogressofdifferentschemesrelatingtothelocalizedSDGsprior-itizedforthatvillageaspertheresolutionpassedbythatGramPanchayaton21stApril22,onNational PanchayatiRajDay(Copyoftheresolutiontobetakenfromwww.jkpanchayat.inportalunderthelinkof GramSwarajMonth)

1.       SDGs AGREED FORTHATVILLAGE,TOBEIMPLEMENTED BYMARCH2024:

2.       STATUSOFWORKSUNDERTHEFOLLOWINGSCHEMES:

1      Cleanandgreenvillage

i.InitiativestakenbythePanchayatformanagingSolidandLiquidWaste Yes cont. of soak pits.

ii.     InitiatiestakenbythePanchayatforusinggreensourcesoffuellikesolar,biogas

NA

iii.  Hasmappingoflanduse,waterbodies,forest,slopes,wetlands,degradedforestwithintheGram

Panchayatbeendone?Yes/No.IfNo,reason,thereofNA

iv.    HastheClimateResiliencePlanbeendevelopedfortheGP?No

v.     StepstakenbytheGramSabhaabouttheclimatechangemitigationfactorslikereducingenergy consumption,usageoffossilfuels,plastics,non-renewablebuildingmaterialsandalsotopromote measureslikeplantingoftrees,conservingforests,usageofgoodagriculturalpracticeslikedrip irrigation,waterconservationmeasuresandconservationofwetlands.No

vi.  WhetherschoolshavestartedsegregatingwasteNo

vii. Whetherschoolshavetheirowncompost/soakagepitsforsolid/liquidwastemanagementNO

2     Healthyvillage

i)    AremeetingsrelatedtoVillageHealthandSanitationCommitteebeingheldregularly?Yes

ii)   DoalltheeligibleindividualsbeenprovidedtheGoldenCard?Yes

iii)  ArealltheChildrenbeingimmunizedaspertheSchedulerecommendedbyGovt.ofIndia?YES

iv)  ArealltheeligibleindividualsbeenvaccinatedagainstCOVID-19?Yes

v)   DoesGramPanchayatensurethatallpregnantwomenaregettingnecessaryprenatalcheckups?YES

vi)  WhetherallthedeliverieswereInstitutionalizedorconductedbytrainedMidwives?YES

3     Watersufficientvillage

i)    DoalltheIHHsintheGramPanchayathavewaterpipelineconnections?Yes

ii)   WhetherGramPanchayathastakenstepsforgreywatermanagement.IfYespleasespecifyYes, by way of constructed soak pits

iii)  DoalltheIHHsintheGramPanchayathavetoilets?Yes

iv)  ArealltheIHHstoiletsfunctionalornot?  Yes

v)   DoalltheSchools/Anganwadicentershavea toiletfacilityornot?Yes

vi)  Areallthetoiletsintheschools/Aaganwadifunctionalornot?Yes

vii) WhetherGramPachachayatBhawanhasseparate toiletsforwomenornot?NO

4      ChildFriendlyvillage

i)	Doallthechildrenundertheageof0-6yearsbeenenrolledintheAnganwadicentersforpre- schooling?Yes

ii)    HowmanyBalSabha’swereorganizedintheGramPanchayat----------------02

iii)  WhethertheissuesraisedbyBalSabhaareaddressedduringtheGramSabha. Yes

iv)	WhetherGramPanchayatistrackingthedatarelatedtodropoutchildrenandchildrenwithirregular attendance?Yes

v)   DoalltheschoolsundertheGramPanchayathaveseparate toiletsforgirlsandboys?Yes

5      Villagewithgoodgovernance

- i)    IsCSClocatedintheGramPanchayatBhawanornot?Yes

- IsthelistofbeneficiariesrelatedtotheSchemes/ProgramsdisplayedontheGrampanchayatwallor not?YES

- DoestheGramPanchayathasitsbuildingornot?YES

- IstheGramPanchayatofficefunctionalornot?Yes

- Aretheactivities approved undertheHalqaPanchayatDevelopmentPlandisplayedontheGram

- Panchayatwallornot ?NO

- IsSocialAuditofearlierSchemes/Programscarriedoutornot?Yes

6      Povertyfreeandenhancedlivelihoodvillage

- HasGramPanchayatdevelopedanycriteria fortheidentificationofthepoor?YES – 1) income less than 40,000/ per year and 2) Home less

- HavealltheeligiblehouseholdsregisteredinPDSornot?NO

iii)	HasGramPanchayatprovidedspaceforSelf-helpGroupsinPanchyatGharforholdingmeetings  or not?NO

iv)  HavealltheeligiblehouseholdsbeenregisteredforPensionornot?Yes

v)   HasGramPanchayatfacilitatedYouthforSkillEnhancementCoursesandPlacement?Yes

vi)  HasJobCardsbeendistributedtoalltheeligibleindividualsunderMGNREGA?YES

vii) HasGramPanchayatfacilitatedSHGsforBankAccountLinkages?No

7     Sociallysecuredvillage

i)    WhetherGramPanchayatismaintainingdatarelatedtoDifferentlyAbledPeople? No

ii)   IsGramPanchayatOfficeDisabledFriendlyornot?YES

iii)	Areprovisionsfora separate BudgetundertheResourceEnvelopeforWomenandChildrenmadeornot? NO

iv)	DoalltheSchools intheGramPanchayathavefacilitiesforDifferentlyAbledChildrenliketoilets, barrier-freeaccess,etc.,ornot?Yes

v)   Arealltheeligibleindividualsaregettingpensions,likeoldagepension,widowpension,etc? Yes, All rgistered and are receiving .

vi)  ArealltheeligiblehouseholdsgettingbenefitsfromIAYornot?

YES , only deserving one.

8      EngenderedDevelopmentinVillage

i)    HowmanyMahilaSabha’swereorganizedintheGramPanchayat------------ 02----

ii)	WhetherSHGsfederationshavebeenprovidedspaceformeetingsinthePanchayatBhawanNo

iii)  WhetherGPshavetakenstepsforincreasingwomen’sparticipationinGramSabha Yes

iv)  NumberofwomenbeneficiariesheadedhouseholdscoveredunderPDS

system………100%

v)   Numberofbeneficiaries(outoftotaleligiblepopulation)receivingsocialprotectionbenefitsunder

PradhanMantriMatritvaVandanaYojana15

9    Self-sufficientinfrastructureinthevillage

i.	WhetherGPhasaCommunityHallwithaccesstoelectricity,furniture,watersupply, toilet… NO community hall available

ii.     WhethertheDisastermanagementplanisavailableattheGPLevel(No)

iii.  Whetherchild-friendlyparkwithrequiredfacilitiesisavailableinGP(No)

iv.    WhethertheGPhaseasyaccesstoGodownforstorage(Yes)

v.     Whetherstreetlightsareprovidedinpublicplacesforensuringsafety(Yes)

DAY2ACTIVITIES

AGENDANO.2

SensitizevillageresidentsaboutmyScheme”portal(myscheme.in)whichincludesinformationaboutall theschemesbeingrunbyCentral/State/UT govtacrossthecountry  (  Sensitized and informed )

(SchemeMaterialavailablefromhttps://jkpanchayat.in/b2v4.php)

DAY2ACTIVITIES

AGENDANO.3

HoldmeetingoftheBiodiversityManagementCommitteestodeliberateonissues pertainingtoconserva- tionofbiodiversityandsustainableutilizationofbiologicalresources.HeshouldcheckPeopleBiodiversity register(PBR)ofthatpanchayatandreviewifBiodiversityManagementCommittee constitutedforthatpanchayatis holdingminimum4meetings inayearandmeeting onceinevery3months (RoleofBMCavailableathttps://jkpanchayat.in/b2v4.php)

COMMITTEEMEMBERS PRESENT

BIODIVERSITYREGISTERPHOTOS

PAST 4MEETINGDETAILS-DATES,MINUTESPHOTOS

DAY2ACTIVITIES

AGENDA4

Visitingofficershallalsoplanandconductpanchayatlevelconvergencemeeting  ofalldepartmentsandprepareVillagedevelopmentplanforvillage,inconsultancywithGrampanchayat,discussitingram sabhaandgetitapproved.

(GPDPformatavailableonhttps://jkpanchayat.in/b2v4.php)

InadditionGPDPplanshallalsoinclude:

           Touristplaceswhichneedtobedeveloped NIL

           SpecificproductwhichneedstobedevelopedApple , walnut ,vegetable, fruit plant may be provide

           Tourism-homestaysNIL

	20candidatesfortrainingunderHimayatschemealongwithtradeinwhich trainingistobegiven 10

DAY2ACTIVITIES

AGENDA5

Ensuresaturationoffollowingschemesandgivestatus:

| NAMEOFTHESCHEME | TOTALELIGIBLE BENEFICIARIESIN THE VILLAGE | TOTALBENEFICIARIESWHO AVAILEDTHEBENEFITSOFTHESCHEME | REASONSFOR PENDENCY |
| --- | --- | --- | --- |
| GoldenHealthCardunder AyushmanBharat | 2579 | 2505 | Unavailability of adhaar card of underage children |
| Jananisurakshayojana | 50 | 50 | Nil |
| OLDAGEpension | 91 | 91 |  |
| Widowpension | 32 | 32 | NIL |
| Disabilitypension | 35 | 35 | NIL |
| Domicilecertificate | 2579 | 750 | Not interested |
| Kisancreditcard | 457 | 453 | 100% saturation Land mutation ownership |
| PMkisansammannidhi | 450 | 330 | Land mutation ownership |

| Landpassbook | - | - | - |
| --- | --- | --- | --- |
| Registrationofvillageven- dorsonGEMportal | 01 | 01 | NIL |
| Registrationofvillagecon- tractorsonjktendersportal | 13 | 13 | NIL |
| Registrationofvillagecon- tractorsonPWDportal | 13 | 13 | NIL |
| Incompletebuildings/pro- jects | NIL | NIL | NIL |

DAY2ACTIVITIES

AGENDA6

NASHAMUKTABHIYAN

1.       WhethergramsabharesolutionpassedYES

2.       Detailsofactivities conducted Awareness about NASHA MUKT Abyan , corruption free society , green and clean village etc.

3.       Whetherallactivities andGSresolutionuploadedonjkpanchayats.inportalYES

4.       HowmanydrugaddictsinthevillageNIL

5.       WhetherreportedtotheDeputyCommissionerNIL

6.       Howmanyregisteredforrehabilitationundergovernmentprogramme

NIL

DAY2ACTIVITIES

AGENDA7

SOCIALAUDIT

Conductsocialauditofatleast5workseachunderfollowingschemes:

| Name of the scheme | Detail of works | Year of work approval | Amount approved for work | whether work executed satisfactorily | geo tagged photos | any grievance recorded relating to that work |
| --- | --- | --- | --- | --- | --- | --- |
| MGNAREGA | C/o drain from H/o Mohd Hussain Shetan | 2022-23 | 2.84 | Yes | Yes | NA |
| PMAY | Manzoor Ali | 2021-22 | 1.32 | Yes | Yes | NA |
| IHHL Under SBM-G | Toilet - Ab Hamid Dal S/o Gh. Bhat | 2021-22 | 0.12 | Yes | Yes | NA |
| CSC under SBMG | c/o CSC | 2020-21 | 2.99 | Yes | Yes | NA |
| AmritSarovars | Development of spring 410 Nazir Ali Mir | 2022-23 | 1.39 | Yes | Yes | NA |

DAY2ACTIVITIES

AGENDA8

MAHILASABHA

Totalwomeninthevillageabovetheageof18

Totalattended

Proceedings:

(Plinsertpointerstobediscussedthere–referpalliproceedings)

DAY2ACTIVITIES

AGENDA9

BALSABHA

HoldabalsabhaandrecordproceedingsHELD

Totalchildreninthevillageabovetheageof…. ( 3-Years )

Totalattended

Proceedings:

(Plinsertpointerstobediscussedthere–referpalliproceedings)

DAY2ACTIVITIES

AGENDA10

INAUGURATIONS

FOLLOWUPOF(B2V1,B2V2&B2V3):

(Prefilledexcelsheettobetakenfromdistrictlevel/andalsotobedownloaded

fromwww.jkpanchayat.in)

| S.No. | Particulars | Action taken | Remarks |
| --- | --- | --- | --- |
| 1 | Reqirement of tubewell in order to improve supply of portable water | No action taken |  |
| 2 | Constrction of additional classrooms for GHSS Rajpora | Work has been started |  |
| 3 | Constrction of new panchayat ghar | Primary school building has been allotted |  |
| 4 | Constrction of new rewnue complex | No action taken |  |
| 5 | Hot line to CHC Rajpora | No action taken |  |
| 6 | Replacement of HT/LT wires with inslators | work has been started | condctors not laid yet |
| 7 | Up gradation of road from Rajpora to Gulshanabad kuthpora | No action taken |  |
| II | Urgent Public reqirements/Demands-B2V2 |  |  |
| 1 | Upgradation of BSNL exchange Rajpora so that Broadband services shall improve | No action taken |  |
| 2 | Panchayat Ghar Rajpora is fnctional from rental bilding | Primary school building has been allotted |  |
| 3 | Improvement of HT/LT in panchayat Halqa | Work has been started | condctors not laid yet |
| 4 | Demand for extra Ration in the pyt Halqa | Srvey has been done by CAPD but fond not feasible |  |
| 5 | Repairing of water pipes | No action taken |  |
| 6 | Project has been submitted for flood protection works | Not taken p |  |
| 7 | Disilting of stream passing through GHSS Rajpora | Work has been done |  |
| III | Major Problems - B2V1 |  |  |
| 1 | Encroachment of irrigation canal passing through Gram Panchayat | No action taken | Encroachment must be stopped |
| 2 | Internal and external drainage system | No action taken |  |
| 3 | Road connectivity to the orchads | Almost done |  |
| 4 | Eratic power supply | Solved | Nearby receiving station made functional |
| 5 | Unemployment | No action taken |  |
| IV | Major Problems - B2V2 |  |  |
| 1 | No destilling of canals/streams | some destilling of streams done | Need more action |
| 2 | Poor broadband service | No action taken |  |
| 3 | Additional accomodation for GHSS | Work has been started |  |
| 4 |  |  |  |
| 5 |  |  |  |
| V | Major Problems - B2V3 |  |  |
| 1 | Providing hotline to CHC Rajpora | No action taken | Pertains to Halqa Rajpora -B |
| 2 | Disilting of stream passing through GHSS Rajpora | Work completed |  |
| 3 |  |  |  |
| 4 |  |  |  |
| 5 |  |  |  |
| VI | Major Complaints - B2V1 |  |  |
| 1 | Additional requirement of staff for GHSS Rajpora | Already taken up with CEO | Needs immediate action |
| 2 | Desilting of irrigation canal | completed |  |
| 3 |  |  |  |
| VII | Major Complaints - B2V2 |  |  |
| 1 | Eratic power supply | Solved | Nearby receiving station made functional |
| 2 | Worst construction of road from main stop to CHC | Solved | Road has been black topped |
| VIII | Major Complaints - B2V3 |  |  |
| 1 | Issue of functioning of receiving station at Hanjeen Payeen(Gulshanabad) Rajpora B has not resolved | Yes, measures has been taken | Remaining station has been made functional |
| 2 |  |  |  |
| 3 |  |  |  |

OVERALLPERCEPTIONOFFUCNTIONING OF GOVERNMENTDEPARTMENTS

1.         BESTDEPARTMENT:

2.       LEASTRESPONSIVEDEPARTMENT:

GENERALASSESSMENTOFTHEVISTINGOFFICER

| I | Any major complaint brought to the notice of the Visiting Officer: - -Conductor not laidover newly erected electricity poles. - Replacement of old wornout pipes laid some decadesback which are passing under the plinth of houses,walls etc and are 5 to 6 feet deep and additional tube well for water supply. - Subcentre not available in Gram Panchayat. - Supply of portable drinking water - New Anganwari centre for Khar Mohalla |
| --- | --- |
| II | Major/urgent public demands that was/were reflected earlier but have not been addressed so far: - Repairing of water pipes. - Requirement of tubewell in order to improve supply of portable drinking water |
| III | Overall assessment of the visit and suggestions: (The visiting officer to ensure that the overall assessment is recorded in details along with concrete sugges- tions) - The back to village program is of great importance and beneficial to the people. It reports the grossroot issues of the people and awareness about varios employment generation schemes. - The panches and Sarpanches need to be elected at the earliest. - There is need of more departmental involvement of RDD, PHE, IT, Revenue, Skill development and also for women empowerment, there is need of tailoring units, Self help groups etc. - The major complaints enlisted above shall be redressed. |
| IV | Overall Rating of govt functioning as given by the Panchayat (Scale of 0 to 10) 07 (Seven) |
| V | Certificate from Sarpanch that the visiting officer has stayed in the panchayat for 2 days PRI not available. |