Muyeezaa

mmm 

4

**15TH OCT to 3RD NOV, 2022**

4

**15TH OCT to 3RD NOV, 2022**

# KEY FEATURES

* Deputy Commissioners to lead the initiative
* Rural development Department to be the nodal department
* Planning Development & Monitoring department and IT to be the support departments

# ACTIONS AND TIMELINES

|  |  |  |  |
| --- | --- | --- | --- |
| **ACTION** | **RESPONSIBILITY** | **LATEST BY** | **REMARKS** |
| **Jan abhiyan** | All departments | Oct 15 -26th | Going on |
| **Deputation of Sectt staff/ HoDs** | GAD | Oct 14 | Done |
| **Deployment of Staff to Panchayats and serving of orders on deployed officers** | DCs | Oct 25 | DCs will deploy senior level staff from the districts. Strict action to be taken against abstentions. No exemptions to be given |
| **Training of district trainors on B2V4** | RDD | Oct 26 |  |
| **Training of visiting officers** | DCs | Oct 27 |  |
| **Field Visits to be completed by** | Visiting Officers | Nov 3 | DCs to supervise and ensure that each Panchayat is visited within the period specified |
| **Data of B2V4 to be uploaded by** | Visiting Officers | Nov 10 | DCs to supervise and ensure that data of all Panchayats is upload- ed by the visiting officer within the period specified |

**INSTRUCTIONS FOR THE VISITING OFFICER (DAY WISE)**

|  |  |  |
| --- | --- | --- |
| **DATE** | **INSTRUCTIONS** | **ACTION POINTS** |
| **Day 0** | Meeting with deputy commissioner and his/her team | 1. Take print outs of filled booklets of B2V1, B2V2 and B2V3 from [www.jkpanchayat.in](http://www.jkpanchayat.in/)
2. Also take print outs of the summarized excel sheets of the previous phases from [www.jkpanchayat.in](http://www.jkpanchayat.in/)
3. Collect ATRs on issues raised during previous 3 phases from the office of Deputy Commissioner (Planning deptt)
4. Take prints of blank 2 booklets of B2V4 from [www.jkpanchayat.in](http://www.jkpanchayat.in/)
5. Take plans for 2 previous years and ATRs from the planning deptt
6. Complete trainings on different components of B2V4 being organized by respective Deputy Commissioners
7. Collect List of new works started/ ongoing/ completed during the previous and current Financial year under the following heads:
	* PRI grants
	* District Plan
	* UT plan
	* MGNREGA
	* Other schemes of other departments
	* Any other work
8. Plans/ beneficiary lists:
	* MGNREGA draft plan document for the year 2022-23.
	* List of Awaas+ beneficiaries alongwith IHHL Convergence
	* List of pension beneficiaries.
	* List of SHGs
	* List of agriculture scheme beneficiaries
9. Lists of beneficiaries for:
	* Various certificates/ benefits to be distributed by the visiting officer.
	* Any other activities identified by different departments
 |

|  |  |  |
| --- | --- | --- |
| **Day 1** | Reach the village | 1. Ensure that all front line workers of different deptts are present.
2. Ensure exhibition by different depts. about individual beneficiary schemes
3. Inspect JKB/PSB counters/outlets
4. Participate/ensure organization of sports activity in playfield, talent hunt/cultural event/youth activity
5. Gandhi Katha (suggested details uploaded on jkpanchayat.in)
6. Visit atleast 2 amritsarovars and get its geo tagged photos
7. Inspect Khidmat (CSC) Centres and create Generate awareness on 225 schemes particularly G2C schemes like BEAMS, Janbhagidari, AapkiZaminAapkiNigrani, Digital J&K
8. Visiting officer shall also plan and conduct panchayat level conver- gence meeting of all departments
9. Check effectiveness of Centrally sponsored schemes
10. Visit and inspect all government establishments including PHE, AWC, FPS, schools, etc
11. Attempt saturation of deliverable so Jan Abhiyan and wherever deficiencies found, lead a drive to achieve all deliverables
12. Assess effectiveness of sanitation campaign in the panchayat
13. Ensure self employment activities for 15 youth per panchayat
14. Identify 20 potential candidates per panchayat for HIMAYAT training alongwith the trade on which they want training
15. Wherever possible, distribute employment letters for people select- ed under various government employments
16. In the evening, hold normal meeting with senior citizens, govt em- ployees including retired employees, ex servicemen, youth club, and any citizens of the village who are enrolled in college/university
17. Open discussion on Nasha Mukt Abhiyan
 |

|  |  |  |
| --- | --- | --- |
| Day2 | Have a meeting with all stakeholders- deptt officials and panchayat members | 1. Discussion on the and assess the progress of different schemes relating to the localized SDGs prioritized for that village as per the resolution passed by that Gram Panchayat on 21st April 22, on National Panchayti Raj Day.
2. Sensitize village residents about myScheme” portal (myscheme.in) which includes information about all the schemes being run by Cen- tral/ State/ UT govt across the country
3. Hold meeting of the Biodiversity Management Committees to deliber- ate on issues pertaining to conservation of biodiversity and sustaina- ble utilization of biological resources.
4. Prepare Village development plan, in consultancy with Gram panchayat, discuss it in gram sabha and get it approved.
5. Ensure saturation of soil health card and golden health card under Gold- en Health Card under Ayushman Bharat,
6. Ensure saturation of Old Age Pension Scheme
7. Ensure Domicile Saturation.
8. Ensure KCC Saturation
9. Ensure saturation of land pass books
10. Ensure registration of village vendors needed for any scheme, on GEM portal
11. Ensure panchayat contractors registration
12. Encourage Panchayat members for importance of plantation drive in Panchayat under Har Gaon Hariyali
13. Ensure painting on digital J&K in panchayat ghars
14. Ensure painting on panchayat activites and CSS in panchayat ghars
15. The visiting office shall check no of kindergarten and playfields present in the panchayat for kids and students, if the infrastructure present in these are good enough.
16. Hold meeting with panchayat members to discuss about corruption menace and steps required to make J&K corruption free
17. Obtain a candid assessment about performance of various deptts in- cluding fair feedback about discrepancies in functioning
18. Check the status of Nasha Mukt Abhiyan and reporting of drug ad- dicts to Deputy Commissioner.
19. Identify Tourist Destinations, Circuits, Theme Treks, Identify Homestays, provide support for tourism activities through Village Cooperative
20. Organize Talent Hunt at Panchayat Level
21. Conduct social audit of atleast 5 works under following schemes:
	1. MGNREGA
	2. PMAY
	3. IHHL toilets and payments
	4. CSCs
	5. AMRIT SAROVARS
22. Hold a mahilasabha and a balsabha and record proceedings in the for- mat given
23. Inaugurate village haat under JKSRLM
24. Check if youth clubs are formed in the panchayat and what activities they are engaged in
25. Organize a village level cultural event to engage panchayat members
26. Sensitize GP about E-kitab kosh an initiative of J&K Govt for empowering youths through online digital literacy
 |

# GENERAL INSTRUCTIONS

1. The visiting officer shall refrain himself/ herself giving or offering any commitment on behalf of the government and shall adopt an unbiased attitude in reporting issues. As far as possible, his/her observation should be based on a fair and analytical view emerging from his/her interaction in the village.
2. He is going to the village as planning officer, not for sanctioning any works or for making any com- mitments.
3. While preparing village development plan, he has to ensure that, demands are prioritized and re- flected under available schemes, wherever necessary the larger works are to be referred to adminis- trative deptt under CSS/UT plans under intimation to DCs and rest of the works to DCs for reflecting it under district/CSS plans
4. His work shall be hard core planning and audit and is not a PR exercise.
5. Every Deputy Commissioner has to ensure that atleast one RDD official (ideally Panchayat Secre- tary) is present in every panchayat with relevant panchayat records, to ensure conduct of all activi- ties as planned. Panchayat wise order needs to be issued in advance.
6. Visiting officer should ideally carry his/her laptop to complete the reports at the panchayat level itself and upload the final report, duly signed both by the sarpanch and by the visiting officer on [www.jkpanchayat.in](http://www.jkpanchayat.in/) portal, before they leave panchayat.
7. Focus of visit are youth, skills, self-employment, nasha mukt, bhrashtrachar mukt, Rozgar yukt J&K, besides to carry forward the activities during Jan Abhiyan and saturate them.
8. In addition attention may be given to the following areas
	1. Make full use of Centrally Sponsored Schemes
	2. Saturation of individual beneficiary schemes
	3. Self-employment schemes
	4. Bank linked schemes- including departmental subsidy schemes
	5. Empowerment and transparency through digital initiatives
	6. Effectiveness of grass roots machinery –
		1. Patwari, VLW present and available
		2. Available funds utilized in public interest and as per Gram Sabha resolutions
		3. Fairness in governance
		4. CSS/Individual beneficiary schemes etc
		5. BrashtacharMukt J&K
		6. Bhai Mukt J&K
		7. NashaMukt J&K
9. The PRI members (Sarpanchs, Panchs, BDC Chairperson) shall be at the forefront of all activities and given due importance and the approach should be to strengthen them and make them feel em- powered. He/she shall ensure that the BDC chairperson and Sarpanch/Panch are present at the time of inauguration and ceremonies.
10. Visiting officer shall not leave the district without uploading the report, duly signed on the [**www.**](http://www/) **jkpanchayat.in** portal. Every Deputy Commissioner has to ensure that.

## Details of Reporting Officer:

Name: MOHD YAHYA KHANDAY Designation: LECTURER Department/ place of posting: SCHOOL EDUCATION/HSS ABHAMA PULWAMA Mobile No: 9541119663 Email ID: khandayyahya@gmail.com Home District: BUDGAM Dates of visit: 30-10-2022 TO 31-10-2022

## Locational details of Panchayat: (to be pre-filled, information to be taken from the previous

**phases booklets/summarized excel sheet uploaded on jkpanchayat.in/b2v4.php) (to be vali- dated by the visiting officer and missing details to be filled)**

Name of the Panchayat: T N PORA Local Government Directory(LGD) code of the Panchayat: 242837 Name of CD Block: NEWA Name of Tehsil: PULWAMA Name of District: PULWAMA

## Panchayat Profile:

No. of revenue villages in the Panchayat: 02 No. of hamlets in the Panchayat: 03 No. of households in the Panchayat: 215

Population (approx) of the Panchayat: 1241

# Part-II:

(To be filled up by the Visiting Officer during his/her two day visit to the Panchayat. All Fields have to be filled by the Visiting Officer before the booklet is handed over to the DC

## Frontline Officers/Officials who were assigned to the Panchayat for the programme:

|  |  |  |
| --- | --- | --- |
| Department | Name | Designation |
| RDD | AASHIQ HUSSAIN | SEC. PYT. |
| RDD | MUSHTAQ AHMAD | J.E |
| RDD | AADIL AH | PH. WATCHER |
| RDD | FIRDOUS AH  | GRS |
| AGRICULTURE | GH MOHD | MECO |
| R AND B | MOHD MAQBOOL | HELPER |
| ANIMAL HUSBANDRY  | GOWHAR BASHIR |  ATTENDANT |
| REVENUE |  GOWHAR AH |  PATHWARI |
| FOREST | NISSAR AH | MALI |
| HEALTH | NIGEENA AKHTER | ASHA |
| ICDS | HAFEEZA BANO | WORKER |
| EDUCATION | SHABIR AH | TEACHER |
|  |  |  |
|  |  |  |
|  |  |  |
|  |  |  |
|  |  |  |

**Details of absent employees vis-à-vis list furnished by the DC office:**

|  |  |  |
| --- | --- | --- |
| Department | Name | Designation |
|  |  |  |
|  |  |  |
|  |  |  |
|  |  |  |
|  |  |  |
|  |  |  |
|  |  |  |
|  |  |  |
|  |  |  |
|  |  |  |
|  |  |  |
|  |  |  |
|  |  |  |
|  |  |  |
|  |  |  |

# DAY 1- ACTIVITIES

## AGENDA 1: PANCHAYAT ASSET REGISTER

**Infrastructure:**

* 1. Panchayat Ghar Infrastructure
		1. Govt building/private: GOVT BUILDING
		2. New/needing repairs: NEW
	2. Furniture (Y/N):N
	3. Computer/printer (Y/N):Y
	4. Internet (Y/N):N
	5. Telephone (Y/N):N
	6. Toilet (CSC/part of panchayat ghar) (Y/N):Y
	7. Water (Y/N):N
	8. Electricity (Y/N):N
	9. Bank branch (Y/N):Y
	10. CSC (Y/N):Y
	11. Patwarkhana (Y/N):N
	12. Village haat (Y/N):Y
	13. Playground (Y/N):Y
	14. School-
		1. Kindergarten (Y/N):N
		2. Primary (Y/N):Y
		3. Secondary (Y/N):N
		4. College (Y/N):N
		5. University (Y/N):N
	15. Anganwadi Centre (Y/N):Y
		1. (govt/private):PRIVATE
		2. Total children enrolled:60
1. Amrit Sarovars – details, location, condition: NIL
2. Government offices- details, whether functional or not FUNCTIONAL
3. Ration shop (Y/N):Y
4. Places of tourism importance – names, little details on historical/cultural importance:NO
5. Village heritage sites/ treks- names, little details on historical/cultural importance :NO
6. VLW Office (Y/N):Y
7. Primary Healthcare Centre (Y/N):N
8. List of Incomplete Buildings- names, year of construction:NA
9. List of Underutilized Buildings- names:NIL

# DAY 1-ACTIVITIES

## AGENDA 2:

**DIFFERENT INSTITUTIONS/INFRASTRUCTURE PROJECTS TO BE VISITED**

|  |  |  |
| --- | --- | --- |
| **AMRIT SAROVARS** | **Visit, verify** | **COMMENTS** |
| Khidmat Centres | Create /Generate awareness on 225 schemes particularly G2C schems Aapki Zamin Aapki Nigrani, Beams, Janbhagidari, Digital J&K | AWARENESS REGARDING DIFFERENT SCHEMES WAS DISSSEMINATED AND QUERIES OF THE PEOPLE WERE ANSWERED |
| JKB/PSB counters/outlets | 1. Status of counter:YES
2. Number of visitors:30
 | YOUTH WERE INTIMATED ABOUT VARIUOS SCHEMES AND THEY WERE MOTIVATED TO TAKE LOANS FOR STARTING THEIR OWN BUSSINESS |
| Incomplete buildings/pro- jects | NIL | NIL |
| PDS | Visit, evaluate, online status | VISITED AND FOUND FUNCTIONAL |
| PHC | Visit- evaluate, status of staff, equipment and quality | NOT IN THE PYT HALQA |
| Youth clubs | Meet, interact, seek suggestions | YOUTH DEMANNDED UPGRADATION OF PLAY FIELD AT HASSANWANI |
| SHG | Meet, identify problems, seek suggestions | PROMOTION OF PASHMINA SHAWLS AND EASY ACCESS TO MARKETS  |
| PMAY | NO PMAY CASE | NO PMAY CASE |
| My school, my pride progress; schools- water, toilets, staff | Visit, check for water, electricity, sanitation, meet students and staff | SCHOOL IS VHAVING GOOD PLAYING FIELD |
| Swachh SBM | Evaluate | PANCH. HALQA IS ODF  |
| Panchayat play ground, Sports kits distribution Village games | Ensure, verify. Participate in at least one game in the playground | THE SPORTS EVENT KABADI WAS ORGANISED |
| Har Gaon Hariyali, Planta- tion drive | Evaluate status, feedback | TWO DEODAR PLANTS WERE PLANTED |
| Village cultural event Dangal/ Haat/Mela | Participate in; ensure that it is held | DANGAL |
| Exhibition of schemes | Ensure that every department participates and that it continues for the entire duration of B2V | INSTALLATION OF STALLS BY ALL DEPARTMENTS |
| Jal Jeewan Mission verifica- tion- WSS/JSDElectricity supply | Verify | ELECTRICITY SUPPLY IS NOT GOOD. |

# DAY 1 - ACTIVITIES

## AGENDA 3: SATURATE JAN BHIYAN DELIVERABLES AND RECORD DEFICIENCIES IF ANY

**(INSERT DELIVERABLES LIST HERE AS PER GAD FORMAT**

DAY 1 BEGAN WITH THE INTRODUCTION AND WELCOME ADDRESS OF THE U/SD..PUBLIC WHO HAD COME TO ATTEND THE GRAM SABHA WERE WELCOMED AND INTIMATED ABOUT THE PURPOSE OF B2V4. IT WAS REVEALED THAT THE GOVT. OF THE UT OF J AND K INTENDS TO REACH THE LAST PERSON IN THE VLINE AND PROVIDE SOLUTIONSC TOP HIS/HER PROBLEMS AND ISSUES. MANAGER J & K BANK BRANCH NEWA, FUNCTIONARIES FROM HORTICULTURE DEPTT,REVENUE ,EDUCATION,PDD,SOCIAL WELFARE,ICDS ETC PROVIDED AWARENESS ABOUT VARIOUS SCHEMES OFFERED BY THEIR DEPARTMENTS..

 IN THE SECOND HALF PLANTATION DRIVE WAS CONDUCTED IN THE SCHOOL PARK.. AFTER THAT THE U/SD VISITED VARIOUS ICDS CENTRES ,SITES WHERE DIFFERENT PUBLIC WORKS WERE EXECUTED AND CONDUCTED THE SOCIAL AUDIT OF VARIOUS DEVELOPMENTAL WORKS. IN THE EVENING ANOTHER MEETING WAS HELD WAS HELD WITH THE OLDER PEOPLE PF THE PYT HALQA AND THE MESSAGE OF THE ADMINISTRATION PERTAINING TO THEIR DE3VELOPMENT WAS GIVEN TO THEM. IT WAS USUALLY A NICE DAY THAT KINDLED PEOPLE AND OPTIMISIM AMONG THE PEOPLE.

 VISITING OFFICER

 PYT HALQA INDER

# DAY 1- ACTIVITIES

## AGENDA 4:

**SELF EMPLOYMENT ACTIVITIES**

Ensure Self-employment activities for youth, distribute employment letters for people selected under various social schemes (15 IS THE TARGET PER PANCHAYAT)

## Number of cases in different categories sanctioned : YOUTH AND THE GENERAL PUBLIC RECEIVED A DETAILED INFORMATION ABOUT VARIOUS SELF- EMPLOYMENT ACTIVIITIES.YOUTH ASKED FOR MORE TIME TO TAKE THE FINAL DECISION.

**Details of the bank sanctioning it :**

**Total amount involved :**

# DAY 1 ACTIVITIES

## AGENDA 5

In the evening, hold informal meetings with senior citizens , govt employees, retd employees, youth club and other citizens who are enrolled on college/university and have discussion on Gandhi Katha, Nasha Mukt Abhiyan, corruption free governance, doubling farmers income and record the proceedings

## DAY 2

1. No of Individual Compost Pits constructed: NIL
2. No of Individual Soak Pits constructed:25
3. No.ofBiodiversity management committee meetings held:02
4. IsthenameofSarpanchdisplayedoncitizeninformationboardsofallRD&PRschemes:Yes/No:NO
5. AreSarpanchsbeinginvolvedinstart/inaugurationofactivities:Yes/No:NO
6. Whethersubjectshavebeenassignedbythe Sarpanchtothe Panchs:Yes/No:NO
7. Whether grievances redressal box is installed:Yes/No:YES
8. No of grievances received pertainingtoPanchayatlevel:NIL
9. No of grievances disposed of at Panchayatlevel:NIL
10. Whetherthe Sarpanch/Panchayat Secretary have digital signatures:Yes/No:YES
11. Whether all MGNREGA/ 14th FC payments are being made by Sarpanch through Digital Signature Certificate (DSC): Yes/ No:YES

# HUMAN RESOURCE AVAILABLE AT THE PANCHAYAT LEVEL:

|  |  |  |  |
| --- | --- | --- | --- |
| **SR NO.** | **DEPARTMENT WISE STAFF** | **NUMBERS** | **NAMES** |
|  |  | SANCTIONED | ACTUAL |  |
|  | Rural development department: BDOJE GRSTA | 0101010101 | 01010101 | Dr. GULZAR BIN REHMANMUSHTAQ AHMADIRSHAD AHMAD WANIASHRAF ALI |
|  | SCHOOL EDUCATION  TEACHER 03HEAD MASTER 01ANY OTHER | 030103 | 02 | MOHD RAFEEQ WANI, SYED SHABNAM. GGPS WANPORA |
|  | JAL JEEVAN: | 1 | 1 | GH MOHI UD DIN |
|  | PDD: LINEMAN JEANY OTHER |  0101 | 0101 |  JAVAID AH BHAT |
|  | FOOD & CIVIL SUPPLIES  |  01 |  01 | GH NABI RATHER |
|  | AGRICULTURE & ANIMAL HUS- BANDARY: SVP ATTENDANT  |  0101 | 0101 |  GH MOHDGOWHAR BASHIIR |
|  | SOCIAL WELFARE | 01 NYC | 010 | SHEERAZ AH DAR |
|  | HEALTH:ASHA ANMAYUSH DOCTORALLOPATHIC DOCTOR | 01 NIL NIL | 01NILNIL |  NIGEENA AKHTER |
|  | ANY OTHER DEPARTMENT |  ------ |  --- |  ----- |

**DAY 2-ACTIVITIES**

## AGENDA NO.1

Discussion on the and assess the progress of different schemes relating to the localized SDGs prior- itized for that village as per the resolution passed by that Gram Panchayat on 21st April 22, on National Panchayati Raj Day (Copy of the resolution to be taken from [www.jkpanchayat.in](http://www.jkpanchayat.in/) portal under the link of Gram Swaraj Month)

* 1. SDGs AGREED FOR THAT VILLAGE, TO BE IMPLEMENTED BY MARCH2024:
	2. STATUS OF WORKS UNDER THE FOLLOWING SCHEMES:

## Clean and green village

1. Initiatives taken by the Panchayat for managing Solid and Liquid Waste AWARENESS LECTURE WAS GIVEN
2. Initiatives taken by the Panchayat for using green sources of fuel like solar, biogas

 YES

1. Has mapping of land use, water bodies, forest, slopes, wet lands, degraded forest within the Gram Panchayat been done? Yes/No. If No, reason, thereof YES
2. Has the Climate Resilience Plan been developed for the GP? Yes /No:YES
3. Steps taken by the Gram Sabha about the climate change mitigation factors like reducing energy consumption, usage of fossil fuels, plastics, non-renewable building materials and also to promote measures like planting of trees, conserving forests, usage of good agricultural practices like drip irrigation, water conservation measures and conservation of wetlands.YES
4. Whether schools have started segregating waste:NO
5. Whether schools have their own compost/soakage pits for solid/liquid waste management:NO

## Healthy village

1. Are meetings related to Village Health and Sanitation Committee being held regularly?:YES
2. Do all the eligible individuals been provided the Golden Card?:YES
3. Are all the Children being immunized as per the Schedule recommended by Govt. of India?:YES
4. Are all the eligible individuals been vaccinated against COVID-19? :YES
5. Does Gram Panchayat ensure that all pregnant women are getting necessary prenatal checkups? :YES
6. Whether all the deliveries were Institutionalized or conducted by trained Midwives? :YES

## Water sufficient village

1. Do all the IHHs in the Gram Panchayat have water pipeline connections? :YES
2. Whether Gram Panchayat has taken steps for grey water management. If Yes please specify :NO
3. Do all the IHHs in the Gram Panchayat have toilets? :YES
4. Are all the IHHs toilets functional or not? FUNCTIONAL
5. Do all the Schools/Anganwadi centers have a toilet facility or not? :YES
6. Are all the toilets in the schools/Aaganwadi functional or not?:YES
7. Whether Gram Pachachayat Bhawan has separate toilets for women or not:NO

## Child Friendly village

1. Do all the children under the age of 0-6 years been enrolled in the Anganwadi centers for pre- schooling? Yes/NO:YES
2. How many Bal Sabha’s were organized in the Gram Panchayat----- 02--------------
3. Whether the issues raised by Bal Sabha are addressed during the Gram Sabha. Yes/NO:YES
4. Whether Gram Panchayat is tracking the data related to dropout children and children with irregular attendance? Yes/NO:NO
5. Do all the schools under the Gram Panchayat have separate toilets for girls and boys? Yes/No:NO

## Village with good governance

1. Is CSC located in the Gram Panchayat Bhawan or not?:YES
2. Is the list of beneficiaries related to the Schemes/Programs displayed on the Gram panchayat wall or not?:YES
3. Does the Gram Panchayat has its building or not?:YES
4. Is the Gram Panchayat office functional or not?:FUNCTIONAL
5. Are the activities approved under the Halqa Panchayat Development Plan displayed on the Gram Panchayat wall or not?:YES
6. Is Social Audit of earlier Schemes/Programs carried out or not?:YES

## Poverty free and enhanced livelihood village

1. Has Gram Panchayat developed any criteria for the identification of the poor? Yes/No if yes specify:YES(HSGS)
2. Have all the eligible households registered in PDS or not? :YES
3. Has Gram Panchayat provided space for Self-help Groups in PanchyatGhar for holding meetings or not? :YES
4. Have all the eligible households been registered for Pension or not? :YES
5. Has Gram Panchayat facilitated Youth for Skill Enhancement Courses and Placement? :YES
6. Has Job Cards been distributed to all the eligible individuals under MGNREGA? :YES
7. Has Gram Panchayat facilitated SHGs for Bank Account Linkages? :YES

## Socially secured village

1. Whether Gram Panchayat is maintaining data related to Differently Abled People? :YES
2. Is Gram Panchayat Office Disabled Friendly or not? YES
3. Are provisions for a separate Budget under the Resource Envelope for Women and Children made or not? : YES
4. Do all the Schools in the Gram Panchayat have facilities for Differently Abled Children like toilets, barrier-free access, etc., or not?: YES
5. Are all the eligible individuals are getting pensions, like old age pension, widow pension, etc?:YES
6. Are all the eligible households getting benefits from IAY or not? YES

 NOT AT ALL

## Engendered Development in Village

1. How many Mahila Sabha’s were organized in the Gram Panchayat-------------02------
2. Whether SHGs federations have been provided space for meetings in the Panchayat Bhawan (Yes/ No):YES
3. Whether GPs have taken steps for increasing women’s participation in Gram Sabha(Yes/No):YES
4. Number of women beneficiaries headed households covered under PDS system……… 09………………
5. Number of beneficiaries (out of total eligible population) receiving social protection benefits under Pradhan Mantri Matritva Vandana Yojana …64…………….
6. Self-sufficient infrastructure in the village
7. Whether GP has a Community Hall with access to electricity, furniture, water supply, toilet……NO………………….
8. Whether the Disaster management plan is available at the GP Level (Yes/No):NO
9. Whether child-friendly park with required facilities is available in GP (Yes/No) :NO
10. Whether the GP has easy access to Godown for storage (Yes/No) : YES
11. Whether street lights are provided in public places for ensuring safety (Yes/No):NO

# DAY 2 ACTIVITIES

## AGENDA NO.2

Sensitize village residents about myScheme” portal (myscheme.in) which includes information about all the schemes being run by Central/ State/ UT govt across the country

*(Scheme Material available from https://jkpanchayat.in/b2v4.php)*

# DAY 2 ACTIVITIES

## AGENDA NO.3

Hold meeting of the Biodiversity Management Committees to deliberate on issues pertaining to conserva- tion of biodiversity and sustainable utilization of biological resources. He should check People Biodiversity register (PBR) of that panchayat and review if Biodiversity Management Committee constituted for that panchayat is holding minimum 4 meetings in a year and meeting once in every 3 months *(Role of BMC available at https://jkpanchayat.in/b2v4.php)*

COMMITTEE MEMBERS PRESENT

BIODIVERSITY REGISTER PHOTOS

PAST 4 MEETING DETAILS- DATES, MINUTES PHOTOS

# DAY 2 ACTIVITIES

## AGENDA 4

Visiting officer shall also plan and conduct panchayat level convergence meeting of all departments and prepare Village development plan for village, in consultancy with Gram panchayat, discuss it in gram sabha and get it approved.

(GPDP format available on https://jkpanchayat.in/b2v4.php)

## In addition GPDP plan shall also include :

Tourist places which need to be developed:

02

Specific product which needs to be developed : PASHMINA SHAWLS

Tourism- home stays: NO SUCH FACILITY AVAILABLE

20 candidates for training under Himayat scheme alongwith trade in which training is to be given: YOUTH WERE MOTIVATED ABOUT THE SCHEME AND THEY VOWED TO OPT FOR THE SCHEME.

# DAY 2 ACTIVITIES

## AGENDA 5

Ensure saturation of following schemes and give status:

|  |  |  |  |
| --- | --- | --- | --- |
| **NAME OF THE SCHEME** | **TOTAL ELIGIBLE BENEFICIARIES IN THE VILLAGE** | **TOTAL BENEFICIARIES WHO****AVAILED THE BENEFITS OF THE SCHEME** | **REASONS FOR PENDENCY** |
| Golden Health Card under Ayushman Bharat | 977 | 977 |  |
| Janani suraksha yojana | NIL | NIL | NIL |
| OLD AGE pension | 80 | 80 | - |
| Widow pension | 20 | 20 | - |
| Disability pension | 38 | 38 | - |
| Domicile certificate | 39 | 39 | 0 |
| Kisan credit card | 21 | 21 | 0 |
| PM kisan sammannidhi | 14  | 14 | 0 |

|  |  |  |  |
| --- | --- | --- | --- |
| Land pass book | 30 | 30 | 0 |
| Registration of village ven- dors on GEM portal | 03 | 03 | - |
| Registration of village con- tractors on jktenders portal | 03 | 03 | - |
| Registration of village con- tractors on PWD portal | 03 | 03 | - |
| Incomplete buildings/pro- jects | NO | NO | NO |

# DAY 2 ACTIVITIES

## AGENDA 6

**NASHA MUKT ABHIYAN**

1. Whether gram sabha resolution passed:YES
2. Details of activities conducted: 10
3. Whether all activities and GS resolution uploaded on jkpanchayats.in portal YES
4. How many drug addicts in the village:NIL
5. Whether reported to the Deputy Commissioner:NIL
6. How many registered for rehabilitation under government programme:NIL

# DAY 2 ACTIVITIES

## AGENDA 7 SOCIAL AUDIT

Conduct social audit of atleast 5 works each under following schemes:

|  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- |
| NAME OF THESCHEME | DETAILS OF THEWORKS | YEAR OF WORKAPPROVAL | AMOUNTAPPROVED FOR THE WORK | WHETHERWORK EXECUTED SATISFACTORILY | GEO-TAGGED PHOTOS | ANY GRIEVANCERECORDED RELATING TO THAT WORK |
| MGNREGA | IMP OF LINK ROAD NEAR H/O GH MOHD KHAN | 2021-22 | 1.26 LAC | YES | YES | NO |
| PMAY | NO CASE | N O | NO | NO | NO | NO |
| IHHLUNDER SBM-G | NO | NO | NO |  NO | NO | NO |
| CSC UNDER SBMG | CSC NEAR MAJID AT BHAGAT MOHALLA  | 2022-23 | 2.99 LAC | SATISFACTORY | YES | DOORS NNOT FITTED |
| AMRIT SAROVARS | NO | NO | NO | NO | NO | NO |

# DAY 2 ACTIVITIES

## AGENDA 8 MAHILA SABHA

Total women in the village above the age of 18: 550

Total attended Proceedings: 20 attendend

*(Pl insert pointers to be discussed there – refer palli proceedings)* **the women of village said that school is without fencing and is on the roadside , they feel there wards are not safe**

# DAY 2 ACTIVITIES

## AGENDA 9 BAL SABHA

Hold a balsabha and record proceedings

Total children in the village above the age of …200

.. Total attended:20

Proceedings:ISSUES PERTAINING TO THEM LIKE PLAYFIELD ETC WERE DISCUSSED.

*(Pl insert pointers to be discussed there – refer palli proceedings) …..***the youth demanded a play field at kareva and a road from village to the play field**

# DAY 2 ACTIVITIES

**AGENDA 10 INAUGURATIONS**

|  |  |  |  |
| --- | --- | --- | --- |
| **SR NO.** | **ASSETS /ACTIVITIES INAUGRATED** | **STATUS OF THE ASSET/AC- TIVITIES (NUMBER, OTHER DETAILS)** | **GEO-TAGGED PHOTOS** |
|  | VILLAGE HAAT under JKSRLM (SUN- DAY MARKET) |  NIL |  NIL |
|  | PMAY houses if any ready for inaugra- tion |  NIL |  NIL |
|  | Swachh gram projects- segregation sheds etc |  NIL |  NIL |
|  | Amrit sarovars | Nil | nil |
|  | Sports kits | NO | NO |
|  | Village cultural events | 01 | 01 |
|  | JJM assets/projects |  NO | NO |
|  | Any other to be identified at district level | NO | NO |

# FOLLOW UP OF (B2V1, B2V2 & B2V3):

*(Pre filled excel sheet to be taken from district level/ and also to be downloaded from www.jkpanchayat.in)*

|  |  |  |  |
| --- | --- | --- | --- |
| S.NO. | Particulars | Action taken | Remarks # |
| I. Urgent Public Requirements/ Demands- B2V1 |
| 1 | WIDENING OF ROAD FROM WANPORA TO KULTREH | NO ACTION TAKEN YET | SHOULD BE DONE |
| 2 | 5 NO. CULVERTS AT TN PORA SARBAND  | NO ACTION TAKEN YET | SHOULD BE DONE |
| 3 | CONSTR. OF ROAD FROM SARBAND TO ONWARDS | NO ACTION TAKEN YET | SHOULD BE DONE |
| 4 |  |  |  |
| 5 |  |  |  |
| 6 |  |  |  |
| 7 |  |  |  |
| II. Urgent Public Requirements/ Demands- B2V2 |
| 1 | PRIMARY HEALTH CENTRE  |  NO ACTION TAKEN YET | SHOULD BE DONE |
| 2 | ANIMAL HUSBANDRY AND ICDS CENTRE AT MUKDAM MOHALLA AND BHAGAT MOHALA | NO ACTION TAKEN  | SHOULD BE DONE |
| 3 | WATER CANAL FROM LIFT IRRIGATION MARVAL VIA VILLAGE NEHAMA TO WANPORA HUNIPORA |  NO ACTION TAKEN | SHOULD BE DONE |
| 4 | DRINKING WATER SUPPLY FACILITY FROM INDRAAZ NAAG | NO ACTION TAKEN | SHOULD BE DONE |
| 5 | REPLACEMENT OF MAIN PIPELINE FROM RABITAR TO NOWPOPRA. | NO ACTION TAKEN | SHOULD BE DONE |
| 6 | UPGRADATION OF BPS WWANPORA AND GPS WANPORA  | NO ACTION TAKEN | SHOULD BE DONE |
| 7 | WIRIG AND POLES AT DIFFERENT SPOTS OF TN PORA | NO ACTION TAKEN | SHOULD BE DONE |
| S.NO. | Particulars | Action taken | Remarks # |
| III. Major Problems – B2V1 |
| 1 |  DRINKING WATER FACILITY AT TNPORA  |  NOT TAKEN  | SHOULD BE DONE |
| 2 | POOR ELECTRIC INFRATUCTURE  |  NOT TAKEN  | SHOULD BE DONE |
| 3 |  NON- AVAILIBILTY OF HEALTH CENTRE AT TNPORA |  NO ACTION TAKEN  | SHOULD BE DONE |

|  |  |  |  |
| --- | --- | --- | --- |
| 4 | NON AVAILIBILTY OF OF ANIMAL HUBANDRY |  NO ACTION TAKEN | SHOULD BE DONE |
| 5 | NON AVAILABILITY OF ICDS CENTRES  |  NO ACTION TAKEN | SHOULD BE DONE |
| IV. Major Problems- B2V2 |
| 1 |  RPELACEMNET OF PIPELINE FROM RABITAR TO TN PORA | NO ACTION TAKEN | SHOULD BE DONE |
| 2 | POOR ELCTRIC INFRASTURE | NO ACTION TAKEN | SHOULD BE DONE |
| 3 | NON AVILABILITY OF HEALTH CENTRE | NO ACTION TAKEN | SHOULD BE DONE |
| 4 |  |  |  |
| 5 |  |  |  |
| V. Major Problems- B2V3 |
| 1 | THERE IS NO PHC IN THE PACH. HALQA  |  NO ACTION TAKEN | SHOULD BE DONE |
| 2 | ELECTRIC SUPPLY IS NOT GOOD. |  NO ACTION TAKEN | SHOULD BE DONE |
| 3 | NON AVAILBILITY OF DRINKING WATER | NO ACTION TAKEN | SHOULD BE DONE |
| 4 | ENCHROACHMENT OF SCHOOL LAND NAMELY PRY. SCHOOL TUMCHI NOWPORA. | NO ACTION TAKEN | SHOULD BE DONE |
| 5 |  |  |  |
| VI. Major Complaints- B2V1 |
| 1 | POOR ELCTRIC INFRASTURE  |  NO ACTION TAKEN | SHOULD BE DONE |
| 2 | UNHYGIENIC CONDITION AT WATER RESERVOIR BUILDING  | NO ACTION TAKEN | PEOPLE ARE UNSATISFIED |
| 3 |  |  |  |
| VII. Major Complaints- B2V2 |
| 1 | REPLACEMENT OF PIPELINE FROM RABITAR TO TNPORA  |  ACTION TAKEN |  SATISFACTORY |
| 2 |  IMPROPER IDENTIFICATION AND DISTRIBUTION OF WORK |  RESOLVED | JUSTICE WITH PEOPLE |
| 3 |  |  |  |
| VIII. Major Complaints- B2V3 |
| 1 | INSUFFICIENT DRINKING WATER | PENDING | UNSATISFACTORY |
| 2 | POOR ELECTRICITY | PENDING | UNSATISFACTORY |
| 3 |  |  |  |

# OVERALL PERCEPTION OF FUCNTIONING OF GOVERNMENT DEPARTMENTS

## BEST DEPARTMENT:

1. **LEAST RESPONSIVE DEPARTMENT:**

# GENERAL ASSESSMENT OF THE VISTING OFFICER

|  |  |
| --- | --- |
| I | Any major complaint brought to the notice of the Visiting Officer: **NEED OF PHC**  |
| II | Major/ urgent public demands that was/ were reflected earlier but have not been addressed so far: **ESTBD. ANIMAL HUSBANDRY**.  |
| III | Overall assessment of the visit and suggestions:(The visiting officer to ensure that the overall assessment is recorded in details along with concrete sugges- tions): **THERE IS DIRE NEED OF WATER SUPPLY AND ELECTRICITY** |
| IV | Overall Rating of govt functioning as given by the Panchayat (Scale of 0 to 10): ***( 08 )***  |
| V | Certificate from Sarpanch that the visiting officer has stayed in the panchayat for 2 days: |

## Signature of Sarpanch Signature of the Visiting Officer Name:FEROZ AHMAD KHAN(LUMBERDAR) Name:MOHD SHAFI RATHER

 **GENERAL ASSESMENT OF VISITIG OFFICER :**

 **1** THE SCHOOL GMS TUMCHINOWPORA IS ON THE ROADSIDE AND IS IN NEED OF FENCING . THE SCHOOL IS HAVING A GOOD PLAYINGFIELD . THE SCHOOL MAY KINDLY BE UPGRADED . THERE IS ALSO ENCHROACHMENT OF SCHOOL LAND , NECESSARY ACTION MAY KINDLY BE TAKEN.

2.THERE IS A CANAL FLOWING ALOONG THE RABTAR KUTRI ROAD. THE FP BUND MAY KINDLY BE CONSTRUCTED ON BOTH SIDES OF CANAL.

3.THERE IS INSUFFICIENT DRINKING WATER IN THE PANCH. HALQA ; THE PEOPLE WANTS CLEAN AND SUFFICIENT DRINKING WATER SUPPLY.

4. THE CONDITION OF ELECTRIC SUPPLY IS NOT PROPER. THE POLES AND WIRE IS IN BAD CONDITION.

**Department of Rural Develompent and Panchayati Raj Government of Jammu & Kashmir**