# BACK TO VILLAGE- PHASE IV (15TH OCTOBER TO 3RD NOVEMBER )

# KEY FEATURES

* Deputy Commissioners to lead the initiative
* Rural development Department to be the nodal department
* Planning Development & Monitoring department and IT to be the support departments

# ACTIONS AND TIMELINES

|  |  |  |  |
| --- | --- | --- | --- |
| **ACTION** | **RESPONSIBILITY** | **LATEST BY** | **REMARKS** |
| Jan abhiyan | All departments | Oct 15 -25th | Going on |
| Deputation of Sectt staff/HoDs | GAD | Oct 14 | Done |
| Deployment of Staff to Panchayats and serving of orders on deployed officers | DCs | Oct 25 | DCs will deploy senior level staff from the districts. Strict action to be taken against absentations. No exemptions to be given |
| Training of district trainors on B2V4 | RDD | Oct 26 |  |
| Training of visiting officers | DCs | Oct 27 |  |
| Field Visits to be completed by | Visiting Officers | Nov 3 | DCs to supervise and ensure that each Panchayat is visited within the period specified |
| Data of B2V4 to be uploaded by | Visiting Officers | Nov 10 | DCs to supervise and ensure that data of all Panchayats is uploaded by the visiting officer within the period specified |

# INSTRUCTIONS FOR THE VISITING OFFICER (DAY WISE)

|  |  |  |
| --- | --- | --- |
| **DATE** | **INSTRUCTIONS** | **ACTION POINTS** |
| Day 0 | Meeting with deputy commissioner and his/her team | 1. Take print outs of filled booklets of B2V1, B2V2 and B2V3 from [www.jkpanchayat.in](http://www.jkpanchayat.in) 2. Also take print outs of the summarized excel sheets of the previous phases from [www.jkpanchayat.in](http://www.jkpanchayat.in) 3. Collect ATRs on issues raised during previous 3 phases from the office of Deputy Commissioner (Planning deptt) 4. Take prints of blank 2 booklets of B2V4 from [www.jkpanchayat.in](http://www.jkpanchayat.in) 5. Take plans for 2 previous years and ATRs from the planning deptt 6. Complete trainings on different components of B2V4 being organized by respective Deputy Commissioners 7. Collect List of new works started/ ongoing/ completed during the previous and current Financial year under the following heads:  * PRI grants * District Plan * UT plan * MGNREGA * Other schemes of other departments * Any other work  1. Plans/ beneficiary lists:  * MGNREGA draft plan document for the year 2022-23. * List of Awaas+ beneficiaries alongwith IHHL Convergence * List of pension beneficiaries. * List of SHGs * List of agriculture scheme beneficiaries  1. Lists of beneficiaries for:  * Various certificates/ benefits to be distributed by the visiting officer. * Any other activities identified by different departments |
| Day 1 | Reach the village | 1. Ensure that all front line workers of different deptts are present. 2. Ensure exhibition by different depts. about individual beneficiary schemes 3. Inspect JKB/PSB counters/outlets 4. Participate/ensure organization of sports activity in playfield, talent hunt/cultural event/youth activity 5. Visit atleast 2 amritsarovars and get its geo tagged photos 6. Inspect Khidmat (CSC) Centres and create Generate awareness on 225 schemes particularly G2C schemes like BEAMS, Janbhagidari, AapkiZaminAapkiNigrani, Digital J&K 7. Visiting officer shall also plan and conduct panchayat level convergence meeting of all departments 8. Check effectiveness of Centrally sponsored schemes 9. Visit and inspect all government establishments including PHE, AWC, FPS, schools, etc 10. Attempt saturation of deliverable so Janabhiyan and wherever deficiencies found, lead a drive to achieve all deliverables 11. Assess effectiveness of sanitation campaign in the panchayat 12. Ensure self employment activities for 15 youth per panchayat 13. Wherever possible, distribute employment letters for people selected under various government employments 14. In the evening, hold inormal meeting with senior citizens, govt employees including retired employees, ex servicemen, youth club, and any citizens of the village who are enrolled in college/university 15. Open discussion on Nasha Mukt Abhiyan |
| Day2 | Have a meeting with all stakeholders- deptt officials and panchayat members | 1. Discussion on the and assess the progress of different schemes relating to the localized SDGs prioritized for that village as per the resolution passed by that Gram Panchayat on 21st April 22, on National Panchayti Raj Day. 2. **Sensitize village residents about myScheme” portal (myscheme.in)** which includes information about all the schemes being run by Central/ State/ UT govt across the country 3. Hold meeting of the **Biodiversity Management Committees** to deliberate on issues pertaining to conservation of biodiversity and sustainable utilization of biological resources. 4. Prepare Village development plan, in consultancy with Gram panchayat, discuss it in gram sabha and get it approved. 5. Ensure saturation of soil health card and golden health card under **Golden Health Card under Ayushman Bharat**, 6. Ensure saturation of **Old Age Pension Scheme** 7. Ensure Domicile Saturation. 8. Ensure KCC Saturation 9. Ensure saturation of land pass books 10. Ensure registration of village vendors needed for any scheme, on GEM portal 11. Ensure panchayat contractors registration 12. Encourage Panchayat members for importance of plantation drive in Panchayat under Har Gaon Hariyali 13. Ensure painting on digital J&K in panchayat ghars 14. Ensure painting on panchayat activites and CSS in panchayat ghars 15. The visiting office shall check no of kindergarten and playfields present in the panchayat for kids and students, if the infrastructure present in these are good enough. 16. Hold meeting with panchayat members to discuss about corruption menace and steps required to make J&K corruption free 17. Obtain a candid assessment about performance of various deptts including fair feedback about discrepancies in functioning 18. Check the status of Nasha Mukt Abhiyan and reporting of drug addicts to Deputy Commissioner. 19. Identify Tourist Destinations, Circuits, Theme Treks, Identify Homestays, provide support for tourism activities through Village Cooperative 20. Organize Talent Hunt at Panchayat Level 21. Conduct social audit of atleast 5 works under following schemes:     1. MGNREGA     2. PMAY     3. IHHL toilets and payments     4. CSCs     5. AMRIT SAROVARS 22. Hold a mahilasabha and a balsabha and record proceedings in the format given 23. Inaugurate village haat under JKSRLM 24. Check if youth clubs are formed in the panchayat and what activities they are engaged in 25. Organize a village level cultural event to engage panchayat members 26. Sensitize GP about E-kitab kosh an initiative of J&K Govt for empowering youths through online digital literacy |

# GENERAL INSTRUUTIONS

1. The visiting officer shall refrain himself/ herself giving or offering any commitment on behalf of the government and shall adopt an unbiased attitude in reporting issues. As far as possible, his/her observation should be based on a fair and analytical view emerging from his/her interaction in the village.
2. He is going to the village as planning officer, not for sanctioning any works or for making any commitments.
3. While preparing village development plan, he has to ensure that, demands are prioritized and reflected under available schemes, wherever necessary the larger works are to be referred to administrative deptt under CSS/UT plans under intimation to DCs and rest of the works to DCs for reflecting it under district/CSS plans
4. His work shall be hard core planning and audit and is not a PR exercise.
5. **Focus of visit are youth, skills, self-employment, nasha mukt, bhrashtrachar mukt, Rozgar yukt J&K, besides to carry forward the activities during Jan Abhiyan and saturate them.**
6. **In addition attention may be given to the following areas**
   1. Make full use of Centrally Sponsored Schemes
   2. Saturation of individual beneficiary schemes
   3. Self-employment schemes
   4. Bank linked schemes- including departmental subsidy schemes
   5. Empowerment and transparency through digital initiatives
   6. Effectiveness of grass roots machinery –
      1. Patwari, VLW present and available
      2. Available funds utilized in public interest and as per Gram Sabha resolutions
      3. Fairness in governance
      4. CSS/Individual beneficiary schemes etc
      5. BrashtacharMukt J&K
      6. Bhai Mukt J&K
      7. NashaMukt J&K
7. The PRI members (Sarpanchs, Panchs, BDC Chairperson) shall be kept at the forefront of all activities and given due importance and the approach should be to strengthen them and make them feel empowered. He/she shall ensure that the BDC chairperson and Sarpanch/Panch are present at the time of inauguration and ceremonies.
8. The visitingofficer shall ensure that COVID protocols are strictly followed during the visits.

## BACK TO VILLAGE (B2V4) October 27th to November 3rd

### A) DetailsofReportingOfficer:

Name: \_MUSHTAQ AHMAD GANAI.

Designation: Incharge Headmaster

Department/Education .Place of posting: Govt. High School Hapatnard.

Mobile No: 7889814016

#### Email ID: [mushtaqah.ganie1@gmail.com](mailto:mushtaqah.ganie1@gmail.com)

Home District: \_\_ Anantnag

Dates of visit: \_\_02 November 2022

**B)LocationaldetailsofPanchayat: (to be pre-filled, information to be taken from the previous phases booklets/summarized excel sheet uploaded on** [**jkpanchayat.in**](http://www.jkpanchayat.in)**/b2v4.php ) (to be validated by the visiting officer and missing details to be filled)**

Name of the Panchayat: \_\_ Hapatnard B

##### Local Government Directory(LGD) code of the Panchayat: 242643

Name of CD Block: KHOVRIPORA

Name of Tehsil: PAHALGAM

Name of District: ANANTNAG

###### C)PanchayatProfile:

No. of revenue villages in the Panchayat: 01

No. of hamlets in the Panchayat ;-07

No. of households in the Panchayat: 503

Population (approx) of the Panchayat: 3018 (Approx)

**PartII : (To be filled up by the Visiting Officer during his/her two day visit to the Panchayat. All Fields have to be filled by the Visiting Officer before the booklet is handed over to the DC**

###### FrontlineOfficers/Officialswhowereassignedtothe Panchayatfortheprogramme:

|  |  |  |
| --- | --- | --- |
| **Department** | **Name** | **Designation** |
| RDD | Ishfaq Yaseen Shah | GRS |
| Education | Abdul Hameed Khan | Teacher |
| PDD | Muzaffer Hussain Ganie | TDL/PDL |
| Agriculture | Javaid Ahmad Malik | JAFFO |
| Handicrafts | Javaid Ahmad Ganaie | JCI |
| PHE | Mohd Altaf Bhat | Fitter |
| NRHM | Ab. Rashid Khan | CRP |
| ICDS | Shabnum Akhter | AWW |
| CAPD | Shakeel Ahmad Baba | Store Keeper |
| R&B | Bashir Ahmad Mir | Road Worker |
| Sericulture | Farooq Ahmad Khan | Mulberry Guard |
| PR | Kaka Bashir | PR |
| Health | Dr. Abdul Rasheed | Medical Officer |

###### Detailsofabsentemployeesvis-à-vislistfurnished bytheDC office:

|  |  |  |
| --- | --- | --- |
| **Department** | **Name** | **Designation** |
| NIL | NIL | Nil |

DAY 1 ACTIVITIES

# AGENDA 1: PANCHAYAT ASSET REGISTER

**Infrastructure:**

1. Panchayat Ghar Infrastructure :-private building needing repairs.
2. Furniture (Y)
3. Computer/printer (N)
4. Internet (N)
5. Telephone (N)
6. Toilet (CSC/part of panchayat ghar) (Y) Under Construction.
7. Water (N)
8. Electricity (N)
9. Bank branch (N)
10. CSC (Y)
11. Patwarkhana (N)
12. Village haat (N)
13. Playground (N)
14. School-
15. Kindergarten (N)
16. Primary (Y)
17. Secondary (N)
18. College (N)
19. University (N)
20. Anganwadi Centre (Y)
    1. (govt in private building)
    2. Total children enrolled:-150

15. Amrit Sarovars – details, location, condition :- No

16. Government offices- details, whether functional or not

17. Ration shop (Y)

18. Places of tourism importance – names, little details on historical/cultural importance:- No

19. Village heritage sites/ treks- names, little details on historical/cultural importance:- Anganpathri, Lawenpathri, Chithri Madan

20.VLW Office (N)

21. Primary Healthcare Centre (N),

22. List of Incomplete Buildings- names, year of construction

23. List of Underutilized Buildings- Not avilable

# DAY 1 ACTIVITIES

# AGENDA 2: DIFFERENT INSTITUTIONS/INFRASTRUCTURE PROJECTS TO BE VISITED

|  |  |  |
| --- | --- | --- |
| AMRIT SAROVARS | Visit, verify | Comments |
| KhidmatCentres and 4. | create Generate awareness on 225 schemes particularly G2C schemsAapkiZaminAapkiNigrani, Beams, janbhagidari, digital J&K | Satisfactory |
| CSC counters/JKB/PSB counters/outlets | a) Status of counter  b) Number of visitors | Nil. Least response |
| INCOMPLETE BUILDINGS/PROJECTS | Verify whether identification and redistribution done | Satisfactory |
| PDS | Visit, evaluate, online status | Satisfactory |
| PHC | Visit- evaluate, status of staff, equipment and quality | Satisfactory |
| YOUTH CLUBS | Meet, interact, seek suggestions | Satisfactory |
| SHG | Meet, identify problems, seek suggestions | Satisfactory |
| PMAY | Inspect, Inaugurate | Satisfactory |
| MY SCHOOL, MY PRIDE PROGRESS; SCHOOLS- WATER, TOILETS, STAFF | Visit, check for water, electricity, sanitation, meet students and staff | Excellent,  Except Staff Strength. |
| SWACHH GRAM SBM | Evaluate | Satisfactory |
| PANCHAYAT PLAY GROUND  SPORTS KITS DISTRIBUTION  VILLAGE GAMES | Ensure, verify. Participate in at least one game in the playground | UnSatisfactory |
| HAR GAON HARIYALI , PLANTATION DRIVE | Evaluate status, feedback | Satisfactory |
| VILLAGE CULTURAL EVENT  DANGAL/HAAT/MELA | Participate in; ensure that it is held | Satisfactory |
| EXHIBITION OF SCHEMES | Ensure that every department participates and that it continues for the entire duration of B2V | Satisfactory |
| JAL JIWAN MISSION VERIFICATION- WSS/JSD  ELECTRICITY SUPPLY | Verify | Satisfactory |

# DAY 1 ACTIVITIES

## AGENDA 3: SATURATE JAN BHIYANDELIVERABLES AND RECORD DEFICIENCIES IF ANY

**DAY 1 ACTIVITIES**

**AGENDA 4:**

## SELF EMPLOYMENT ACTIVITIES

**Ensure Self-employment activities for youth, distribute employment letters for people selected under various social schemes:**

Number of cases in different categories sanctioned :- Nil

Details of the bank sanctioning it :- Nil

Total amount involved :- Nil

# DAY 1 ACTIVITIES

# AGENDA 5

* In the evening, hold informal meetings with senior citizens , govt employees, retd employees , youth club and other citizens who are enrolled on college/university and have discussion on Nasha Mukt Abhiyan, corruption free governance, doubling farmers income and record their suggestions

# DAY 2

**Check functionality of panchayats (data filled in the excel sheet and B2V1-3 reports to be validated and gaps to be filled) insert the link**

1. Maintenance of records: Gram Sabha registers(7 registers): yes
2. Social Audit Committee details
3. Swachta Status – Village is ODF or ODF +
4. *MGNREGA/SBM convergence*
   1. *No of Individual Compost Pits constructed:362 out of 382*
   2. *No of Individual Soak Pits constructed;50*
5. No.ofBiodiversity management committee meetingsheld: Nil
6. IsthenameofSarpanchdisplayedoncitizeninformationboardsofallRD&PRschemes:Yes
7. AreSarpanchsbeinginvolvedinstart/inaugurationofactivities:Yes
8. Whethersubjectshavebeenassignedbythe Sarpanchtothe Panchs:Yes
9. Whethergrievancesredressalboxisinstalled:Yes
10. NoofgrievancesreceivedpertainingtoPanchayatlevel: Nil
11. NoofgrievancesdisposedofatPanchayatleve: Nil
12. Whetherthe Sarpanch/PanchayatSecretaryhavedigitalsignatures:Yes
13. Whether all MGNREGA/ 14th FC payments are being made by Sarpanch through Digital Signature Certificate (DSC): Yes

# HUMAN RESOURCE AVAILABLE AT THE PANCHAYAT LEVEL:

|  |  |  |  |  |
| --- | --- | --- | --- | --- |
| SR NO. | DEPARTMENT WISE STAFF | NUMBERS | | NAMES |
|  |  | SANCTIONED | ACTUAL |  |
|  | Rural development department:  BDO  JE  GRS  TA |  |  | Ashfan Ali Khan  Sajad Hussain Dar  Ishfaq Yaseen Shah  Aijaz Hussain Sheikh |
|  | SCHOOL EDUCATION:  Teacher  Head master  Any other |  |  | Abdul Hameed Khan |
|  | JAL JEEVAN |  |  | Nisar Ahmad Ganie, Supervisor |
|  | PDD:  LINEMAN  JE  Any other |  |  | Bashir Ahmad Sheikh |
|  | FOOD & CIVIL SUPPLIES |  |  | Shakeel Ahmad Baba |
|  | AGRICULTURE & ANIMAL HUSBANDARY |  |  | Javaid Ahmad Malik  Agriculture AEA |
|  | SOCIAL WELFARE |  |  | Chodary Waseem |
|  | HEALTH:  ASHA  ANM  AYUSH DOCTOR  ALLOPATHIC DOCTOR |  |  | Lal Jan & Shaheena |

# DAY 2 ACTIVITIES

**AGENDA NO.1** Discussion on the and assess the progress of different schemes relating to the localized SDGs prioritized for that village as per the resolution passed by that Gram Panchayat on 21st April 22, on National PanchayatiRaj Day **(Copy of the resolution to be taken from** [**www.jkpanchayat.in**](http://www.jkpanchayat.in) **portal under the link of Gram Swaraj Month)**

1. SDGs AGREED FOR THAT VILLAGE, TO BE IMPLEMENTED BY MARCH2024:
2. STATUS OF WORKS UNDER THE FOLLOWING SCHEMES:

## 1 Clean and green village

1. Initiatives taken by the Panchayat for managing Solid and Liquid Waste Plan Projected
2. Initiatives taken by the Panchayat for using green sources of fuel like solar, biogas :NIl
3. Has mapping of land use, water bodies, forest, slopes, wet lands, degraded forest within the Gram Panchayat been done? No. If No, reason, thereof Not taken by concerned authorities.
4. Has the Climate Resilience Plan been developed for the GP? No
5. Steps taken by the Gram Sabha about the climate change mitigation factors like reducing energy consumption, usage of fossil fuels, plastics, non-renewable building materials and also to promote measures like planting of trees, conserving forests, usage of good agricultural practices like drip irrigation, water conservation measures and conservation of wetlands.
6. Whether schools have started segregating waste :Yes
7. Whether schools have their own compost/soakage pits for solid/liquid waste management

Yes/ under construction

1. **Healthy village**
2. Are meetings related to Village Health and Sanitation Committee being held regularly? No.
3. Do all the eligible individuals been provided the Golden Card? No.
4. Are all the Children being immunized as per the Schedule recommended by Govt. of India? Yes.
5. Are all the eligible individuals been vaccinated against COVID-19? Yes.
6. Does Gram Panchayat ensure that all pregnant women are getting necessary prenatal checkups? Yes.
7. Whether all the deliveries were Institutionalized or conducted by trained Midwives? Yes.

## 3 Water sufficient village

1. Do all the IHHs in the Gram Panchayat have water pipeline connections? No.
2. Whether Gram Panchayat has taken steps for grey water management. If Yes please specify.yes. through soaking pits.
3. Do all the IHHs in the Gram Panchayat have toilets? Yes.
4. Are all the IHHs toilets functional or not? Yes.
5. Do all the Schools/Anganwadi centers have a toilet facility or not? Not.
6. Are all the toilets in the schools/Aaganwadi functional or not? Yes.but some need to be renovated.
7. Whether Gram Pachachayat Bhawan has separate toilets for women or not? Not.

## 4 Child Friendly village

1. Do all the children under the age of 0-6 years been enrolled in the Anganwadi centers for pre-schooling? Yes.
2. How many Bal Sabha’s were organized in the Gram Panchayat:- 01
3. Whether the issues raised by Bal Sabha are addressed during the Gram Sabha. Yes.
4. Whether Gram Panchayat is tracking the data related to dropout children and children with irregular attendance? NO.
5. Do all the schools under the Gram Panchayat have separate toilets for girls and boys? yes.

## 5 Village with good governance

1. Is CSC located in the Gram Panchayat Bhawan :- Yes.
2. Is the list of beneficiaries related to the Schemes/Programs displayed on the Gram panchayat wall or not? Yes.
3. Does the Gram Panchayat has its building or not? Yes under construction.
4. Is the Gram Panchayat office functional or not? Not.
5. Are the activities approved under the Halqa Panchayat Development Plan displayed on the Gram Panchayat wall or not?Yes.
6. Is Social Audit of earlier Schemes/Programs carried out or not? Yes.

## 6 Poverty free and enhanced livelihood village

1. Has Gram Panchayat developed any criteria for the identification of the poor? Yes/No if yes specify . Yes, Houseless and Homeless.
2. Have all the eligible households registered in PDS or not? Yes.
3. Has Gram Panchayat provided space for Self-help Groups in PanchyatGhar for holding meetings or not? Not.
4. Have all the eligible households been registered for Pension or not? Not.
5. Has Gram Panchayat facilitated Youth for Skill Enhancement Courses and Placement?Yes.
6. Has Job Cards been distributed to all the eligible individuals under MGNREGA? Yes,
7. Has Gram Panchayat facilitated SHGs for Bank Account Linkages? Yes.

## 7 Socially secured village

1. Whether Gram Panchayat is maintaining data related to Differently Abled People? Yes.
2. Is Gram Panchayat Office Disabled Friendly or not? Not yet.
3. Are provisions for a separate Budget under the Resource Envelope for Women and Children made or not? Not.
4. Do all the Schools in the Gram Panchayat have facilities for Differently Abled Children like toilets, barrier-free access, etc., or not? Yes.
5. Are all the eligible individuals are getting pensions, like old age pension, widow pension, etc? Yes.
6. Are all the eligible households getting benefits from IAY or not? Yes.

# DAY 2 ACTIVITIES

## AGENDA NO.2

**Sensitize village residents about myScheme” portal (myscheme.in) which includes information about all the schemes being run by Central/ State/ UT govt across the country**

**(Scheme Material available from** [**https://jkpanchayat.in/b2v4.php**](https://jkpanchayat.in/b2v4.php)**)**

# DAY 2 ACTIVITIES

## AGENDA NO.3

**Hold meeting of the Biodiversity Management Committees to deliberate on issues pertaining to conservation of biodiversity and sustainable utilization of biological resources. He should check People Biodiversity register (PBR) of that panchayat and review if Biodiversity Management Committee constituted for that panchayat is holding minimum 4 meetings in a year and meeting once in every 3 months(Role of BMC available at** [**https://jkpanchayat.in/b2v4.php**](https://jkpanchayat.in/b2v4.php)**)**

### COMMITTEE MEMBERS

PRESENT

BIODIVERSITY REGISTER PHOTOS

PAST 4 MEETING DETAILS- DATES, MINUTES PHOTOS

# DAY 2 ACTIVITIES

## AGENDA 4

**Visiting officer shall also plan and conduct panchayat level convergence meeting of all departments and prepare Village development plan for village, in consultancy with Gram panchayat, discuss it in gram sabha and get it approved.**

**(GPDP format available on** <https://jkpanchayat.in/b2v4.php>)

In addition GPDP plan shall also include :

* Tourist places which need to be developed
* Specific product which needs to be developed
* Tourism- home stays

# DAY 2 ACTIVITIES

## AGENDA 5

###### Ensure saturation of following schemes and give status:

|  |  |  |  |
| --- | --- | --- | --- |
| **NAME OF THE SCHEME** | **TOTAL ELIGIBLE BENEFICIARIES IN THE VILLAGE** | **TOTAL BENEFICIARIES WHO AVAILED THE BENEFITS OF THE SCHEME** | **REASONS FOR PENDENCY** |
| **Golden Health Card under Ayushman Bharat** | **2100** | **1900** | **Adhar updation issue.** |
| **Janani suraksha yojana** | **500** | **500** | **Nil** |
| **OLD AGE pension** | **216** | **216** | **Nil.** |
| **Widow pension** | **66** | **66** | **Nil.** |
| **Disability pension** | **75** | **75** | **Nil.** |
| **Domicile certificate** | **700** | **700** | **Nil.** |
| **Kisan credit card** | **414** | **414** | **Nil.** |
| **PM kisan sammannidhi** | **311** | **311** | **Nil.** |
| **Land pass book** | **819** | **160** | **Nil.** |
| **Registration of village vendors on GEM portal** | **16** | **16** | **Nil.** |
| **Registration of village contractors on jktenders portal** | **Nil.** | **Nil.** | **Nil.** |
| **Registration of village contractors on PWD portal** | **Nil.** | **Nil.** | **Nil.** |
| **Incomplete buildings/projects** | **Nil.** | **Nil.** | **Nil.** |

# DAY 2 ACTIVITIES

## AGENDA 6

## NASHA MUKT ABHIYAN

1. Whether gram sabha resolution passed:- Yes.
2. Details of activities conducted:-Meeting conducted as Nasha Mukt Abhiyan Diwas at GP level.
3. Whether all activities and GS resolution uploaded on jkpanchayats.in portal:- Yes.
4. How many drug addicts in the village:-Nil.
5. Whether reported to the Deputy Commissioner:- N.A
6. How many registered for rehabilitation under government programme:- N.A

# DAY 2 ACTIVITIES

## AGENDA 7

## SOCIAL AUDIT

Conduct social audit of atleast 5 works under following schemes:

|  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- |
| NAME OF THE SCHEME | DETAILS OF THE WORKS | YEAR OF WORK APPROVAL | AMOUNT APPROVED FOR THE WORK | WHETHER WORK EXECUTED SATISFACTORILY | GEO-TAGGED PHOTOS | ANY GRIEVANCE RECORDED RELATING TO THAT WORK |
| MGNREGA | Drain from House of Bashir Mushtaq to Manzoor Ah. At Khak Mohalla | 2021-2022 | 2.99989 | Yes | Yes | No |
| PMAY | Mohd Arif Khan s/o Feroz | 2019-2020 | First instalment +30days | Yes ongoing | Yes | No |
| IHHL UNDER SBM-G | Pervaiz Ahmad Khan s/o Ab Aziz | 2021-2022 | 12000 | Yes | Yes | No |
| CSC UNDER SBMG | NIL | NIL | NIL | NIL | NIL | NIL |
| AMRIT SAROVARS |  | NIL | NIL | NIL | NIL | NIL |
|  |  |  |  |  |  |  |

# DAY 2 ACTIVITIES

## AGENDA 8

## MAHILA SABHA

Total women in the village above the age of 18

Total attended :- 40

Proceedings:Empowerment of women

(Pl insert pointers to be discussed there – refer palli proceedings)

# DAY 2 ACTIVITIES

## AGENDA 9

## BAL SABHA

Hold a balsabha and record proceedings

Total children in the village above the age of 600

Total attended 250

Proceedings: A sound mind is found in asound body.

(Pl insert pointers to be discussed there – refer palli proceedings)

# DAY 2 ACTIVITIES

## AGENDA 10

## INAUGRATIONS

|  |  |  |  |
| --- | --- | --- | --- |
| **SR NO.** | **ASSETS /ACTIVITIES INAUGRATED** | **STATUS OF THE ASSET/ACTIVITIES (NUMBER, OTHER DETAILS)** | **GEO-TAGGED PHOTOS** |
|  | VILLAGE HAAT under JKSRLM (SUNDAY MARKET) | NIL |  |
|  | PMAY houses if any ready for inaugration | Visited under construction |  |
|  | Swachh gram projects- segregation sheds etc | NIL |  |
|  | Amrit sarovars | NIL |  |
|  | Sports kits | NIL |  |
|  | Village cultural events | Yes conducted at schools. |  |
|  | JJM assets/projects | NIL |  |
|  | Any other to be identified at district level | NIL |  |

**FOLLOW UP OF (B2V1, B2V2 & B2V3):(Pre filled excel sheet to be taken from district level/ and also to be downloaded from** [**www.jkpanchayat.in**](http://www.jkpanchayat.in)**)**

|  |  |  |  |
| --- | --- | --- | --- |
| S.NO. | Particulars | Action taken | Remarks # |
| 1. Urgent Public Requirements/ Demands- B2V1 | | | |
| 1 | Community Hall & Disaster Management at Dragdan. | No action taken | Urgent need |
| 2 | Road from Gogarwani to Anganpathri | No action taken | Urgent need |
| 3 | Bridge over nallah connecting Dragdon | No action taken | Urgent need |
| 4 | PMGSY Road Ward No 2 | No action taken | Urgent need |
| 5 | Animal Husbandry Unit at Gogaldar | No action taken | Urgent need |
| 6 | Road from High School Hapatnar to Musakeeni | No action taken | Urgent need |
| 7 | Additional class rooms to High School | No action taken | Urgent need |
| 1. Urgent Public Requirements/ Demands- B2V2 | | | |
| 1 | Play Ground at H S Hapatnard | Ist Phase Completed | Urgent need |
| 2 | J & K Bank Branch | No action taken | Urgent need |
| 3 | Upgradation of electricity | No action taken | Urgent need |
| 4 | Animal Husbandry Unit at Gogaldar | No action taken | Urgent need |
| 5 | SRTC Bus service | Fulfilled |  |
| 6 | Bridge at Syed Mohalla | Fulfilled |  |
| 7 | Upgrdation of wter Supply | No action taken |  |
| S.NO. | Particulars | Action taken | Remarks # |
| 1. Major Problems – B2V1 | | | |
| 1 | CAPD outlet at Dragdan | No Action taken |  |
| 2 | P/wall at M.S Nagbal | Fulfilled |  |
| 3 | Hospital facility at Dragden | No Action taken |  |
| 4 |  |  |  |
| 5 |  |  |  |
| 1. Major Problems- B2V2 | | | |
| 1 |  |  |  |
| 2 |  |  |  |
| 3 |  |  |  |
| 4 |  |  |  |
| 5 |  |  |  |
| 1. Major Problems- B2V3 | | | |
| 1 |  |  |  |
| 2 |  |  |  |
| 3 |  |  |  |
| 4 |  |  |  |
| 5 |  |  |  |
| 1. Major Complaints- B2V1 | | | |
| 1 | Bad condition of roads | Roads magdamised |  |
| 2 | Electricity problems | New transformer installed |  |
| 3 | Unavailability of tap water | Not fulfilled |  |
| 1. Major Complaints- B2V2 | | | |
| 1 | Bad condition of roads | Roads magdamised |  |
| 2 | Electricity problems | New transformer installed |  |
| 3 | Unavailability of tap water | Under rocess |  |
| 1. Major Complaints- B2V3 | | | |
| 1 | Non availability of Doctors at PHC | Demand fulfilled |  |
| 2 | Poor condition of roads | Roads magdamised |  |
| 3 | Poor distribution of electricity | New transformer installed |  |

# OVERALL PERCEPTION OF FUCNTIONING OF GOVERNMENT DEPARTMENTS

BEST DEPARTMENT: Rural Development Department

LEAST RESPONSIVE: J & K Bank

**GENERAL ASSESSMENT OF THE VISTING OFFICER**

|  |  |
| --- | --- |
| I | Any major complaint brought to the notice of the Visiting Officer: Non aviability of Physical Education teachers in all educational institutions. |
|  |  |
| II | Major/ urgent public demands that was/ were reflected earlier but have not been addressed so far: Up gradation of High School to Higher Secondary Level. |
|  |  |
| III | Overall assessment of the visit and suggestions: Plan and Demand attached.  (The visiting officer to ensure that the overall assessment is recorded in details along with concrete suggestions) Excellent (9). |
| IV | Overall Rating of govt functioning as given by the Panchayat (Scale of 0 to 10) |
| V | Certificate from Sarpanch that the visiting officer has stayed in the panchayat for 2 days |

Signature of Sarpanch Signature of the Visiting Officer

Name :- Zaina Banoo Name :- Mushtaq Ahmad Ganai

**Attachments**

* + - * 1. MGNREGA PLAN 2022-23

|  |  |  |  |
| --- | --- | --- | --- |
| ***SNOs*** | ***CATEGORY*** | ***NAME OF THE WORK.*** | ***ESTT COST.*** |
| ***1*** | ***Ruaral Connectivity*** | ***C/O Lane from Masjid Shareef to Syed Mohalla Ward 01.*** | ***1.5*** |
| ***2*** | ***Rural Connectivity*** | ***C/O Lane from PMGSY Road to Masjid Shareef Maidan Mohalla.*** | ***1.5*** |
| ***3*** | ***Ruaral Connectivity*** | ***C/O Lane from Block Raod to H/O Mubarak ShahWard 01.*** | ***1*** |
| ***4*** | ***Rural Connectivity*** | ***C/O Lane FHO Hidayatulla Khan to H/O Nazir Khan.*** | ***1*** |
| ***5*** | ***Ruaral Connectivity*** | ***C/O Lane with E wall from Block Road to H/O Shameema Bano wt Khan Mohalla.*** | ***1.5*** |
| ***6*** | ***Rural Connectivity*** | ***C/O Lane from PMGSY Road to H/O Gulal Khan Ward 01.*** | ***1*** |
| ***7*** | ***Rural Connectivity*** | ***C/O Lane from PMGSY Road to Bhatiakhodia.*** | ***1*** |
| ***8*** | ***Ruaral Connectivity*** | ***C/O Lane from PMGSY Road to H/O Mohd Yousuf Khan.*** | ***1*** |
| ***9*** | ***Ruaral Connectivity*** | ***C/O Link Road from Masjid Sharif to HO Sakeena at Bhat Mohalla Ward 03.*** | ***1.5*** |
| ***$10*** | ***Ruaral Connectivity*** | ***C/O Link Road from HO Noora Begum to HO Sajad Tantray.*** | ***2*** |
| ***11*** | ***Rural connectivity*** | ***C/O Lane from H/O Yousuf Khan to H/O Wali Mohd Khan at Moosakani Ward 3.*** | ***1*** |
| ***12*** | ***Rural Connectivity*** | ***Upgradation of Link Road from Xing to Jamai Masjid Pahse Ist*** | ***2*** |
| ***13*** | ***Rural Connectivity*** | ***C/O Link Road from Bridge to Aheliedees Jamaia at ward 4.*** | ***2*** |
| ***14*** | ***Rural Connectivity*** | ***C/O Lane from Block Road to H/O Ab Hamid Khan .*** | ***1*** |
| ***15*** | ***Rural Connectivity*** | ***C/O Lane FHO Muneer Tantray to Hayatullah Tantray.*** | ***1.5*** |
| ***16*** | ***Rural Connectivity*** | ***C/O Lane FLO Wakeel Tantray to Onwards at ward 5.*** | ***1*** |
| ***17*** | ***Rural Connectivity*** | ***C/O Lane FHO Mushtaq Tantray to Suderdin Tantray at ward 5.*** | ***1.5*** |
| ***18*** | ***Ruaral Connectivity*** | ***C/O Lane from Block Road to H/O Mushtaq Lone.*** | ***1.9*** |
| ***19*** | ***Rural Connectivity*** | ***C/O Lane /E Wall FLO Imran Tantray to Yaqoob Tantray at Dragdan.*** | ***1.5*** |
| ***20*** | ***Rural Connectivity*** | ***C/O Lane FHO Aziz Tantray to HO Ashraf Tantray at Dragdan.*** | ***1.9*** |
| ***21*** | ***Rural Connectivity*** | ***C/O Lane FHO Amin Tantray to HO Gh Hassan Tantray at Gogaldar.*** | ***1*** |
| ***22*** | ***Rural Connectivity*** | ***C/O Lane FHO Rashid Tantray to Nallah Gogaldar.*** | ***1.5*** |
| ***23*** | ***Rural Connectivity*** | ***C/O Lane FLO Bashir Khan to Wazir Tantray at dragdan Ward 7.*** | ***1.5*** |
| ***24*** | ***Rural Connectivity*** | ***C/O Lane FHO Ahmad Ali to HO Qayoom Khan Ward 3.*** | ***1*** |
| ***25*** | ***Rural Connectivity*** | ***C/O Lane /E wall FHO Nazir Bhat to Bhat Mohalla.*** | ***1.5*** |
| ***26*** | ***Rural Connectivity*** | ***C/O Lane FHO Ab Radhid Khan to Graveyard ward 04.*** | ***1*** |
| ***27*** | ***Rural Connectivity*** | ***C/O Lane /E Wall FHO Amin Khan to HO Dullah Khan & Others.*** | ***1.5*** |
| ***28*** | ***Rural Connectivity*** | ***C/O Lane /E Wall from Nallah to Irshad Hyder Lone at Gogaldar.*** | ***1.9*** |
| ***29*** | ***Rural Connectivity*** | ***C/O Lane FHO Rustum Tantray to HO Aziz Tantray.*** | ***1*** |
| ***30*** | ***Rural Connectivity*** | ***C/O Lane FHO Showkat Bhat yo MAmin Bhat at Gogaldar.*** | ***1*** |
| ***31*** | ***Rural Connectivity*** | ***C/O Lane from Nallah to HO Pervaiz Tantray at Dragdan Ward 7.*** | ***1.5*** |
| ***32*** | ***Rural Connectivity*** | ***C/O Lane from Nallah to HO Bashir Tantray at Dragdan ward 5.*** | ***1*** |
| ***33*** | ***Rural Connectivity*** | ***Dev Of Link Road from Xing to Jamai Masjid Phase IInd Ward 04..*** | ***2*** |
| ***34*** | ***Rural connectivity*** | ***C/O Lane FHO Ghulam Jhon to Qamardin Bhat at Gogaldar.*** | ***1*** |
| ***35*** | ***Rural Sanitation*** | ***C/O Drain FLO Farooq Ahmad Khan to LO Yar Ali Khan Ward 3.*** | ***1.5*** |
| ***36*** | ***Rural Sanitation*** | ***C/O Drain FHO Wali Mohd Khan to HO Shabir Khan at Mosajani ward 3.*** | ***1.2*** |
| ***37*** | ***Rural Sanitation*** | ***C/O Drain FLO Tariq Qureshi to LO Gull Mohd Khan Ward 03.*** | ***1*** |
| ***38*** | ***Rural Sanitation*** | ***C/O Drain from FLO Pervaiz Khan to LO Mohd Jan at Ward 6.*** | ***1.5*** |
| ***39*** | ***Rural Sanitation*** | ***C/O Drain FLO Ayoub khan to Gh Mohd Khan Ward3.*** | ***1*** |
| ***40*** | ***Rural Sanitation*** | ***C/O Drain FLO Nazir Khan to LO Mousidin Khan.*** | ***1.5*** |
| ***41*** | ***Rural Sanitation*** | ***C/O Drain FLO Sirajdin Tantray to LO Gani Tantray.*** | ***1*** |
| ***42*** | ***Rural Sanitation*** | ***C/O Drain FHO Nisar Tantray to HO GH Hyder Lone.*** | ***1.5*** |
| ***43*** | ***Rural Sanitation*** | ***C/O Drain FHO Sharif Tantray to Onwards ward5.*** | ***1*** |
| ***44*** | ***Rural Sanitation*** | ***C/O Drain FHO Laldin Tantray to LO Gulzar Tantray Ward 5.*** | ***1*** |
| ***45*** | ***Rural Sanitation*** | ***C/O Drain FLO Hassan Tantray to Bashir khan .*** | ***1*** |
| ***46*** | ***Rural Sanitation*** | ***C/O Drain FLO Syed Muder Shah to LO Farooq Khan.*** | ***1*** |
| ***47*** | ***Rural Sanitation*** | ***C/O Drain FHO Reshma Bano to Gh Hyder Lone.*** | ***1.5*** |
| ***48*** | ***Rural sanitation*** | ***C/O Drain FHO Sikandar Khan to Mohd Sharif Ward2.*** | ***1.2*** |
| ***49*** | ***Rural Sanitation*** | ***C/O Drain FLO Altaf Bhat to Ahelidees Jamia ward4..*** | ***1.5*** |
| ***50*** | ***Rural Sanitation*** | ***C/O Drain from Shabir Medical to Mohd Jan khan..*** | ***1.5*** |
| ***51*** | ***Rural sanitation*** | ***C/O Drain FHO Hilal khan to Bilal Rashid at Khan Mohalla.*** | ***1*** |
| ***52*** | ***Micro Irrigation*** | ***C/O Irrg ladh FLO Majid Tantray to LO Gani Tantray ward 7.*** | ***1.5*** |
| ***53*** | ***Micro Irrigation*** | ***C/O Irrg ladh FLO Farooq Khan to Sadeeq Khan and others.*** | ***1.5*** |
| ***54*** | ***Micro Irrigation*** | ***C/O irrg ladh FLO Ghulam Tantray to LO Yaqoob Tantray ward7.*** | ***1.5*** |
| ***55*** | ***Water Conservation*** | ***Dev Of Spring NLO Pervaiz Tantray at Ward 7.*** | ***1*** |
| ***56*** | ***Flood Protection*** | ***C/O R Wall NLO Hameeda Bano & Others at chamra.*** | ***1*** |
| ***57*** | ***Flood Protection*** | ***C/O FP Bund from PMGSY Road to Mohd Sharif Syed Mohalla.*** | ***1.5*** |
| ***58*** | ***Land Development*** | ***C/O R Wall NLO Khurshid Tantray & Others at Dragdan.*** | ***1.9*** |
| ***59*** | ***Land Development*** | ***C/O R Wall NLO Nisar Ah Bhat & Others at Check Mohalla ward 3.*** | ***1*** |
| ***60*** | ***Land Development*** | ***C/O R Wall NLO Nazir Ah Baht and Others at Bhat Mohalla ward3.*** | ***1*** |
| ***61*** | ***Land Development*** | ***C/O R Wall NLO Habibullah Khan and Others Ward 3.*** | ***1.2*** |
| ***62*** | ***Land Development*** | ***C/O R Wall FLO Gulbaz Molvi to Hamid Abdullah Ward1.*** | ***1*** |
| ***63*** | ***Land Development*** | ***C/O R Wall FHO Bashir khan to HO Lal khanat Khaka Mohalla.*** | ***1*** |
| ***64*** | ***Land Development*** | ***C/O R Wall NLO Iqbal khan ,Mustafa Khan & Others .*** | ***1.5*** |
| ***65*** | ***Land Development*** | ***C/O R Wall NLO Bashir Ahmad Khan &Others at ward4.*** | ***1*** |
| ***66*** | ***Land Development*** | ***C/O R Wall NLO Saleem Khan,Feroz Khan & Others Ward4.*** | ***1*** |
| ***67*** | ***Land Development*** | ***C/O R Wall NLO Pervaiz Khan & Others at ward 6.*** | ***1.5*** |
| ***68*** | ***Land Development*** | ***C/O R Wall NLO Shameem Khan and Others at Ward 6.*** | ***1.5*** |
| ***69*** | ***Land Development*** | ***C/O R Wall NLO M Sharif Bhat and Others Ward 6.*** | ***1.2*** |
| ***70*** | ***Land Development*** | ***C/O R Wall NHO Javid Khan Sadeeq khan,Amin Khan & Others.*** | ***1.2*** |
| ***71*** | ***Land Development*** | ***C/O R Wall Different Spots at Dragdan Ward 5.*** | ***2*** |
| ***72*** | ***Land Development*** | ***C/O R Wall NLO Majid Tantray & Others ward7.*** | ***1.2*** |
| ***73*** | ***Land Development*** | ***C/O R Wall NLO Amin Tantray,Tariq Tantray & Others.*** | ***1*** |
| ***74*** | ***Land Development*** | ***C/O R Wall NLO Javid Tantray & Others wt Dragdan.*** | ***1*** |
| ***75*** | ***Land Development*** | ***C/O R Wall NHO Farid Khan , Saleem Khan & Others.*** | ***1*** |
| ***76*** | ***Land Development*** | ***C/O R Wall FHO Nisar Bashir to Shameema Banoo .*** | ***1*** |
| ***77*** | ***Land Development*** | ***C/O R Wall NHO Pervaiz khan ,Imran Khan & Others.*** | ***1.5*** |
| ***78*** | ***Land Development*** | ***C/O R Wall NHO Mushtaq Hyder Lone & Others.*** | ***1.5*** |
| ***79*** | ***Land Development*** | ***C/ O R wall NLO Gull Aashiq Tantray ,Gh Hassan Bhat and Others at Dragdan*** | ***1*** |
| ***80*** | ***Land Development*** | ***C/O R Wall NHO Manzoor Khan & Others Ward01.*** | ***1.5*** |
| ***81*** | ***Land Development*** | ***C/O R Wall NHO Farooq Talib & Others at Gogaldar Ward 6.*** | ***1*** |
| ***82*** | ***Land Development*** | ***C/O R Wall Bashir Ahmad Khan and Othersat Chamra.*** | ***1*** |
| ***83*** | ***Land Development*** | ***C/O R wallFHO Nisar Khan to Amin Khan ward1.*** | ***1.2*** |
| ***84*** | ***Land Development*** | ***C/O R Wall NLO Syed Mohiudin Syed Amin & Others.{BDC}.*** | ***1.99*** |
| *85* | ***Rural Connectivity*** | ***Dev.Of Link Road from PMGSY Road to Syed Arif {BDC}.*** | *1.99* |
|  |  |  |  |

* + - * 1. DEMANDS

|  |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| **S NO.s** | | **Halqa** | | | **NAME OF THE WORK** | | | **ESTT COST.** | | |
| **1** | | **Hapatnard Middle** | | | **C/O Bridge Over Nallah Dragdan and Gogaldar near Darasgah.** | | | **10** | | |
| **2** | | **Hapatnard Middle** | | | **C/O Link Road from Jamia masjid to Maidan Mohalla Hapatnard.** | | | **5** | | |
| **3** | | **Hapatnard Middle** | | | **Dev.of Ground at GMs Dragdan .** | | | **3** | | |
| **4** | | **Hapatnard Middle** | | | **C/O Link Road FLO Ghulam Khan to LO Farooq Kawa at Hapatnard.** | | | **4** | | |
| **5** | | **Hapatnard Middle** | | | **C/O L/R from Nalla to Upper Dragdan Tantray pora.** | | | **4** | | |
| **6** | | **Hapatnard Middle** | | | **Creation of J&K Bank Branch at Hapatnard Middle.** | | | **15** | | |
| **7** | | **Hapatnard Middle** | | | **C/O Bridge over Nallah Gagerwani near High School.** | | | **10** | | |
| **8** | | **Hapatnard Middle** | | | **Installation of 63kv Transformer at Gogaldar khan mohalla.** | | | **6** | | |
| **9** | | **Hapatnard Middle** | | | **Animal Husbandry at Hapatnard Middle.** | | | **10** | | |
| **10** | | **Hapatnard Middle** | | | **Dev of playfeild at Hapatnard Middle.** | | | **6** | | |
| **11** | | **Hapatnard Middle** | | | **Installation of 100kv transformer atNagbal nera Jamia masjid.** | | | **7** | | |
| **12** | | **Hapatnard Middle** | | | **Dev of Chandraswami Cave at Hapatnard Gogaldar as tourist destination.** | | | **10** | | |
| **13** | | **Hapatnard Middle** | | | **Renovation of pipelines at Bhat Mohalla Hapatnard.** | | | **5** | | |
| **14** | | **Hapatnard Middle** | | | **C/O Sheep Extension Centre at Hapatnard Middle.** | | | **8** | | |
| **15** | | **Hapatnard Middle** | | | **AWC at Syed Mohalla Hapatnard nagbal.** | | | **4** | | |
| **16** | | **Hapatnard Middle** | | | **C/O Link Road from PMGSY Road to Check Mohalla under PMGSY.** | | | **4** | | |
| **17** | | **Hapatnard Middle** | | | **Boundary walls around GMS Nagbal.** | | | **4** | | |
| **18** | | **Hapatnard Middle** | | | **Provision of traning Centre along with machines at Hapatnard Middle for SHG'S.** | | | **5** | | |
| **19** | | **Hapatnard Middle** | | | **Fire Emergency Service at Hapatnard Middle.** | | | **4** | | |
| **20** | | **Hapatnard Middle** | | | **C/O CSC at Dragdan.** | | | **2** | | |
| **21** | | **Hapatnard Middle** | | | **Installation of Electric Poles along with network at Hapatnard Middle Dragdan.** | | | **5** | | |
| **22** | | **Hapatnard Middle** | | | **C/O Drain from HO pervaiz khan to HO Ahmad Ali khan at Maidan Mohalla.** | | | **2** | | |
| **23** | | **Hapatnard Middle** | | | **AWC at Batikhodia Hapatnard Middle.** | | | **5** | | |
| **24** | | **Hapatnard Middle** | | | **Bridge Over Nallah Dragdan NHO Pervain Tantray.** | | | **8** | | |
| **25** | | **Hapatnard Middle** | | | **C/O Xing Near Hanfia Jamia Masjid Hapatnard Nagbal.** | | | **4** | | |
| **26** | | **Hapatnard Middle** | | | **Renovation of Pipelines at Hapatnard Middle Khan Mohalla.** | | | **4** | | |
| **27** | | **Hapatnard Middle** | | | **Porvision of 30Nos Street lights for some Porminent Places at Hapatnard Middle.** | | | **6** | | |
| **29** | | **Hapatnard Middle** | | | **R Wall Different spots at Hapatnard Middle wird 1,2,3,4,5,6,7.** | | | **8** | | |
| **30** | | **Hapatnard Middle** | | | **Renovation of Khaka Mohalla Xing.** | | | **2** | | |
| **31** | | **Hapatnard Middle** | | | **Dev of Chitteri Maidan Sonchalpathri Hapatnard.** | | | **4** | | |
| **32** | | **Hapatnard Middle** | | | **Dev of Anganpathri at Hapatnard Middle.** | | | **5** | | |
| **33** | | **Hapatnard Middle** | | | **CSC at Hapatnard Middle khan Mohalla.** | | | **2** | | |
| **34** | | **Hapatnard Middle** | | | **C/O Link Road from PMGSY Road to Bhat Mohalla.** | | | **3** | | |
| **33** | | **Hapatnard Middle** | | | **Renovation of pipelines at ward no 04 Hapatnard Middle.** | | | **3** | | |
| **34** | | **Hapatnard Middle** | | | **C/O Rwall NHO Ag Gani Khan and others at Hapatnard Middle.** | | | **1.5** | | |
| **35** | | **Hapatnard Middle** | | | **Check Dams NHO Suderdin khan and other at Hapatnard Middle.** | | | **1.5** | | |
| **36** | | **Hapatnard Middle** | | | **Upgradation of link Road from Mirbaz khan to Chech Mohalla.** | | | **2** | | |
| **37** | | **Hapatnard Middle** | | | **F p bund with Drain NHI Wakeel Tantray and others at Dragdan.** | | | **1.5** | | |
| **38** | | **Hapatnard Middle** | | | **FP Bund Nallah Dragdan Gogaldar NHO Majid Tantray and others.** | | | **3** | | |
| **39** | | **Hapatnard Middle** | | | **C/O Drain from HO Naseer khan to HO Yaqoob khan.** | | | **2** | | |
|  | |  | | |  | | |  | | |
| * + - * 1. Capex Plan for the year 2022-23 | | | | | | | | | | |
| **HALQA** | | | | **NAME OF THE WORK.** | | | **ESTT.COSTT.** | | |
| **Hapatnard Middle** | | | | **C/O Fencing around Panchayat Ghar Hapatnard Middle.** | | | **2** | | |
| **Hapatnard Middle** | | | | **C/O Tile Lane from PMGSY Road to H/O Mushtaq Bashir at Khan Mohalla.** | | | **1.1** | | |
| **Hapatnard Middle** | | | | **C/O Tile Lane from PMGSY Road to H/O Gulzar khaka Ward 1.** | | | **1.1** | | |
| **Hapatnard Middle** | | | | **C/O Xing NearGovt Middle School ward 2.** | | | **2.5** | | |
| **Hapatnard Middle** | | | | **C/O Lane with E wall from PMGSY Road to Onwards via L/O Iqbal ward 02.** | | | **1** | | |
| **Hapatnard Middle** | | | | **C/O Lane FHO Yousuf Khan to HO Wali Mohd Khan ward3.** | | | **2.3** | | |
| **Hapatnard Middle** | | | | **Dev Of Spring NHO Rashid Khan & Others Ward 4.** | | | **1.2** | | |
| **Hapatnard Middle** | | | | **C/O Fencing around Graveyard Dragdan Ward 5.** | | | **2.4** | | |
| **Hapatnard Middle** | | | | **C/O Flash Point Laterine Near Jamai Masjid Baji Mohalla Ward 6.** | | | **2.5** | | |
| **Hapatnard Middle** | | | | **C/O Bathroom Anganpathri Ward 7.** | | | **1.25** | | |
| **Hapatnard Middle** | | | | **C/O Lane FHO Wazir Lone to H/O Mohd Amin Tantray Ward 7.** | | | **1.25** | | |
| **Hapatnard Middle** | | | | **C/O B/Side Approach Wall of Syedpora Xing.** | | | **1** | | |
| **Hapatnard Middle** | | | | **C/O R wall NHO Javaid Khan and Others. khan ,BashirSadiq khan ,Amin and others.** | | | **2.4** | | |