4





**15TH OCTto3RD NOV,2022**

**KEYFEATURES**

• DeputyCommissionerstoleadtheinitiative

• RuraldevelopmentDepartmenttobethenodaldepartment

• PlanningDevelopment&MonitoringdepartmentandITtobethesupport departments

**ACTIONSANDTIMELINES**

|  |  |  |  |
| --- | --- | --- | --- |
| **ACTION** | **RESPONSIBILITY** | **LATESTBY** | **REMARKS** |
| **Janabhiyan** | Alldepartments | Oct15-26th | Goingon |
| **DeputationofSecttstaff/ HoDs** | GAD | Oct14 | Done |
| **DeploymentofStaffto Panchayatsandservingof ordersondeployedofficers** | DCs | Oct25 | DCswilldeployseniorlevelstaff fromthedistricts.Strictactionto betakenagainstabstentions.No exemptionstobegiven |
| **Trainingofdistricttrainors onB2V4** | RDD | Oct26 |  |
| **Trainingofvisitingofficers** | DCs | Oct27 |  |
| **FieldVisitstobecompleted by** | VisitingOfficers | Nov3 | DCstosuperviseandensurethat eachPanchayatisvisitedwithin theperiodspecified |
| **DataofB2V4tobe uploadedby** | VisitingOfficers | Nov10 | DCstosuperviseandensurethat dataofallPanchayatsisupload- edbythevisitingofficerwithin theperiodspecified |

**INSTRUCTIONSFORTHEVISITINGOFFICER(DAYWISE)**

|  |  |  |
| --- | --- | --- |
| **DATE** | **INSTRUCTIONS** | **ACTIONPOINTS** |
| **Day0** | Meetingwithdeputy commissionerandhis/her team | a. TakeprintoutsoffilledbookletsofB2V1,B2V2andB2V3from [www.jkpanchayat.in](http://www.jkpanchayat.in)b.Alsotakeprintoutsofthesummarizedexcelsheetsofthe previousphasesfrom[www.jkpanchayat.in](http://www.jkpanchayat.in)c. CollectATRsonissuesraisedduringprevious3phasesfromthe officeofDeputyCommissioner(Planningdeptt)d.Takeprintsofblank 2bookletsofB2V4from[www.jkpanchayat.in](http://www.jkpanchayat.in)e.Takeplansfor2previousyearsandATRsfromtheplanningdeptt f. CompletetrainingsondifferentcomponentsofB2V4beingorganizedbyrespectiveDeputyCommissionersg.CollectListofnewworksstarted/ongoing/completedduringthe previousandcurrentFinancialyearunderthefollowingheads:• PRIgrants• DistrictPlan• UTplan• MGNREGA• Otherschemesofotherdepartments• Anyotherworkh. Plans/beneficiarylists:• MGNREGAdraftplandocumentfortheyear2022-23.• ListofAwaas+beneficiariesalongwithIHHL Convergence• Listofpensionbeneficiaries.• ListofSHGs• Listofagricultureschemebeneficiariesi. Listsofbeneficiariesfor:• Variouscertificates/benefitstobedistributedbythe visitingofficer.• Anyotheractivitiesidentifiedbydifferentdepartments |

|  |  |  |  |
| --- | --- | --- | --- |
| **Day1** | Reachthevillage | 1. | Ensurethatallfrontlineworkersofdifferentdepttsarepresent. |
|  |  | 2. | Ensureexhibitionbydifferentdepts.aboutindividualbeneficiary schemes |
|  |  | 3. | InspectJKB/PSBcounters/outlets |
|  |  | 4. | Participate/ensureorganizationofsportsactivityinplayfield,talent hunt/culturalevent/youthactivity |
|  |  | 5. | GandhiKatha(suggesteddetailsuploadedonjkpanchayat.in) |
|  |  | 6. | Visitatleast2amritsarovarsandgetitsgeotaggedphotos |
|  |  | 7. | InspectKhidmat(CSC)CentresandcreateGenerateawarenesson225schemesparticularlyG2CschemeslikeBEAMS,Janbhagidari, AapkiZaminAapkiNigrani,DigitalJ&K |
|  |  | 8. | Visitingofficershallalsoplanandconductpanchayatlevelconver- gencemeetingofalldepartments |
|  |  | 9. | CheckeffectivenessofCentrallysponsoredschemes |
|  |  | 10. | VisitandinspectallgovernmentestablishmentsincludingPHE, AWC,FPS,schools,etc |
|  |  | 11. | Attemptsaturationofdeliverableso JanAbhiyanandwherever deficienciesfound,leadadrivetoachievealldeliverables |
|  |  | 12. | Assesseffectivenessofsanitationcampaigninthepanchayat |
|  |  | 13. | Ensureselfemploymentactivitiesfor15youthperpanchayat |
|  |  | 14. | Identify20potentialcandidatesperpanchayatforHIMAYATtraining alongwiththetradeonwhichtheywanttraining |
|  |  | 15. | Whereverpossible,distributeemploymentlettersforpeopleselect- edundervariousgovernmentemployments |
|  |  | 16. | Intheevening,holdnormalmeetingwith seniorcitizens,govtem- ployeesincludingretiredemployees,exservicemen,youthclub,and any citizens ofthevillagewhoareenrolledincollege/university |
|  |  | 17. | OpendiscussiononNashaMuktAbhiyan |

Day2 Haveameetingwithall stakeholders-depttofficials andpanchayatmembers

1. Discussionontheandassesstheprogressofdifferentschemesrelating tothelocalizedSDGsprioritizedforthatvillageaspertheresolution passedby thatGramPanchayaton21st April22,onNationalPanchayti RajDay.

2. Sensitizevillage residentsaboutmyScheme”portal(myscheme.in) whichincludesinformationaboutalltheschemesbeingrunbyCen- tral/State/UTgovtacrossthecountry

3. Hold meeting of theBiodiversityManagementCommitteestodeliber- ateonissuespertaining toconservation of biodiversityandsustaina- bleutilizationof biologicalresources.

4. PrepareVillagedevelopmentplan,inconsultancywithGrampanchayat, discussitingramsabhaandgetitapproved.

5. Ensure saturationofsoilhealthcardandgoldenhealthcardunderGold- enHealthCardunderAyushmanBharat,

6. Ensuresaturation of OldAge PensionScheme

7. EnsureDomicileSaturation.

8. EnsureKCCSaturation

9. Ensure saturationoflandpassbooks

10. Ensureregistrationofvillagevendorsneededforanyscheme,onGEM

portal

11. Ensurepanchayatcontractors registration

12. EncouragePanchayatmembers forimportanceofplantationdrivein

PanchayatunderHarGaonHariyali

13. Ensure paintingondigitalJ&Kinpanchayatghars

14. Ensure paintingonpanchayatactivitesandCSSinpanchayatghars

15. Thevisiting officeshallchecknoof kindergarten andplayfields present inthepanchayat for kidsandstudents,iftheinfrastructure present inthesearegoodenough.

16. Holdmeeting withpanchayatmembers todiscussaboutcorruption menaceandstepsrequiredtomakeJ&Kcorruptionfree

17. Obtaina candidassessmentaboutperformanceofvariousdeptts in- cludingfairfeedbackaboutdiscrepanciesinfunctioning

18. Check thestatusof NashaMuktAbhiyanandreporting of drugad- dictstoDeputyCommissioner.

19. IdentifyTouristDestinations,Circuits,ThemeTreks,IdentifyHomestays, providesupportfortourismactivities throughVillageCooperative

20. OrganizeTalentHuntatPanchayatLevel

21. Conductsocialauditofatleast5worksunderfollowingschemes:

a. MGNREGA

b.PMAY

c. IHHLtoiletsandpayments d.CSCs

e.AMRITSAROVARS

22. Holda mahilasabha anda balsabhaandrecordproceedingsinthefor- matgiven

23. InauguratevillagehaatunderJKSRLM

24. Checkifyouthclubsareformedinthepanchayatandwhatactivities theyareengagedin

25. Organizea villagelevelculturaleventtoengagepanchayatmembers

26. SensitizeGPaboutE-kitabkoshaninitiativeofJ&KGovtforempowering youthsthrough onlinedigitalliteracy

**GENERALINSTRUCTIONS**

1. Thevisitingofficershallrefrainhimself/herselfgivingorofferinganycommitmentonbehalfofthe governmentandshalladoptanunbiasedattitudeinreportingissues.As faraspossible,his/her observation shouldbebasedona fairandanalytical viewemergingfromhis/herinteractioninthe village.

2. Heisgoingtothevillageasplanningofficer,notforsanctioninganyworksorformakinganycom- mitments.

3. Whilepreparingvillagedevelopmentplan,hehastoensurethat,demandsareprioritizedandre- flectedunderavailableschemes,wherevernecessarythelargerworksaretobereferredtoadminis- trativedepttunderCSS/UTplansunderintimationtoDCsandrestoftheworkstoDCsforreflecting itunderdistrict/CSS plans

4. His workshallbehardcoreplanningandauditandisnota PRexercise.

5. EveryDeputyCommissionerhastoensurethatatleastoneRDDofficial(ideallyPanchayatSecre- tary)ispresent ineverypanchayatwithrelevantpanchayatrecords,toensureconductofallactivi- tiesasplanned.Panchayatwiseorderneedstobeissuedinadvance.

6. Visitingofficershouldideallycarryhis/herlaptoptocompletethereportsatthepanchayatlevel itselfanduploadthefinalreport,duly signedbothbythesarpanchandbythevisitingofficeron [www.jkpanchayat.in](http://www.jkpanchayat.in)portal,beforetheyleavepanchayat.

7. Focus ofvisitareyouth,skills,self-employment,nashamukt,bhrashtracharmukt,Rozgaryukt J&K, besidestocarryforwardtheactivities duringJanAbhiyanandsaturatethem.

8. Inadditionattentionmaybegiventothefollowingareas a. MakefulluseofCentrallySponsoredSchemes

b.Saturationofindividualbeneficiaryschemes c. Self-employmentschemes

d.Banklinkedschemes-includingdepartmentalsubsidyschemes e.Empowermentandtransparencythrough digitalinitiatives

f. Effectivenessofgrassrootsmachinery–

i. Patwari,VLWpresent andavailable

ii. AvailablefundsutilizedinpublicinterestandasperGramSabharesolutions iii. Fairness ingovernance

iv. CSS/Individual beneficiaryschemesetc v. BrashtacharMuktJ&K

vi. BhaiMuktJ&K

vii. NashaMuktJ&K

9. ThePRImembers (Sarpanchs,Panchs,BDCChairperson)shallbeattheforefrontofallactivities and givendueimportanceandtheapproach shouldbetostrengthenthemandmakethemfeelem- powered.He/sheshallensurethattheBDCchairpersonandSarpanch/Panch arepresent atthetime ofinaugurationandceremonies.

10. Visitingofficershallnotleavethedistrictwithoutuploadingthereport,duly signedonthe**www. jkpanchayat.in**portal.EveryDeputyCommissionerhastoensurethat.

**A) Details of Reporting Officer:**

Name: Er Shabir Hassan Lohar

Designation: Assistant Engineer

Department/place of posting: Electric Division Awantipora

Mobile No: 9622826553

EmailID: shabir.pdd.awp33@gmail.com

Home District: Pulwama

Dates of visit: 30/10/2022 & 31/10/2022

**B) LocationaldetailsofPanchayat:(tobepre-filled,informationtobetakenfromtheprevious phasesbooklets/summarizedexcelsheetuploadedonjkpanchayat.in/b2v4.php)(tobevali- datedbythevisitingofficerandmissingdetailstobefilled)**

NameofthePanchayat: GULISTAN

LocalGovernmentDirectory(LGD)codeof thePanchayat: 242942

Nameof CD Block: ARIPAL

NameofTehsil: ARIPAL

Nameof District:PULWAMA

**C) PanchayatProfile:**

No.ofrevenuevillagesinthePanchayat: 03

No.ofhamletsinthePanchayat: 05

No.ofhouseholdsinthePanchayat: 276

Population(approx)of thePanchayat: 1534

**Part-II:**

(TobefilledupbytheVisitingOfficerduringhis/hertwodayvisittothePanchayat.AllFieldshavetobe

filledbytheVisitingOfficerbeforethebookletishandedovertotheDC

**FrontlineOfficers/OfficialswhowereassignedtothePanchayatfortheprogramme:**

|  |  |  |
| --- | --- | --- |
| Department | Name | Designation |
| RDD | FAROOQ AHMAD DAR | PYT SECRETARY |
| RDD | PERVEZ AHMAD | ACCOUNTS ASSISTANT |
| FLOOD CONTROL | MUSHTAQ AHMAD | WS |
| YSS | BILAL AHMAD LONE | PT |
| ANIMAL HUSBANDRY | FAYAZ AHMAD DAR | VETR PHARMICIST |
| SHEEP HUSBANDRY | MANZOOR AHMAD BHAT | ASM |
| REVENUE | BILAL AHMAD BHAT  | PATWARI |
| HANDICRAFTS | PERVEENA AKHTER | OCC |
| HEALTH | DR BILAL AHMAD | DOCTOR(MLHP) |
| SUMAYAH ISMAIL | FMPHW |
| GULSHANA AKHTER | ASHA WORKER |
| HANEEFA AKHTER | ASHA WORKER |
| FOOD AND SUPPLIES | TABASSUM FAYAZ | CLB DEALER |
| ICDS | RUKHSANAH ISMAI | AWW |
| RUBY JAN |
| SAMEENA |
| JAMEELA AKHTER |
| AGRICULTURE | RAVINDER NATH SINGH | CIRCLE OFFICER |
| FISHRIES | ALTAF HUSSAIN WANI | FG |
| FOREST | MOHD MAQBOOL AHANGAR | WATCHER |
| WLPD | GH HASSAN SHEIKH | HELPER |
| GH NABI MIR | HELPER |
| MOHD IQBAL KHAN | CASUAL LABOUR |
| MOHD SHAFI WANI | HELPER |
| AB MAJEED SHEIKH | BLOCK OFFICER |
| PDD | FAYAZ AHMAD MIR | TECH-3RD |
| MUSHTAQ AHMAD DAR | PDL |
| GULZAR AHMAD DAR | PDL |
| CSCE GOVERNANCE | MUZAFFAR KHALID | MODEL CSC |
| SERICULTURE | ASHAQ HUSSAIN RATHER | HELPER |
| SOCIAL FORESTRY | MOHD ABDULLAH KHAN | JUNIOR MALI |
| PWD(R&B) | FAROOQ AHMAD WANI | R WORKER |
| HORTICULTURE | SARTAJ AHMAD BHAT | HTG-4 |
| PHE | ALI MOHD WANI | LM |
| MOHD YOUSUF TRAG | FITTER |
| GH HASSAN | CASUAL LABOUR |
| SOCIAL WELFARE | AJAZ AHMAD | YSS |
| FOREST DEV CORPORATION | AMREEK SINGH | F SUPERVISOR |
|  |  |  |

**Detailsofabsentemployeesvis-à-vislistfurnishedbytheDCoffice:**

|  |  |  |
| --- | --- | --- |
| Department | Name | Designation |
|  |  |  |
|  |  |  |
|  |  |  |
|  |  |  |
|  |  |  |
|  |  |  |
|  |  |  |
|  |  |  |
|  |  |  |
|  |  |  |
|  |  |  |
|  |  |  |
|  |  |  |
|  |  |  |
|  |  |  |

**DAY1-ACTIVITIES**

**AGENDA1:PANCHAYATASSETREGISTER**

**Infrastructure:**

1. PanchayatGharInfrastructure:

a. Govt building/private

b. New/needingrepairs

 **Panchayat Ghar in rented room. Govt building under construction/partially constructed & languishing. Needs to be completely constructed.**

2. Furniture(Y/N)--------------Y

3. Computer/printer(Y/N)--------Y

4. Internet(Y/N)---------N

5. Telephone(Y/N) ---------N

6. Toilet (CSC/part of panchayat ghar)(Y/N) -------------- N

7. Water(Y/N) ------------N

8. Electricity(Y/N) ------------- N

9. Bank branch(Y/N) -------------N

10. CSC(Y/N) ---------------N

 **SINCE PYT GHAR IS IN RENTED ROOM ,HENCE THE FACILITIES FRO 4 TO 10 ARE NOT EXCLUSIVELY AVAILBLE**

11. Patwarkhana(Y/N) -----------N (JOINT OF FEW PYT HALQAS AT KHANGUND)

12. Village haat(Y/N) ------------- N

13. Playground(Y/N)------------- N

14. School-

a. Kindergarten(Y/N) --------- N

b.Primary(Y/N)-------------Y

c. Secondary(Y/N) -------------- Y

d. College (Y/N) -----------N

e.University(Y/N) -----------N

15. Anganwadi Centre(Y/N) --------Y

a. (govt/private) ---PRIVATE

b. Total children enrolled --------- 168

15. Amrit Sarovars–details,location,condition -------Astannard Hajin (Satisfactory and closed top)

16. Government offices-details, whether functional or not -------Satisfactory

17. Ration shop (Y/N) --------Y

18. Places of tourism importance–names, little detailson historical/culturalimportance----- Nagaberi (without road connectivity)

19. Village heritage sites/treks-names,little details on historical/cultural importance -----N

20. VLWOffice (Y/N) ------Y (rented)

21. Primary Healthcare Centre(Y/N), ----Y (sub centre in rented room)

22. List of Incomplete Buildings-names,year of construction------Panchayat Ghar (2014)

23. List of Underutilized Buildings-names----- None

**DAY1-ACTIVITIES**

**AGENDA2:**

**DIFFERENTINSTITUTIONS/INFRASTRUCTUREPROJECTSTOBEVISITED**

|  |  |  |
| --- | --- | --- |
| **AMRITSAROVARS** | **Visit,verify** | **COMMENTS** |
| KhidmatCentres | Create/Generateawarenesson225schemes particularlyG2CschemsAapkiZaminAapkiNigrani, Beams,Janbhagidari,DigitalJ&K |  Not available  |
| JKB/PSBcounters/outlets | a)Statusofcounter b)Numberofvisitors | Not available |
| Incompletebuildings/pro- jects | Verify whetheridentificationandredistribution done | Panchayat Ghar Building (Languishing) |
| PDS | Visit,evaluate,onlinestatus | Satisfactory 100% online |
| PHC | Visit-evaluate,statusofstaff,equipmentand quality | Health subcentre (rented) Doctor (ayush) ---1 NRHM (FMPHW)-1 |
| Youthclubs | Meet,interact,seeksuggestions | Major demand of Youth is playground |
| SHG | Meet,identifyproblems,seeksuggestions |  No SGH formed yet |
| PMAY | Inspect,Inaugurate | Inspected and inaugurated  |
| Myschool,mypride progress;schools-water, toilets,staff | Visit,checkforwater,electricity,sanitation,meet studentsandstaff | Visted and checked. Overall satisfactory except PS Pranigam(WO sanitation) |
| SwachhSBM | Evaluate | Checked one at Pranigam (satisfactory) |
| Panchayatplayground, Sportskitsdistribution Villagegames | Ensure,verify.Participateinatleastonegamein theplayground | Panchayat Playground not available.  Sports kits distribution done |
| HarGaonHariyali, Planta- tiondrive | Evaluatestatus,feedback | Carried out at Hajin village onlyNeed to be carried out in every village |
| VillageculturaleventDangal/Haat/Mela | Participatein;ensurethatitisheld |  Haatt held at hajin |
| Exhibitionofschemes | Ensurethateverydepartmentparticipatesand thatitcontinuesfortheentiredurationofB2V | Carried out during JAN ABHIYAN |
| JalJeewan Mission verifica- tion- WSS/JSDElectricitysupply | Verify | 1520 meters of pipe being replaced under JJM (Work going on).Natural spring electricity not needed |

**DAY1-ACTIVITIES**

**AGENDA3:SATURATEJANBHIYAN**

**DELIVERABLESANDRECORDDEFICIENCIESIFANY(INSERTDELIVERABLESLISTHEREASPERGADFORMAT**

 S.No. Department Observattions

 1 RDD Saturated all JAN ABHIYAN activities

 2 IT CSC Joint with Satoora. No Seprate CSC

 3 Finance No self Employment as part of JAN ABHIYAN.

 No counters set

 4 Revenue Patwar Khana not available in Panchayat.

 Inheritance Mutations complete (FY:2022-23 -----33 cases).

 Land passbooks --- All generated and few issued by VO on spot

 5 Health -🡪PMJAY Golden Cards

 Total Population: 1534 Pending 74-60=14

 Saturated :- 1460 +60= 1520

 -🡪 SWACHH Hospitals ; Health subcentre in rented room found clean

 6 Social Welfare

 Divyang Camps----- not available

 Disability cards 14 Beneficiaries all of which have been saturated online

 Anemia checkups being conducted regularly

 Aadhaar seeding : Ladli Beti ----63 , Aanganwari benefeciaries--168

 7 Forest One Forest guard for each village of Panchyat already available

 No plantation drive carried out in the Halqa as part of Jan Abhiyan

 8 Tourism Nagaberi can become the best tourist destination if road connectivity is provided to it or else access can be made possible by providing Gandola facility

 9 Labour e-SHRAM --- 90- 95% already saturated but none as part of JAN ABHIYAN

 10 School Education

 Bringing back all out of school children------ 29 children were out of school in Panchyat all of them were enrolled

1. Transport No transport facility (Service) available

 Mumkin Scheme --- Not available

1. PDD a. Unique Nos checked.

 b DTs with low oil --Topped up

 c. Not DT found with load imbalance.

 d. No non standard fuses found

 e. Proper earthing ensured

 f. Foliage removed

 g. No claims pending

13. CAPD Shift to RCMS –100%

14. PWD 100% online payment with no manual interface---YES

15. GAD -🡪100% Biometric attendance in Govt offices like Schools Health centres etc (offices available panchyat)

 -🡪EPM by all employees present

 -🡪100% property returns filled in by are present employees.

 🡪Online APKS HRMS impletation under progress

16. JALSHAKTI

17. Youth Services & Sports: Sport activities carried out at PH Gulistan

18. Public Grivances Perception of departments among public is good and satisfying overall.

19. Agriculture & allied Sectors PM Kissan – 107, Target -98, Saturated – 98 ( out of which 16 in Jan Abhiyan)

 Skill Health and target 145, Saturated – 100%

 Kissan Mella – one held during current year

**DAY1-ACTIVITIES**

**AGENDA4:**

**SELFEMPLOYMENTACTIVITIES**

EnsureSelf-employmentactivities foryouth,distributeemploymentlettersforpeopleselectedunder varioussocialschemes(15ISTHETARGETPERPANCHAYAT)

**-🡪Numberofcasesindifferentcategoriessanctioned**------09 already sanctioned by different departments **(Detailsofthebanksanctioningit: 07 out of 09**

**Totalamount involved: 16 lacs**

**DAY1ACTIVITIES**

**AGENDA5**

Intheevening,holdinformalmeetings withseniorcitizens,govtemployees,retdemployees,youthclub andothercitizenswhoareenrolledoncollege/universityandhavediscussiononGandhiKatha,Nasha MuktAbhiyan,corruptionfreegovernance,doublingfarmersincomeandrecordtheproceedings

 Procedings recorded as below:--

 A meeting in which senior citizens and Govt employees, rated employees youth club and other citizens was held as

 part of B2V4 program inside the premises of Govt. High School Gulistan. The deliberations on the following topics

 were made by the visiting officer.

1. Gandhi Katha :- The role of Gandhi Ji in the independence of India, his policy of none violence, his simplicity, his life style and steadfastness were discussed in detail. Awareness about Gandhi Katha being broadcasted on radio and telecasted on TV was given so that people from different walks could benefit from it.
2. Nasha Mukt Abhiyan :- The bad effects on the life of the drug dependent people and that on the life and property of others was deliberated in detail. Various methods like how counseling and treatment facilities in hospitals and rehabilition centres, capacity building programs with special focus on young population can help in avoiding/giving away this mence
3. Corruption free govervance:- The focus was given on the fact that how can we build a corruption free society which inturn will lead to corruption free governance .
4. Doubling farmers income:- Detailed deliberations were made by visiting officer on the initiative by PM to focus on how to double the income of farmers by the year 2022-23. Awareness about the fact that when was the scheme launched and it’s purpose was given.

**DAY2**

a. No of Individual Compost Pits constructed-------Nil

 b. No of IndividualSoakPitsconstructed: target--206 constructed---100

V. No.of Biodiversity management committee meetings held---01 held last year & none this year

VI. IsthenameofSarpanchdisplayedoncitizeninformationboardsofallRD&PRschemes:Yes/No --Yes

VII. AreSarpanchsbeinginvolvedinstart/inaugurationofactivities:Yes/No ------ Yes

VIII. WhethersubjectshavebeenassignedbytheSarpanchtothePanchs:Yes/No ------Yes

IX. Whether grievances redressalboxisinstalled:Yes/N ------- Yes ( on the wall of partially constructed

 Panchayat Ghar building)

X. NoofgrievancesreceivedpertainingtoPanchayatlevel----Nil XI. NoofgrievancesdisposedofatPanchayatlevel: Nil

XII. WhethertheSarpanch/PanchayatSecretaryhavedigitalsignatures:Yes/No ------Yes

XIII. Whether all MGNREGA/14thFCpayments arebeingmadebySarpanchthrough DigitalSignature

Certificate(DSC):Yes/No ------- Yes

 **HUMAN RESOURCEAVAILABLEATTHEPANCHAYAT LEVEL:**

|  |  |  |  |
| --- | --- | --- | --- |
| **SRNO.** | **DEPARTMENTWISESTAFF** | **NUMBERS** | **NAMES** |
|  |  | SANCTIONED | ACTUAL |  |
|  | Ruraldevelopmentdepartment: BDOJE GRS TA PS |  |  0101010101 | Farooq Ahmad Mir(block)Shamsudin ShahShowkat Ahmad DarAdil Manzoor Farooq Ahmad Dar |
|  | SCHOOLEDUCATION: TEACHERHEADMASTER ANYOTHER |  |  | Go to next page |
|  | JAL JEEVAN: |  |  | Go to next page |
|  | PDD: LINEMAN JEANYOTHER(PDL) |  | 010101 | Fayaz Ahmad Mir (Tech 3rd)Harmindar Pal SinghMushtaq Ahmad Dar |
|  | FOOD & CIVILSUPPLIESDEALER |  | 01 | Tabassum Fayaz  |
|  | AGRICULTUREC IRCLE OFFICERANIMAL HUSBANDRY |  | 01NIL | Dr Hafizullah TEELI  |
|  | SOCIALWELFARE |  | NIL |  |
|  | HEALTH: ASHA ANMAYUSHDOCTOR FMPSW |  | 0101 | Dr. Bilal Ahmad (MLHP) Sumayah Ismail |
|  | ANYOTHERDEPARTMENT |  |  | List Of other departments in next two pages |

**School Education:-**

|  |  |  |  |  |
| --- | --- | --- | --- | --- |
| **Sr. No** | **Name of the Teacher**  | **Residence**  | **Designation**  |  **POP** |
| 1 | Gh Mohd Mir  | Arigam | Master HOI | Govt High School Gulistan |
| 2 | Mohd Ashraf Dar  | Satoora  | Master  | Govt High School Gulistan |
|  3 | Nazir Ahmad Bhat | Khanagund | Master  | Govt High School Gulistan |
|  4 | Farooq Ahmad Dar | Satoora | RRet | Govt High School Gulistan |
|  5 | Ab Rashid Sheikh | Dar Ganai Gund | RRet | Govt High School Gulistan |
|  6 | Gh Nabi Bhat  | Luragam | Teacher | Govt High School Gulistan |
|  7 | Irshad Ahmad Bhat | Luragam | 3rd Teacher RRet | Govt High School Gulistan |
|  8 | Altaf Ahmad Bhat | Khanagund  | Teacher grade III | Govt High School Gulistan |
|  9 | Rayees Ahmad Bhat  | Khanagund  | Teacher | Govt High School Gulistan |
|  10 | Javed Ahmad Chopan | Lorow | Teacher | Govt High School Gulistan |
|  11 | Ab Rashid Dar | Satoora | RRet  | Govt Pry. School Pranigam |
|  12 | Gh Hassan Ahanger | Satoora | RRet | Govt Pry. School Pranigam |
|  13 | S. Nirmal Singh  | Arigam | Master | Govt Upper Pry. School Hajinnar |
|  14 | Mohd Maqbool Dar | Satoora  | RRet | Govt Upper Pry. School Hajinnar |
|  15 | Nazir Ahmad Bhat | Lurgam | RRet | Govt Upper Pry. School Hajinnar |
|  16 | Mohd Iqbal Dar | Satoora | Teacher Grade III | Govt Upper Pry. School Hajinnar |
|  17 | Mohd Yousuf Gojar | Hajinnar | RRet | Govt Upper Pry. School Hajinnar |
|  18 | Shahida Parveen  | Gulistan | RRet | Govt Upper Pry. School Hajinnar |
|  19 | Mohd Yousuf Khan  | Check Satoora | Teacher Gade III  | Govt Pry. School Upper Hajin |
|  20 | Mohd Amin Khan | Check Satoora | Teacher Grade III | Govt Pry. School Upper Hajin |
|  21 | Javaid Ahmad Bhat  | Satoora  | Teacher Gade III  | Govt Pry. School Check Hajin |
|  22 | Fayaz Ahmad Trag | Syedabad | Teacher Gade III  | Govt Pry. School Check Hajin |
|  23 | Mohd Shafi Dar  | Satoora | Teacher Gade II | Govt Pry. School Hakwan |
|  24 | Irfan Nazir | Satoora | Teacher Gade II | Govt Pry. School Hakwan |
|  25 | Shahnawaz Yousuf Dar | Satoora | Teacher Gade II | Govt Pry. School Hakwan |

 Designation Available Name

🡪JAl Jeevan /Jal Shakti

 Line Man 01 Shaya kuli

 Helper 01 Ali Mohd Wani

 Casual Lavour 04 Ab Rashid Gojar

 Gh Hassan Kuli

Mohd Shafi Gojar

Gafoor Khan

 Daily Wager 01 Mohd Yousuf Trag

 🡪Revenue

 Patwari 01 Bilal Ahmad Bhat

 (Joint with Satoora, patwari Halqa)

 Which include Satoora, Gutroo, Nargistan PHs)

 🡪Sericulture

 Helper 01 Ashiq Hussain rather

 (Joint withSatoora, Gutroo & Nargistan PHs)

 🡪Wild life & Protection

 Block Officer 01 Ab Majeed Sheikh

 Guard 04 Reyaz Ahmad Wani

 Gh Hassan Sheikh

 Gh Nabi Mir

 Mohd Shafi Mir

 🡪Social Forestry

 Jr. Mali 02 Khursheed Ahmad Rather

 Mohd Maqbool Mir

 🡪Sheep Husbandry

 Stock Man 01 Manzoor Ahmad Bhat

 Flock Inspector 01 Farooq Ahmad Najar

 (Joint with Satoora, Gutroo & Nargistan PHs)

 🡪Youth service & Sports

 ---------- Nil------------

 🡪Social Welfare

 ---------- Nill ------------

 🡪ICDS

 Anganwari Worker 04 Rukhsanah Ismail

 Ruby jan

 Sameena

 Jameela Akhter

**DAY2-ACTIVITIES**

**AGENDANO.1**

DiscussionontheandassesstheprogressofdifferentschemesrelatingtothelocalizedSDGsprior-itizedforthatvillageaspertheresolutionpassedbythatGramPanchayaton21stApril22,onNational PanchayatiRajDay(Copyoftheresolutiontobetakenfrom[www.jkpanchayat.in](http://www.jkpanchayat.in)portalunderthelinkof GramSwarajMonth)

1. SDGs AGREED FORTHATVILLAGE,TOBEIMPLEMENTED BYMARCH2024:

2. STATUSOFWORKSUNDERTHEFOLLOWINGSCHEMES:

**1 Cleanandgreenvillage**

I .InitiativestakenbythePanchayatformanagingSolidandLiquidWaste--Soakage pit construction under MGNREGA

 InitiativestakenbythePanchayatforusinggreensourcesoffuellikesolar,biogas ---NIL

iii. Hasmappingoflanduse,waterbodies,forest,slopes,wetlands,degradedforestwithintheGram

Panchayatbeendone?Yes/No.IfNo,reason,thereof: -----No (Demarcation not yet made)

iv. HastheClimateResiliencePlanbeendevelopedfortheGP?Yes/No --------No

v. StepstakenbytheGramSabhaabouttheclimatechangemitigationfactorslikereducingenergy consumption,usageoffossilfuels,plastics,non-renewablebuildingmaterialsandalsotopromote measureslikeplantingoftrees,conservingforests,usageofgoodagriculturalpracticeslikedrip irrigation,waterconservationmeasuresandconservationofwetlands.-----AWARENESS AMONG PUBLIC

 & PLANTATION DRIVE CARRIED OUT LAST YEAR

vi. Whetherschoolshavestartedsegregatingwaste---------only solid waste

vii. Whetherschoolshavetheirowncompost/soakagepitsforsolid/liquidwastemanagemen---Liquid waste🡪 Yes Solid Waste 🡪 No

**2 Healthyvillage**

i) Aremeetings relatedtoVillageHealthandSanitationCommitteebeingheldregularly? ----Yes

ii) DoalltheeligibleindividualsbeenprovidedtheGoldenCard? ----- Pending only 14 Nos.

iii) ArealltheChildrenbeingimmunizedaspertheSchedulerecommendedbyGovt.ofIndia?: -----Yes

iv) ArealltheeligibleindividualsbeenvaccinatedagainstCOVID-19? : ------ Yes

v) DoesGramPanchayatensurethatallpregnantwomenaregettingnecessaryprenatalcheckups? ---- Yes

vi) WhetherallthedeliverieswereInstitutionalizedorconductedbytrainedMidwives? : All institutionalized

**3 Watersufficientvillage**

i) DoalltheIHHsintheGramPanchayathavewaterpipelineconnections? ----20 pending for whom pipe is being laid

ii) WhetherGramPanchayathastakenstepsforgreywatermanagement.IfYespleasespecify ---- No iii) DoalltheIHHsintheGramPanchayathavetoilets? :----Almost all

iv) ArealltheIHHstoiletsfunctionalornot? : Barring few yes

v) DoalltheSchools/Anganwadicentershavea toiletfacilityornot? : PRANIGAM PS ---- No

vi) Areallthetoiletsintheschools/Aaganwadifunctionalornot? ------ Damaged fully at PS PRANIGM & the one at UPS Hajin Nard needs repairement

vii) WhetherGramPachachayatBhawanhasseparate toiletsforwomenornot? ----- No (Rented Building)

**4 ChildFriendlyvillage**

i) Doallthechildrenundertheageof0-6yearsbeenenrolledintheAnganwadicentersforpre- schooling?Yes/NO ---- Yes

ii) HowmanyBalSabha’swereorganizedintheGramPanchayat----- 02

iii) WhethertheissuesraisedbyBalSabhaareaddressedduringtheGramSabha. Yes/NO ----- Yes

iv) WhetherGramPanchayatistrackingthedatarelatedtodropoutchildrenandchildrenwithirregular attendance?Yes/NO. ------- Yes

v) DoalltheschoolsundertheGramPanchayathaveseparate toiletsforgirlsandboys?Yes/No --- Yes except PS Pranigam

**5 Villagewithgoodgovernance**

i) IsCSClocatedintheGramPanchayatBhawanornot? No ( Panchayat ghar in rented accomudation)

ii) IsthelistofbeneficiariesrelatedtotheSchemes/ProgramsdisplayedontheGrampanchayatwallor not? --Yes

iii) DoestheGramPanchayathasitsbuildingornot? ---- No ( Building Partially Constructed & is Languishing)

iv) IstheGramPanchayatofficefunctionalornot? ------ Yes

v) Aretheactivities approved undertheHalqaPanchayatDevelopmentPlandisplayedontheGram Panchayatwall or not -----YES

vi) IsSocialAuditofearlierSchemes/Programscarriedoutornot? ---- Yes

**6 Povertyfreeandenhancedlivelihoodvillage**

i) HasGramPanchayatdevelopedanycriteria fortheidentificationofthepoor?Yes/Noifyesspecify – No ii) HavealltheeligiblehouseholdsregisteredinPDSornot? ------Yes

iii) HasGramPanchayatprovidedspaceforSelf-helpGroupsinPanchyatGharforholdingmeetings or not---- SHG not available

iv) HavealltheeligiblehouseholdsbeenregisteredforPensionornot? ----- Yes (all eligible registered)

v) HasGramPanchayatfacilitatedYouthforSkillEnhancementCoursesandPlacement? --- No

vi) HasJobCardsbeendistributedtoalltheeligibleindividualsunderMGNREGA? ---- Yes

vii) HasGramPanchayatfacilitatedSHGsforBankAccountLinkages? SHG not available

**7 Sociallysecuredvillage**

i) WhetherGramPanchayatismaintainingdatarelatedtoDifferentlyAbledPeople? ------ Yes

ii) IsGramPanchayatOffice DisabledFriendlyornot? ---- Yes

iii) Areprovisionsfora separate BudgetundertheResourceEnvelopeforWomenandChildrenmadeor not? ----No

iv) DoalltheSchools intheGramPanchayathavefacilitiesforDifferentlyAbledChildrenliketoilets, barrier-freeaccess,etc.,ornot? ----- Available in few schools

v) Arealltheeligibleindividualsaregettingpensions,likeoldagepension,widowpension,etc? ----- Yes

vi) ArealltheeligiblehouseholdsgettingbenefitsfromIAYornot?

------ Yes

**8 EngenderedDevelopmentinVillage**

i) HowmanyMahilaSabha’swereorganizedintheGramPanchayat------- 01

ii) WhetherSHGsfederationshavebeenprovidedspaceformeetings inthePanchayatBhawan(Yes/ No) --- No SHG formed Yet

iii) WhetherGPshavetakenstepsforincreasingwomen’sparticipationinGramSabha(Yes/No) ------ Yes

iv) NumberofwomenbeneficiariesheadedhouseholdscoveredunderPDS

system…… 16

v) Numberofbeneficiaries(outoftotaleligiblepopulation)receivingsocialprotectionbenefitsunder

PradhanMantriMatritvaVandanaYojana……… 61

9 Self-sufficientinfrastructureinthevillage

i. WhetherGPhasa CommunityHallwithaccesstoelectricity,furniture,watersupply, toilet…………… under construction

ii. WhethertheDisastermanagementplanisavailableattheGPLevel(Yes/No) ----- No iii. Whetherchild-friendlyparkwithrequiredfacilitiesisavailableinGP(Yes/No) ---No iv. WhethertheGPhaseasyaccesstoGodownforstorage(Yes/No) ------ Yes

v. Whetherstreetlightsareprovidedinpublicplacesforensuringsafety(Yes/No) –YES at few places but require more

**DAY2ACTIVITIES**

**AGENDANO.2**

SensitizevillageresidentsaboutmyScheme”portal(myscheme.in)whichincludesinformationaboutall theschemesbeingrunbyCentral/State/UT govtacrossthecountry------- Activity carried out & awareness about “My scheme portal given.

*(SchemeMaterialavailablefromhttps://jkpanchayat.in/b2v4.php)*

**DAY2ACTIVITIES**

**AGENDANO.3**

HoldmeetingoftheBiodiversityManagementCommitteestodeliberateonissues pertainingtoconserva- tionofbiodiversityandsustainableutilizationofbiologicalresources.HeshouldcheckPeopleBiodiversity register(PBR)ofthatpanchayatandreviewifBiodiversityManagementCommittee constitutedforthat panchayatis holdingminimum4meetings inayearandmeeting onceinevery3months *(RoleofBMC availableathttps://jkpanchayat.in/b2v4.php)*

COMMITTEEMEMBERS PRESENT ----- ------------------08

BIODIVERSITYREGISTERPHOTOS ----------------------- Register not framed yet

PAST 4MEETINGDETAILS-DATES,MINUTESPHOTOS

 ------------------------- No meeting during current year (HOWEVER Members of the committee were asked to ensure 04 meetings (Biodiversity) per year i.e. Meeting after EVERY 03 months)

**DAY2ACTIVITIES**

**AGENDA4**

Visitingofficershallalsoplanandconductpanchayatlevelconvergencemeeting ofalldepartmentsand prepareVillagedevelopmentplanforvillage,inconsultancywithGrampanchayat,discussitingram sabhaandgetitapproved. ------ **Meeting held & demands are enumerated BELOW:**

1. Upgradation of road from satoora to hajin & Hajin to Gulistan
2. Construction of flood protection bund at many vulnerable locations.
3. Construction of fencing wall at upper Primary school Hajin.
4. Improvement of electric infrastructure at chek-i-satoora & upgradation of 25KVA transformer installed at Hakwan
5. Establishment of 02 additional awanwari centres at Hajin Village.
6. Construction of bridge at Nallah Hajin Astannard
7. Construction of safety bund at Bilal Masjid JAT Mohallah Hajin.
8. Seprate health sub centre for Hajin Village.
9. Replacement of deteriorated under ground pipe line at check-i- Satoora.
10. Construction of foot bridge for Govt HS Gulistan

**InadditionGPDPplanshallalsoinclude:**

 Touristplaceswhichneedtobedeveloped-------Nagaberi

 Specificproductwhichneedstobedeveloped------Maize Production

 Tourism-homestays---Need to be constructed

 20candidatesfortrainingunderHimayatschemealongwithtradeinwhich trainingistobegiven :

|  |  |  |  |  |
| --- | --- | --- | --- | --- |
| Sr. No. | Name  | Parentage | Qualification | Residence |
| 01 | Saifullah Fayaz | Fayaz Ahmad Dar | 12th | Gulistan |
| 02 | Junaid Ahamad Dar  | Nazir Ahmad Dar | 12th | Gulistan |
| 03 | Muzamil Ahmad Dar | Mohd yousuf Dar | 12th | Gulistan |
| 04 | Shareef din Gojar | Mohd Iqbal Dar | 10th | Check Satoora |
| 05 | Asif Ahmad Wani | Mohd Altaf Wani | 12th | Gulistan |
| 06 | Faizal Ahmad Mir | Javed Ahmad Mir | 10th | Gulistan |
| 07 | Rasikh Ahmad Khan | Mohd Yousuf khan | 12th | Pronigam |
| 08 | Zahid Ahmad Dar | Ali Mohd Dar | BA | Gulistan |
| 09 | Mahjabeena Akhtar | Mohd Sultan Khan | 12th | Pronigam |
| 10 | Rafiq Ahmad Gojar | Mohd Iqbal Gojar | 10th | Check Satoora |
| 11 | Zubaid Ahmad khan | Ab Hameed Khan | 12th | Gulistan |
| 12 | Zaffar Ahmad Khan | Bashir Ahmad Khan | 12th | Gulistan |
| 13 | Zeeshan Ahmad Khan | Gh Hassan Khan | BA | Gulistan |
| 14 | Rasik Ahmad Dar | Ali Mohd Dar | 12th | Gulistan |
| 15 | Mudasir Ahmad Bhat | Ab Rashid Bhat | 10th | Gulistan |
| 16 | Nadeem Ahmad Khan | Mohd Yousuf Khan | 12th | Gulistan |
| 17 | Mehboob Ahmad Dar | Gh Qadir Dar | 12th | Gulistan |
| 18 | Yawar Ahmad khan | Ab Gani Khan | 12th | Gulistan |
| 19 | Mukhtar Ahmad Gojar | Qasim Gojar | 8th  | Gulistan |
| 20 | Rafiq Ahmad Gojar | Mohd Yaseen Gojar | 10th | Hajin Gulistan |

**DAY2ACTIVITIES**

**AGENDA5**

Ensuresaturationoffollowingschemesandgivestatus:

|  |  |  |  |
| --- | --- | --- | --- |
| **NAMEOFTHESCHEME** | **TOTALELIGIBLE BENEFICIARIESIN THE VILLAGE** | **TOTALBENEFICIARIESWHO AVAILEDTHEBENEFITSOFTHESCHEME** | **REASONSFOR PENDENCY** |
| GoldenHealthCardunderAyushmanBharat |  1534 |  1520 | 14 |
| Jananisurakshayojana |  53 |  53 | 0 |
| OLDAGEpension |  84 |  84 | 0 |
| Widowpension |  16 |  16 | 0 |
| Disabilitypension |  14 |  14 | 0 |
| Domicilecertificate |  1534 |  575 | 959 (who have not applied yet) |
| Kisancreditcard |  282 |  188 | 94 |
| PMkisansammannidhi |   103 |  103 | 0 |
| Landpassbook | 280 | 16 issued during B2V4 Programme | All the balance have been generated |
| Registrationofvillageven- dorsonGEMportal | -------- N/A --------- |
| Registrationofvillagecon- tractorsonjktendersportal |  05 |  05 |  0 |
| Registrationofvillagecon- tractorsonPWDportal |   |  -------- Nill-------- |  |
| Incompletebuildings/pro- jects | Panchayat building partially constructed is languishing |

**DAY2ACTIVITIES**

**AGENDA6**

**NASHAMUKTABHIYAN**

1. Whethergramsabharesolutionpassed---------------Yes

2. Detailsofactivities conducted ------- Public awareness, Road shows, programs in schools like

 Run for fun etc.

3. Whetherallactivities andGSresolutionuploadedonjkpanchayats.inportal -----Yes

4. Howmanydrugaddictsinthevillage ------Nil

5. WhetherreportedtotheDeputyCommissioner------yes

6. Howmanyregisteredforrehabilitationundergovernmentprogramme----Nil

 **DAY2ACTIVITIES**

**AGENDA7**

**SOCIALAUDIT**

Conductsocialauditofatleast5workseachunderfollowingschemes:

|  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- |
| NAMEOFTHE SCHEME | DETAILSOFTHE WORKS | YEAROFWORK APPROVAL | AMOUNT APPROVEDFORTHEWORK | WHETHERWORKEXECUTED SATISFACTORILY | GEO- TAGGED PHOTOS | ANY GRIEVANCE RECORDED RELATINGTOTHAT WORK |
| MGNREGA | Details provided below |
| PMAY |
| IHHLUNDERSBM-G |
| CSCUNDER SBMG |
| AMRIT SAROVARS |

|  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- |
| Name of the Scheme | Details of Works | Year of work approval | Amount approved for the work | Whether work executed | Geotagged photos | Any Grievance recorded relating to that work |
| MG-NREGA | C/O P.Bund near Graveyard at Gojar Basti Puranigam | 2021-22 | 1.9715 |  | Yes |  |
| C/O create Bund near H/o Gh Hassan Banday and others at Check Satoora | 2021-22 | 4.9047 |  | Yes |  |
| C/O P.Bund near Graveyard at Chanipand check Satoora | 2021-22 | 1.7166 |  | Yes |  |
| C/O lane/ P. bund from land of Gh Jaggad and Taj Khatana at Hajin | 2021-22 | 2.08 |  | Yes |  |
| C/O P. Bund near Koot Masjid at Hajin | 2021-22 | 1.3384 |  | Yes |  |
| PMAY | C/O PMAY house of Ab Gani Gojar at Puranogam Gulistan | 2021-22 | 1.50 |  | Yes |  |
| C/O PMAY house of Javed Ahmad Gojar at Puranigam Gulistan | 2021-22 | 1.50 |  | Yes |  |
| C/O PMAY house of Lal din Gojar at Hajin Gulistan | 2021-22 | 1.50 |  | Yes |  |
| C/O PMAY house of Ahmad Gojar at Hajin Gulistan | 2021-22 | 1.50 |  | Yes |  |
| C/O PMAY house of Akbar Gojar at Hajin Gulistan | 2021-22 | 1.50 |  | Yes |  |
| IHHL UNDER SBM-G | C/O SBM Point at house of Reyaz ahmad Gojar at Puranigam | 2020-21 | 12000.00 |  | Yes |  |
| C/O SBM Point at house of Shamsdin Gojar at Puranigam | 2019-20 | 12000.00 |  | Yes |  |
| C/O SBM Point at house of Bashir Koot at Check Satoora hajin | 2020-21 | 12000.00 |  | Yes  |  |
| C/O SBM Point at house of Ab Rashid Jaged at Hajin | 2019-20 | 12000.00 |  | Yes |  |
| C/O SBM Point at house of Ab Rashid Bhat at Gulistan | 2020-21 | 12000.00 |  | Yes |  |
| CSC Under SBM-G | C/O CSC near Jamia Masjid Shareef at Gulistan | 2020-21 | 2.00 |  | Yes |  |
| Amrit Sarovar | Development of Asran nard Gulistan | 2022-23 | 0.38 |  |  |  |

**DAY2ACTIVITIES**

**AGENDA8**

**MAHILASABHA**

Totalwomeninthevillageabovetheageof18----

Totalattended-----18

**Proceedings of MAHILA SABHA**

 The Mahila Sabha was conducted as part of B2V4 Program on 31/10/2022 in the Panchayat Halqa Gulistan in which the visiting

 Officer emphasized the importance of Panchayati Raj to the women present. The visiting officer also deliberated on the fact that

 why Mahila Sabha is being conducted and what kind of demands women folk can raise before him and / or the Panchayat members

 in general. Later on the visiting officer asked the women present to put forth their demands and noted down which are produced as

 under:-

1. Separate health sub centre for Hajin Village.
2. Road connectivity to Pranigm village and koote hamlet of Hajinard village as pregnant Ladies face lot of difficulties particularly at the time of their delivery.
3. Aanganwari workers also demanded that the ration should be delivered at the respective villages instead of Satoora which involves extra carriage charges which they have to bore by themselves in addition to facing lot of other difficulties.

 The Sabha concluded with vote of thanks to the chair.

**DAY2ACTIVITIES**

**AGENDA9**

**BALSABHA**

Holda balsabhaandrecordproceedings:

Totalchildreninthevillageabovetheageof: 06 to 18years =102 , Total attended: 52

 **Proceedings of BAL SABHA:**

 The Bal Sabha was conducted in the premises of Govt. High School Gulistan in which almost 50 to 55 children participated. The Sabha was witnessed by all the teachers of the school, employees / front line workers of the departments present and few civil citizens. The proceeding were started byMr Showkat Ahmad Dar of RDD department with the introductory remarks and later on the visiting officer very candidly interacted with the children, participated in sports activities with them. The visiting officer emphasized the importance of education and the hard work needed there in, in addition to the importance of extracurricular activities. The visiting officer awared the children about the facilities available in the schools now a days which were not there when he visiting officer used to go to school. The visiting officer then asked the children to ask questions and put forth the demands which are produced as under:

1. A class 9 child demanded that a projector set should be made available to the school.
2. Another class 5 child demanded playground suitable for playing cricket.

The children then presented cultural shows which impressed the audience.

 The Bal Sabha concluded with the vote of thanks

*(Plinsertpointerstobediscussedthere–referpalliproceedings)*

**DAY2ACTIVITIES**

**AGENDA10**

**INAUGURATIONS**

|  |  |  |  |
| --- | --- | --- | --- |
| **SR NO.** | **ASSETS/ACTIVITIES INAUGRATED** | **STATUSOFTHEASSET/AC- TIVITIES(NUMBER,OTHER DETAILS)** | **GEO-TAGGED PHOTOS** |
|  | VILLAGEHAATunderJKSRLM (SUN- DAYMARKET) |  -------- N/A -------- |  |
|  | PMAYhousesifanyreadyforinaugra- tion |  04 houses |  |
|  | Swachhgramprojects-segregation shedsetc |  -------- N/A -------- |  |
|  | Amritsarovars |  01 ---- Which is located away from local population |  |
|  | Sportskits |  02 ---- Issued to senior citizens during B2V4  |  |
|  | Villageculturalevents |  Conducted at High School Gulistan in which 52 children, employees of different departments & some civil members of locality participated  |  |
|  | JJMassets/projects |  -------- Nil-------- |  |
|  | Anyothertobeidentifiedatdistrict level | Inaugurations of 02 culverts & one flood protection Bund  |  |

**FOLLOWUPOF(B2V1,B2V2&B2V3):**

*(Prefilledexcelsheet tobetakenfromdistrictlevel/andalsotobedownloaded*

*from*[*www.jkpanchayat.in)*](http://www.jkpanchayat.in)

|  |  |  |  |
| --- | --- | --- | --- |
| S.NO. | Particulars | Actiontaken | Remarks# |
| I. UrgentPublicRequirements/Demands-B2V1 |
| 1 |  Mobile Telecom Connectivity |  No action taken on ground yet, (except in Hajin)  |
| 2 | Upgradation of road from Gulistan to Hajin  | Macadamized1/2 km at Gulistan  |
| 3 | Flood Protection work under 14 FC | Completed by RDD but FPW needed at many other places |
| 4 | Upgradation of road from Satoora to Pranigam | Except Macadamization of ½ km nothing done |
| 5 | Separate village guard for panchayat | Not fulfilled  |
| 6 | Establishment of new Aaganwari centre  | Not Fulfilled |
| 7 | Replacement of electric poles and conductor | Work carried out |
| II. UrgentPublicRequirements/Demands-B2V2 |
| 1 | Up gradation of electric infrastructure  | electric infrastructure upgraded barring very few locations  |
| 2 | Concrete bunding of Zwestan Nalla  | Work carried out by RDD but needs to be executed at balance locations also  |
| 3 | Construction of culvert near HS Gulistan | Executed by RDD |
| 4 | Construction of road Hakwan Satoora | Not Constructed yet |
| 5 | Road connectivity from HS Hajinard to PS Hajinard | Not Constructed yet |
| 6 | Construction of girls Toilet in PS Hajinard | Not yet |
| S.NO. | Particulars | Actiontaken | Remarks# |
| III. MajorProblems–B2V1 |
| 1 |  Mobile Telecom Connectivity |  No action on ground yet, (except at Hajin)  |
| 2 | Dilapidated road from Satoora to Pranigam |  No action taken (except ½ km at gulistan) |   |
| 3 | Dilapidated road from Gulistan To Hajin | No action taken yet (except ½ kmr at Gulistan) |
|  |  |  |

|  |  |  |
| --- | --- | --- |
| 4 | Bridge at Astan nard | No action taken yet |
| 5 | Flood protection works on Gulistan Nallah | Done at few places, pending at others |
| IV. MajorProblems-B2V2 |
| 1 | Construction of Soil Conservation Bunds in the Pyt. Area to protect the soil from errosion |  No action  |
|  2 | Mobile Telecom Connectivity | Jio Net work Available at various locations but not all. More needs to be done  |
|  |  |  |
|  |  |  |
|  |  |  |
| V. MajorProblems-B2V3 |
| 1 | Replacement of electric poles and conductor in gram pyt. Gulistan and Hajin | Improvement in electric infrastructure carried out at many locations and few are pending |
| 2 | Mobile Telecom Connectivity | Barring few places Mobile net work not available  |
| 3 | Establishment of new Aanganwari centre at Hajin | No action taken yet |
| 4 | Upgradation of road from Gulistan to Hajin |  No Action taken except macadamization of ½ km at Gulistan |
| 5 |  |  |
| VI. MajorComplaints-B2V1 |
| 1 | Non availability of animal/ sheep husbandry at GP Gulistan  | No Progress yet  |
| 2 | Forest Land encroachment by Nomads | No action yet |
| 3 |  |  |
| VII. MajorComplaints-B2V2 |
| 1 | Non availability of animal/ sheep husbandry  | No Progress yet  |
| 2 | Forest Land encroachment by Nomads | No action yet |
| 3 |  |  |
| VIII. MajorComplaints-B2V3 |
| 1 | Replacement of electric poles and conductor in gram pyt. Gulistan | Improvement in electric infrastructure carried out at many locations and few are pending |
| 2 | Establishment of new Aanganwari centre at Hajin | No action taken yet |
| 3 |  |  |

**OVERALLPERCEPTIONOFFUCNTIONING OF GOVERNMENTDEPARTMENTS**

1. **BESTDEPARTMENT: RDD, PDD**

**2. LEASTRESPONSIVEDEPARTMENT: Animal Husbandry**

**GENERALASSESSMENTOFTHEVISTINGOFFICER**

|  |  |
| --- | --- |
| I | AnymajorcomplaintbroughttothenoticeoftheVisitingOfficer: S. No. 1 Next Page |
| II | Major/urgentpublicdemandsthatwas/werereflectedearlierbuthavenotbeenaddressedsofar: S. No. 2 Next Page |
| III | Overallassessmentofthevisitandsuggestions:(Thevisitingofficertoensurethattheoverallassessmentisrecordedindetailsalongwithconcretesugges- tions) S. No. 3 Next Page |
| IV | OverallRatingofgovtfunctioningas givenbythePanchayat(Scaleof0to10) S. No. 4 Next Page |
| V | CertificatefromSarpanchthatthevisitingofficerhasstayedinthepanchayatfor2days S. No. 5 Next Page |

**SignatureofSarpanch SignatureoftheVisitingOfficer**

**Name……………………… Name………………………**

**S. No 1**

 **Major complaint :-** The major complaint brought forward by the public is that many demands like telecom/ mobile Connectivity, upgradation of road from Satoora to Pranigam & Satoora to Hajinar were repeatedly reflected in all previous B2V programs but have not yet been fulfilled. Also Govt has not promoted NAGABERI as Tourist Destination by way of making it accessible via road connectivity or installation of GANDOLA, despite having immense potential.

 **S. No. 2**

 **Major / urgent public demands reflected earlier:-**

1. Up gradation of road from Satoora to Pranigam and Satoora to Hajinar.
2. Telecom/ Mobile connectivity issues.
3. Separate village guard.
4. Construction of foot bridge for Govt High school Gulistan

**S. No. 3**

 The visit was satisfying overall. People very candidly raised their demands and their expectations were found very high . However due to non addressal of few urgent public demands some were hopeless. Most of them demanded timely addressal of the balance demands already raised in B2V1, B2V2 and B2V3 programs.

 Further public demanded promotion of NAGABERI as tourist destination which has got immense potential to become the BEST tourist destination of Jammu & Kashmir. The need could be primarily fulfilled by either road connectivity or making it accessible by installation of GANDOLA like the one at Gulmarg (J&K ). This could be very helpful in the revenue generation besides reducing or in fact eradicating the poverty of TRAL area as whole and Gulistan Panchayat Halqa in particular. Moreover the overall functioning of Govt machinery was found satisfactory.

**S. No. 4**

 Overall Govt Functioning rated by Panchayat is ‘7’

**S. No. 5**

 **Certificate:-**

 Certified that the visiting officer Namely Er. Shabir Hassan Lohar has stayed in the Panchayat Halqa for two (02) days i.e, 30/10/2022 and 31/10/2022 in connection with B2V4

SD

sarpach halqa Gulistan

**Major demands put forth by public before the visiting officer which require immediate and urgent attention**:-

1. NAGABERI should be declared as tourist destination and should thus be made accessible by road connectivity or installation of GONDOLA like the one at Gulmarg. Nagaberi can become J&K’s best tourist destination if made accessible and has immense potential to change the fortunes of the people of Tral area in general and Panchayat Halqa Gulistan in particular.
2. Upgradation of road from Satoora to Pranigam and Satoora to Hajin which is totally dilapidated.
3. Up gradation of 25 Kva transformers installed at Pranigam and Hakwan falling under PH Gulistan to 63 KVA as the same get damaged during winters and due to unavailability of road connectivity have to be dragged down up to 1.0 Km distance.
4. Very poor telecom connectivity at most places and unavailability at other places like puranigam and Zwestan (Gulistan).
5. Establishment of 03 new Aaganwari centres one each at Jagad mohalla Hajin, Jat Mohalla Hajin and another at Gulistan.
6. Up gradation/ improvement of electric infrastructure at Check –i-Satoora.
7. Construction of Bridge at Nallah Hajin Astanard
8. Construction of safety bund at Bilal Masjid Jat Mohalla Hajin.
9. Construction of fencing wall to Jamia Masjid at Check-i-Satoora and upper Primary School Hajinard .
10. Repairment of building (damaged in floods), repairmen of toilets and enhancement of accomudation at Govt upper Primary School Hajinard
11. Separate health sub centre for Hajin village
12. Route to Primary School Hakwan needs repairment. Further since the front veranda was damaged due to cloud burst which occurred in the hills needs its reconstruction on war footing basis as the rainy water peeps in to class rooms and this hinders the routine work of the school. Accomudation of the school needs to enhanced for which land is already available .
13. Up gradation of UPS Hajin to High school and primary school Hakwan to middle school was an unequivocal demand of public.
14. Separate Patwari office, separate village guard, separate CSC centre, Separate Khidmat centre was also an unequivocal demand of public.
15. Construction of flood control bunds at many places of need and concrete bunds to avoid lands sliding at many places of requirement particularly near H/O Bashir Ahmad Hajam and Ab Rashid Sangu.
16. Replacement of deteriorated under ground pipe line at Check-i- Satoora.
17. The water tanks run by PHE department at Gulistan and Pranigam are very old constructions and are in damaged condition. The proposal for new construction has already been forwarded to higher ups as reported by one PHE front line worker present. One more tank at Hajinard which was partially damaged by flood needs to be constructed afresh in order to give a good quality of water supply to people.
18. Animal Husbandry or Sheep Husbandry not available.
19. Unavailability of regular/permanent staff at primary sub center Gulistan.
20. Construction of toilet at PS Puranigam.

21)CONSTRUCTION of foot bridge for HS gulistan.





































