`

4

15TH OCTto3RD NOV,2022

KEYFEATURES

•     DeputyCommissionerstoleadtheinitiative

•    RuraldevelopmentDepartmenttobethenodaldepartment

•	PlanningDevelopment&MonitoringdepartmentandITtobethesupport departments

ACTIONSANDTIMELINES

| ACTION | RESPONSIBILITY | LATESTBY | REMARKS |
| --- | --- | --- | --- |
| Janabhiyan | All departments | Oct15-26th | Going on |
| DeputationofSecttstaff/ HoDs | GAD | Oct14 | Done |
| DeploymentofStaffto Panchayatsandservingof ordersondeployedofficers | DCs | Oct25 | DCswilldeployseniorlevelstaff fromthedistricts.Strictactionto betakenagainstabstentions.No exemptionstobegiven |
| Trainingofdistricttrainors onB2V4 | RDD | Oct26 |  |
| Trainingofvisitingofficers | DCs | Oct27 |  |
| FieldVisitstobecompleted by | VisitingOfficers | Nov3 | DCstosuperviseandensurethat eachPanchayatisvisitedwithin theperiodspecified |
| DataofB2V4tobe uploadedby | VisitingOfficers | Nov10 | DCstosuperviseandensurethat dataofallPanchayatsisupload- edbythevisitingofficerwithin theperiodspecified |

INSTRUCTIONSFORTHEVISITINGOFFICER(DAYWISE)

| DATE | INSTRUCTIONS | ACTIONPOINTS |
| --- | --- | --- |
| Day0 | Meetingwithdeputy commissionerandhis/her team | a. TakeprintoutsoffilledbookletsofB2V1,B2V2andB2V3from www.jkpanchayat.in b.Alsotakeprintoutsofthesummarizedexcelsheetsofthe previousphasesfromwww.jkpanchayat.in c. CollectATRsonissuesraisedduringprevious3phasesfromthe officeofDeputyCommissioner(Planningdeptt) d.Takeprintsofblank 2bookletsofB2V4fromwww.jkpanchayat.ine.Takeplansfor2previousyearsandATRsfromtheplanningdeptt f. CompletetrainingsondifferentcomponentsofB2V4being organizedbyrespectiveDeputyCommissioners g.CollectListofnewworksstarted/ongoing/completedduringthe previousandcurrentFinancialyearunderthefollowingheads: • PRIgrants • DistrictPlan • UTplan • MGNREGA • Otherschemesofotherdepartments • Anyotherwork h. Plans/beneficiarylists: • MGNREGAdraftplandocumentfortheyear2022-23. • ListofAwaas+beneficiariesalongwithIHHL Convergence • Listofpensionbeneficiaries. • ListofSHGs • Listofagricultureschemebeneficiaries i. Listsofbeneficiariesfor: • Variouscertificates/benefitstobedistributedbythe visitingofficer. • Anyotheractivitiesidentifiedbydifferentdepartments |

| Day1 | Reachthevillage | 1. | Ensurethatallfrontlineworkersofdifferentdepttsarepresent. |
| --- | --- | --- | --- |
|  |  | 2. | Ensureexhibitionbydifferentdepts.aboutindividualbeneficiary schemes |
|  |  | 3. | InspectJKB/PSBcounters/outlets |
|  |  | 4. | Participate/ensureorganizationofsportsactivityinplayfield,talent hunt/culturalevent/youthactivity |
|  |  | 5. | GandhiKatha(suggesteddetailsuploadedonjkpanchayat.in) |
|  |  | 6. | Visitatleast2amritsarovarsandgetitsgeotaggedphotos |
|  |  | 7. | InspectKhidmat(CSC)CentresandcreateGenerateawarenesson 225schemesparticularlyG2CschemeslikeBEAMS,Janbhagidari, AapkiZaminAapkiNigrani,DigitalJ&K |
|  |  | 8. | Visitingofficershallalsoplanandconductpanchayatlevelconver- gencemeetingofalldepartments |
|  |  | 9. | CheckeffectivenessofCentrallysponsoredschemes |
|  |  | 10. | VisitandinspectallgovernmentestablishmentsincludingPHE, AWC,FPS,schools,etc |
|  |  | 11. | Attemptsaturationofdeliverableso JanAbhiyanandwherever deficienciesfound,leadadrivetoachievealldeliverables |
|  |  | 12. | Assesseffectivenessofsanitationcampaigninthepanchayat |
|  |  | 13. | Ensureselfemploymentactivitiesfor15youthperpanchayat |
|  |  | 14. | Identify20potentialcandidatesperpanchayatforHIMAYATtraining alongwiththetradeonwhichtheywanttraining |
|  |  | 15. | Whereverpossible,distributeemploymentlettersforpeopleselect- edundervariousgovernmentemployments |
|  |  | 16. | Intheevening,holdnormalmeetingwith seniorcitizens,govtem- ployeesincludingretiredemployees,exservicemen,youthclub,and any citizens ofthevillagewhoareenrolledincollege/university |
|  |  | 17. | OpendiscussiononNashaMuktAbhiyan |

Day2            Haveameetingwithall stakeholders-depttofficials andpanchayatmembers

1.       Discussionontheandassesstheprogressofdifferentschemesrelating tothelocalizedSDGsprioritizedforthatvillageaspertheresolution passedby thatGramPanchayaton21st April22,onNationalPanchayti RajDay.

2.	Sensitizevillage residentsaboutmyScheme”portal(myscheme.in) whichincludesinformationaboutalltheschemesbeingrunbyCen- tral/State/UTgovtacrossthecountry

3.	Hold meeting of theBiodiversityManagementCommitteestodeliber- ateonissuespertaining toconservation of biodiversityandsustaina- bleutilizationof biologicalresources.

4.       PrepareVillagedevelopmentplan,inconsultancywithGrampanchayat, discussitingramsabhaandgetitapproved.

5.       Ensure saturationofsoilhealthcardandgoldenhealthcardunderGold- enHealthCardunderAyushmanBharat,

6.       Ensuresaturation  of OldAge PensionScheme

7.       EnsureDomicileSaturation.

8.       EnsureKCCSaturation

9.       Ensure saturationoflandpassbooks

10.     Ensureregistrationofvillagevendorsneededforanyscheme,onGEM

portal

11.     Ensurepanchayatcontractors registration

12.     EncouragePanchayatmembers forimportanceofplantationdrivein

PanchayatunderHarGaonHariyali

13.     Ensure paintingondigitalJ&Kinpanchayatghars

14.     Ensure paintingonpanchayatactivitesandCSSinpanchayatghars

15.	Thevisiting officeshallchecknoof kindergarten andplayfields present inthepanchayat for kidsandstudents,iftheinfrastructure present inthesearegoodenough.

16.     Holdmeeting withpanchayatmembers todiscussaboutcorruption menaceandstepsrequiredtomakeJ&Kcorruptionfree

17.     Obtaina candidassessmentaboutperformanceofvariousdeptts in- cludingfairfeedbackaboutdiscrepanciesinfunctioning

18.	Check thestatusof NashaMuktAbhiyanandreporting of drugad- dictstoDeputyCommissioner.

19.     IdentifyTouristDestinations,Circuits,ThemeTreks,IdentifyHomestays, providesupportfortourismactivities throughVillageCooperative

20.     OrganizeTalentHuntatPanchayatLevel

21.     Conductsocialauditofatleast5worksunderfollowingschemes:

a.       MGNREGA

b.PMAY

c.        IHHLtoiletsandpayments d.CSCs

e.AMRITSAROVARS

22.     Holda mahilasabha anda balsabhaandrecordproceedingsinthefor- matgiven

23.     InauguratevillagehaatunderJKSRLM

24.     Checkifyouthclubsareformedinthepanchayatandwhatactivities theyareengagedin

25.     Organizea villagelevelculturaleventtoengagepanchayatmembers

26.     SensitizeGPaboutE-kitabkoshaninitiativeofJ&KGovtforempowering youthsthrough onlinedigitalliteracy

GENERALINSTRUCTIONS

1.	Thevisitingofficershallrefrainhimself/herselfgivingorofferinganycommitmentonbehalfofthe governmentandshalladoptanunbiasedattitudeinreportingissues.As faraspossible,his/her observation shouldbebasedona fairandanalytical viewemergingfromhis/herinteractioninthe village.

2.	Heisgoingtothevillageasplanningofficer,notforsanctioninganyworksorformakinganycom- mitments.

3.	Whilepreparingvillagedevelopmentplan,hehastoensurethat,demandsareprioritizedandre- flectedunderavailableschemes,wherevernecessarythelargerworksaretobereferredtoadminis- trativedepttunderCSS/UTplansunderintimationtoDCsandrestoftheworkstoDCsforreflecting itunderdistrict/CSS plans

4.    His workshallbehardcoreplanningandauditandisnota PRexercise.

5.	EveryDeputyCommissionerhastoensurethatatleastoneRDDofficial(ideallyPanchayatSecre- tary)ispresent  ineverypanchayatwithrelevantpanchayatrecords,toensureconductofallactivi- tiesasplanned.Panchayatwiseorderneedstobeissuedinadvance.

6.	Visitingofficershouldideallycarryhis/herlaptoptocompletethereportsatthepanchayatlevel itselfanduploadthefinalreport,duly signedbothbythesarpanchandbythevisitingofficeron www.jkpanchayat.inportal,beforetheyleavepanchayat.

7.	Focus ofvisitareyouth,skills,self-employment,nashamukt,bhrashtracharmukt,Rozgaryukt J&K, besidestocarryforwardtheactivities duringJanAbhiyanandsaturatethem.

8.    Inadditionattentionmaybegiventothefollowingareas a.     MakefulluseofCentrallySponsoredSchemes

b.Saturationofindividualbeneficiaryschemes c.     Self-employmentschemes

d.Banklinkedschemes-includingdepartmentalsubsidyschemes e.Empowermentandtransparencythrough digitalinitiatives

f.       Effectivenessofgrassrootsmachinery–

i.       Patwari,VLWpresent  andavailable

ii.      AvailablefundsutilizedinpublicinterestandasperGramSabharesolutions iii.   Fairness ingovernance

iv.    CSS/Individual beneficiaryschemesetc v.      BrashtacharMuktJ&K

vi.   BhaiMuktJ&K

vii.  NashaMuktJ&K

9.	ThePRImembers (Sarpanchs,Panchs,BDCChairperson)shallbeattheforefrontofallactivities and givendueimportanceandtheapproach shouldbetostrengthenthemandmakethemfeelem- powered.He/sheshallensurethattheBDCchairpersonandSarpanch/Panch arepresent  atthetime ofinaugurationandceremonies.

10.	Visitingofficershallnotleavethedistrictwithoutuploadingthereport,duly signedonthewww. jkpanchayat.inportal.EveryDeputyCommissionerhastoensurethat.

A)   DetailsofReportingOfficer:

Name:   	Mrs Tanveer Ali

Designation:	Chief Engineer PMGSY Kashmir

Department/placeof  posting:	PMGSY/Kashmir division

Mobile No:	9469046525

EmailID:

Home District:

Datesof  visit:	30-31 Oct 2022

B)	LocationaldetailsofPanchayat:(tobepre-filled,informationtobetakenfromtheprevious phasesbooklets/summarizedexcelsheetuploadedonjkpanchayat.in/b2v4.php)(tobevali- datedbythevisitingofficerandmissingdetailstobefilled)

Nameof thePanchayat:	Seer

Local Government Directory(LGD )codeof  the Panchayat:	242913

Nameof  CD Block:	Aripal

NameofTehsil:	Aripal

Nameof    District:	Pulwama

C)     PanchayatProfile:

No.ofrevenuevillagesinthePanchayat:df	1

No.ofhamletsinthePanchayat:	02(Seer and Gang)

No.ofhouseholdsinthePanchayat:	247

Population(approx)of  thePanchayat:	1338

Part-II:

(TobefilledupbytheVisitingOfficerduringhis/hertwodayvisittothePanchayat.AllFieldshavetobe

filledbytheVisitingOfficerbeforethebookletishandedovertotheDC

FrontlineOfficers/OfficialswhowereassignedtothePanchayatfortheprogramme:

| Department | Name | Designation |
| --- | --- | --- |
| RDD | Mohd Yousuf Wani | Panchayat Secretary(Nodal officer) |
| PMGSY | Shabir Ahmad Tak | AEE |
| Agriculture | Madinat UL Nisa | Jr. AEO |
| Health | Waheeda Bano | Aisha Worker |
| Education | Zahoor Ahmad Bhat | Teacher |
| RDD | Manzoor Ahmad Waza | GRS |
| ICDS | Ameena Bano | Anganwadi Worker |
| FCS and CA | Obaid Bashir | Head Assistant |
| Forest Department | Manzoor Ahmad shah | Orderly |
| PDD | Manzoor Ahmad Khan | Jr. Line man |
| Jal Shakti | Ab Hamid Dar | Assistant Line man |
| Social Welfare | Zareefa Bano | Craft assistant |
| irrigation | Gh Hassan Bhat | JE |

Details of absent employees vis-à-vis list furnished by the DC office:

| Department | Name | Designation |
| --- | --- | --- |
| NIL |  |  |
| NIL |  |  |
| NIL |  |  |
| NIL |  |  |
| NIL |  |  |
| NIL |  |  |
| NIL |  |  |
| NIL |  |  |
| NIL |  |  |
| NIL |  |  |
| NIL |  |  |

DAY1-ACTIVITIES

AGENDA1:PANCHAYATASSETREGISTER

Infrastructure: Red color indicates availibility

1.		PanchayatGharInfrastructure a.  Govtbuilding/private

b.  New/needingrepairs

2.       Furniture(Y/N)

3.       Computer/printer(Y/N)

4.       Internet(Y/N)

5.       Telephone(Y/N)

6.       Toilet(CSC/partofpanchayatghar)(Y/N)

7.       Water(Y/N)

8.       Electricity(Y/N)

9.       Bankbranch(Y/N)

10.     CSC(Y/N)

11.     Patwarkhana(Y/N)

12.     Villagehaat(Y/N)

13.     Playground(Y/N)	needs upgradation

14.     School-

a.        Kindergarten(Y/N)

b.Primary(Y/N)

c.         Secondary(Y/N)

d. College (Y/N)

e.University(Y/N)

15.     AnganwadiCentre(Y/N)

a.        (govt/private)

b.Totalchildren enrolled	99

15.     AmritSarovars–details,location,condition	Nill

16.     Governmentoffices-details,whetherfunctional or not	Yes Functional

17.     Rationshop(Y/N)

18.      Placesoftourismimportance–names,littledetailsonhistorical/culturalimportance	Nill

19.      Villageheritagesites/treks-names,littledetailson historical/culturalimportance  (Trek Connection can be produced to Tarsar and Marsar)

20.     VLWOffice (Y/N)

21.     PrimaryHealthcareCentre(Y/N),

22.     ListofIncompleteBuildings-names,yearofconstruction	Nill

23.     ListofUnderutilizedBuildings-names   Nill

DAY1-ACTIVITIES

AGENDA2:

DIFFERENTINSTITUTIONS/INFRASTRUCTUREPROJECTSTOBEVISITED

| AMRITSAROVARS | Visit,verify | COMMENTS |
| --- | --- | --- |
| KhidmatCentres | Create/Generateawarenesson225schemes particularlyG2CschemsAapkiZaminAapkiNigrani, Beams,Janbhagidari,DigitalJ&K | Awareness done by Csc operator near about 225 schemees in Gram Panchayt Seer |
| JKB/PSBcounters/outlets | a)Statusofcounter b)Numberofvisitors |  |
| Incompletebuildings/pro- jects | Verify whetheridentificationandredistribution done | Nill |
| PDS | Visit,evaluate,onlinestatus | Satisfactory |
| PHC | Visit-evaluate,statusofstaff,equipmentand quality | Establish PHC for Pyt Halqa seer and this the most genuine demand of local people |
| Youthclubs | Meet,interact,seeksuggestions | Needs more awareness regarding employment generation schemes |
| SHG | Meet,identifyproblems,seeksuggestions | Emphasis on Bank to provide loans for establishment of new SHGs in Seer |
| PMAY | Inspect,Inaugurate | Great Job done by RDD department |
| Myschool,mypride progress;schools-water, toilets,staff | Visit,checkforwater,electricity,sanitation,meet studentsandstaff | Satisfactory but needs improvement |
| SwachhSBM | Evaluate | Satisfactory |
| Panchayatplayground, Sportskitsdistribution Villagegames | Ensure,verify.Participateinatleastonegamein theplayground | Sport events organized by Middle school seer and overall performance was quite remarkable |
| HarGaonHariyali, Planta- tiondrive | Evaluatestatus,feedback | Done by forest department at Py Halqa seer |
| Villageculturalevent Dangal/Haat/Mela | Participatein;ensurethatitisheld | Organized by school students and local youths and performance was really remarkable |
| Exhibitionofschemes | Ensurethateverydepartmentparticipatesand thatitcontinuesfortheentiredurationofB2V | Exhibitions by Social welfare, Handicraft and ICDS was good |
| JalJeewanMission verifica- tion- WSS/JSD Electricitysupply | Verify | Lalgam- Gulshanpora Scheme verified and inspected and suggested to improvement |

DAY1-ACTIVITIES

AGENDA3:SATURATEJANBHIYAN

DELIVERABLESANDRECORDDEFICIENCIESIFANY(INSERTDELIVERABLESLISTHEREASPERGADFORMAT

S.No.	Department 				Observattions

1		RDD			Saturated all JAN ABHIYAN activities

2 		IT			CSC Joint with Gang. No Seprate Gang

3		Finance		No self Employment as part of JAN ABHIYAN.

4              Revenue 		Patwar Khana not available  in Panchayat.

Inheritance Mutations  complete (FY:2022-23  -----10 cases).

Land passbooks  --- All generated and few issued by VO on spot

5              Health		-PMJAY Golden Cards

Total Population: 1338  Pending 23

- SWACHH Hospitals ;  No Health subcentre .

6              Social Welfare

Divyang Camps----- not available

Disability cards  14 Beneficiaries all of which have been saturated online

Anemia checkups being conducted regularly

7             Forest	One Forest guard for each village of Panchyat already available

plantation drive carried out  in the Halqa as part of Jan Abhiyan

8           Tourism   	Nagaberi(Tarsar Marsar) can  become the best tourist destination if road connectivity is provided to it or else access can be made possible by providing Gandola facility

9           Labour 	e-SHRAM --- 90- 95% already saturated but none as part of JAN ABHIYAN

10        School Education

Bringing back all out of school children------ 2 children were out of school in Panchyat  all of them were enrolled

- Transport 		No transport facility (Service) available

Mumkin Scheme --- Not available

- PDD		a. Unique  Nos checked.

b DTs with low oil --Topped up

c. Not DT found with load imbalance.

d. No non standard fuses found

e. Proper earthing ensured

f. Foliage removed

g. No claims pending

13.	CAPD		Shift to RCMS –100%

14. PWD		100% online payment with no manual interface---YES

15.  GAD	-100% Biometric attendance in Govt offices like Schools Health centres etc (offices     available panchyat)

-EPM  by all employees present

-100% property returns filled in by are present employees.

Online APKS HRMS impletation under progress

16. JALSHAKTI

17. Youth Services & Sports:      Sport activities carried out at PH Seer

18. Public Grivances                    Perception of departments among public is good and satisfying overall.

19. Agriculture & allied Sectors	PM Kissan – 122, Target -122, Saturated – 122		Skill

Kissan Mella – one held during current year

DAY1-ACTIVITIES

AGENDA4:

SELFEMPLOYMENTACTIVITIES

EnsureSelf-employmentactivities foryouth,distributeemploymentlettersforpeopleselectedunder varioussocialschemes(15ISTHETARGETPERPANCHAYAT)

Numberofcasesindifferentcategoriessanctioned: Detailsofthebanksanctioningit:

Totalamountinvolved:

DAY1ACTIVITIES

AGENDA5

Intheevening,holdinformalmeetings  withseniorcitizens,govtemployees,retdemployees,youthclub andothercitizenswhoareenrolledoncollege/universityandhavediscussiononGandhiKatha,Nasha MuktAbhiyan,corruptionfreegovernance,doublingfarmersincomeandrecordtheproceedings

Procedings recorded as below:--

A meeting in which senior citizens and Govt employees, rated employees youth club and other citizens was held as

part of B2V4 program inside the premises of Govt. UPS School Seer. The deliberations on the following topics

were made by the visiting officer.

- Gandhi Katha :- The role of Gandhi Ji in the independence of India, his policy of none violence, his simplicity, his life style and steadfastness were discussed in detail. Awareness about Gandhi Katha being broadcasted on radio and telecasted on TV was given so that people from different walks could benefit from it.

- Nasha Mukt Abhiyan :- The bad effects on the life of the drug dependent  people and that on the life and property of others was deliberated in detail. Various  methods like how counseling and treatment facilities in hospitals and rehabilition centres, capacity building programs with special focus on young population can help in avoiding/giving away this mence

- Corruption free govervance:- The focus was given on the fact that how can we build a corruption free society which inturn will lead to corruption free governance .

- Doubling farmers income:- Detailed deliberations were made by visiting officer on the initiative by PM to focus on how to double the income of farmers by the year 2022-23. Awareness about the fact that when was the scheme launched and it’s purpose was given.

DAY2

a.Noof Individual Compost Pits constructed Nill

b.No ofI ndividualSoak Pitsconstructed 64

V.          No.ofBiodiversitymanagementcommitteemeetingsheld:02

VI.         IsthenameofSarpanchdisplayedoncitizeninformationboardsofallRD&PRschemes:Yes/No

VII.       AreSarpanchsbeinginvolvedinstart/inaugurationofactivities:Yes/No

VIII.      WhethersubjectshavebeenassignedbytheSarpanchtothePanchs:Yes/No

IX.        Whethergrievancesredressalboxisinstalled:Yes/No

X.    NoofgrievancesreceivedpertainingtoPanchayatlevel:Nill

XI.  NoofgrievancesdisposedofatPanchayatlevel:Nill

XII.       WhethertheSarpanch/PanchayatSecretaryhavedigitalsignatures:Yes/No

XIII.      WhetherallMGNREGA/14thFCpayments arebeingmadebySarpanchthrough DigitalSignature

Certificate(DSC):Yes/No

HUMAN RESOURCEAVAILABLEATTHEPANCHAYAT LEVEL:

| SRNO. | DEPARTMENTWISESTAFF | NUMBERS |  | NAMES |
| --- | --- | --- | --- | --- |
|  |  | SANCTIONED | ACTUAL |  |
|  | Ruraldevelopmentdepartment: BDO JE GRS TA | 0 1 1 | 0 1 1 | At block level Ruksana maqbool Manzoor ahmad waza |
|  | SCHOOLEDUCATION: TEACHER HEADMASTER ANYOTHER | 11 1 NyC | 10 1 1 | List Enclosed Anx- 1, List Enclosed Anx-2 Mohd Maqbool waza |
|  | JAL JEEVAN: | 02 | 02 | Showkat Ahmad Ab Hamid |
|  | PDD: LINEMAN JE ANYOTHER | 01 01 02(PDL) | 01 01 02 | Manzoor Ahmad Khan Harmindar Singh Jan Mohd Rather and Zafar |
|  | FOOD&CIVILSUPPLIES | 01 | 01 | List Enclosed |
|  | AGRICULTURE&ANIMALHUS- BANDARY | 01 | 01 | Ravindar Nain Singh |
|  | SOCIALWELFARE | 01 | 01 | Zareefa |
|  | HEALTH: ASHA ANM AYUSHDOCTOR ALLOPATHICDOCTOR | 03 01 Nill Nill | 02 01 Nill | Nahida Bano and Sarwa Sabi Jan |
|  | ANYOTHERDEPARTMENT | Nill |  |  |

Annuxure I and II

DAY2-ACTIVITIES

AGENDANO.1

DiscussionontheandassesstheprogressofdifferentschemesrelatingtothelocalizedSDGsprior-itizedforthatvillageaspertheresolutionpassedbythatGramPanchayaton21stApril22,onNational PanchayatiRajDay(Copyoftheresolutiontobetakenfromwww.jkpanchayat.inportalunderthelinkof GramSwarajMonth)

1.       SDGs AGREED FORTHATVILLAGE,TOBEIMPLEMENTED BYMARCH2024:

2.       STATUSOFWORKSUNDERTHEFOLLOWINGSCHEMES:

1      Cleanandgreenvillage

  - i.InitiativestakenbythePanchayatformanagingSolidandLiquidWaste	under progress

  - ii.     InitiativestakenbythePanchayatforusinggreensourcesoffuellikesolar,biogas

      - NO

  - iii.  Hasmappingoflanduse,waterbodies,forest,slopes,wetlands,degradedforestwithintheGram

    - Panchayatbeendone?Yes/No.IfNo,reason,thereof   	In Progress

  - iv.    HastheClimateResiliencePlanbeendevelopedfortheGP?Yes/No

  - v.     StepstakenbytheGramSabhaabouttheclimatechangemitigationfactorslikereducingenergy consumption,usageoffossilfuels,plastics,non-renewablebuildingmaterialsandalsotopromote measureslikeplantingoftrees,conservingforests,usageofgoodagriculturalpracticeslikedrip irrigation,waterconservationmeasuresandconservationofwetlands.(Awareness and Motivation among people)

  - vi.  Whether schools have started segregating waste   In Progress

  - vii. Whetherschoolshavetheirowncompost/soakagepitsforsolid/liquidwastemanagement   proposed in Current plan

2     Healthyvillage

i)    Aremeetings  relatedtoVillageHealthandSanitationCommitteebeingheldregularly?NO

ii)   DoalltheeligibleindividualsbeenprovidedtheGoldenCard?NO

iii)  ArealltheChildrenbeingimmunizedaspertheSchedulerecommendedbyGovt.ofIndia?Yes

iv)  ArealltheeligibleindividualsbeenvaccinatedagainstCOVID-19?Yes

v)   DoesGramPanchayatensurethatallpregnantwomenaregettingnecessaryprenatalcheckups?Yes

vi)  WhetherallthedeliverieswereInstitutionalizedorconductedbytrainedMidwives?yes

3     Watersufficientvillage

i)    DoalltheIHHsintheGramPanchayathavewaterpipelineconnections?Yes

ii)   WhetherGramPanchayathastakenstepsforgreywatermanagement.IfYespleasespecify yes(Through soakage Pits)

iii)  DoalltheIHHsintheGramPanchayathavetoilets?yes

iv)  ArealltheIHHstoiletsfunctionalornot?Yes

v)   DoalltheSchools/Anganwadicentershavea toiletfacilityornot?Yes

vi)  Areallthetoiletsintheschools/Aaganwadifunctionalornot?yes

vii) WhetherGramPachachayatBhawanhasseparate toiletsforwomenornot?

NO

4      ChildFriendlyvillage

i)	Doallthechildrenundertheageof0-6yearsbeenenrolledintheAnganwadicentersforpre- schooling?Yes/NO

ii)    HowmanyBalSabha’swereorganizedintheGramPanchayat-------02------------

iii)  WhethertheissuesraisedbyBalSabhaareaddressedduringtheGramSabha. Yes/NO

iv)	WhetherGramPanchayatistrackingthedatarelatedtodropoutchildrenandchildrenwithirregular attendance?Yes/NO.

v)   DoalltheschoolsundertheGramPanchayathaveseparate toiletsforgirlsandboys?Yes/No

5      Villagewithgoodgovernance

i)    IsCSClocatedintheGramPanchayatBhawanornot?Yes

ii)	IsthelistofbeneficiariesrelatedtotheSchemes/ProgramsdisplayedontheGrampanchayatwallor not?Yes

iii)  DoestheGramPanchayathasitsbuildingornot?Yes

iv)  IstheGramPanchayatofficefunctionalornot?Yes

v) Aretheactivities approved undertheHalqaPanchayatDevelopmentPlandisplayedontheGram

Panchayatwallornot:

Yes

vi)  IsSocialAuditofearlierSchemes/Programscarriedoutornot?Yes

6      Povertyfreeandenhancedlivelihoodvillage

i)    HasGramPanchayatdevelopedanycriteria fortheidentificationofthepoor?Yes/Noifyesspecify ii)   HavealltheeligiblehouseholdsregisteredinPDSornot?yes

iii)	HasGramPanchayatprovidedspaceforSelf-helpGroupsinPanchyatGharforholdingmeetings  or not?Yes

iv)  HavealltheeligiblehouseholdsbeenregisteredforPensionornot?yes

v)   HasGramPanchayatfacilitatedYouthforSkillEnhancementCoursesandPlacement?

vi)  HasJobCardsbeendistributedtoalltheeligibleindividualsunderMGNREGA?Yes

vii) HasGramPanchayatfacilitatedSHGsforBankAccountLinkages?Yes

7     Sociallysecuredvillage

i)    WhetherGramPanchayatismaintainingdatarelatedtoDifferentlyAbledPeople?NO

ii)   IsGramPanchayatOffice DisabledFriendlyornot?NO

iii)	Areprovisionsfora separate BudgetundertheResourceEnvelopeforWomenandChildrenmadeor not?NO

iv)	DoalltheSchools intheGramPanchayathavefacilitiesforDifferentlyAbledChildrenliketoilets, barrier-freeaccess,etc.,ornot?NO

v)   Arealltheeligibleindividualsaregettingpensions,likeoldagepension,widowpension,etc?Yes

vi)  ArealltheeligiblehouseholdsgettingbenefitsfromIAYornot?

yes

8      EngenderedDevelopmentinVillage

i)    HowmanyMahilaSabha’swereorganizedintheGramPanchayat-----------04--------

ii)	WhetherSHGsfederationshavebeenprovidedspaceformeetings  inthePanchayatBhawan(Yes/ No)

iii)  WhetherGPshavetakenstepsforincreasingwomen’sparticipationinGramSabha(Yes/No)

iv)  NumberofwomenbeneficiariesheadedhouseholdscoveredunderPDS

system………12………………

v)   Numberofbeneficiaries(outoftotaleligiblepopulation)receivingsocialprotectionbenefitsunder

PradhanMantriMatritvaVandanaYojana……15…………….

9    Self-sufficientinfrastructureinthevillage

i.	WhetherGPhasa CommunityHallwithaccesstoelectricity,furniture,watersupply, toilet………NO……………….

ii.     WhethertheDisastermanagementplanisavailableattheGPLevel(Yes/No)

iii.  Whetherchild-friendlyparkwithrequiredfacilitiesisavailableinGP(Yes/No) iv.    WhethertheGPhaseasyaccesstoGodownforstorage(Yes/No)

v.     Whetherstreetlightsareprovidedinpublicplacesforensuringsafety(Yes/No)

DAY2ACTIVITIES

AGENDANO.2

SensitizevillageresidentsaboutmyScheme”portal(myscheme.in)whichincludesinformationaboutall theschemesbeingrunbyCentral/State/UT govtacrossthecountry

(SchemeMaterialavailablefromhttps://jkpanchayat.in/b2v4.php)

DAY2ACTIVITIES

AGENDANO.3

HoldmeetingoftheBiodiversityManagementCommitteestodeliberateonissues pertainingtoconserva- tionofbiodiversityandsustainableutilizationofbiologicalresources.HeshouldcheckPeopleBiodiversity register(PBR)ofthatpanchayatandreviewifBiodiversityManagementCommittee constitutedforthat panchayatis holdingminimum4meetings inayearandmeeting onceinevery3months (RoleofBMC availableathttps://jkpanchayat.in/b2v4.php)

COMMITTEEMEMBER:ListEnclosed

Present

BIODIVERSITYREGISTERPHOTOS

PAST 4MEETINGDETAILS-DATES,MINUTESPHOTOS

DAY2ACTIVITIES

AGENDA4

Visitingofficershallalsoplanandconductpanchayatlevelconvergencemeeting  ofalldepartmentsand prepareVillagedevelopmentplanforvillage,inconsultancywithGrampanchayat,discussitingram sabhaandgetitapproved.

(GPDPformatavailableonhttps://jkpanchayat.in/b2v4.php)

InadditionGPDPplanshallalsoinclude:

           Touristplaceswhichneedtobedeveloped Tarsar and Marsar and wasturwan top

Specificproductwhichneedstobedeveloped Animal Husbandry and sheep husbandry

           Tourism-homestays Nill

	20candidatesfortrainingunderHimayatschemealongwithtradeinwhich trainingistobegiven

List enclosed

DAY2ACTIVITIES

AGENDA5

Ensuresaturationoffollowingschemesandgivestatus:

| NAMEOFTHESCHEME | TOTALELIGIBLE BENEFICIARIESIN THE VILLAGE | TOTALBENEFICIARIESWHO AVAILEDTHEBENEFITSOFTHESCHEME | REASONSFOR PENDENCY |
| --- | --- | --- | --- |
| GoldenHealthCardunder AyushmanBharat | 1338 | 1120 | Ration Card Problem |
| Jananisurakshayojana | 11 | 08 | 03 Under progress |
| OLDAGEpension | 102 | 102 |  |
| Widowpension | 41 | 41 |  |
| Disabilitypension | 33 | 33 |  |
| Domicilecertificate | 1338 | 645 | Not Applied yet |
| Kisancreditcard | 128 | 76 | Not Applied yet |
| PMkisansammannidhi | 122 | 122 |  |

| Landpassbook | 181 | 100 | Under Progress |
| --- | --- | --- | --- |
| Registrationofvillageven- dorsonGEMportal | Nill |  |  |
| Registrationofvillagecon- tractorsonjktendersportal | 40 | 4 | Not Applied |
| Registrationofvillagecon- tractorsonPWDportal | 01 | 1 |  |
| Incompletebuildings/pro- jects | nill |  |  |

DAY2ACTIVITIES

AGENDA6

NASHAMUKTABHIYAN

1.       Whethergramsabharesolutionpassed Yes

2.       Detailsofactivities conducted List enclosed in Karwai

3.       Whetherallactivities andGSresolutionuploadedonjkpanchayats.inportal Yes

4.       Howmanydrugaddictsinthevillage  Nill

5.       WhetherreportedtotheDeputyCommissioner  Yes

6.       Howmanyregisteredforrehabilitationundergovernmentprogramme  Nill

DAY2ACTIVITIES

AGENDA7

SOCIALAUDIT

Conductsocialauditofatleast5workseachunderfollowingschemes:

| NAMEOFTHE SCHEME | DETAILSOFTHE WORKS | YEAROFWORK APPROVAL | AMOUNT APPROVED FORTHEWORK | WHETHER WORKEXECUTED SATISFACTORILY | GEO- TAGGED PHOTOS | ANY GRIEVANCE RECORDED RELATINGTOTHAT WORK |
| --- | --- | --- | --- | --- | --- | --- |
| MGNREGA | 5 | 2021-22 | 31 lacs | yes | yes | No |
| PMAY | 02 | 2021 | 1.50 lacs per beneficiary | Yes | Yes | No |
| IHHL UNDERSBM-G | 05 | 2021-22 | 12000 per beneficiary | Yes | Yes | NO |
| CSCUNDER SBMG | 03 | 2020-21 | 1.80 per unit | Yes | Yes | no |
| AMRIT SAROVARS | Nill | NIll |  |  |  |  |

DAY2ACTIVITIES

AGENDA8

MAHILASABHA

Totalwomeninthevillageabovetheageof18  554

Totalattended  232

Proceedings:  Awareness regarding women empowerment, gender inequality, Mal Nuitrition

(Plinsertpointerstobediscussedthere–referpalliproceedings)

DAY2ACTIVITIES

AGENDA9

BALSABHA

Holda balsabhaandrecordproceedings Yes

Totalchildreninthevillageabovetheageof…..  218 Totalattended 145

Proceedings:  Awareness regarding Nasha Mukht Bharat and Corruption free

(Plinsertpointerstobediscussedthere–referpalliproceedings)

DAY2ACTIVITIES

AGENDA10

INAUGURATIONS

| SR NO. | ASSETS/ACTIVITIES INAUGRATED | STATUSOFTHEASSET/AC- TIVITIES(NUMBER,OTHER DETAILS) | GEO-TAGGED PHOTOS |
| --- | --- | --- | --- |
|  | VILLAGEHAATunderJKSRLM (SUN- DAYMARKET) | Paper Machie, Copper Utensils Manufacture,Sozni etc |  |
|  | PMAYhousesifanyreadyforinaugra- tion | 02(01 Complete and 01 under progress | Yes |
|  | Swachhgramprojects-segregation shedsetc | Under Construction | Yes |
|  | Amritsarovars | nill |  |
|  | Sportskits | In Progress for Purchase |  |
|  | Villageculturalevents | Folk songs, National Song and Ladisha | Yes |
|  | JJMassets/projects | 02 Projects Completed | Yes |
|  | Anyothertobeidentifiedatdistrict level | Nill |  |

FOLLOWUPOF(B2V1,B2V2&B2V3):

(Prefilledexcelsheet tobetakenfromdistrictlevel/andalsotobedownloaded

fromwww.jkpanchayat.in)

| S.NO. | Particulars | Actiontaken | Remarks# |
| --- | --- | --- | --- |
| I. UrgentPublicRequirements/Demands-B2V1 |  |  |  |
| 1 | Road connectivity from seer to gong | Yes | funds r not availbale |
| 2 | establishment of primary health centre | NO | population cause |
| 3 | establishment of sheep and animal husbandary | no | already existing with in 2 kms |
| 4 | channalisation of chandi nallah lorow taar to bunkawan | no | authorisation not received and covered in B2v1 |
| 5 | Road connectivity from nagbal gulshnapora to astan mohalla seer | no | authorisation not received |
| 6 | Upgradation of ups seer to high school | no | availble in adjacent village batagund |
| 7 | construction of bridge at chandri nallah | no | authorisation not received |
| II. UrgentPublicRequirements/Demands-B2V2 |  |  |  |  | no |
| 1 | improvement of electric infra structure at seer | no | tendered |
| 2 | completion of 33 kv receiving station at takiya batagund | yes | completed |
| 3 | channelisation of chandri nallah with p bund on both sides at seer and gang | No | 5 lacs may b arranged for channelisation from B2v2 |
| 4 | upgradation of interior roads/ lanes at seer | No | tendered |
| 5 | levelling of playground at UPS seer | yes | completed |
| 6 | c/o brige near ups seer and flour mill | No | included in 14th and 15th fc plan |
| 7 | c/o brige seer to lorow | No | funds not available |
| S.NO. | Particulars | Actiontaken | Remarks# |
| III. MajorProblems–B2V1 |  |  |  |
| 1 | channelisation of chandri nallah with p bund on both side seer and gang | NO |  |
| 2 | improvement of electric infra structure at seer | Yes but needs to improve |  |
| 3 | PHC at Seer | Not feasible |  |

| 4 |  |  |  |
| --- | --- | --- | --- |
| 5 |  |  |  |
| IV. MajorProblems-B2V2 |  |  |  |
| 1 | Upgradation of ups seer to high school | NO | authorisation not received |
| 2 | Road connectivity from nagbal gulshnapora to astan | no | availble in adjacent village batagund |
| 3 | PHC at Seer | No |  |
| 4 |  |  |  |
| 5 |  |  |  |
| V. MajorProblems-B2V3 |  |  |  |
| 1 | Road Connectivity between Seer and Gang | Action taken by RDD and in Progreess |  |
| 2 | Establishment of Sheep Centre | Not Feasible |  |
| 3 | Establishment of PHC Seer | Available in adjacent village |  |
| 4 | Upgradation of UPS Seer |  |  |
| 5 |  | Available in adjacent village |  |
| VI. MajorComplaints-B2V1 |  |  |  |  |  |
| 1 | improvement of drainage system at gang | funds not availble |  |
| 2 | establishment of CAPD at Gang | funds not availble |  |
| 3 | Establishment of PHC at Seer |  |  |
| VII. MajorComplaints-B2V2 |  |  |  |
| 1 |  |  |  |
| 2 | establishment of CAPD at Gang | funds not availble |  |
| 3 | Establishment of PHC at Seer | funds not availble |  |
| VIII. MajorComplaints-B2V3 |  |  |  |
| 1 | Lack of drinking water at Seer | funds not availble |  |
| 2 | Road Connectivity to upper Pry School seer | funds not availble |  |
| 3 | Reverification of Social Welfare Schemees | Under progress |  |

OVERALLPERCEPTIONOFFUCNTIONING OF GOVERNMENTDEPARTMENTS

1.         BESTDEPARTMENT:    RDD

2.       LEASTRESPONSIVEDEPARTMENT:

GENERALASSESSMENTOFTHEVISTINGOFFICER

| I | AnymajorcomplaintbroughttothenoticeoftheVisitingOfficer: |
| --- | --- |
| II | Major/urgentpublicdemandsthatwas/werereflectedearlierbuthavenotbeenaddressedsofar: |
| III | Overallassessmentofthevisitandsuggestions: (Thevisitingofficertoensurethattheoverallassessmentisrecordedindetailsalongwithconcretesugges- tions) |
| IV | OverallRatingofgovtfunctioningas givenbythePanchayat(Scaleof0to10) |
| V | CertificatefromSarpanchthatthevisitingofficerhasstayedinthepanchayatfor2days |

SignatureofSarpanch                                                                              SignatureoftheVisitingOfficer

Name………………………                                                                               Name………………………

URGENT PUBLIC DEMANDS

Major complaint :- The major complaint brought forward by the public is that many demands Govt has not promoted NAGABERI as Tourist Destination by way of making it accessible via road connectivity or installation of GANDOLA, despite having immense potential.

S. No. 2

Major / urgent public demands reflected earlier:-

- Up gradation of road from Satoora to Pranigam and Satoora to Hajinar.

- Health Centre Establishment.

- Separate village guard.

- Construction of foot bridge from gang to seer

S. No. 3

The visit was satisfying overall. People very candidly raised their demands and their expectations were found very high . However  due to non addressal of few urgent public demands some were hopeless. Most of them demanded timely addressal of the balance demands already raised in B2V1, B2V2 and B2V3 programs.

Further public demanded promotion  of NAGABERI as tourist destination which has got immense potential to become the BEST tourist destination of Jammu & Kashmir. The need could be primarily fulfilled by either road connectivity or making it accessible by installation of  GANDOLA like the one at Gulmarg (J&K ). This could be very helpful in the revenue generation besides reducing or in fact eradicating the poverty of TRAL area as whole and seer Panchayat Halqa in particular. Moreover the overall functioning of Govt machinery was found satisfactory.

S. No.  4

Overall Govt Functioning rated by Panchayat is  ‘7’

S. No.  5

Certificate:-

Certified  that the visiting officer  has stayed in the Panchayat Halqa for two (02) days i.e, 30/10/2022 and 31/10/2022 in connection with B2V4

SD

sarpach halqa Seer

DepartmentofRuralDevelompentandPanchayatiRaj

GovernmentofJammu &Kashmir