4

15TH OCTto3RD NOV,2022

KEYFEATURES

•     DeputyCommissionerstoleadtheinitiative

•    RuraldevelopmentDepartmenttobethenodaldepartment

•	PlanningDevelopment&MonitoringdepartmentandITtobethesupport departments

ACTIONSANDTIMELINES

| ACTION | RESPONSIBILITY | LATESTBY | REMARKS |
| --- | --- | --- | --- |
| Janabhiyan | Alldepartments | Oct15-26th | Goingon |
| DeputationofSecttstaff/ HoDs | GAD | Oct14 | Done |
| DeploymentofStaffto Panchayatsandservingof ordersondeployedofficers | DCs | Oct25 | DCswilldeployseniorlevelstaff fromthedistricts.Strictactionto betakenagainstabstentions.No exemptionstobegiven |
| Trainingofdistricttrainors onB2V4 | RDD | Oct26 |  |
| Trainingofvisitingofficers | DCs | Oct27 |  |
| FieldVisitstobecompleted by | VisitingOfficers | Nov3 | DCstosuperviseandensurethat eachPanchayatisvisitedwithin theperiodspecified |
| DataofB2V4tobe uploadedby | VisitingOfficers | Nov10 | DCstosuperviseandensurethat dataofallPanchayatsisupload- edbythevisitingofficerwithin theperiodspecified |

INSTRUCTIONSFORTHEVISITINGOFFICER(DAYWISE)

| DATE | INSTRUCTIONS | ACTIONPOINTS |
| --- | --- | --- |
| Day0 | Meetingwithdeputy commissionerandhis/her team | a. TakeprintoutsoffilledbookletsofB2V1,B2V2andB2V3from www.jkpanchayat.in b.Alsotakeprintoutsofthesummarizedexcelsheetsofthe previousphasesfromwww.jkpanchayat.in c. CollectATRsonissuesraisedduringprevious3phasesfromthe officeofDeputyCommissioner(Planningdeptt) d.Takeprintsofblank 2bookletsofB2V4fromwww.jkpanchayat.ine.Takeplansfor2previousyearsandATRsfromtheplanningdeptt f. CompletetrainingsondifferentcomponentsofB2V4being organizedbyrespectiveDeputyCommissioners g.CollectListofnewworksstarted/ongoing/completedduringthe previousandcurrentFinancialyearunderthefollowingheads: • PRIgrants • DistrictPlan • UTplan • MGNREGA • Otherschemesofotherdepartments • Anyotherwork h. Plans/beneficiarylists: • MGNREGAdraftplandocumentfortheyear2022-23. • ListofAwaas+beneficiariesalongwithIHHL Convergence • Listofpensionbeneficiaries. • ListofSHGs • Listofagricultureschemebeneficiaries i. Listsofbeneficiariesfor: • Variouscertificates/benefitstobedistributedbythe visitingofficer. • Anyotheractivitiesidentifiedbydifferentdepartments |

| Day1 | Reachthevillage | 1. | Ensurethatallfrontlineworkersofdifferentdepttsarepresent. |
| --- | --- | --- | --- |
|  |  | 2. | Ensureexhibitionbydifferentdepts.aboutindividualbeneficiary schemes |
|  |  | 3. | InspectJKB/PSBcounters/outlets |
|  |  | 4. | Participate/ensureorganizationofsportsactivityinplayfield,talent hunt/culturalevent/youthactivity |
|  |  | 5. | GandhiKatha(suggesteddetailsuploadedonjkpanchayat.in) |
|  |  | 6. | Visitatleast2amritsarovarsandgetitsgeotaggedphotos |
|  |  | 7. | InspectKhidmat(CSC)CentresandcreateGenerateawarenesson 225schemesparticularlyG2CschemeslikeBEAMS,Janbhagidari, AapkiZaminAapkiNigrani,DigitalJ&K |
|  |  | 8. | Visitingofficershallalsoplanandconductpanchayatlevelconver- gencemeetingofalldepartments |
|  |  | 9. | CheckeffectivenessofCentrallysponsoredschemes |
|  |  | 10. | VisitandinspectallgovernmentestablishmentsincludingPHE, AWC,FPS,schools,etc |
|  |  | 11. | Attemptsaturationofdeliverableso JanAbhiyanandwherever deficienciesfound,leadadrivetoachievealldeliverables |
|  |  | 12. | Assesseffectivenessofsanitationcampaigninthepanchayat |
|  |  | 13. | Ensureselfemploymentactivitiesfor15youthperpanchayat |
|  |  | 14. | Identify20potentialcandidatesperpanchayatforHIMAYATtraining alongwiththetradeonwhichtheywanttraining |
|  |  | 15. | Whereverpossible,distributeemploymentlettersforpeopleselect- edundervariousgovernmentemployments |
|  |  | 16. | Intheevening,holdnormalmeetingwith seniorcitizens,govtem- ployeesincludingretiredemployees,exservicemen,youthclub,and any citizens ofthevillagewhoareenrolledincollege/university |
|  |  | 17. | OpendiscussiononNashaMuktAbhiyan |

Day2            Haveameetingwithall stakeholders-depttofficials andpanchayatmembers

1.       Discussionontheandassesstheprogressofdifferentschemesrelating tothelocalizedSDGsprioritizedforthatvillageaspertheresolution passedby thatGramPanchayaton21st April22,onNationalPanchayti RajDay.

2.	Sensitizevillage residentsaboutmyScheme”portal(myscheme.in) whichincludesinformationaboutalltheschemesbeingrunbyCen- tral/State/UTgovtacrossthecountry

3.	Hold meeting of theBiodiversityManagementCommitteestodeliber- ateonissuespertaining toconservation of biodiversityandsustaina- bleutilizationof biologicalresources.

4.       PrepareVillagedevelopmentplan,inconsultancywithGrampanchayat, discussitingramsabhaandgetitapproved.

5.       Ensure saturationofsoilhealthcardandgoldenhealthcardunderGold- enHealthCardunderAyushmanBharat,

6.       Ensuresaturation  of OldAge PensionScheme

7.       EnsureDomicileSaturation.

8.       EnsureKCCSaturation

9.       Ensure saturationoflandpassbooks

10.     Ensureregistrationofvillagevendorsneededforanyscheme,onGEM

portal

11.     Ensurepanchayatcontractors registration

12.     EncouragePanchayatmembers forimportanceofplantationdrivein

PanchayatunderHarGaonHariyali

13.     Ensure paintingondigitalJ&Kinpanchayatghars

14.     Ensure paintingonpanchayatactivitesandCSSinpanchayatghars

15.	Thevisiting officeshallchecknoof kindergarten andplayfields present inthepanchayat for kidsandstudents,iftheinfrastructure present inthesearegoodenough.

16.     Holdmeeting withpanchayatmembers todiscussaboutcorruption menaceandstepsrequiredtomakeJ&Kcorruptionfree

17.     Obtaina candidassessmentaboutperformanceofvariousdeptts in- cludingfairfeedbackaboutdiscrepanciesinfunctioning

18.	Check thestatusof NashaMuktAbhiyanandreporting of drugad- dictstoDeputyCommissioner.

19.     IdentifyTouristDestinations,Circuits,ThemeTreks,IdentifyHomestays, providesupportfortourismactivities throughVillageCooperative

20.     OrganizeTalentHuntatPanchayatLevel

21.     Conductsocialauditofatleast5worksunderfollowingschemes:

a.       MGNREGA

b.PMAY

c.        IHHLtoiletsandpayments d.CSCs

e.AMRITSAROVARS

22.     Holda mahilasabha anda balsabhaandrecordproceedingsinthefor- matgiven

23.     InauguratevillagehaatunderJKSRLM

24.     Checkifyouthclubsareformedinthepanchayatandwhatactivities theyareengagedin

25.     Organizea villagelevelculturaleventtoengagepanchayatmembers

26.     SensitizeGPaboutE-kitabkoshaninitiativeofJ&KGovtforempowering youthsthrough onlinedigitalliteracy

GENERALINSTRUCTIONS

1.	Thevisitingofficershallrefrainhimself/herselfgivingorofferinganycommitmentonbehalfofthe governmentandshalladoptanunbiasedattitudeinreportingissues.As faraspossible,his/her observation shouldbebasedona fairandanalytical viewemergingfromhis/herinteractioninthe village.

2.	Heisgoingtothevillageasplanningofficer,notforsanctioninganyworksorformakinganycom- mitments.

3.	Whilepreparingvillagedevelopmentplan,hehastoensurethat,demandsareprioritizedandre- flectedunderavailableschemes,wherevernecessarythelargerworksaretobereferredtoadminis- trativedepttunderCSS/UTplansunderintimationtoDCsandrestoftheworkstoDCsforreflecting itunderdistrict/CSS plans

4.    His workshallbehardcoreplanningandauditandisnota PRexercise.

5.	EveryDeputyCommissionerhastoensurethatatleastoneRDDofficial(ideallyPanchayatSecre- tary)ispresent  ineverypanchayatwithrelevantpanchayatrecords,toensureconductofallactivi- tiesasplanned.Panchayatwiseorderneedstobeissuedinadvance.

6.	Visitingofficershouldideallycarryhis/herlaptoptocompletethereportsatthepanchayatlevel itselfanduploadthefinalreport,duly signedbothbythesarpanchandbythevisitingofficeron www.jkpanchayat.inportal,beforetheyleavepanchayat.

7.	Focus ofvisitareyouth,skills,self-employment,nashamukt,bhrashtracharmukt,Rozgaryukt J&K, besidestocarryforwardtheactivities duringJanAbhiyanandsaturatethem.

8.    Inadditionattentionmaybegiventothefollowingareas a.     MakefulluseofCentrallySponsoredSchemes

b.Saturationofindividualbeneficiaryschemes c.     Self-employmentschemes

d.Banklinkedschemes-includingdepartmentalsubsidyschemes e.Empowermentandtransparencythrough digitalinitiatives

f.       Effectivenessofgrassrootsmachinery–

i.       Patwari,VLWpresent  andavailable

ii.      AvailablefundsutilizedinpublicinterestandasperGramSabharesolutions iii.   Fairness ingovernance

iv.    CSS/Individual beneficiaryschemesetc v.      BrashtacharMuktJ&K

vi.   BhaiMuktJ&K

vii.  NashaMuktJ&K

9.	ThePRImembers (Sarpanchs,Panchs,BDCChairperson)shallbeattheforefrontofallactivities and givendueimportanceandtheapproach shouldbetostrengthenthemandmakethemfeelem- powered.He/sheshallensurethattheBDCchairpersonandSarpanch/Panch arepresent  atthetime ofinaugurationandceremonies.

10.	Visitingofficershallnotleavethedistrictwithoutuploadingthereport,duly signedonthewww. jkpanchayat.inportal.EveryDeputyCommissionerhastoensurethat.

A)   DetailsofReportingOfficer:

Name:   Showkat Ahmad Bhat

Designation:Incharge Lecturer Chemistry

Department/placeof  posting: Education/BHSS Hiller Arhama

MobileNo:9596113110

EmailID:bshowkat595@gmail.com

HomeDistrict: Anantnag

Datesof  visit: 31-10-2022 to 01-11-2022

B)	LocationaldetailsofPanchayat:(tobepre-filled,informationtobetakenfromtheprevious phasesbooklets/summarizedexcelsheetuploadedonjkpanchayat.in/b2v4.php)(tobevali- datedbythevisitingofficerandmissingdetailstobefilled)

NameofthePanchayat:          Khalahar

LocalGovernmentDirectory(LGD)codeof  thePanchayat:274733

Nameof  CDBlock: Sagam

NameofTehsil:  Kokernag

Nameof    District:  Anantnag

C)     PanchayatProfile:

No.ofrevenuevillagesinthePanchayat:df   02

No.ofhamletsinthePanchayat:  07

No.ofhouseholdsinthePanchayat:392

Population(approx)of  thePanchayat: 1960

Part-II:

(TobefilledupbytheVisitingOfficerduringhis/hertwodayvisittothePanchayat.AllFieldshavetobe

filledbytheVisitingOfficerbeforethebookletishandedovertotheDC

FrontlineOfficers/OfficialswhowereassignedtothePanchayatfortheprogramme:

| Department | Name | Designation |
| --- | --- | --- |
| Education | Ajaz Ahmad Sheergogry | Teacher |
| Jalshakti | Gh Ahmad Sheergojri | Fitter |
| PDD | Bashir Ahmad Bhat | Lineman |
| Health | Bilkeesa Samad | FMPHW |
| RDD | Altaf hussain Dar | Panchayat secretary |
| ICDS | Haseena AKther | AWW |
| ICDS | Muneera Akther | AWW |
| Agriculture | Jan Shahid | SMS |
| R & B | Ab salam wani | Road Worker |
| Industries and commerce | Gh Mohiui din wani | MTS |
| Horticulture | Tariq Ahmad Parray | Tech-iv |
| Education | Gh Mohd Wani | Teacher |
| Irrigation &FC | Nisar Ahmad wani | TE |

Detailsofabsentemployeesvis-à-vislistfurnishedbytheDCoffice:

| Department | Name | Designation |
| --- | --- | --- |

DAY1-ACTIVITIES

AGENDA1:PANCHAYATASSETREGISTER

Infrastructure:

1.		PanchayatGharInfrastructure a.  Govtbuilding/private  Government building under dispute

b.  New/needingrepairs needs repairment

2.       Furniture(Y/N)  YES

3.       Computer/printer(Y/N) YES

4.       Internet(Y/N) YES

5.       Telephone(Y/N) NO

6.       Toilet(CSC/partofpanchayatghar)(Y/N) NO

7.       Water(Y/N) NO

8.       Electricity(Y/N) NO

9.       Bankbranch(Y/N) NO

10.     CSC(Y/N) NO

11.     Patwarkhana(Y/N) NO

12.     Villagehaat(Y/N) NO

13.     Playground(Y/N) NO

14.     School-

a.        Kindergarten(Y/N) YES

b.Primary(Y/N) YES

c.         Secondary(Y/N) NO

d. College (Y/N) NO

e.University(Y/N) NO

15.     AnganwadiCentre(Y/N) YES

a.        (govt/private) govt.

b.Totalchildrenenrolled  112

15.     AmritSarovars–details,location,condition  Nil

16.     Governmentoffices-details,whetherfunctionalornot

17.     Rationshop(Y/N) yes

18.      Placesoftourismimportance–names,littledetailsonhistorical/culturalimportance Nil

19.      Villageheritagesites/treks-names,littledetailson historical/culturalimportance Nil

20.     VLWOffice (Y/N) Yes but  rented

21.     PrimaryHealthcareCentre(Y/N) Yes,

22.     ListofIncompleteBuildings-names,yearofconstruction Panchayat Ghar-2011-12

23.     ListofUnderutilizedBuildings-names Nil

DAY1-ACTIVITIES

AGENDA2:

DIFFERENTINSTITUTIONS/INFRASTRUCTUREPROJECTSTOBEVISITED

| AMRITSAROVARS | Visit,verify | COMMENTS |
| --- | --- | --- |
| KhidmatCentres | Create/Generateawarenesson225schemes particularlyG2CschemsAapkiZaminAapkiNigrani, Beams,Janbhagidari,DigitalJ&K | Not available |
| JKB/PSBcounters/outlets | a)Statusofcounter b)Numberofvisitors | Installed. 40 |
| Incompletebuildings/pro- jects | Verify whetheridentificationandredistribution done | Panchayat ghar,Jal shakti project from Sagam to Khalhar |
| PDS | Visit,evaluate,onlinestatus | Fully online and functional |
| PHC | Visit-evaluate,statusofstaff,equipmentand quality | Visited.03 staff-MLHP,FMPHW,Sweaper |
| Youthclubs | Meet,interact,seeksuggestions | Meeting conducted . |
| SHG | Meet,identifyproblems,seeksuggestions | In need of meeting hall. |
| PMAY | Inspect,Inaugurate | Inaugrated.01 |
| Myschool,mypride progress;schools-water, toilets,staff | Visit,checkforwater,electricity,sanitation,meet studentsandstaff | Meeting conducted .water and electricity available but toilet needs repairmen.MS Ardpora |
| SwachhSBM | Evaluate | ODF |
| Panchayatplayground, Sportskitsdistribution Villagegames | Ensure,verify.Participateinatleastonegamein theplayground | Playground not available |
| HarGaonHariyali, Planta- tiondrive | Evaluatestatus,feedback | Plantation drive done |
| Villageculturalevent Dangal/Haat/Mela | Participatein;ensurethatitisheld | Cultural programme done at MS Ardpora |
| Exhibitionofschemes | Ensurethateverydepartmentparticipatesand thatitcontinuesfortheentiredurationofB2V | Almost all departments. |
| JalJeewanMission verifica- tion- WSS/JSD Electricitysupply | Verify | Verified,JJM project ongoing |

DAY1-ACTIVITIES

AGENDA3:SATURATEJANBHIYAN

DELIVERABLESANDRECORDDEFICIENCIESIFANY(INSERTDELIVERABLESLISTHEREASPERGADFORMAT

DAY1-ACTIVITIES

AGENDA4:

SELFEMPLOYMENTACTIVITIES

EnsureSelf-employmentactivities foryouth,distributeemploymentlettersforpeopleselectedunder varioussocialschemes(15ISTHETARGETPERPANCHAYAT)

Numberofcasesindifferentcategoriessanctioned:4  Detailsofthebanksanctioningit: under process at Bank

Totalamountinvolved: 15 lakh

DAY1ACTIVITIES

AGENDA5

Intheevening,holdinformalmeetings  withseniorcitizens,govtemployees,retdemployees,youthclub andothercitizenswhoareenrolledoncollege/universityandhavediscussiononGandhiKatha,Nasha MuktAbhiyan,corruptionfreegovernance,doublingfarmersincomeandrecordtheproceedings

Meeting conducted with youth club ,with govt. employees.also discussion on Gandhi ktha. Nasha Mukhta abhiyan and take pledge on corruption free governance.

DAY2

a.       NoofIndividualCompostPitsconstructed  99 b.NoofIndividualSoakPitsconstructed  70

V.          No.ofBiodiversitymanagementcommitteemeetingsheld:05

VI.         IsthenameofSarpanchdisplayedoncitizeninformationboardsofallRD&PRschemes:Yes/No YES

VII.       AreSarpanchsbeinginvolvedinstart/inaugurationofactivities:Yes/No YES

VIII.      WhethersubjectshavebeenassignedbytheSarpanchtothePanchs:Yes/No YES

IX.        Whethergrievancesredressalboxisinstalled:Yes/No YES

X.         NoofgrievancesreceivedpertainingtoPanchayatlevel:2  XI.        NoofgrievancesdisposedofatPanchayatlevel:2

XII.       WhethertheSarpanch/PanchayatSecretaryhavedigitalsignatures:Yes/No YES

XIII.      WhetherallMGNREGA/14thFCpayments arebeingmadebySarpanchthrough DigitalSignature

Certificate(DSC):Yes/No YES

HUMAN RESOURCEAVAILABLEATTHEPANCHAYAT LEVEL:

| SRNO. | DEPARTMENTWISESTAFF | NUMBERS |  | NAMES |
| --- | --- | --- | --- | --- |
|  |  | SANCTIONED | ACTUAL |  |
|  | Ruraldevelopmentdepartment: BDO/PS JE GRS TA | 01,0,01,01 | 01,0,01,01 | Altaf Hussain Dar,Towheeda Akhter,Mysara Shamus |
|  | SCHOOLEDUCATION: TEACHER HEADMASTER ANYOTHER | 12,02 | 12,02 | Mohd Younus,Aejaz Ahmad,Gh Nabi etc. Imtiyaz Ahmad |
|  | JAL JEEVAN: | 03 | 03 | Gh ahmad etc |
|  | PDD: LINEMAN JE ANYOTHER | 03 | 03 | Bashir Ahmad,Adil Bashir,Ab Hamid Mir |
|  | FOOD&CIVILSUPPLIES | 04 | 01 | Mushtaq Ahmad Sheikh(store keeper) |
|  | AGRICULTURE&ANIMALHUS- BANDARY | 01 | 01 | Aejaz Ahmad Shan |
|  | SOCIALWELFARE | nil | Nil | Nil |
|  | HEALTH: ASHA ANM AYUSHDOCTOR ALLOPATHICDOCTOR | 04,01(ASHA),)!(ANM),)!(MLHP) | 04,01,01 | Mumtaza,Sakina etc Bilkeesa Samad,Shahid Bashir |
|  | ANYOTHERDEPARTMENT | nil | Nil | Nil |

DAY2-ACTIVITIES

AGENDANO.1

DiscussionontheandassesstheprogressofdifferentschemesrelatingtothelocalizedSDGsprior-itizedforthatvillageaspertheresolutionpassedbythatGramPanchayaton21stApril22,onNational PanchayatiRajDay(Copyoftheresolutiontobetakenfromwww.jkpanchayat.inportalunderthelinkof GramSwarajMonth)

1.       SDGs AGREED FORTHATVILLAGE,TOBEIMPLEMENTED BYMARCH2024:

2.       STATUSOFWORKSUNDERTHEFOLLOWINGSCHEMES:

1      Cleanandgreenvillage

i.InitiativestakenbythePanchayatformanagingSolidandLiquidWaste Yes (Soak and Compost pits)

ii.     InitiativestakenbythePanchayatforusinggreensourcesoffuellikesolar,biogas

iii.  Hasmappingoflanduse,waterbodies,forest,slopes,wetlands,degradedforestwithintheGram

Panchayatbeendone?Yes/No.IfNo,reason,thereof YES

iv.    HastheClimateResiliencePlanbeendevelopedfortheGP?Yes/No YES

v.     StepstakenbytheGramSabhaabouttheclimatechangemitigationfactorslikereducingenergy consumption,usageoffossilfuels,plastics,non-renewablebuildingmaterialsandalsotopromote measureslikeplantingoftrees,conservingforests,usageofgoodagriculturalpracticeslikedrip irrigation,waterconservationmeasuresandconservationofwetlands.Swachta hi Sewa Program

vi.  Whetherschoolshavestartedsegregatingwaste YES

vii. Whetherschoolshavetheirowncompost/soakagepitsforsolid/liquidwastemanagement YES

2     Healthyvillage

i)    Aremeetings  relatedtoVillageHealthandSanitationCommitteebeingheldregularly?YES

ii)   DoalltheeligibleindividualsbeenprovidedtheGoldenCard?YES (except 0-3 years)

iii)  ArealltheChildrenbeingimmunizedaspertheSchedulerecommendedbyGovt.ofIndia? YES

iv)  ArealltheeligibleindividualsbeenvaccinatedagainstCOVID-19? YES

v)   DoesGramPanchayatensurethatallpregnantwomenaregettingnecessaryprenatalcheckups?YES

vi)  WhetherallthedeliverieswereInstitutionalizedorconductedbytrainedMidwives? YES

3     Watersufficientvillage

i)    DoalltheIHHsintheGramPanchayathavewaterpipelineconnections?YES

ii)   WhetherGramPanchayathastakenstepsforgreywatermanagement.IfYespleasespecifyYES(Soak pits)

iii)   DoalltheIHHsintheGramPanchayathavetoilets? YES

iv)  ArealltheIHHstoiletsfunctionalornot?YES

v)   DoalltheSchools/Anganwadicentershavea toiletfacilityornot?YES

vi)  Areallthetoiletsintheschools/Aaganwadifunctionalornot? Functional except one

vii) WhetherGramPachachayatBhawanhasseparate toiletsforwomenornot?NO(Under dispute)

4      ChildFriendlyvillage

i)	Doallthechildrenundertheageof0-6yearsbeenenrolledintheAnganwadicentersforpre- schooling?Yes/NO YES

ii)    HowmanyBalSabha’swereorganizedintheGramPanchayat-----03--------------

iii)  WhethertheissuesraisedbyBalSabhaareaddressedduringtheGramSabha. Yes/NO YES

iv)	WhetherGramPanchayatistrackingthedatarelatedtodropoutchildrenandchildrenwithirregular attendance?Yes/NO.YES

v)   DoalltheschoolsundertheGramPanchayathaveseparate toiletsforgirlsandboys?Yes/No YES

5      Villagewithgoodgovernance

i)    IsCSClocatedintheGramPanchayatBhawanornot? NO

ii)	IsthelistofbeneficiariesrelatedtotheSchemes/ProgramsdisplayedontheGrampanchayatwallor not? NO

iii)  DoestheGramPanchayathasitsbuildingornot? Under dispute

iv)  IstheGramPanchayatofficefunctionalornot?YES (In rented room)

v)   Aretheactivities approved undertheHalqaPanchayatDevelopmentPlandisplayedontheGram

Panchayatwallornot?

NO

vi)  IsSocialAuditofearlierSchemes/Programscarriedoutornot? YES

6      Povertyfreeandenhancedlivelihoodvillage

- HasGramPanchayatdevelopedanycriteria fortheidentificationofthepoor?Yes/Noifyesspecify

YES  (Ration Card)

ii)   HavealltheeligiblehouseholdsregisteredinPDSornot? YES

iii)	HasGramPanchayatprovidedspaceforSelf-helpGroupsinPanchyatGharforholdingmeetings  or not?NO

iv)  HavealltheeligiblehouseholdsbeenregisteredforPensionornot? YES

v)   HasGramPanchayatfacilitatedYouthforSkillEnhancementCoursesandPlacement? Facilatated

vi)  HasJobCardsbeendistributedtoalltheeligibleindividualsunderMGNREGA? YES

vii) HasGramPanchayatfacilitatedSHGsforBankAccountLinkages? YES

7     Sociallysecuredvillage

i)    WhetherGramPanchayatismaintainingdatarelatedtoDifferentlyAbledPeople? NO

ii)   IsGramPanchayatOffice DisabledFriendlyornot? NO

iii)	Areprovisionsfora separate BudgetundertheResourceEnvelopeforWomenandChildrenmadeor not? NO

iv)	DoalltheSchools intheGramPanchayathavefacilitiesforDifferentlyAbledChildrenliketoilets, barrier-freeaccess,etc.,ornot? NO

v)   Arealltheeligibleindividualsaregettingpensions,likeoldagepension,widowpension,etc? YES

vi)  ArealltheeligiblehouseholdsgettingbenefitsfromIAYornot? YES

8      EngenderedDevelopmentinVillage

i)    HowmanyMahilaSabha’swereorganizedintheGramPanchayat------02-------------

ii)	WhetherSHGsfederationshavebeenprovidedspaceformeetings  inthePanchayatBhawan(Yes/ No) NO

iii)  WhetherGPshavetakenstepsforincreasingwomen’sparticipationinGramSabha(Yes/No) YES

iv)  NumberofwomenbeneficiariesheadedhouseholdscoveredunderPDS

system…15……………………

v)   Numberofbeneficiaries(outoftotaleligiblepopulation)receivingsocialprotectionbenefitsunder

PradhanMantriMatritvaVandanaYojana…13……………….

9    Self-sufficientinfrastructureinthevillage

i.	WhetherGPhasa CommunityHallwithaccesstoelectricity,furniture,watersupply, toilet…………NO…………….

ii.     WhethertheDisastermanagementplanisavailableattheGPLevel(Yes/No) NO

iii.  Whetherchild-friendlyparkwithrequiredfacilitiesisavailableinGP(Yes/No) NO

iv.    WhethertheGPhaseasyaccesstoGodownforstorage(Yes/No) NO

v.     Whetherstreetlightsareprovidedinpublicplacesforensuringsafety(Yes/No) YES

DAY2ACTIVITIES

AGENDANO.2

SensitizevillageresidentsaboutmyScheme”portal(myscheme.in)whichincludesinformationaboutall theschemesbeingrunbyCentral/State/UT govtacrossthecountry   YES

(SchemeMaterialavailablefromhttps://jkpanchayat.in/b2v4.php)

DAY2ACTIVITIES

AGENDANO.3

HoldmeetingoftheBiodiversityManagementCommitteestodeliberateonissues pertainingtoconserva- tionofbiodiversityandsustainableutilizationofbiologicalresources.HeshouldcheckPeopleBiodiversity register(PBR)ofthatpanchayatandreviewifBiodiversityManagementCommittee constitutedforthat panchayatis holdingminimum4meetings inayearandmeeting onceinevery3months (RoleofBMC availableathttps://jkpanchayat.in/b2v4.php)

COMMITTEEMEMBERS

11

PRESENT  05

BIODIVERSITYREGISTERPHOTOS

PAST 4MEETINGDETAILS-DATES,MINUTESPHOTOS  Not Available

DAY2ACTIVITIES

AGENDA4

Visitingofficershallalsoplanandconductpanchayatlevelconvergencemeeting  ofalldepartmentsand prepareVillagedevelopmentplanforvillage,inconsultancywithGrampanchayat,discussitingram sabhaandgetitapproved.

(GPDPformatavailableonhttps://jkpanchayat.in/b2v4.php)

InadditionGPDPplanshallalsoinclude:

           Touristplaceswhichneedtobedeveloped

           Specificproductwhichneedstobedeveloped

           Tourism-homestays

	20candidatesfortrainingunderHimayatschemealongwithtradeinwhich trainingistobegiven

DAY2ACTIVITIES

AGENDA5

Ensuresaturationoffollowingschemesandgivestatus:

| NAMEOFTHESCHEME | TOTALELIGIBLE BENEFICIARIESIN THE VILLAGE | TOTALBENEFICIARIESWHO AVAILEDTHEBENEFITSOFTHESCHEME | REASONSFOR PENDENCY |
| --- | --- | --- | --- |
| GoldenHealthCardunder AyushmanBharat | 1960 | 1910 | Un,atching of finger prints (0-3) |
| Jananisurakshayojana | 25 | 20 | Funds not available |
| OLDAGEpension | 150 | 150 | ------ |
| Widowpension | 42 | 42 | ------ |
| Disabilitypension | 59 | 59 | ----- |
| Domicilecertificate | 1960 | 963 | Not applied yet |
| Kisancreditcard | 271 | 230 | Pending at bank |
| PMkisansammannidhi | 124 | 124 | ------ |

| Landpassbook | 450 | 75 | Not printed yet |
| --- | --- | --- | --- |
| Registrationofvillageven- dorsonGEMportal | ------- | ------ | --- |
| Registrationofvillagecon- tractorsonjktendersportal | 45 | 16 | Under process |
| Registrationofvillagecon- tractorsonPWDportal | ---------- | ------- | ----- |
| Incompletebuildings/pro- jects | Panchayat ghar/JJM project | ------- | Dispute on panchayatghar Project ongoing |

DAY2ACTIVITIES

AGENDA6

NASHAMUKTABHIYAN

1.       Whethergramsabharesolutionpassed YES

2.       Detailsofactivities conducted Awarness among youth via ralies, counseling etc.

3.       Whetherallactivities andGSresolutionuploadedonjkpanchayats.inportal YES

4.       Howmanydrugaddictsinthevillage NA

5.       WhetherreportedtotheDeputyCommissioner --------

6.       Howmanyregisteredforrehabilitationundergovernmentprogramme ------

DAY2ACTIVITIES

AGENDA7

SOCIALAUDIT

Conductsocialauditofatleast5workseachunderfollowingschemes:

| NAMEOFTHE SCHEME | DETAILSOFTHE WORKS | YEAROFWORK APPROVAL | AMOUNT APPROVED FORTHEWORK | WHETHER WORKEXECUTED SATISFACTORILY | GEO- TAGGED PHOTOS | ANY GRIEVANCE RECORDED RELATINGTOTHAT WORK |
| --- | --- | --- | --- | --- | --- | --- |
| MGNREGA | Irrigation ladh graveyard | 2021-22 | 0.80 | Satisfactory |  | NO |
| PMAY | Javaid Ahmad Sheergogry | 2021-22 | 1.50 | Satisfactory |  | NO |
| IHHL UNDERSBM-G | Ab.Rashid Ganie | 2021-22 | 12000 | Satisfactory |  | NO |
| CSCUNDER SBMG | CSC at masjid Tawheed | 2019-20 | 2.0 | Satisfactory |  | NO |
| AMRIT sarovorsSAROVARS | ------- | ------- | ------ | ----- | ------ | ---- |

DAY2ACTIVITIES

AGENDA8

MAHILASABHA

Totalwomeninthevillageabovetheageof18  367

Totalattended 10

Proceedings:

(Plinsertpointerstobediscussedthere–referpalliproceedings)

DAY2ACTIVITIES

AGENDA9

BALSABHA

Holda balsabhaandrecordproceedings

Totalchildreninthevillageabovetheageof….. Totalattended

Proceedings:

(Plinsertpointerstobediscussedthere–referpalliproceedings)

DAY2ACTIVITIES

AGENDA10

INAUGURATIONS

| SR NO. | ASSETS/ACTIVITIES INAUGRATED | STATUSOFTHEASSET/AC- TIVITIES(NUMBER,OTHER DETAILS) | GEO-TAGGED PHOTOS |
| --- | --- | --- | --- |
|  | VILLAGEHAATunderJKSRLM (SUN- DAYMARKET) | Nil | nil |
|  | PMAYhousesifanyreadyforinaugra- tion | Inaugrated 0ne | yes |
|  | Swachhgramprojects-segregation shedsetc | Compost and Soak Pits | Yes |
|  | Amritsarovars | Nil | nil |
|  | Sportskits | Bat given to MS Ardpora | Yes |
|  | Villageculturalevents | Conducted by MS Ardpora | Yes |
|  | JJMassets/projects | Ongoing. |  |
|  | Anyothertobeidentifiedatdistrict level | ------- |  |

FOLLOWUPOF(B2V1,B2V2&B2V3):

(Prefilledexcelsheet tobetakenfromdistrictlevel/andalsotobedownloaded

fromwww.jkpanchayat.in)

| S.NO. | Particulars | Actiontaken | Remarks# |
| --- | --- | --- | --- |
| I. UrgentPublicRequirements/Demands-B2V1 |  |  |  |
| 1 | Proper drinking water | Done | Satisfactory |
| 2 | Ply field | Land not Available |  |
| 3 | Medical facility | Available | Health and Wealth |
| 4 | Public Transport | Not available |  |
| 5 | Kandiwara bridge | Ongoing |  |
| 6 | Flood control band | Done |  |
| 7 | Solid waste management | Ongoing | Compost pits |
| II. UrgentPublicRequirements/Demands-B2V2 |  |  |  |
| 1 | Upgradation of water supply | Ongoing |  |
| 2 | Road from Ardpora to Kandikot | Completed |  |
| 3 | Road from Khalhar to Buchoo | Not taken yet |  |
| 4 | Installation of transformer | Done |  |
| 5 | p.bund near Ab Gaffar | Not taken yet |  |
| 6 | Chanalization of N.Brangi from Kandiwara to Cyphon | Not taken yet |  |
| 7 |  |  |  |
| S.NO. | Particulars | Actiontaken | Remarks# |
| III. MajorProblems–B2V1 |  |  |  |
| 1 | Drinking water | Done |  |
| 2 | Public transport | Not available |  |
| 3 | Solid waste management | Ongoing |  |

| 4 | playfield | Not available |  |
| --- | --- | --- | --- |
| 5 | Medical facility | Done |  |
| IV. MajorProblems-B2V2 |  |  |  |
| 1 |  |  |  |
| 2 |  |  |  |
| 3 | nil | Nil |  |
| 4 |  |  |  |
| 5 |  |  |  |
| V. MajorProblems-B2V3 |  |  |  |
| 1 |  |  |  |
| 2 |  |  |  |
| 3 | nil | Nil |  |
| 4 |  |  |  |
| 5 |  |  |  |
| VI. MajorComplaints-B2V1 |  |  |  |
| 1 | Lack of drinking water | Done |  |
| 2 |  |  |  |
| 3 |  |  |  |
| VII. MajorComplaints-B2V2 |  |  |  |
| 1 |  |  |  |
| 2 |  |  |  |
| 3 | nil | Nil |  |
| VIII. MajorComplaints-B2V3 |  |  |  |
| 1 | Widening of irrigation canal feeding Ardpora | Not taken yet |  |
| 2 | Relaxation and Consideration to disabled persons | Benefited by schemes |  |
| 3 | Shifting of ICDS | Done |  |

OVERALLPERCEPTIONOFFUCNTIONING OF GOVERNMENTDEPARTMENTS

1.         BESTDEPARTMENT:

2.       LEASTRESPONSIVEDEPARTMENT:

GENERALASSESSMENTOFTHEVISTINGOFFICER

| I | AnymajorcomplaintbroughttothenoticeoftheVisitingOfficer: Khalhar to Buchoo road |
| --- | --- |
| II | Major/urgentpublicdemandsthatwas/werereflectedearlierbuthavenotbeenaddressedsofar: Public transport |
| III | Overallassessmentofthevisitandsuggestions: Overall visit satisfactory as general public appreciated the programme as most of the previous demands were fulfilled .Moreover public become aware about the various schemes of government (Thevisitingofficertoensurethattheoverallassessmentisrecordedindetailsalongwithconcretesugges- tions) |
| IV | OverallRatingofgovtfunctioningas givenbythePanchayat(Scaleof0to10) |
| V | CertificatefromSarpanchthatthevisitingofficerhasstayedinthepanchayatfor2days |

SignatureofSarpanch                                                                              SignatureoftheVisitingOfficer

Name………………………                                                                               Name………………………

DepartmentofRuralDevelompentandPanchayatiRaj

GovernmentofJammu &Kashmir