**BACK TO VILLAGE- PHASE IV (15TH OCTOBER TO 3RD NOVEMBER )**

**KEY FEATURES**

* Deputy Commissioners to lead the initiative
* Rural development Department to be the nodal department
* Planning Development & Monitoring department and IT to be the support departments

**ACTIONS AND TIMELINES**

|  |  |  |  |
| --- | --- | --- | --- |
| **ACTION** | **RESPONSIBILITY** | **LATEST BY** | **REMARKS** |
| Jan abhiyan | All departments | Oct 15 -25th | Going on |
| Deputation of Sectt staff/HoDs | GAD | Oct 14 | Done |
| Deployment of Staff to Panchayats and serving of orders on deployed officers | DCs | Oct 25 | DCs will deploy senior level staff from the districts. Strict action to be taken against absentees. No exemptions to be given |
| Training of district trainers on B2V4 | RDD | Oct 26 |  |
| Training of visiting officers | DCs | Oct 27 |  |
| Field Visits to be completed by | Visiting Officers | Nov 3 | DCs to supervise and ensure that each Panchayat is visited within the period specified |
| Data of B2V4 to be uploaded by | Visiting Officers | Nov 10 | DCs to supervise and ensure that data of all Panchayats is uploaded by the visiting officer within the period specified |

**INSTRUCTIONS FOR THE VISITING OFFICER (DAY WISE)**

|  |  |  |
| --- | --- | --- |
| **DATE** | **INSTRUCTIONS** | **ACTION POINTS** |
| Day 0 | Meeting with deputy commissioner and his/her team | 1. Take print outs of filled booklets of B2V1, B2V2 and B2V3 from [www.jkpanchayat.in](http://www.jkpanchayat.in) 2. Also take print outs of the summarized excel sheets of the previous phases from [www.jkpanchayat.in](http://www.jkpanchayat.in) 3. Collect ATRs on issues raised during previous 3 phases from the office of Deputy Commissioner (Planning deptt) 4. Take prints of blank 2 booklets of B2V4 from [www.jkpanchayat.in](http://www.jkpanchayat.in) 5. Take plans for 2 previous years and ATRs from the planning deptt 6. Complete trainings on different components of B2V4 being organized by respective Deputy Commissioners 7. Collect List of new works started/ ongoing/ completed during the previous and current Financial year under the following heads:  * PRI grants * District Plan * UT plan * MGNREGA * Other schemes of other departments * Any other work  1. Plans/ beneficiary lists:  * MGNREGA draft plan document for the year 2022-23. * List of Awaas+ beneficiaries alongwith IHHL Convergence * List of pension beneficiaries. * List of SHGs * List of agriculture scheme beneficiaries  1. Lists of beneficiaries for:  * Various certificates/ benefits to be distributed by the visiting officer. * Any other activities identified by different departments |
| Day 1 | Reach the village | 1. Ensure that all front line workers of different deptts are present. 2. Ensure exhibition by different depts. about individual beneficiary schemes 3. Inspect JKB/PSB counters/outlets 4. Participate/ensure organization of sports activity in playfield, talent hunt/cultural event/youth activity 5. Visit atleast 2 amritsarovars and get its geo tagged photos 6. Inspect Khidmat (CSC) Centres and create Generate awareness on 225 schemes particularly G2C schemes like BEAMS, Janbhagidari, AapkiZaminAapkiNigrani, Digital J&K 7. Visiting officer shall also plan and conduct panchayat level convergence meeting of all departments 8. Check effectiveness of Centrally sponsored schemes 9. Visit and inspect all government establishments including PHE, AWC, FPS, schools, etc 10. Attempt saturation of deliverable so Janabhiyan and wherever deficiencies found, lead a drive to achieve all deliverables 11. Assess effectiveness of sanitation campaign in the panchayat 12. Ensure self employment activities for 15 youth per panchayat 13. Wherever possible, distribute employment letters for people selected under various government employments 14. In the evening, hold inormal meeting with senior citizens, govt employees including retired employees, ex servicemen, youth club, and any citizens of the village who are enrolled in college/university 15. Open discussion on Nasha Mukt Abhiyan |
| Day2 | Have a meeting with all stakeholders- deptt officials and panchayat members | 1. Discussion on the and assess the progress of different schemes relating to the localized SDGs prioritized for that village as per the resolution passed by that Gram Panchayat on 21st April 22, on National Panchayti Raj Day. 2. **Sensitize village residents about myScheme” portal (myscheme.in)** which includes information about all the schemes being run by Central/ State/ UT govt across the country 3. Hold meeting of the **Biodiversity Management Committees** to deliberate on issues pertaining to conservation of biodiversity and sustainable utilization of biological resources. 4. Prepare Village development plan, in consultancy with Gram panchayat, discuss it in gram sabha and get it approved. 5. Ensure saturation of soil health card and golden health card under **Golden Health Card under Ayushman Bharat**, 6. Ensure saturation of **Old Age Pension Scheme** 7. Ensure Domicile Saturation. 8. Ensure KCC Saturation 9. Ensure saturation of land pass books 10. Ensure registration of village vendors needed for any scheme, on GEM portal 11. Ensure panchayat contractors registration 12. Encourage Panchayat members for importance of plantation drive in Panchayat under Har Gaon Hariyali 13. Ensure painting on digital J&K in panchayat ghars 14. Ensure painting on panchayat activites and CSS in panchayat ghars 15. The visiting office shall check no of kindergarten and playfields present in the panchayat for kids and students, if the infrastructure present in these are good enough. 16. Hold meeting with panchayat members to discuss about corruption menace and steps required to make J&K corruption free 17. Obtain a candid assessment about performance of various deptts including fair feedback about discrepancies in functioning 18. Check the status of Nasha Mukt Abhiyan and reporting of drug addicts to Deputy Commissioner. 19. Identify Tourist Destinations, Circuits, Theme Treks, Identify Homestays, provide support for tourism activities through Village Cooperative 20. Organize Talent Hunt at Panchayat Level 21. Conduct social audit of atleast 5 works under following schemes:     1. MGNREGA     2. PMAY     3. IHHL toilets and payments     4. CSCs     5. AMRIT SAROVARS 22. Hold a mahilasabha and a balsabha and record proceedings in the format given 23. Inaugurate village haat under JKSRLM 24. Check if youth clubs are formed in the panchayat and what activities they are engaged in 25. Organize a village level cultural event to engage panchayat members 26. Sensitize GP about E-kitab kosh an initiative of J&K Govt for empowering youths through online digital literacy |

**GENERAL INSTRUUTIONS**

1. The visiting officer shall refrain himself/ herself giving or offering any commitment on behalf of the government and shall adopt an unbiased attitude in reporting issues. As far as possible, his/her observation should be based on a fair and analytical view emerging from his/her interaction in the village.
2. He is going to the village as planning officer, not for sanctioning any works or for making any commitments.
3. While preparing village development plan, he has to ensure that, demands are prioritized and reflected under available schemes, wherever necessary the larger works are to be referred to administrative deptt under CSS/UT plans under intimation to DCs and rest of the works to DCs for reflecting it under district/CSS plans
4. His work shall be hard core planning and audit and is not a PR exercise.
5. **Focus of visit are youth, skills, self-employment, nasha mukt, bhrashtrachar mukt, Rozgar yukt J&K, besides to carry forward the activities during Jan Abhiyan and saturate them.**
6. **In addition attention may be given to the following areas**
   1. Make full use of Centrally Sponsored Schemes
   2. Saturation of individual beneficiary schemes
   3. Self-employment schemes
   4. Bank linked schemes- including departmental subsidy schemes
   5. Empowerment and transparency through digital initiatives
   6. Effectiveness of grass roots machinery –
      1. Patwari, VLW present and available
      2. Available funds utilized in public interest and as per Gram Sabha resolutions
      3. Fairness in governance
      4. CSS/Individual beneficiary schemes etc
      5. BrashtacharMukt J&K
      6. Bhai Mukt J&K
      7. NashaMukt J&K
7. The PRI members (Sarpanchs, Panchs, BDC Chairperson) shall be kept at the forefront of all activities and given due importance and the approach should be to strengthen them and make them feel empowered. He/she shall ensure that the BDC chairperson and Sarpanch/Panch are present at the time of inauguration and ceremonies.
8. The visitingofficer shall ensure that COVID protocols are strictly followed during the visits.

**BACK TO VILLAGE (B2V4) October 27th to November 3rd**

**A) Details of Reporting Officer:**

Name: Sabzar Ahmad Malik

Designation Senior Lecturer

Department/GBHSS Panpore

Mobile No: 9622663399

Email ID: smz.chem123@gmail.com

Home District: Anantnag

Dates of visit: 28/10/2022 & 29/10/2022

**B)Locational details of Panchayat: (to be pre-filled, information to be taken from the previous phases booklets/summarized excel sheet uploaded on** [**jkpanchayat.in**](http://www.jkpanchayat.in)**/b2v4.php ) (to be validated by the visiting officer and missing details to be filled)**

Name of the Panchayat: Bonura

Local Government Directory(LGD) code of the Panchayat: 242861

Name of CD Block: Pulwama

Name of Tehsil: Pulwama

Name of District: Pulwama

**C)Panchayat Profile:**

No. of revenue villages in the Panchayat: 04

No. of hamlets in the Panchayat: 01

No. of households in the Panchayat: 768

Population of the Panchayat (approx.): 4899

**PartII : (To be filled up by the Visiting Officer during his/her two day visit to the Panchayat. All Fields have to be filled by the Visiting Officer before the booklet is handed over to the DC**

**Frontline Officers/Officials who were assigned to the Panchayat for the program:**

|  |  |  |
| --- | --- | --- |
| **Department** | **Name** | **Designation** |
| RDD | Gh Rasool Dar | Panchayat Secretary |
| RDD | Jabeena Noor | GRS |
| Revenue | Sheikh Samiullah | Pathwari |
| CSC Bundzoo | Shabir Ahmad Dar |  |
| J&K Bank | Ab hamid bhat |  |
| J&K Bank | Arshid Wani |  |
| FCS & CA | Aabid Hussain Lone |  |
| RDD | Ab Salam |  |
| PHE | Manzoor Ahmad |  |
| ICDS | Fareeda Ji | Supervisor |
| RDD | Roshan Ara |  |
| Asha Worker | Rukhsana (etal) |  |
| Health | Saja Ji | FMPHW |
|  |  |  |
|  |  |  |

**Details of absentee employees vis-à-vis list furnished by the DC office:**

|  |  |  |
| --- | --- | --- |
| **Department** | **Name** | **Designation** |
|  |  |  |
|  |  |  |
|  |  |  |
|  |  |  |

**DAY 1 ACTIVITIES**

**AGENDA 1: PANCHAYAT ASSET REGISTER**

**Infrastructure:**

1. Panchayat Ghar Infrastructure

Govt building/private (Govt)

New/needing repairs ( Need repairs)

1. Furniture (Y/N): Yes but damaged
2. Computer/printer (Y/N): Y
3. Internet (Y/N): N
4. Telephone (Y/N): N
5. Toilet (CSC/part of panchayat ghar) (Y/N) : Y
6. Water (Y/N) :Yes but not in proper way
7. Electricity (Y/N): N
8. Bank branch (Y/N): N
9. CSC (Y/N): Y
10. Patwarkhana (Y/N): N
11. Village haat (Y/N): Y
12. Playground (Y/N): Y
13. School-
14. Kindergarten (Y/N): Y
15. Primary (Y/N): Y
16. Secondary (Y/N): Y
17. College (Y/N) : N
18. University (Y/N) : N
19. Anganwadi Centre (Y/N)
    1. (govt/private) :YES
    2. Total children enrolled:397

15. Amrit Sarovars – details, location, condition: NOT AVAILABLE

16. Government offices- details, whether functional or not: Schools,

17. Ration shop (Y/N): Y

18. Places of tourism importance – names, little details on historical/cultural importance

19. Village heritage sites/ treks- names, little details on historical/cultural importance

20.VLW Office (Y/N): Y

21. Primary Healthcare Centre (Y/N), : N

22. List of Incomplete Buildings- names, year of construction : Nil

23. List of Underutilized Buildings- names: NIL

**DAY 1 ACTIVITIES**

**AGENDA 2: DIFFERENT INSTITUTIONS/INFRASTRUCTURE PROJECTS TO BE VISITED**

|  |  |  |
| --- | --- | --- |
| AMRIT SAROVARS | Visit, verify | Comments |
| Khidmat Centre | create Generate awareness on 225 schemes particularly G2C schems Aapki Zamin Aap ki Nigrani, Beams, janbhagidari, digital J&K | Need more awareness camps to be organized |
| CSC counters/JKB/PSB counters/outlets | a) Status of counter  b) Number of visitors | No bank in the panchayat halqa |
| INCOMPLETE BUILDINGS/PROJECTS | Verify whether identification and redistribution done | Nil |
| PDS | Visit, evaluate, online status | Ok |
| PHC | Visit- evaluate, status of staff, equipment and quality | Not at all |
| YOUTH CLUBS | Meet, interact, seek suggestions | No youth clubs |
| SHG | Meet, identify problems, seek suggestions | Only one self help group |
| PMAY | Inspect, Inaugurate | 01 inspected |
| MY SCHOOL, MY PRIDE PROGRESS; SCHOOLS- WATER, TOILETS, STAFF | Visit, check for water, electricity, sanitation, meet students and staff | All the schools in the halqa need upliftment |
| SWACHH GRAM SBM | Evaluate | OK |
| PANCHAYAT PLAY GROUND  SPORTS KITS DISTRIBUTION  VILLAGE GAMES | Ensure, verify. Participate in at least one game in the playground | Done (Tug Of War)/A Cricket Match |
| HAR GAON HARIYALI , PLANTATION DRIVE | Evaluate status, feedback | Done |
| VILLAGE CULTURAL EVENT  DANGAL/HAAT/MELA | Participate in; ensure that it is held | Stall Installed |
| EXHIBITION OF SCHEMES | Ensure that every department participates and that it continues for the entire duration of B2V | Yes |
| JAL JIWAN MISSION VERIFICATION- WSS/JSD  ELECTRICITY SUPPLY | Verify | Needs Improvement |

**DAY 1 ACTIVITIES**

**AGENDA 3: SATURATE JAN BHIYAN DELIVERABLES AND RECORD DEFICIENCIES IF ANY**

|  |  |  |
| --- | --- | --- |
| **DEPARTMENT** | **DELIVERABLES** | **SATURATION** |
| Health | Golden healh card |  |
| Health | Janani suraksha yojna |  |
| Social welfare | Old age pension |  |
| do | Disablity Pention |  |
| do | Widow Pension |  |
| Agriculture | Kissan credit Card |  |
| do | PM Kissan Sammanidhi |  |
| Forest | Plantation & tree guard |  |
| RDD | Distribution Of Job Cards |  |
|  |  |  |

**DAY 1 ACTIVITIES**

**AGENDA 4:**

**SELF EMPLOYMENT ACTIVITIES**

**Ensure Self-employment activities for youth, distribute employment letters for people selected under various social schemes:**

Number of cases in different categories sanctioned 13

Details of the bank sanctioning it: 08( jkb Pulwama Main)+05(JKB B/U DRUSOO)

Total amount involved: #6870000/=

**DAY 1 ACTIVITIES**

**AGENDA 5**

* In the evening, hold informal meetings with senior citizens , govt employees, retd employees , youth club and other citizens who are enrolled on college/university and have discussion on Nasha Mukt Abhiyan, corruption free governance, doubling farmers income and record their suggestions

**DAY 2**

**Check functionality of panchayats (data filled in the excel sheet and B2V1-3 reports to be validated and gaps to be filled) insert the link**

1. Maintenance of records: Gram Sabha registers (7 registers)
2. Social Audit Committee details
3. Swachta Status – Village is ODF or ODF +
4. *MGNREGA/SBM convergence*
   1. *No of Individual Compost Pits constructed: Nil*
   2. *No of Individual Soak Pits constructed: 36 All payment Pending*
5. No.of Biodiversity management committee meetings held: NIL
6. IsthenameofSarpanchdisplayedoncitizeninformationboardsofallRD&PR schemes:Yes/No: NO
7. Are Sarpanchs being involved in start/inauguration of activities: Yes/No : Yes
8. Whether subjects have been assigned by the Sarpanch to the Panchs :Yes/No: Yes
9. Whether grievances redressal box is installed :Yes/No: NO
10. No of grievances received pertaining to Panchayat level: Nil
11. No of grievances disposed of at Panchayat level: Nil
12. Whether the Sarpanch/Panchayat Secretary have digital signatures :Yes/No: NO
13. Whether all MGNREGA/ 14th FC payments are being made by Sarpanch through Digital Signature Certificate (DSC): Yes/ No:NO

**HUMAN RESOURCE AVAILABLE AT THE PANCHAYAT LEVEL:**

|  |  |  |  |  |
| --- | --- | --- | --- | --- |
| SR NO. | DEPARTMENT WISE STAFF | NUMBERS | | NAMES |
|  |  | SANCTIONED | ACTUAL |  |
|  | Rural development department:  BDO  JE  GRS  TA | 01  01  01  01 | 01  01  01  01 |  |
|  | SCHOOL EDUCATION:  Teacher  Head master  Any other | 42  01  08 | 29  01  05 |  |
|  | JAL JEEVAN(PHE) | 04 | 04 |  |
|  | PDD (Inspector)  LINEMAN  JE  Any other (Daily Wagers) | 01  02  01  0 | 01  02  01  08 |  |
|  | FOOD & CIVIL SUPPLIES  (GOVT)  Sale Center | 02  01 | 02  01 |  |
|  | AGRICULTURE & ANIMAL HUSBANDARY | 02 | 02 |  |
|  | SOCIAL WELFARE  Aww  Helper  Supervior | 11  11  01 | 11  11  01 |  |
|  | HEALTH:  ASHA  ANM  AYUSH DOCTOR  ALLOPATHIC DOCTOR  Any other Department  SERICULTURE | 3  0  0  0  01 | 3  0  0  0  01 | No health center  A PHC is needed on warfooting basis |

**DAY 2 ACTIVITIES**

**AGENDA NO.1** Discussion on the and assess the progress of different schemes relating to the localized SDGs prioritized for that village as per the resolution passed by that Gram Panchayat on 21st April 22, on National PanchayatiRaj Day **(Copy of the resolution to be taken from** [**www.jkpanchayat.in**](http://www.jkpanchayat.in) **portal under the link of Gram Swaraj Month)**

1. SDGs AGREED FOR THAT VILLAGE, TO BE IMPLEMENTED BY MARCH2024:
2. STATUS OF WORKS UNDER THE FOLLOWING SCHEMES:

1 **Clean and green village**

1. Initiatives taken by the Panchayat for managing Solid and Liquid Waste : yes
2. Initiatives taken by the Panchayat for using green sources of fuel like solar, biogas : No
3. Has mapping of land use, water bodies, forest, slopes, wet lands, degraded forest within the Gram Panchayat been done? Yes/No. If No, reason, thereof : NO(Digitalization and progress)
4. Has the Climate Resilience Plan been developed for the GP? Yes /No: No
5. Steps taken by the Gram Sabha about the climate change mitigation factors like reducing energy consumption, usage of fossil fuels, plastics, non-renewable building materials and also to promote measures like planting of trees, conserving forests, usage of good agricultural practices like drip irrigation, water conservation measures and conservation of wetlands. : NIL
6. Whether schools have started segregating waste:NO
7. Whether schools have their own compost/soakage pits for solid/liquid waste management: No
8. **Healthy village**
9. Are meetings related to Village Health and Sanitation Committee being held regularly?: Yes
10. Do all the eligible individuals been provided the Golden Card?: Yes
11. Are all the Children being immunized as per the Schedule recommended by Govt. of India?: Yes
12. Are all the eligible individuals been vaccinated against COVID-19? Yes
13. Does Gram Panchayat ensure that all pregnant women are getting necessary prenatal checkups? Yes
14. Whether all the deliveries were Institutionalized or conducted by trained Midwives? Yes

**3 Water sufficient village**

1. Do all the IHHs in the Gram Panchayat have water pipeline connections? No
2. Whether Gram Panchayat has taken steps for grey water management. If Yes please specify Yes,( by means of soakage pits in progress )
3. Do all the IHHs in the Gram Panchayat have toilets?Yes
4. Are all the IHHs toilets functional or not? Functional :Yes
5. Do all the Schools/Anganwadi centers have a toilet facility or not? Yes
6. Are all the toilets in the schools/Aaganwadi functional or not? No
7. Whether Gram Pachachayat Bhawan has separate toilets for women or not? No

**4 Child Friendly village**

1. Do all the children under the age of 0-6 years been enrolled in the Anganwadi centers for pre-schooling? Yes/NO : Yes
2. How many Bal Sabha’s were organized in the Gram Panchayat: 01
3. Whether the issues raised by Bal Sabha are addressed during the Gram Sabha. Yes/NO: NO
4. Whether Gram Panchayat is tracking the data related to dropout children and children with irregular attendance? Yes/NO. :- No
5. Do all the schools under the Gram Panchayat have separate toilets for girls and boys? Yes/No:- NO

**5 Village with good governance**

1. Is CSC located in the Gram Panchayat Bhawan or not?:-NO
2. Is the list of beneficiaries related to the Schemes/Programs displayed on the Gram panchayat wall or not?:Yes but pyt building is in abondoned condition
3. Does the Gram Panchayat has its building or not?: Yes
4. Is the Gram Panchayat office functional or not?: No
5. Are the activities approved under the Halqa Panchayat Development Plan displayed on the Gram Panchayat wall or not?: Yes
6. Is Social Audit of earlier Schemes/Programs carried out or not?: No

**6 Poverty free and enhanced livelihood village**

1. Has Gram Panchayat developed any criteria for the identification of the poor? Yes/No if yes specify: Yes PMAY, SBM, soakage pits
2. Have all the eligible households registered in PDS or not?:
3. Has Gram Panchayat provided space for Self-help Groups in PanchyatGhar for holding meetings or not?: Yes
4. Have all the eligible households been registered for Pension or not?:Yes
5. Has Gram Panchayat facilitated Youth for Skill Enhancement Courses and Placement?: No
6. Has Job Cards been distributed to all the eligible individuals under MGNREGA?Yes
7. Has Gram Panchayat facilitated SHGs for Bank Account Linkages? No

**7 Socially secured village**

1. Whether Gram Panchayat is maintaining data related to Differently Abled People: Yes
2. Is Gram Panchayat Office Disabled Friendly or not? Yes. Yes
3. Are provisions for a separate Budget under the Resource Envelope for Women and Children made or not? : Yes
4. Do all the Schools in the Gram Panchayat have facilities for Differently Abled Children like toilets, barrier-free access, etc., or not?: Yes
5. Are all the eligible individuals are getting pensions, like old age pension, widow pension, etc? Yes
6. Are all the eligible households getting benefits from IAY or not?: Yes

**DAY 2 ACTIVITIES**

**AGENDA NO.2**

**Sensitize village residents about my Scheme” portal (myscheme.in) which includes information about all the schemes being run by Central/ State/ UT govt across the country**

**(Scheme Material available from** [**https://jkpanchayat.in/b2v4.php**](https://jkpanchayat.in/b2v4.php)**) : Activity done but meagre participation of people due to harvesting season**

**DAY 2 ACTIVITIES**

**AGENDA NO.3**

**Hold meeting of the Biodiversity Management Committees to deliberate on issues pertaining to conservation of biodiversity and sustainable utilization of biological resources. He should check People Biodiversity register (PBR) of that panchayat and review if Biodiversity Management Committee constituted for that panchayat is holding minimum 4 meetings in a year and meeting once in every 3 months(Role of BMC available at https://jkpanchayat.in/b2v4.php)**

COMMITTEE MEMBERS: NO

PRESENT: NA

BIODIVERSITY REGISTER PHOTOS: NA

PAST 4 MEETING DETAILS- DATES, MINUTES PHOTOS: NA

**DAY 2 ACTIVITIES**

**AGENDA 4**

**Visiting officer shall also plan and conduct panchayat level convergence meeting of all departments and prepare Village development plan for village, in consultancy with Gram panchayat, discuss it in gram sabha and get it approved.**

**(GPDP format available on** <https://jkpanchayat.in/b2v4.php>)

In addition GPDP plan shall also include :

* Tourist places which need to be developed : NIL
* Specific product which needs to be developed: NIL
* Tourism- home stays: NIL

**DAY 2 ACTIVITIES**

**AGENDA 5**

**Ensure saturation of following schemes and give status:**

|  |  |  |  |
| --- | --- | --- | --- |
| **NAME OF THE SCHEME** | **TOTAL ELIGIBLE BENEFICIARIES IN THE VILLAGE** | **TOTAL BENEFICIARIES WHO AVAILED THE BENEFITS OF THE SCHEME** | **REASONS FOR PENDENCY** |
| **Golden Health Card under Ayushman Bharat** | **5144** | **4427** | **717 In Progress** |
| **Janani suraksha yojana** | **70** | **Nil** | **Non Availability of Funds** |
| **OLD AGE pension** | **243** | **243** |  |
| **Widow pension** | **86** | **86** |  |
| **Disability pension** | **70** | **70** |  |
| **Domicile certificate** | **NA** | **NA** | **NA** |
| **Kisan credit card** | **NA** | **NA** | **NA** |
| **PM kisan sammannidhi** | **NA** | **NA** | **NA** |
| **Land pass book** | **NA** | **NA** | **NA** |
| **Registration of village vendors on GEM portal** | **NIL** | **NIL** | **NIL** |
| **Registration of village contractors on jktenders portal** | **06** | **NIL** | **NIL** |
| **Registration of village contractors on PWD portal** | **01** | **NIL** | **NIL** |
| **Incomplete buildings/projects** | **NIL** | **NIL** | **NIL** |

**DAY 2 ACTIVITIES**

**AGENDA 6**

**NASHA MUKT ABHIYAN**

1. Whether gram sabha resolution passed: Yes
2. Details of activities conducted: YES Sports activities, Nukad NaTak, Pledge, Road shows , cultural activities
3. Whether all activities and GS resolution uploaded on jkpanchayats.in portal: Yes
4. How many drug addicts in the village: NA
5. Whether reported to the Deputy Commissioner:NA
6. How many registered for rehabilitation under government programme: NA

**DA DAY 2 ACTIVITIES**

**AGENDA 7**

**SOCIAL AUDIT**

Conduct social audit of at least 5 works under following schemes:

|  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- |
| NAME OF THE SCHEME | DETAILS OF THE WORKS | YEAROF WORK APPROVAL | AMOUNT APPROVED FOR THE WORK | WHETHER WORK EXECUTED SATISFACTORILY | GEO-TAGGED PHOTOS | ANY GRIEVANCE RECORDED RELATING TO THAT WORK |
| MGNREGA | 05 | 2021-22 | 31 lac | Yes | Yes | No |
| PMAY | 01 | 2022 | 1.5430 lac | Yes | Yes | No |
| IHHL UNDER SBM-G | 05 | 2021-22 | 0.6 lac | Yes | Yes | No |
| CSC UNDER SBMG |  |  |  |  |  |  |
| AMRIT SAROVARS |  |  |  |  |  |  |
|  |  |  |  |  |  |  |

**DAY 2 ACTIVITIES**

**AGENDA 8**

**MAHILA SABHA**

Total women in the village above the age of 18 =1511

Total attended :50 (the people were busy with harvesting)

Proceedings:

(Pl insert pointers to be discussed there – refer palli proceedings)

**DAY 2 ACTIVITIES**

**AGENDA 9**

**BAL SABHA**

Hold a bal sabha and record proceedings

Total children in the village above the age of …..

Total attended ;70

Proceedings:

(Pl insert pointers to be discussed there – refer palli proceedings)

**DAY 2 ACTIVITIES**

**AGENDA 10**

**INAUGRATIONS**

|  |  |  |  |
| --- | --- | --- | --- |
| **SR NO.** | **ASSETS /ACTIVITIES INAUGRATED** | **STATUS OF THE ASSET/ACTIVITIES (NUMBER, OTHER DETAILS)** | **GEO-TAGGED PHOTOS** |
|  | VILLAGE HAAT under JKSRLM (SUNDAY MARKET) | YES |  |
|  | PMAY houses if any ready for inaugration | YES |  |
|  | Swachh gram projects- segregation sheds etc |  |  |
|  | Amrit sarovars | Not Available |  |
|  | Sports kits | Distributed carrom and chess kits to old age persons (one each) | YES |
|  | Village cultural events | YES | Yes |
|  | JJM assets/projects |  |  |
|  | Any other to be identified at district level | NIL | NIL |

**FOLLOW UP OF (B2V1, B2V2 & B2V3):(Pre filled excel sheet to be taken from district level/ and also to be downloaded from www.jkpanchayat.in)**

|  |  |  |  |
| --- | --- | --- | --- |
| S.NO. | Particulars | Action taken | Remarks # |
| 1. Urgent Public Requirements/ Demands- B2V1 | | | |
| 1 | Irrigation of fields | Partially | Needs improvement to be done urgently |
| 2 | Drinking water | Not resolved |  |
| 3 | Power supply | Improved but partially |  |
| 4 | Health sector | No PHC |  |
| 5 | Sasaara nallah | Const Of protection bund |  |
| 6 |  |  |  |
| 7 |  |  |  |
| 1. Urgent Public Requirements/ Demands- B2V2 | | | |
| 1 | Drinking water filtration plants |  | Needs Immediate redressal |
| 2 | Power supply |  |  |
| 3 | Helth sector |  | Needs PHC |
| 4 | Education |  | Needs Upliftment |
| 5 | sasarara nallah | Const of protection bund |  |
| 6 |  |  |  |
| 7 |  |  |  |
| S.NO. |  | Action taken | Remarks # |
| 1. Major Problems – B2V1 | | | |
| 1 | Same as B2V1 but unresolved fully |  |  |
| 2 |  |  |  |
| 3 |  |  |  |
| 4 |  |  |  |
| 5 |  |  |  |
| 1. Major Problems- B2V2 | | | |
| 1 |  |  |  |
| 2 |  |  |  |
| 3 |  |  |  |
| 4 |  |  |  |
| 5 |  |  |  |
| 1. Major Problems- B2V3 | | | |
| 1 | Health sector |  | No PHC Still not resolved |
| 2 | Sasaara nallah | Protection bund |  |
| 3 | Power supply |  | Not Resolved |
| 4 | Drinking water |  | Not Resolved |
| 5 |  |  |  |
| 1. Major Complaints- B2V1 (the problems identified but not resolved) | | | |
| 1. Major Complaints- B2V2(The problem redressal needs a pragmatic approach) | | | |
| 1 |  |  |  |
| 2 |  |  |  |
| 3 |  |  |  |
| 1. Major Complaints- B2V3: | | | |
| 1 | PHC |  | Problems unresolved |
| 2 | Drinking water |  | Problems unresolved |
| 3 | Protection bund |  | Problems unresolved |

**OVERALL PERCEPTION OF FUCNTIONING OF GOVERNMENT DEPARTMENTS**

BEST DEPARTMENT:

LEAST RESPONSIVE:

**GENERAL ASSESSMENT OF THE VISTING OFFICER**

|  |  |
| --- | --- |
| I | Any major complaint brought to the notice of the Visiting Officer: |
|  | No major complaint |
| II | Major/ urgent public demands that was/ were reflected earlier but have not been addressed so far: |
|  | Nothing specific more expectations |
| III | Overall assessment of the visit and suggestions:  (The visiting officer to ensure that the overall assessment is recorded in details along with concrete suggestions): Discussion with public with issues and proper recording and prioritization. |
| IV | Overall Rating of govt functioning as given by the Panchayat (Scale of 0 to 10):- 07 |
| V | Certificate from Sarpanch that the visiting officer has stayed in the panchayat for 2 days |

This is to certify that the visiting officer stayed at the venue M/S Bandzoo Designated at Hq for pyt halqa boonura for two days I.e 28Th & 29Th of octuber 2022.

Signature of Sarpanch Signature of the Visiting Officer

Name ……………………… Name…………………………..