4





**15TH OCTto3RD NOV,2022**

**KEYFEATURES**

• DeputyCommissionerstoleadtheinitiative

• RuraldevelopmentDepartmenttobethenodaldepartment

• PlanningDevelopment&MonitoringdepartmentandITtobethesupport departments

**ACTIONSANDTIMELINES**

|  |  |  |  |
| --- | --- | --- | --- |
| **ACTION** | **RESPONSIBILITY** | **LATESTBY** | **REMARKS** |
| **Janabhiyan** | Alldepartments | Oct15-26th | Goingon |
| **DeputationofSecttstaff/ HoDs** | GAD | Oct14 | Done |
| **DeploymentofStaffto Panchayatsandservingof ordersondeployedofficers** | DCs | Oct25 | DCswilldeployseniorlevelstaff fromthedistricts.Strictactionto betakenagainstabstentions.No exemptionstobegiven |
| **TrainingofdistricttrainorsonB2V4** | RDD | Oct26 |  |
| **Trainingofvisitingofficers** | DCs | Oct27 |  |
| **FieldVisitstobecompleted by** | VisitingOfficers | Nov3 | DCstosuperviseandensurethat eachPanchayatisvisitedwithin theperiodspecified |
| **DataofB2V4tobe uploadedby** | VisitingOfficers | Nov10 | DCstosuperviseandensurethat dataofallPanchayatsisupload- edbythevisitingofficerwithin theperiodspecified |

**INSTRUCTIONSFORTHEVISITINGOFFICER(DAYWISE)**

|  |  |  |
| --- | --- | --- |
| **DATE** | **INSTRUCTIONS** | **ACTIONPOINTS** |
| **Day0** | Meetingwithdeputy commissionerandhis/her team | a. TakeprintoutsoffilledbookletsofB2V1,B2V2andB2V3from [www.jkpanchayat.in](http://www.jkpanchayat.in)  b.Alsotakeprintoutsofthesummarizedexcelsheetsofthe previousphasesfrom[www.jkpanchayat.in](http://www.jkpanchayat.in)  c. CollectATRsonissuesraisedduringprevious3phasesfromthe officeofDeputyCommissioner(Planningdeptt)  d.Takeprintsofblank 2bookletsofB2V4from[www.jkpanchayat.in](http://www.jkpanchayat.in)e.Takeplansfor2previousyearsandATRsfromtheplanningdepttf. CompletetrainingsondifferentcomponentsofB2V4being  organizedbyrespectiveDeputyCommissioners  g.CollectListofnewworksstarted/ongoing/completedduringthe previousandcurrentFinancialyearunderthefollowingheads:  • PRIgrants  • DistrictPlan  • UTplan  • MGNREGA  • Otherschemesofotherdepartments  • Anyotherwork  h. Plans/beneficiarylists:  • MGNREGAdraftplandocumentfortheyear2022-23.  • ListofAwaas+beneficiariesalongwithIHHL Convergence  • Listofpensionbeneficiaries.  • ListofSHGs  • Listofagricultureschemebeneficiaries  i. Listsofbeneficiariesfor:  • Variouscertificates/benefitstobedistributedbythe visitingofficer.  • Anyotheractivitiesidentifiedbydifferentdepartments |

|  |  |  |  |
| --- | --- | --- | --- |
| **Day1** | Reachthevillage | 1. | Ensurethatallfrontlineworkersofdifferentdepttsarepresent. |
|  |  | 2. | Ensureexhibitionbydifferentdepts.aboutindividualbeneficiary schemes |
|  |  | 3. | InspectJKB/PSBcounters/outlets |
|  |  | 4. | Participate/ensureorganizationofsportsactivityinplayfield,talent hunt/culturalevent/youthactivity |
|  |  | 5. | GandhiKatha(suggesteddetailsuploadedonjkpanchayat.in) |
|  |  | 6. | Visitatleast2amritsarovarsandgetitsgeotaggedphotos |
|  |  | 7. | InspectKhidmat(CSC)CentresandcreateGenerateawarenesson  225schemesparticularlyG2CschemeslikeBEAMS,Janbhagidari, AapkiZaminAapkiNigrani,DigitalJ&K |
|  |  | 8. | Visitingofficershallalsoplanandconductpanchayatlevelconver- gencemeetingofalldepartments |
|  |  | 9. | CheckeffectivenessofCentrallysponsoredschemes |
|  |  | 10. | VisitandinspectallgovernmentestablishmentsincludingPHE, AWC,FPS,schools,etc |
|  |  | 11. | Attemptsaturationofdeliverableso JanAbhiyanandwherever deficienciesfound,leadadrivetoachievealldeliverables |
|  |  | 12. | Assesseffectivenessofsanitationcampaigninthepanchayat |
|  |  | 13. | Ensureselfemploymentactivitiesfor15youthperpanchayat |
|  |  | 14. | Identify20potentialcandidatesperpanchayatforHIMAYATtraining alongwiththetradeonwhichtheywanttraining |
|  |  | 15. | Whereverpossible,distributeemploymentlettersforpeopleselect- edundervariousgovernmentemployments |
|  |  | 16. | Intheevening,holdnormalmeetingwith seniorcitizens,govtem- ployeesincludingretiredemployees,exservicemen,youthclub,and any citizens ofthevillagewhoareenrolledincollege/university |
|  |  | 17. | OpendiscussiononNashaMuktAbhiyan |

Day2 Haveameetingwithall stakeholders-depttofficials andpanchayatmembers

1. Discussionontheandassesstheprogressofdifferentschemesrelating tothelocalizedSDGsprioritizedforthatvillageaspertheresolution passedby thatGramPanchayaton21stApril22,onNationalPanchaytiRajDay.

2. Sensitizevillage residentsaboutmyScheme”portal(myscheme.in) whichincludesinformationaboutalltheschemesbeingrunbyCen- tral/State/UTgovtacrossthecountry

3. Hold meeting oftheBiodiversityManagementCommitteestodeliber- ateonissuespertaining toconservation of biodiversityandsustaina- bleutilizationof biologicalresources.

4. PrepareVillagedevelopmentplan,inconsultancywithGrampanchayat, discussitingramsabhaandgetitapproved.

5. Ensure saturationofsoilhealthcardandgoldenhealthcardunderGold- enHealthCardunderAyushmanBharat,

6. Ensuresaturation ofOldAge PensionScheme

7. EnsureDomicileSaturation.

8. EnsureKCCSaturation

9. Ensure saturationoflandpassbooks

10. Ensureregistrationofvillagevendorsneededforanyscheme,onGEM

portal

11. Ensurepanchayatcontractors registration

12. EncouragePanchayatmembers forimportanceofplantationdrivein

PanchayatunderHarGaonHariyali

13. Ensure paintingondigitalJ&Kinpanchayatghars

14. Ensure paintingonpanchayatactivitesandCSSinpanchayatghars

15. Thevisiting officeshallchecknoof kindergarten andplayfields present inthepanchayatfor kidsandstudents,iftheinfrastructure present inthesearegoodenough.

16. Holdmeeting withpanchayatmembers todiscussaboutcorruption menaceandstepsrequiredtomakeJ&Kcorruptionfree

17. Obtaina candidassessmentaboutperformanceofvariousdepttsin- cludingfairfeedbackaboutdiscrepanciesinfunctioning

18. Check thestatusof NashaMuktAbhiyanandreporting ofdrugad- dictstoDeputyCommissioner.

19. IdentifyTouristDestinations,Circuits,ThemeTreks,IdentifyHomestays, providesupportfortourismactivities throughVillageCooperative

20. OrganizeTalentHuntatPanchayatLevel

21. Conductsocialauditofatleast5worksunderfollowingschemes:

a. MGNREGA

b.PMAY

c. IHHLtoiletsandpayments d.CSCs

e.AMRITSAROVARS

22. Holdamahilasabhaandabalsabhaandrecordproceedingsinthefor- matgiven

23. InauguratevillagehaatunderJKSRLM

24. Checkifyouthclubsareformedinthepanchayatandwhatactivities theyareengagedin

25. Organizea villagelevelculturaleventtoengagepanchayatmembers

26. SensitizeGPaboutE-kitabkoshaninitiativeofJ&KGovtforempowering youthsthrough onlinedigitalliteracy

**GENERALINSTRUCTIONS**

1. Thevisitingofficershallrefrainhimself/herselfgivingorofferinganycommitmentonbehalfofthe governmentandshalladoptanunbiasedattitudeinreportingissues.As faraspossible,his/her observation shouldbebasedona fairandanalytical viewemergingfromhis/herinteractioninthe village.

2. Heisgoingtothevillageasplanningofficer,notforsanctioninganyworksorformakinganycom- mitments.

3. Whilepreparingvillagedevelopmentplan,hehastoensurethat,demandsareprioritizedandre- flectedunderavailableschemes,wherevernecessarythelargerworksaretobereferredtoadminis- trativedepttunderCSS/UTplansunderintimationtoDCsandrestoftheworkstoDCsforreflecting itunderdistrict/CSS plans

4. His workshallbehardcoreplanningandauditandisnota PRexercise.

5. EveryDeputyCommissionerhastoensurethatatleastoneRDDofficial(ideallyPanchayatSecre- tary)ispresent ineverypanchayatwithrelevantpanchayatrecords,toensureconductofallactivi- tiesasplanned.Panchayatwiseorderneedstobeissuedinadvance.

6. Visitingofficershouldideallycarryhis/herlaptoptocompletethereportsatthepanchayatlevel itselfanduploadthefinalreport,duly signedbothbythesarpanchandbythevisitingofficeron [www.jkpanchayat.in](http://www.jkpanchayat.in)portal,beforetheyleavepanchayat.

7. Focus ofvisitareyouth,skills,self-employment,nashamukt,bhrashtracharmukt,RozgaryuktJ&K, besidestocarryforwardtheactivities duringJanAbhiyanandsaturatethem.

8. Inadditionattentionmaybegiventothefollowingareas a. MakefulluseofCentrallySponsoredSchemes

b.Saturationofindividualbeneficiaryschemes c. Self-employmentschemes

d.Banklinkedschemes-includingdepartmentalsubsidyschemes e.Empowermentandtransparencythrough digitalinitiatives

f. Effectivenessofgrassrootsmachinery–

i. Patwari,VLWpresent andavailable

ii. AvailablefundsutilizedinpublicinterestandasperGramSabharesolutions iii. Fairness ingovernance

iv. CSS/Individual beneficiaryschemesetcv. BrashtacharMuktJ&K

vi. BhaiMuktJ&K

vii. NashaMuktJ&K

9. ThePRImembers (Sarpanchs,Panchs,BDCChairperson)shallbeattheforefrontofallactivities and givendueimportanceandtheapproach shouldbetostrengthenthemandmakethemfeelem- powered.He/sheshallensurethattheBDCchairpersonandSarpanch/Pancharepresent atthetime ofinaugurationandceremonies.

10. Visitingofficershallnotleavethedistrictwithoutuploadingthereport,duly signedonthe**www. jkpanchayat.in**portal.EveryDeputyCommissionerhastoensurethat.

**A) DetailsofReportingOfficer:**

Name: GHULAM MOHD MIR

Designation: Sr. Lecturer

Department/placeof posting: Education/ GHSS WATERHAIL

MobileNo:9541244127

EmailID:mirgm6365@gmail.com

HomeDistrict:BUDGAM

Datesof visit:01/11/2022 & 02/11/2022

**B) LocationaldetailsofPanchayat:(tobepre-filled,informationtobetakenfromtheprevious phasesbooklets/summarizedexcelsheetuploadedonjkpanchayat.in/b2v4.php)(tobevali- datedbythevisitingofficerandmissingdetailstobefilled)**

NameofthePanchayat: PARIS ABAD

LocalGovernmentDirectory(LGD)codeof thePanchayat:241287

Nameof CDBlock:WATERHAIL

NameofTehsil:BUDGAM

Nameof District:Budgam

**C) PanchayatProfile:**

No.ofrevenuevillagesinthePanchayat:02 (PARIS ABAD & ABADPORA)

No.ofhamletsinthePanchayat:01 (KATROO)

2No.ofhouseholdsinthePanchayat: 351

Population(approx)of thePanchayat: 2210 AS PER CENSUS 2011

**Part-II:**

(TobefilledupbytheVisitingOfficerduringhis/hertwodayvisittothePanchayat.AllFieldshavetobe

filledbytheVisitingOfficerbeforethebookletishandedovertotheDC

**FrontlineOfficers/OfficialswhowereassignedtothePanchayatfortheprogramme:**

|  |  |  |
| --- | --- | --- |
| Department | Name | Designation |
| J&K BANK | AIJAZ AHMAD WANI | I/C ADVANCES |
| DIC | BASHIR AHMAD | CLASS IV |
| HEALTH | Dr.ZAKIR HUSSAIN | MEDICAL OFFICER |
| SHEEP & HUSBANDARY | IRFAN AHMAD TANTARY | STOCK ASSISTANT |
| SOCIAL WELFARE | MEHRAJ U DIN | ACCOUNTANT |
| ARTO | MOHD AMIN | Sr.ASSISTANT |
| Revenue | ALTAF HUSSAIN | Patwari |
| FOOD AND SUPPLIES | KUMAIL ALI | AFSO |
| CSCVLE | GH MOHI U DIN AND GOWHER | CSC VLE |
| ICDS | ABIDA WANI | I/C SUPERVISER |
| AGGRICULTURE | M.Y. BHAT | AFA |
| DYS & SPORTS | M.Y.WANI | PET |
| HOTICULTURE | MUNEER AHMAD | TECHNICIAN |
| R & B | G.A.DAR | RW |

**Detailsofabsentemployeesvis-à-vislistfurnishedbytheDCoffice:**

|  |  |  |
| --- | --- | --- |
| Department | Name | Designation |
| NIL | NIL | NIL |
| NIL | NIL | NIL |
| NIL | NIL | NIL |
| NIL | NIL | NIL |
| NIL | NIL | NIL |
| NIL | NIL | NIL |
| NIL | NIL | NIL |
| NIL | NIL | NIL |
| NIL | NIL | NIL |
| NIL | NIL | NIL |
| NIL | NIL | NIL |
| NIL | NIL | NIL |
| NIL | NIL | NIL |
| NIL | NIL | NIL |
|  |  |  |

**DAY1-ACTIVITIES**

**AGENDA1:PANCHAYATASSETREGISTER**

**Infrastructure:**

1. PanchayatGharInfrastructure a.Govtbuilding/private: GB

b. New/needingrepairs: New

2. Furniture(Y/N): NO

3. Computer/printer(Y/N): Y

4. Internet(Y/N): N

5. Telephone(Y/N): N

6. Toilet(CSC/partofpanchayatghar)(Y/N): N

7. Water(Y/N): Y

8. Electricity(Y/N): Y

9. Bankbranch(Y/N): N

10. CSC(Y/N): N

11. Patwarkhana(Y/N): Y

12. Villagehaat(Y/N): N

13. Playground(Y/N): Y

14. School-

a. Kindergarten(Y/N): N

b.Primary(Y/N): Y

c. Secondary(Y/N): Y

d. College (Y/N): N

e.University(Y/N): N

15. AnganwadiCentre(Y/N): Y

a. (govt/private): PVT.

b.Totalchildrenenrolled: (109)

15. AmritSarovars–details,location,condition: Nil

16. Governmentoffices-details,whetherfunctionalornot:Panchayat& Middle School (Functional)

17. Rationshop(Y/N): Y

18. Placesoftourismimportance–names,littledetailsonhistorical/culturalimportance: Nil

19. Villageheritagesites/treks-names,littledetailson historical/culturalimportance: Nil

20. VLWOffice (Y/N): Y

21. PrimaryHealthcareCentre(Y/N): Y (NTPHC)

22. ListofIncompleteBuildings-names,yearofconstruction: 1 AT HS PARIS ABAD

23. ListofUnderutilizedBuildings-names: 1 SCHOOL BUILDING AT ABAD PORA IS COMPLETELY LOCKED

**DAY1-ACTIVITIES**

**AGENDA2:**

**DIFFERENTINSTITUTIONS/INFRASTRUCTUREPROJECTSTOBEVISITED**

|  |  |  |
| --- | --- | --- |
| **AMRITSAROVARS** | **Visit,verify** | **COMMENTS** |
| KhidmatCentres | Create/Generateawarenesson225schemes particularlyG2CschemsAapkiZaminAapkiNigrani, Beams,Janbhagidari,DigitalJ&K | KHIDMAT CENTRE AT SHOLIPORA CATERS THE NEED OF THE PANCHAYAT |
| JKB/PSBcounters/outlets | a)Statusofcounter 01 b)Numberofvisitors 20 | No JKBIN PANCHAYAT HALQA.JK BANK SHOLIPORA IS AVAILABLE. |
| Incompletebuildings/pro- jects | Verify whetheridentificationandredistribution done | 1 AT HS PARIS ABAD IS INCOMPLETE,CONSTRUCTED IN 2016 |
| PDS | Visit,evaluate,onlinestatus | SATISFACTORY |
| PHC | Visit-evaluate,statusofstaff,equipmentand quality | NTPHC,STAFF DERTH ACUTE,NO EQUIPMENTS,NO LAB FACILITY,EQUILENT TO IST AID CENTRE |
| Youthclubs | Meet,interact,seeksuggestions | SATISFACTORY |
| SHG | Meet,identifyproblems,seeksuggestions | 1,NEED COPERATION AND ENTHAUSISM IN WORK |
| PMAY | Inspect,Inaugurate | NIL (LACK OF FUNDS) |
| Myschool,mypride progress;schools-water, toilets,staff | Visit,checkforwater,electricity,sanitation,meet studentsandstaff | NEED SEPARATE TOILETS FOR ADOLSCENT GIRLS,ACUTE STAFF DERTH IN HS PARIS |
| SwachhSBM | Evaluate | COMPLETE |
| Panchayatplayground, Sportskitsdistribution Villagegames | Ensure,verify.Participateinatleastonegamein theplayground | UNDER CONSTRUCTION,SPORTS KIT DISTRIBUTED |
| HarGaonHariyali, Planta- tiondrive | Evaluatestatus,feedback | GOOD,FOREST DEPT.PLANTED SAPLINGS OF PINUS IN HS PARIS |
| Villageculturalevent  Dangal/Haat/Mela | Participatein;ensurethatitisheld | HELD IN PREMISES OF HS PARIS |
| Exhibitionofschemes | Ensurethateverydepartmentparticipatesand thatitcontinuesfortheentiredurationofB2V | VARIOUS DEPARTMENTS EXPLAINED THE MASES THE VARIOUS SCHEMES IN VOGUE |
| JalJeewanMission verifica- tion- WSS/JSD  Electricitysupply | Verify | WATER SUPPLY NEEDS IMPROVEMENT |

**DAY1-ACTIVITIES**

**AGENDA3:SATURATEJANBHIYAN**

**DELIVERABLESANDRECORDDEFICIENCIESIFANY(INSERTDELIVERABLESLISTHEREASPERGADFORMAT**

|  |  |  |
| --- | --- | --- |
| **S No** | **Department** | **Work / Deliverabkle** |
| **1** | Revenue | Land Passbooks DELIVERD BY PATWAHAR CONCERNED. |
| **2** | AGGRICULTURE | OIL SEED PACKS DELIVERD |
| **3** | SOCIAL WELFARE | SPORTS KIT DELIVERD |
| **4** | FORESTERY | SAPLINGS OF PINUS |

**DAY1-ACTIVITIES**

**AGENDA4:**

**SELFEMPLOYMENTACTIVITIES**

EnsureSelf-employmentactivities foryouth,distributeemploymentlettersforpeopleselectedunder varioussocialschemes(15ISTHETARGETPERPANCHAYAT)

**Numberofcasesindifferentcategoriessanctioned :15 Detailsofthebanksanctioningit: J&K Bank SHOLIPORA**

**Totalamountinvolved: 1 Cr Appox.**

**DAY1ACTIVITIES**

**AGENDA5**

Intheevening,holdinformalmeetings withseniorcitizens,govtemployees,retdemployees,youthclub andothercitizenswhoareenrolledoncollege/universityandhavediscussiononGandhiKatha,NashaMuktAbhiyan,corruptionfreegovernance,doublingfarmersincomeandrecordtheproceedings

**DAY2**

a. NoofIndividualCompostPitsconstructed: 15

b.NoofIndividualSoakPitsconstructed: 55

V. No.ofBiodiversitymanagementcommitteemeetingsheld: 02

VI. IsthenameofSarpanchdisplayedoncitizeninformationboardsofallRD&PRschemes:Yes/No: Yes

VII. AreSarpanchsbeinginvolvedinstart/inaugurationofactivities:Yes/No: Yes

VIII. WhethersubjectshavebeenassignedbytheSarpanchtothePanchs:Yes/No: Yes

IX. Whethergrievancesredressalboxisinstalled:Yes/No: YES

X. NoofgrievancesreceivedpertainingtoPanchayatlevel: 05

XI. NoofgrievancesdisposedofatPanchayatlevel: 05

XII. WhethertheSarpanch/PanchayatSecretaryhavedigitalsignatures:Yes/No: Yes

XIII. WhetherallMGNREGA/14thFCpayments arebeingmadebySarpanchthrough DigitalSignature

Certificate(DSC):Yes/No: Yes

**HUMAN RESOURCEAVAILABLEATTHEPANCHAYAT LEVEL:**

|  |  |  |  |  |
| --- | --- | --- | --- | --- |
| **SRNO.** | **DEPARTMENTWISESTAFF** | **NUMBERS** | | **NAMES** |
|  |  | SANCTIONED | ACTUAL |  |
|  | Ruraldevelopmentdepartment: BDO  JE GRS TA | 01  01  01 | 01  01  01 | AVAILABLE AT BLOCK LEVEL  ALTAF HUSSAIN  FIRDOUS AHMAD  SYED SHAH FASIL  Niyaz Ahmad Mir |
|  | SCHOOLEDUCATION: TEACHER  HEADMASTER ANYOTHER | 16  01  06 | 16  01  02 | \_\_\_\_ |
|  | JAL JEEVAN: | 01 | 01 | BASHIR AHMAD MALIK |
|  | PDD: LINEMAN JE  ANYOTHER | 01  \_\_\_\_  \_\_\_\_ | 01 | JEHANGIR ALI KHAN  AVAILABLE  AVAILABLE |
|  | FOOD&CIVILSUPPLIES | 01 | 01 | FAIR PRICE SHOP |
|  | AGRICULTURE&ANIMALHUS- BANDARY | 01  01 | 01  01 | BASHIR AH DAR (Agriculture)  \_\_\_\_ |
|  | SOCIALWELFARE | Nil | Nil | Nil |
|  | HEALTH: ASHA ANM  AYUSHDOCTOR ALLOPATHICDOCTOR | 01  01  01  01 | 01  01  01  01 | ZEENAT WALI (NO)  ShafeeqaBano  HAFFEZA BANO (FMPHW)  MIR GHULAM HUSSAIN (PHRAMACIST)  Dr.Zakir Hussain  NAZIR AHMAD (SWEEPER) |
|  | ANYOTHERDEPARTMENT: REVENUE | 01 | 01 | ALTAF AHMAD (PATHWAR) |
|  | ICDS WORKERS | 03 | 02 | SAKEENA BANO & SAMEELA BANO |

**DAY2-ACTIVITIES**

**AGENDANO.1**

DiscussionontheandassesstheprogressofdifferentschemesrelatingtothelocalizedSDGsprior-itizedforthatvillageaspertheresolutionpassedbythatGramPanchayaton21stApril22,onNational PanchayatiRajDay(Copyoftheresolutiontobetakenfrom[www.jkpanchayat.in](http://www.jkpanchayat.in)portalunderthelinkof GramSwarajMonth)

1. SDGs AGREEDFORTHATVILLAGE,TOBEIMPLEMENTED BYMARCH2024:

2. STATUSOFWORKSUNDERTHEFOLLOWINGSCHEMES:

**1 Cleanandgreenvillage**

i.InitiativestakenbythePanchayatformanagingSolidandLiquidWaste SEGREGATION SHED CONSTRUCTED

ii. InitiativestakenbythePanchayatforusinggreensourcesoffuellikesolar,biogas

NIL

iii. Hasmappingoflanduse,waterbodies,forest,slopes,wetlands,degradedforestwithintheGram

Panchayatbeendone?Yes/No.IfNo,reason,thereof : No,.

iv. HastheClimateResiliencePlanbeendevelopedfortheGP?Yes/No: No

v. StepstakenbytheGramSabhaabouttheclimatechangemitigationfactorslikereducingenergy consumption,usageoffossilfuels,plastics,non-renewablebuildingmaterialsandalsotopromote measureslikeplantingoftrees,conservingforests,usageofgoodagriculturalpracticeslikedrip irrigation,waterconservationmeasuresandconservationofwetlands.: NO

vi. Whetherschoolshavestartedsegregatingwaste: Yes

vii. Whetherschoolshavetheirowncompost/soakagepitsforsolid/liquidwastemanagement: No

**2 Healthyvillage**

i) Aremeetings relatedtoVillageHealthandSanitationCommitteebeingheldregularly? Yes

ii) DoalltheeligibleindividualsbeenprovidedtheGoldenCard? 90%

iii) ArealltheChildrenbeingimmunizedaspertheSchedulerecommendedbyGovt.ofIndia? Yes

iv) ArealltheeligibleindividualsbeenvaccinatedagainstCOVID-19? Yes

v) DoesGramPanchayatensurethatallpregnantwomenaregettingnecessaryprenatalcheckups? Yes

vi) WhetherallthedeliverieswereInstitutionalizedorconductedbytrainedMidwives? Yes

**3 Watersufficientvillage**

i) DoalltheIHHsintheGramPanchayathavewaterpipelineconnections? YES

ii) WhetherGramPanchayathastakenstepsforgreywatermanagement.IfYespleasespecify: YES (SOAKAGE PITS AND DRAINS)

iii) DoalltheIHHsintheGramPanchayathavetoilets? Yes

iv) ArealltheIHHstoiletsfunctionalornot? Yes

v) DoalltheSchools/Anganwadicentershavea toiletfacilityornot? Yes

vi) Areallthetoiletsintheschools/Aaganwadifunctionalornot? Yes (NEEDS IMPROVEMENT)

vii) WhetherGramPachachayatBhawanhasseparate toiletsforwomenornot?No

**4 ChildFriendlyvillage**

i) Doallthechildrenundertheageof0-6yearsbeenenrolledintheAnganwadicentersforpre- schooling?Yes/No: YES

ii) HowmanyBalSabha’swereorganizedintheGramPanchayat------02-------------

iii) WhethertheissuesraisedbyBalSabhaareaddressedduringtheGramSabha. Yes/No: Yes

iv) WhetherGramPanchayatistrackingthedatarelatedtodropoutchildrenandchildrenwithirregular attendance?Yes/No: Yes.

v) DoalltheschoolsundertheGramPanchayathaveseparate toiletsforgirlsandboys?Yes/No: YES (INSUFFICIENT NEEDS IMPROVISATION)

**5 Villagewithgoodgovernance**

i) IsCSClocatedintheGramPanchayatBhawanornot? No

ii) IsthelistofbeneficiariesrelatedtotheSchemes/ProgramsdisplayedontheGrampanchayatwallor not? YES

iii) DoestheGramPanchayathasitsbuildingornot? Yes

iv) IstheGramPanchayatofficefunctionalornot? Yes (functional)

v) Aretheactivities approved undertheHalqaPanchayatDevelopmentPlandisplayedontheGram

Panchayatwallornot? Yes

vi) IsSocialAuditofearlierSchemes/Programscarriedoutornot? Yes

**6 Povertyfreeandenhancedlivelihoodvillage**

1. HasGramPanchayatdevelopedanycriteria fortheidentificationofthepoor?Yes/Noifyesspecify : Yes (Ration Cards)
2. HavealltheeligiblehouseholdsregisteredinPDSornot? Yes

iii) HasGramPanchayatprovidedspaceforSelf-helpGroupsinPanchyatGharforholdingmeetings ornot? NO

iv) HavealltheeligiblehouseholdsbeenregisteredforPensionornot? Yes

v) HasGramPanchayatfacilitatedYouthforSkillEnhancementCoursesandPlacement? NO

vi) HasJobCardsbeendistributedtoalltheeligibleindividualsunderMGNREGA? Yes

vii) HasGramPanchayatfacilitatedSHGsforBankAccountLinkages? Yes

**7 Sociallysecuredvillage**

i) WhetherGramPanchayatismaintainingdatarelatedtoDifferentlyAbledPeople? Yes

ii) IsGramPanchayatOffice DisabledFriendlyornot? NO (NEEDS IMPROVISATION)

iii) Areprovisionsfora separate BudgetundertheResourceEnvelopeforWomenandChildrenmadeor not? No

iv) DoalltheSchools intheGramPanchayathavefacilitiesforDifferentlyAbledChildrenliketoilets, barrier-freeaccess,etc.,ornot? No (NEEDS IMPROVIASTION)

v) Arealltheeligibleindividualsaregettingpensions,likeoldagepension,widowpension,etc? Yes

vi) ArealltheeligiblehouseholdsgettingbenefitsfromIAYornot? NO (LACK OF FUNDS)

**8 EngenderedDevelopmentinVillage**

i) HowmanyMahilaSabha’swereorganizedintheGramPanchayat: 01

ii) WhetherSHGsfederationshavebeenprovidedspaceformeetings inthePanchayatBhawan(Yes/ No): NO

iii) WhetherGPshavetakenstepsforincreasingwomen’sparticipationinGramSabha(Yes/No): Yes

iv) NumberofwomenbeneficiariesheadedhouseholdscoveredunderPDS

system………01………………

v) Numberofbeneficiaries(outoftotaleligiblepopulation)receivingsocialprotectionbenefitsunder

PradhanMantriMatritvaVandanaYojana………23………….

9 Self-sufficientinfrastructureinthevillage

i. WhetherGPhasa CommunityHallwithaccesstoelectricity,furniture,watersupply, toilet: ………No………

ii. WhethertheDisastermanagementplanisavailableattheGPLevel(Yes/No) : No

iii. Whetherchild-friendlyparkwithrequiredfacilitiesisavailableinGP(Yes/No) : No

iv. WhethertheGPhaseasyaccesstoGodownforstorage(Yes/No) : No

v. Whetherstreetlightsareprovidedinpublicplacesforensuringsafety(Yes/No): YES

**DAY2ACTIVITIES**

**AGENDANO.2**

SensitizevillageresidentsaboutmyScheme”portal(myscheme.in)whichincludesinformationaboutall theschemesbeingrunbyCentral/State/UT govtacrossthecountry

*(SchemeMaterialavailablefromhttps://jkpanchayat.in/b2v4.php) DONE*

**DAY2ACTIVITIES**

**AGENDANO.3**

HoldmeetingoftheBiodiversityManagementCommitteestodeliberateonissues pertainingtoconserva- tionofbiodiversityandsustainableutilizationofbiologicalresources.HeshouldcheckPeopleBiodiversity register(PBR)ofthatpanchayatandreviewifBiodiversityManagementCommittee constitutedforthat panchayatis holdingminimum4meetings inayearandmeeting onceinevery3months *(RoleofBMC availableathttps://jkpanchayat.in/b2v4.php)*

COMMITTEEMEMBERS: 06

PRESENT

BIODIVERSITYREGISTERPHOTOS : YES

PAST 4MEETINGDETAILS-DATES,MINUTESPHOTOS:

AVAILABLE

**DAY2ACTIVITIES**

**AGENDA4**

Visitingofficershallalsoplanandconductpanchayatlevelconvergencemeeting ofalldepartmentsand prepareVillagedevelopmentplanforvillage,inconsultancywithGrampanchayat,discussitingram sabhaandgetitapproved.

(GPDPformatavailableonhttps://jkpanchayat.in/b2v4.php)

**InadditionGPDPplanshallalsoinclude:**

 Touristplaceswhichneedtobedeveloped: NIL

 Specificproductwhichneedstobedeveloped: NIL

 Tourism-homestays: NIL

 20candidatesfortrainingunderHimayatschemealongwithtradeinwhich trainingistobegiven: FRAMED A LIST FOR TRAINING IN VARIOUS FIELDS.

**DAY2ACTIVITIES**

**AGENDA5**

Ensuresaturationoffollowingschemesandgivestatus:

|  |  |  |  |
| --- | --- | --- | --- |
| **NAMEOFTHESCHEME** | **TOTALELIGIBLE BENEFICIARIESIN THE VILLAGE** | **TOTALBENEFICIARIESWHO AVAILEDTHEBENEFITSOFTHESCHEME** | **REASONSFOR PENDENCY** |
| GoldenHealthCardunder  AyushmanBharat | 2210 | 1989 | IRIS SCANING SHOULD BE TAKEN INSTEAD OF FINGERPRINTS BECAUSE OF WERA AND TERA OF WORKING CLASAS |
| Jananisurakshayojana | 20 | 19 | 01 DISCHARGE CERTIFICATE NOT PRODUCED |
| OLDAGEpension | 183 | 183 | \_\_\_\_\_\_\_\_ |
| Widowpension | 31 | 31 | \_\_\_\_\_\_\_ |
| Disabilitypension | 18 | 18 | \_\_\_\_\_\_\_ |
| Domicilecertificate | 1450 | 850 | DOCUMENTS AWAITED |
| Kisancreditcard | HC. AG. AH. SH.  330 285 40 0 | HC. AG. AH. SH.  98 86 40 0 | INCOMPLETE DOCUMENTATION |
| PMkisansammannidhi | 285 | 268 | INCOMPLETE DOCUMENTATION |
| SOIL HEALTH CARDS | 285 | 285 | \_\_\_\_\_\_\_\_\_\_ |

|  |  |  |  |
| --- | --- | --- | --- |
| Landpassbook | 898 | 250 | Under Process |
| Registrationofvillageven- dorsonGEMportal | Nil | Nil | LACK OF AWARNESS |
| Registrationofvillagecon- tractorsonjktendersportal | 01 | 01 | LACK OF AWARNES |
| Registrationofvillagecon- tractorsonPWDportal | 01 | 01 | LACK OF AWARNESS |
| Incompletebuildings/pro- jects | 01 | 01 | 1 BUILDING AT HS PARISABD IS INCOMPLETE |

**DAY2ACTIVITIES**

**AGENDA6**

**NASHAMUKTABHIYAN**

1. Whethergramsabharesolutionpassed: Yes

2. Detailsofactivities conducted: PLANS FRAMED UNDER VARIOUS SCHEMES

3. Whetherallactivities andGSresolutionuploadedonjkpanchayats.inportal: Yes

4. Howmanydrugaddictsinthevillage: Nil

5. WhetherreportedtotheDeputyCommissioner: Nil

6. Howmanyregisteredforrehabilitationundergovernmentprogramme: Nil

**DAY2ACTIVITIES**

**AGENDA7**

**SOCIALAUDIT**

Conductsocialauditofatleast5workseachunderfollowingschemes:

|  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- |
| NAMEOFTHE SCHEME | DETAILSOFTHE WORKS | YEAROFWORK APPROVAL | AMOUNT APPROVED  FORTHEWORK | WHETHER  WORKEXECUTED SATISFACTORILY | GEO- TAGGED PHOTOS | ANY GRIEVANCE RECORDED RELATINGTOTHAT WORK |
| MGNREGA | WATER HARVEST TANK | 2022-23 | 1.84 lacs | Yes | YES | NO |
| PMAY | \_\_\_\_ |  |  |  |  |  |
| IHHL  UNDERSBM-G | SOAKAGE PIT (GA WANI) | 2021-22 | 12000 | YES | YES | NO |
| CSCUNDER SBMG | SANITARY COMPLEX AT PARIS | 2020-21 | 2.00 Lacs | yes | YES | NO |
| AMRIT SAROVARS | Nil |  |  |  |  |  |

**DAY2ACTIVITIES**

**AGENDA8**

**MAHILASABHA**

Totalwomeninthevillageabovetheageof: 844

Totalattended : 06

Proceedings: DISCUSSED WOMEN RELATED SOCIAL ISSUES AND THEIR REDRESSEL AT PANCHAYAT LEVEL

*(Plinsertpointerstobediscussedthere–referpalliproceedings)*

**DAY2ACTIVITIES**

**AGENDA9**

**BALSABHA**

Holda balsabhaandrecordproceedings

Totalchildreninthevillageabovetheageof….. :449 Totalattended : 15

Proceedings:DISCUSSED TEEN AGE AND ADOLSCENT RELATED ISSUES AND THEIR REDRESSEL AT PANCHAYAT LEVEL

*(Plinsertpointerstobediscussedthere–referpalliproceedings)*

**DAY2ACTIVITIES**

**AGENDA10**

**INAUGURATIONS**

|  |  |  |  |
| --- | --- | --- | --- |
| **SR NO.** | **ASSETS/ACTIVITIES INAUGRATED** | **STATUSOFTHEASSET/AC- TIVITIES(NUMBER,OTHER DETAILS)** | **GEO-TAGGED PHOTOS** |
|  | VILLAGEHAATunderJKSRLM (SUN- DAYMARKET) | NA  N |  |
|  | PMAYhousesifanyreadyforinaugra- tion | NA |  |
|  | Swachhgramprojects-segregation shedsetc | COMPLEATE | YES |
|  | Amritsarovars | NA |  |
|  | Sportskits | DISTRIBUTED | YES |
|  | Villageculturalevents | CONDUCTED AT HS PARIS | YES |
|  | JJMassets/projects | NA |  |
|  | Anyothertobeidentifiedatdistrict level | Nil |  |

**FOLLOWUPOF(B2V1,B2V2&B2V3):**

*(Prefilledexcelsheet tobetakenfromdistrictlevel/andalsotobedownloaded*

*from*[*www.jkpanchayat.in)*](http://www.jkpanchayat.in)

|  |  |  |  |  |
| --- | --- | --- | --- | --- |
| S.NO. | | Particulars | Actiontaken | Remarks# |
| I. UrgentPublicRequirements/Demands-B2V1 | | | | |
| 1 | DRINKING WATER FACILITY TO ALL MOHALLAS | | WORK COMPLETED UNDER B2V1 | NEEDS IMPROVEMENT AND REPAIR |
| 2 | Electric Poles | | ESTIMATES DOPNE AND WILL BE TAKEN UP WHEN FUNDS AVAILABLE | AEE CONCERNED SAID THAT 3.5 LACS FOR 13 POLES AND LT HT LINES WILL BE INSTALLED SOON |
| 3 | STAFF FOR PHC PARIS ABAD | | 1 M.O PHARMA  1 N.O  1F.M ARE AVAILABLE | STAFF DERTH IS AS SUCH |
| 4 | ROOFING AND GATE FENCING WALL OF HS PARIS ABAD | | IN DISTRICT PLAN 20-21 | ROOFING AND FENCING DONE |
| 5 | BLACK TOPING OF MAIN ROAD AND UPGRADATION OF LINK ROAD | | THE ROAD IS APPROVED UNDER NABARD AND WILL BE TAKEN UP IN NEXT FINANCIAL YEAR | MAIN ROAD WITH OUT BLACK TOPING TILL DATE |
| II. UrgentPublicRequirements/Demands-B2V2 | | | | |
| 1 | HT LT POLES IN THE GP | | 6.50LACS UNDER B2V2 ESTIMATES PREAPERD TO MAKE FUNDS AVAILABLE | NEEDS IMPROVEMENT |
| 2 | UTILISATION OF NEWLY CONSTRUCTED PHC BUILDING WITH FULL STAFF | | HAS BEEN UTILIZED AS COVID 19 CENTRE | NTPHC IS WORKING IN NEW BUILDING,FENCING DONE |
| 3 | CREATION OF COMMUNITY CENTRE AT ABADPORA | | \_\_\_\_\_\_ |  |
| 4 | IMP[ROVEMENT OF DRINKING WATER PIPES | | 3.30 LACS UNDER B2V2 | WORK COMPLETED YNDER B2V1 (needs improvement) |
| 5 | Creation of icds centre for mugdam mohallah and katroo mohallah | | ICDS norms do not allow as the population of mohallas is less | Worker for centre A should be provided |
| 6 |  | |  |  |
| 7 |  | |  |  |
| S.NO. | Particulars | | Actiontaken | Remarks# |
| III. MajorProblems–B2V1 | | | | |
| 1 | SHORTAGE OF DRINKING WATER IN SOME MOHALLAS | | WORK COMPLETED UNDER B2V1 | NEEDS IMPROVEMENT |
| 2 | FULL COVERAGE OF RATION CARDS,RENEWAL OF LAND PAPERS,WARASAT INTIKALS | | \_\_\_\_\_\_\_\_\_\_\_\_ |  |
| 3 | SMOOTH SUPPLY OF ELECTRICITY AND LACK OF HT LT POLES | | ESTIMATES PREAPERD AND WORK WILL BE TAKEN UP ON AVAILABILITY OF FUNDS | NEED OF INSTALLATION OF LT HT LINES WITH NEW POLES AT SOME PLACESES |

|  |  |  |  |
| --- | --- | --- | --- |
| IV. MajorProblems-B2V2 | | | |
| 1 | CREATION OF AANGANWADI CENTRE FOR MUGDAM MOHALLAH PARIS AND DAR MOHALLAH ABADPORA | ICDS NORMS DONOT ALLOW | \_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_. |
| V. MajorProblems-B2V3 | | | |
| 1 | NO PMAY BENEFIT TO THE GP. | \_\_\_\_\_\_ |  |
| 2 | NO WATCH AND WARD FOR GP BUILDIND AND OTHER ASSESTS | \_\_\_\_\_\_\_\_\_\_\_\_\_ |  |
| VI. MajorComplaints-B2V1 | | | |
| 1 | 1 AANGAWADI CENTRE AT GAMANDAR MOHALLAH WITH OUT WORKER | \_\_\_\_\_\_\_\_\_\_\_\_ | STILL WITH OUT WORKER |
| 2 | SHORTAGE OF DRINKING WATER FACILITY AT SOME MOHALLAS OF THE GP | WORK COMPLETED UNDER B2V1 PROGRAMMEE | NEEDS IMPROVEMENT |
| VII. MajorComplaints-B2V2 | | | |
| 1 | MEDICAL STAFF DERTH AT NTPHC AT PARIS ABAD. | \_\_\_\_\_\_\_\_\_\_\_\_\_ | STAFF DERTH EXISTS AS SUCH |
| 2 | ANIMAL AND SHEEP HUSBANDARY IS NOT OPERATIONAL IN THE GP. | \_\_\_\_\_\_\_\_\_\_\_\_ | \_\_\_\_\_\_\_\_ |
| 3 | IRREGULAR WATER AND ELECTRICITY SUPPLY | \_\_\_\_\_\_\_\_ | IN WINTER PROBLEM INCREASES |
| VIII. MajorComplaints-B2V3 | | | |
| 1 | AANGANWADI CENTRES WITHOUT INFRASTRUCTURE | \_\_\_\_\_\_\_\_\_\_ |  |
| 2 | ROAD NOT BLACK TOPPED | APPROVED UNDER NABARD | ROAD TILL DATE WITHOUT MAGDAMISATION |
| 3 | LT HT WIRES WITH OUT POLES | \_\_\_\_\_ | STILL IMPROVISATION IS NEEDED |

**OVERALLPERCEPTIONOFFUCNTIONING OFGOVERNMENTDEPARTMENTS**

1. **BESTDEPARTMENT: Rural Development Department & EDUCATION .**

**2. LEASTRESPONSIVEDEPARTMENT: \_\_\_\_\_\_\_\_\_\_**

**GENERALASSESSMENTOFTHEVISTINGOFFICER**

|  |  |
| --- | --- |
| I | AnymajorcomplaintbroughttothenoticeoftheVisitingOfficer: SHOLIPORA PARIS ROAD NOT BLACK TOPPED TILL DATE. |
| II | Major/urgentpublicdemandsthatwas/werereflectedearlierbuthavenotbeenaddressedsofar: BASIC MEDICAL LAB FACILITY,DENTAL SECTION,X RAY UNIT AT NTPHC PARIS ABAD NOT AVAILABLE,HS PARIS ABAD HAS ACCUTE STAFF DERTH |
| III | Overallassessmentofthevisitandsuggestions:  NTPHC SHOULD BE PROVIDED WITH BASIC LAB FACILITY AS THE PEOPLE CANOT EFFORT TO GO BUDGAM FOR BASIC TESTS WHICH LEADS TO NEGLECT OF HEALTH CARE |
| IV | OverallRatingofgovtfunctioningas givenbythePanchayat(Scaleof0to10): 08 |
| V | CertificatefromSarpanchthatthevisitingofficerhasstayedinthepanchayatfor2days  VISITING OFFICER ALONG WITH FRONT LINE WORKERS REMAINED PRESENT IN THE PANCHAYAT FOR FULL 2 DAYS |

s/d

**SignatureofSarpanch SignatureoftheVisitingOfficer**

**Name:**GH AHMAD WANI **Name:GH MOHD MIR**

Basic Demands of the gram panchayat

No.1) Basic lab facility like CBC,URINE,BLOOD SUGAR,TEST KITS

B) DENTAL SECTION :-

C) GENERAL X RAY UNIT

D) ECG

E) STABLIZER

F) ADEQUATE STAFF

G) GEN SET

H) AMBULANCE

I) DELIVARY TABLE

J) CHOWKIDAR FOR EARD AND WASTCH

2) CONSTRUCTION OF MAIN GATE FOR HIGH SCHOOL PARIS

3) BLACK TOPPING OF SHOLIPORA PARIS ROAD

4)PROVISION OF NEW UTENSILS ,STORAGE BINS,MATTING TEACHING LEARNING MATERIALS TO ICDS CENTERS

5)REPAIRMENT OF IRRIGATION CANAL AT ABADPORA NEAR NAGRI KUL.

6)COMPLETION OF INCOMPLETELY CONSTRUCTED BUILDING AT HS PARIS ABAD AND ITS UTILIZATION AS SCIENCE COMPUTER LAB.

7) DEVELOPMENT OF CHILDREN FRIENDLY PARK NEAR HS PARIS ALONG MAIN ROAD AND KARSHAN NALLAH NORTH SIDE

8)PROVISIOPN FOR MORE PHE PIPES TO RESTORE WATER TO ALL HOUSE HOLDS

9)PROVISION FOR HT LT LINES AND NEW POLES TO SUPPLY ELECTRICITY HASSLE FREE

10) ESTABLISHMENT OF SKILL DEVELOPMENT CENTRE TO REDUCE UNEMPLOYMENT IN GP.



**DepartmentofRuralDevelompentandPanchayatiRaj**

**GovernmentofJammu &Kashmir**