4





**15TH OCTto3RD NOV,2022**

**KEYFEATURES**

• DeputyCommissionerstoleadtheinitiative

• RuraldevelopmentDepartmenttobethenodaldepartment

• PlanningDevelopment&MonitoringdepartmentandITtobethesupport departments

**ACTIONSANDTIMELINES**

|  |  |  |  |
| --- | --- | --- | --- |
| **ACTION** | **RESPONSIBILITY** | **LATESTBY** | **REMARKS** |
| **Janabhiyan** | All departments | Oct15-26th | Goingon |
| **DeputationofSecttstaff/ HoDs** | GAD | Oct14 | Done |
| **DeploymentofStaffto Panchayatsandservingof ordersondeployedofficers** | DCs | Oct25 | DCswilldeployseniorlevelstaff fromthedistricts.Strictactionto betakenagainstabstentions.No exemptionstobegiven |
| **TrainingofdistricttrainorsonB2V4** | RDD | Oct26 |  |
| **Trainingofvisitingofficers** | DCs | Oct27 |  |
| **FieldVisitstobecompleted by** | VisitingOfficers | Nov3 | DCstosuperviseandensurethat eachPanchayatisvisitedwithin theperiodspecified |
| **DataofB2V4tobe uploadedby** | VisitingOfficers | Nov10 | DCstosuperviseandensurethat dataofallPanchayatsisupload- edbythevisitingofficerwithin theperiodspecified |

**INSTRUCTIONSFORTHEVISITINGOFFICER(DAYWISE)**

|  |  |  |
| --- | --- | --- |
| **DATE** | **INSTRUCTIONS** | **ACTIONPOINTS** |
| **Day0** | Meeting with deputy commissioner and his/her team | a. TakeprintoutsoffilledbookletsofB2V1,B2V2andB2V3from [www.jkpanchayat.in](http://www.jkpanchayat.in)  b.Alsotakeprintoutsofthesummarizedexcelsheetsofthe previousphasesfrom[www.jkpanchayat.in](http://www.jkpanchayat.in)  c. CollectATRsonissuesraisedduringprevious3phasesfromthe officeofDeputyCommissioner(Planningdeptt)  d.Takeprintsofblank 2bookletsofB2V4from[www.jkpanchayat.in](http://www.jkpanchayat.in)e.Takeplansfor2previousyearsandATRsfromtheplanningdepttf. CompletetrainingsondifferentcomponentsofB2V4being  organizedbyrespectiveDeputyCommissioners  g.CollectListofnewworksstarted/ongoing/completedduringthe previousandcurrentFinancialyearunderthefollowingheads:  • PRIgrants  • District Plan  • UT plan  • MGNREGA  • Other schemes of other departments  • Any other work  h. Plans/beneficiary lists:  • MGNREGAdraftplandocumentfortheyear2022-23.  • ListofAwaas+beneficiariesalongwithIHHL Convergence  • Listofpensionbeneficiaries.  • ListofSHGs  • Listofagricultureschemebeneficiaries  i. Listsofbeneficiariesfor:  • Variouscertificates/benefitstobedistributedbythe visitingofficer.  • Anyotheractivitiesidentifiedbydifferentdepartments |

|  |  |  |  |
| --- | --- | --- | --- |
| **Day1** | Reachthevillage | 1. | Ensurethatallfrontlineworkersofdifferentdepttsarepresent. |
|  |  | 2. | Ensureexhibitionbydifferentdepts.aboutindividualbeneficiary schemes |
|  |  | 3. | InspectJKB/PSBcounters/outlets |
|  |  | 4. | Participate/ensureorganizationofsportsactivityinplayfield,talent hunt/culturalevent/youthactivity |
|  |  | 5. | GandhiKatha(suggesteddetailsuploadedonjkpanchayat.in) |
|  |  | 6. | Visitatleast2amritsarovarsandgetitsgeotaggedphotos |
|  |  | 7. | InspectKhidmat(CSC)CentresandcreateGenerateawarenesson  225schemesparticularlyG2CschemeslikeBEAMS,Janbhagidari, AapkiZaminAapkiNigrani,DigitalJ&K |
|  |  | 8. | Visitingofficershallalsoplanandconductpanchayatlevelconver- gencemeetingofalldepartments |
|  |  | 9. | CheckeffectivenessofCentrallysponsoredschemes |
|  |  | 10. | VisitandinspectallgovernmentestablishmentsincludingPHE, AWC,FPS,schools,etc |
|  |  | 11. | Attemptsaturationofdeliverableso JanAbhiyanandwherever deficienciesfound,leadadrivetoachievealldeliverables |
|  |  | 12. | Assesseffectivenessofsanitationcampaigninthepanchayat |
|  |  | 13. | Ensureselfemploymentactivitiesfor15youthperpanchayat |
|  |  | 14. | Identify20potentialcandidatesperpanchayatforHIMAYATtraining alongwiththetradeonwhichtheywanttraining |
|  |  | 15. | Whereverpossible,distributeemploymentlettersforpeopleselect- edundervariousgovernmentemployments |
|  |  | 16. | Intheevening,holdnormalmeetingwith seniorcitizens,govtem- ployeesincludingretiredemployees,exservicemen,youthclub,and any citizens ofthevillagewhoareenrolledincollege/university |
|  |  | 17. | OpendiscussiononNashaMuktAbhiyan |

Day2 Haveameetingwithall stakeholders-depttofficials andpanchayatmembers

1. Discussionontheandassesstheprogressofdifferentschemesrelating tothelocalizedSDGsprioritizedforthatvillageaspertheresolution passedby thatGramPanchayaton21stApril22,onNationalPanchaytiRajDay.

2. Sensitizevillage residentsaboutmyScheme”portal(myscheme.in) whichincludesinformationaboutalltheschemesbeingrunbyCen- tral/State/UTgovtacrossthecountry

3. Hold meeting of theBiodiversityManagementCommitteestodeliber- ateonissuespertaining toconservation of biodiversityandsustaina- bleutilizationof biologicalresources.

4. PrepareVillagedevelopmentplan,inconsultancywithGrampanchayat, discussitingramsabhaandgetitapproved.

5. Ensure saturationofsoilhealthcardandgoldenhealthcardunderGold- enHealthCardunderAyushmanBharat,

6. Ensuresaturation of OldAge PensionScheme

7. EnsureDomicileSaturation.

8. EnsureKCCSaturation

9. Ensure saturationoflandpassbooks

10. Ensureregistrationofvillagevendorsneededforanyscheme,onGEM

portal

11. Ensurepanchayatcontractors registration

12. EncouragePanchayatmembers forimportanceofplantationdrivein

PanchayatunderHarGaonHariyali

13. Ensure paintingondigitalJ&Kinpanchayatghars

14. Ensure paintingonpanchayatactivitesandCSSinpanchayatghars

15. Thevisiting officeshallchecknoof kindergarten andplayfields present inthepanchayat for kidsandstudents,iftheinfrastructure present inthesearegoodenough.

16. Holdmeeting withpanchayatmembers todiscussaboutcorruption menaceandstepsrequiredtomakeJ&Kcorruptionfree

17. Obtaina candidassessmentaboutperformanceofvariousdepttsin- cludingfairfeedbackaboutdiscrepanciesinfunctioning

18. Check thestatusof NashaMuktAbhiyanandreporting of drugad- dictstoDeputyCommissioner.

19. IdentifyTouristDestinations,Circuits,ThemeTreks,IdentifyHomestays, providesupportfortourismactivities throughVillageCooperative

20. OrganizeTalentHuntatPanchayatLevel

21. Conductsocialauditofatleast5worksunderfollowingschemes:

a. MGNREGA

b.PMAY

c. IHHLtoiletsandpayments d.CSCs

e.AMRITSAROVARS

22. Holdamahilasabhaandabalsabhaandrecordproceedingsinthefor- matgiven

23. InauguratevillagehaatunderJKSRLM

24. Checkifyouthclubsareformedinthepanchayatandwhatactivities theyareengagedin

25. Organizea villagelevelculturaleventtoengagepanchayatmembers

26. SensitizeGPaboutE-kitabkoshaninitiativeofJ&KGovtforempowering youthsthrough onlinedigitalliteracy

**GENERALINSTRUCTIONS**

1. Thevisitingofficershallrefrainhimself/herselfgivingorofferinganycommitmentonbehalfofthe governmentandshalladoptanunbiasedattitudeinreportingissues.As faraspossible,his/her observation shouldbebasedona fairandanalytical viewemergingfromhis/herinteractioninthe village.

2. Heisgoingtothevillageasplanningofficer,notforsanctioninganyworksorformakinganycom- mitments.

3. Whilepreparingvillagedevelopmentplan,hehastoensurethat,demandsareprioritizedandre- flectedunderavailableschemes,wherevernecessarythelargerworksaretobereferredtoadminis- trativedepttunderCSS/UTplansunderintimationtoDCsandrestoftheworkstoDCsforreflecting itunderdistrict/CSS plans

4. His workshallbehardcoreplanningandauditandisnota PRexercise.

5. EveryDeputyCommissionerhastoensurethatatleastoneRDDofficial(ideallyPanchayatSecre- tary)ispresent ineverypanchayatwithrelevantpanchayatrecords,toensureconductofallactivi- tiesasplanned.Panchayatwiseorderneedstobeissuedinadvance.

6. Visitingofficershouldideallycarryhis/herlaptoptocompletethereportsatthepanchayatlevel itselfanduploadthefinalreport,duly signedbothbythesarpanchandbythevisitingofficeron [www.jkpanchayat.in](http://www.jkpanchayat.in)portal,beforetheyleavepanchayat.

7. Focus ofvisitareyouth,skills,self-employment,nashamukt,bhrashtracharmukt,RozgaryuktJ&K, besidestocarryforwardtheactivities duringJanAbhiyanandsaturatethem.

8. Inadditionattentionmaybegiventothefollowingareas a. MakefulluseofCentrallySponsoredSchemes

b.Saturationofindividualbeneficiaryschemes c. Self-employmentschemes

d.Banklinkedschemes-includingdepartmentalsubsidyschemes e.Empowermentandtransparencythrough digitalinitiatives

f. Effectivenessofgrassrootsmachinery–

i. Patwari,VLWpresent andavailable

ii. AvailablefundsutilizedinpublicinterestandasperGramSabharesolutions iii. Fairness ingovernance

iv. CSS/Individual beneficiaryschemesetcv. BrashtacharMuktJ&K

vi. BhaiMuktJ&K

vii. NashaMuktJ&K

9. ThePRImembers (Sarpanchs,Panchs,BDCChairperson)shallbeattheforefrontofallactivities and givendueimportanceandtheapproach shouldbetostrengthenthemandmakethemfeelem- powered.He/sheshallensurethattheBDCchairpersonandSarpanch/Pancharepresent atthetime ofinaugurationandceremonies.

10. Visitingofficershallnotleavethedistrictwithoutuploadingthereport,duly signedonthe**www. jkpanchayat.in**portal.EveryDeputyCommissionerhastoensurethat.

**A) DetailsofReportingOfficer:**

Name: Fayaz Ahmad Sheikh

Designation:Assistant Executive Engineer

Department/placeof posting:R&B Division Qazigund

MobileNo:7006843552

EmailID:erfayazsheikh@gmail.com

HomeDistrict:Anantnag

Datesof visit: 2nd and 3rd of November 2022

**B) LocationaldetailsofPanchayat:(tobepre-filled,informationtobetakenfromtheprevious phasesbooklets/summarizedexcelsheetuploadedonjkpanchayat.in/b2v4.php)(tobevali- datedbythevisitingofficerandmissingdetailstobefilled)**

Name of the Panchayat: Bon-Nambal Middle

Local Government Directory(LGD)code of the Panchayat: 242660

Name of CD Block: Khoveripora

Nameof Tehsil: Mattan (Anantnag East)

Name of District: Anantnag

**C) PanchayatProfile:**

No.of revenue villages in the Panchayat: 02

No.of hamlets in the Panchayat: 07

No.of households in the Panchayat: 387

Population(approx)of the Panchayat: 3192

**Part-II:**

(TobefilledupbytheVisitingOfficerduringhis/hertwodayvisittothePanchayat.AllFieldshavetobe

filledbytheVisitingOfficerbeforethebookletishandedovertotheDC

**FrontlineOfficers/OfficialswhowereassignedtothePanchayatfortheprogramme:**

|  |  |  |
| --- | --- | --- |
| Department | Name | Designation |
| **Rural Development** | **Quarat ul Ain** | **Panchayats Secretary** |
| ICDS | Urfee Jan | Angan Wadi worker |
| ICPS | Anjum Ayoub | Counselor |
| Health | Muneera Jabeen | FMPHW |
| Education | Nisar Ahmad Bhat | Teacher |
| R&B | Javaid Ahmad Shah | J.E |
| P.H.E | Manzoor Ahmad Ahanger | J.E |

**Details of absent employees vis-à-vis list furnished by the DCoffice:**

|  |  |  |
| --- | --- | --- |
| Department | Name | Designation |
|  |  |  |
|  |  |  |
|  |  |  |
|  |  |  |
|  |  |  |
|  |  |  |
|  |  |  |
|  |  |  |
|  |  |  |
|  |  |  |
|  |  |  |
|  |  |  |
|  |  |  |
|  |  |  |
|  |  |  |

**DAY1-ACTIVITIES**

**AGENDA1:PANCHAYATASSETREGISTER**

**Infrastructure:**

1.Panchayat Ghar Infrastructure

a. Govt building/private : Govt building

b. New/needingrepairs : Needing repairs

2. Furniture(Y/N): No

3. Computer/printer(Y/N): No

4. Internet(Y/N): No

5. Telephone(Y/N): No

6. Toilet(CSC/partofpanchayatghar)(Y/N): No

7. Water(Y/N): No

8. Electricity(Y/N): No

9. Bankbranch(Y/N): No

10. CSC(Y/N): No

11. Patwarkhana(Y/N): No

12. Villagehaat(Y/N): No

13. Playground(Y/N): Yes

14. School-

a. Kindergarten(Y/N): Yes

b.Primary(Y/N): Yes

c. Secondary(Y/N): No

d. College (Y/N) :No

e.University(Y/N) : No

15. AnganwadiCentre(Y/N): Yes

a. (govt/private): Private

b.Totalchildrenenrolled: 204

15. AmritSarovars–details,location,condition: N/A

16. Governmentoffices-details,whetherfunctionalornot : Functional

17. Rationshop(Y/N): Yes

18. Placesoftourismimportance–names,littledetailsonhistorical/culturalimportance: N/A

19. Villageheritagesites/treks-names,littledetailson historical/culturalimportance: Ziyarat Sharief Sheikhul Alam

20. VLWOffice (Y/N): No

21. PrimaryHealthcareCentre(Y/N): No

22. ListofIncompleteBuildings-names,yearofconstruction: N/A

23. ListofUnderutilizedBuildings-names : N/A

**DAY1-ACTIVITIES**

**AGENDA2:**

**DIFFERENTINSTITUTIONS/INFRASTRUCTUREPROJECTSTOBEVISITED**

|  |  |  |
| --- | --- | --- |
| **AMRITSAROVARS** | **Visit,verify** | **COMMENTS** |
| KhidmatCentres | Create/Generateawarenesson225schemes particularlyG2CschemsAapkiZaminAapkiNigrani, Beams,Janbhagidari,DigitalJ&K | General Public Awareness camp organised |
| JKB/PSBcounters/outlets | a)Statusofcounter b)Numberofvisitors | N/A |
| Incompletebuildings/pro- jects | Verify whetheridentificationandredistribution done | N/A |
| PDS | Visit,evaluate,onlinestatus | Visited and found functional. |
| PHC | Visit-evaluate,statusofstaff,equipmentand quality | Building of Health and Wellness Centre in a mess, accommodation issue needs to be redressed on priority. |
| Youthclubs | Meet,interact,seeksuggestions | Met and interacted. |
| SHG | Meet,identifyproblems,seeksuggestions | Met and interacted. |
| PMAY | Inspect,Inaugurate | Inspected, inaugurated. |
| Myschool,mypride progress;schools-water, toilets,staff | Visit,checkforwater,electricity,sanitation,meet studentsandstaff | Inspected and interacted, need modified electricity and sanitation facilities. |
| SwachhSBM | Evaluate | Evaluated, target achieved |
| Panchayatplayground, Sportskitsdistribution Villagegames | Ensure,verify.Participateinatleastonegamein theplayground | Particpated in a game and distributed volley ball kit among youth. |
| HarGaonHariyali, Planta- tiondrive | Evaluatestatus,feedback | Evaluated, afforestration needs to be intensified. |
| Villageculturalevent  Dangal/Haat/Mela | Participatein;ensurethatitisheld | Participated |
| Exhibitionofschemes | Ensurethateverydepartmentparticipatesand thatitcontinuesfortheentiredurationofB2V | All departments participated |
| JalJeewanMission verifica- tion- WSS/JSD  Electricitysupply | Verify | Verified. |

**DAY1-ACTIVITIES**

**AGENDA3:SATURATEJANBHIYAN**

**DELIVERABLESANDRECORDDEFICIENCIESIFANY(INSERTDELIVERABLESLISTHEREASPERGADFORMAT**

**DAY1-ACTIVITIES**

**AGENDA4:**

**SELFEMPLOYMENTACTIVITIES**

Ensure Self-employment activities for youth,distribute employment letters for people selected under various socialschemes(15 IS THE TARGET PER PANCHAYAT)

**Number of cases indifferentcategories sanctioned: 04 (U/P)**

**Details of the bank sanctioning it: Punjab National Bank**

**Total amount involved: 4.00 Lacs**

**DAY1 ACTIVITIES**

**AGENDA 5**

In the evening, hold informal meetings with senior citizens, govt employees, retd employees, youth club and other citizens who are enrolled on college/university and have discussion on Gandhi Katha, NashaMukt Abhiyan, corruption free governance, doubling farmers income and record the proceedings

**DAY2**

a. No. of Individual Compost Pits constructed : 50

b.No of Individual Soak Pits constructed: 12

V. No.of Biodiversity management committee meetings held:04

VI. IsthenameofSarpanchdisplayedoncitizeninformationboardsofallRD&PRschemes:Yes/No: Yes

VII. AreSarpanchsbeinginvolvedinstart/inaugurationofactivities:Yes/No: Yes

VIII. WhethersubjectshavebeenassignedbytheSarpanchtothePanchs:Yes/No: Yes

IX. Whethergrievancesredressalboxisinstalled:Yes/No: Yes

X. NoofgrievancesreceivedpertainingtoPanchayatlevel: 10

XI. NoofgrievancesdisposedofatPanchayatlevel: 10

XII. WhethertheSarpanch/PanchayatSecretaryhavedigitalsignatures:Yes/No: Yes

XIII. WhetherallMGNREGA/14thFCpayments arebeingmadebySarpanchthrough DigitalSignature

Certificate(DSC):Yes.

**HUMAN RESOURCEAVAILABLEATTHEPANCHAYAT LEVEL:**

|  |  |  |  |  |
| --- | --- | --- | --- | --- |
| **S.No** | **Department Wise Staff** | **Numbers** | | **Names** |
|  |  | **Sanctioned** | **Actual** |  |
|  | Rural Development Department:  Pyt Secretary  JE  GRS  TA | 01  01  01  01 | 01  01  01  01 | Quratul Ain  Sajad Ahmad  Sameer Ahmad  Aejaz Ahmad |
|  | School Education:  Teacher  Headmaster  Any other (NYC) | 08  03  02 | 07  03  02 |  |
|  | Jal Jeevan:  Astt Lineman | 02 | 02 | Farooq Ah Misgar  Gh Mohd Shah |
|  | PDD:  Lineman  JE  Any other (sector incharge) | 02  01  01 | 02  01  01 | Mohd Shaban, Gull Zaman  Mohd Yaqoob Teeli  Ab Rashid |
|  | Food and Civil Supplies:  Store Keeper | 01 | 01 | Mehraj Ud Din |
|  | Agriculture and Animal Husbandary:  JAEO | 01 | 01 | Rafi Ahmad Dar |
|  | Social welfare |  |  |  |
|  | Health:  Asha  ANM  Ayush Doctor  Allopathic Doctor | 02  02  --  -- | 02  02  --  -- | Dilshada, Shakeela  Shaista, Muneera |
|  | Revenue  (Patwari) | 02 | 02 | Mudasir Ahmad, Samiullah |
|  | ICDS  AWW’s | 07 | 06 | Urfy Jan,Dilshada, Zubaida, Nusrat Ara, Nusrat jan,Rifat Parveen |

**DAY2-ACTIVITIES**

**AGENDANO.1**

DiscussionontheandassesstheprogressofdifferentschemesrelatingtothelocalizedSDGsprior-itizedforthatvillageaspertheresolutionpassedbythatGramPanchayaton21stApril22,onNational PanchayatiRajDay(Copyoftheresolutiontobetakenfrom[www.jkpanchayat.in](http://www.jkpanchayat.in)portalunderthelinkof GramSwarajMonth)

1. SDGs AGREED FORTHATVILLAGE,TOBEIMPLEMENTED BYMARCH2024: SBM, Employment Generation, Solid & Liquid waste management,Cleaniliness Drive, Plantation Drive, Nasha Mukt Abhiyan, Plastic Free Panchayat.

2. STATUSOFWORKSUNDERTHEFOLLOWINGSCHEMES:

**1 Cleanandgreenvillage**

i.InitiativestakenbythePanchayatformanagingSolidandLiquidWaste C/o Compost and Soakage pits

ii. InitiativestakenbythePanchayatforusinggreensourcesoffuellikesolar,biogas

iii. Hasmappingoflanduse,waterbodies,forest,slopes,wetlands,degradedforestwithintheGram

Panchayatbeendone?Yes/No.IfNo,reason,thereof Yes

iv. HastheClimateResiliencePlanbeendevelopedfortheGP?Yes/No: No

v. StepstakenbytheGramSabhaabouttheclimatechangemitigationfactorslikereducingenergy consumption,usageoffossilfuels,plastics,non-renewablebuildingmaterialsandalsotopromote measureslikeplantingoftrees,conservingforests,usageofgoodagriculturalpracticeslikedrip irrigation,waterconservationmeasuresandconservationofwetlands. Awareness and informative camps organised

vi. Whetherschoolshavestartedsegregatingwaste Yes

vii. Whetherschoolshavetheirowncompost/soakagepitsforsolid/liquidwastemanagement: Yes

**2 Healthyvillage**

i) Aremeetings relatedtoVillageHealthandSanitationCommitteebeingheldregularly? Yes

ii) DoalltheeligibleindividualsbeenprovidedtheGoldenCard? Yes

iii) ArealltheChildrenbeingimmunizedaspertheSchedulerecommendedbyGovt.ofIndia? Yes

iv) ArealltheeligibleindividualsbeenvaccinatedagainstCOVID-19? Yes

v) DoesGramPanchayatensurethatallpregnantwomenaregettingnecessaryprenatalcheckups? Yes

vi) WhetherallthedeliverieswereInstitutionalizedorconductedbytrainedMidwives? Yes

**3 Watersufficientvillage**

i) DoalltheIHHsintheGramPanchayathavewaterpipelineconnections? Yes

ii) WhetherGramPanchayathastakenstepsforgreywatermanagement.IfYespleasespecify No

iii) DoalltheIHHsintheGramPanchayathavetoilets? Yes

iv) ArealltheIHHstoiletsfunctionalornot? Functional

v) DoalltheSchools/Anganwadicentershavea toiletfacilityornot? Yes

vi) Areallthetoiletsintheschools/Aaganwadifunctionalornot? Yes

vii) WhetherGramPachachayatBhawanhasseparate toiletsforwomenornot? No

**4 ChildFriendlyvillage**

i) Doallthechildrenundertheageof0-6yearsbeenenrolledintheAnganwadicentersforpre- schooling?Yes/NO Yes

ii) HowmanyBalSabha’swereorganizedintheGramPanchayat---03----------------

iii) WhethertheissuesraisedbyBalSabhaareaddressedduringtheGramSabha. Yes/NO Yes

iv) WhetherGramPanchayatistrackingthedatarelatedtodropoutchildrenandchildrenwithirregular attendance?Yes/NO.Yes

v) DoalltheschoolsundertheGramPanchayathaveseparate toiletsforgirlsandboys?Yes/No No

**5 Villagewithgoodgovernance**

i) IsCSClocatedintheGramPanchayatBhawanornot? Yes

ii) IsthelistofbeneficiariesrelatedtotheSchemes/ProgramsdisplayedontheGrampanchayatwallor not? Yes

iii) DoestheGramPanchayathasitsbuildingornot? Yes

iv) IstheGramPanchayatofficefunctionalornot? No

v) Aretheactivities approved undertheHalqaPanchayatDevelopmentPlandisplayedontheGram

Panchayatwallornot? No

vi) IsSocialAuditofearlierSchemes/Programscarriedoutornot? Yes

**6 Povertyfreeandenhancedlivelihoodvillage**

1. HasGramPanchayatdevelopedanycriteria fortheidentificationofthepoor?Yes/Noifyesspecify Yes
2. HavealltheeligiblehouseholdsregisteredinPDSornot? Yes

iii) HasGramPanchayatprovidedspaceforSelf-helpGroupsinPanchyatGharforholdingmeetings or not? Panchayat Ghar is non-functional (gutted in fire)

iv) HavealltheeligiblehouseholdsbeenregisteredforPensionornot? Yes

v) HasGramPanchayatfacilitatedYouthforSkillEnhancementCoursesandPlacement? Yes

vi) HasJobCardsbeendistributedtoalltheeligibleindividualsunderMGNREGA? Yes

vii) HasGramPanchayatfacilitatedSHGsforBankAccountLinkages? Yes

**7 Sociallysecuredvillage**

i) WhetherGramPanchayatismaintainingdatarelatedtoDifferentlyAbledPeople? Yes

ii) IsGramPanchayatOffice DisabledFriendlyornot? Yes

iii) Areprovisionsfora separate BudgetundertheResourceEnvelopeforWomenandChildrenmadeor not? Yes

iv) DoalltheSchools intheGramPanchayathavefacilitiesforDifferentlyAbledChildrenliketoilets, barrier-freeaccess,etc.,ornot? No

v) Arealltheeligibleindividualsaregettingpensions,likeoldagepension,widowpension,etc? Yes

vi) ArealltheeligiblehouseholdsgettingbenefitsfromIAYornot?Yes

**8 EngenderedDevelopmentinVillage**

i) HowmanyMahilaSabha’swereorganizedintheGramPanchayat-------05------------

ii) WhetherSHGsfederationshavebeenprovidedspaceformeetings inthePanchayatBhawan(Yes/ No): Yes

iii) WhetherGPshavetakenstepsforincreasingwomen’sparticipationinGramSabha(Yes/No): Yes

iv) NumberofwomenbeneficiariesheadedhouseholdscoveredunderPDS

system……13…………………

v) Numberofbeneficiaries(outoftotaleligiblepopulation)receivingsocialprotectionbenefitsunder

PradhanMantriMatritvaVandanaYojana……14…………….

9 Self-sufficientinfrastructureinthevillage

i. WhetherGPhasa CommunityHallwithaccesstoelectricity,furniture,watersupply, toilet……No………………….

ii. WhethertheDisastermanagementplanisavailableattheGPLevel(Yes/No) No

iii. Whetherchild-friendlyparkwithrequiredfacilitiesisavailableinGP(Yes/No) No

iv. WhethertheGPhaseasyaccesstoGodownforstorage(Yes/No) Yes

v. Whetherstreetlightsareprovidedinpublicplacesforensuringsafety(Yes/No) Yes

**DAY2ACTIVITIES**

**AGENDANO.2**

SensitizevillageresidentsaboutmyScheme”portal(myscheme.in)whichincludesinformationaboutall theschemesbeingrunbyCentral/State/UT govtacrossthecountry

*(SchemeMaterialavailablefromhttps://jkpanchayat.in/b2v4.php)*

**DAY2ACTIVITIES**

**AGENDANO.3**

HoldmeetingoftheBiodiversityManagementCommitteestodeliberateonissues pertainingtoconserva- tionofbiodiversityandsustainableutilizationofbiologicalresources.HeshouldcheckPeopleBiodiversity register(PBR)ofthatpanchayatandreviewifBiodiversityManagementCommittee constitutedforthat panchayatis holdingminimum4meetings inayearandmeeting onceinevery3months *(RoleofBMC availableathttps://jkpanchayat.in/b2v4.php)*

COMMITTEEMEMBERS PRESENT

BIODIVERSITYREGISTERPHOTOS

PAST 4MEETINGDETAILS-DATES,MINUTESPHOTOS

**DAY2ACTIVITIES**

**AGENDA4**

Visitingofficershallalsoplanandconductpanchayatlevelconvergencemeeting ofalldepartmentsand prepareVillagedevelopmentplanforvillage,inconsultancywithGrampanchayat,discussitingram sabhaandgetitapproved.

(GPDPformatavailableonhttps://jkpanchayat.in/b2v4.php)

**In addition GPDP plan shallalsoinclude:**

 Touristplaceswhichneedtobedeveloped: Nil

 Specificproductwhichneedstobedeveloped

 Tourism-homestays

 20candidatesfortrainingunderHimayatschemealongwithtradeinwhich trainingistobegiven (List enclosed)

|  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
| **Gram Panchayat Development Plan of Panchayat Bon Nambal Middle (Mere Sapno ki Panchayat)** | | | | | | | |
| **S.no** | **Name of the Village** | **Name of the concerned Department** | **Scheme** |  | **Name of the proposed work** | **Ward.no** | **Estt Cost** |
|  |  | **Department of Rural Development** | MGNREGA | *1* | R-Wall Graveyard Bonpora | 1 | 1.50 |
|  |  | *2* | Drain NHO Atta Mohd Shah | 1 | 1.00 |
|  |  | *3* | Drain FLO Mohd Ismail to onwards near Ziyarat Sharief | 1 | 1.50 |
|  |  | *4* | R-Wall FHO Muzafar Ah Shah to Bridge | 1 | 1.50 |
|  |  | *5* | R-Wall FHO Manzoor Shah to Bridge | 1 | 1.50 |
|  |  | *6* | Lane with X-ing from Main road to Mohd Yousuf at Bagandar ph 1 | 2 | 1.50 |
|  |  | *7* | Lane with X-ing from Main road to Mohd Yousuf at Bagandar ph 2 | 2 | 1.50 |
|  |  | *8* | Lane with Drain near Masjid Sharief at Kuchey Mohalla | 2 | 1.50 |
|  |  | *9* | R-Wall FLO Mohd Ramzan to Mohd Yousuf | 2 | 1.50 |
|  |  | *10* | R-Wall from Chinar to LO Riyaz Ahmad | 3 | 1.00 |
|  |  | *11* | Lane from Main road to Toyyab Khan | 3 | 1.00 |
|  |  | *12* | Lane with Drain FHO Mohd Shafi Khan to Main Road | 3 | 1.50 |
|  |  | *13* | R-Wall FHO Gh Mohd to Ali Mohd Khan | 3 | 1.50 |
|  |  | *14* | Dev of Trout Nallah with X-ing at Bagandar NHO Muzaffar Ah Sheikh & ors | 3 | 1.50 |
|  |  | *15* | R-Wall FHO Mohd Akbar to Mohd Iqbal | 4 | 1.50 |
|  |  | *16* | Link road from X-ing to onwards at Khakhad Mohalla Ph 1 | 4 | 1.00 |
|  |  | *17* | Link road from X-ing to onwards at Khakhad Mohalla Ph 2 | 4 | 1.00 |
|  |  | *18* | Drain with Lane from Masjid Sharief to Mohd Saleem Shah & onwards | 4 | 1.00 |
|  |  | *19* | Irr Ladh FLO Ab Rehman Shah to LO Mohd Yousuf Shah | 4 | 1.00 |
|  |  | *20* | X-ing Canal NLO Mohd Yousuf Shah near Check Road Ph 1 | 5 | 1.00 |
|  |  | *21* | X-ing Canal NLO Mohd Yousuf Shah near Check Road Ph 2 | 5 | 1.00 |
|  |  | *22* | Irr.Ladh NLO Ab Rehman Shah to Lo Mohd Yousuf Shah Ph 2 | 5 | 1.00 |
|  |  | *23* | Lane with Drain from Main road to HO Taskeen Vaid | 5 | 1.00 |
|  |  | *24* | Drain FHO Nisar Shah to Spring Ph 1 | 5 | 1.00 |
|  |  | *25* | R-Wall FLO Mohd Abdullah Baba to HO Gh Rasool Bhat Ph 1 | 5 | 1.00 |
|  |  | *26* | R-Wall FLO Mohd Abdullah Baba to HO Gh Rasool Bhat Ph 2 | 5 | 1.00 |
|  |  | *27* | Drain FHO Nisar Shah to Spring Ph 2 | 5 | 1.00 |
|  |  | *28* | Drain FHO Nisar Shah to Spring Ph 3 | 6 | 1.00 |
|  |  | *29* | Drain FHO Mehraj Din to John Mohd Shah near graveyard Herpora | 6 | 1.00 |
|  |  | *30* | Dev of Graveyard at Khahpora | 6 | 1.00 |
|  |  | *31* | R-Wall FHO Mohd Ayoub Baba to HO Gh Mohiud Din Sheikh | 6 | 1.00 |
|  |  | *32* | R-Wall FHO Fayaz Shah to LO Mohd Yousuf Shah Ph 1 | 6 | 1.00 |
|  |  | *33* | R-Wall FHO Fayaz Shah to LO Mohd Yousuf Shah Ph 2 | 6 | 1.00 |
|  |  | *34* | R-Wall FLO Mohd Hussain Shah to Lo Tariq Ah Shah Ph 1 | 6 | 1.00 |
|  |  | *35* | R-Wall FLO Mohd Hussain Shah to Lo Tariq Ah Shah Ph 2 | 6 | 1.00 |
|  |  | *36* | Drain FHO Mohd Akbar Shah to Mohd Ayoub Baba | 6 | 1.00 |
|  |  | *37* | Lane with Drain from Masjid Sharief to HO Tariq Ah Shah | 7 | 1.00 |
|  |  | *38* | Irr Ladh FLO Shabir Ah Hakeem to Mohd Shaban Bhat | 7 | 1.50 |
|  |  | *39* | Irr. Ladh FLO Mushtaq Ah hakeem to onwards | 7 | 1.00 |
|  |  | *40* | R Wall NLO Nisar Ah Bhat | 7 | 1.50 |
|  |  | *41* | Dev of Graveyard manznoo | 7 | 1.00 |
|  |  | *42* | Dev of Public park Manznoo | 7 | 1.00 |
|  |  | *43* | Link road FHO Gulzar Hajam to Bilal Hajam | 7 | 1.00 |
|  |  | *44* | Link Road with Drain from Peer Manzoor to HO Mohd Yousuf Hajam Ph 1 (BDC) | 7 | 1.00 |
|  |  | *45* | Link Road with Drain from Peer Manzoor to HO Mohd Yousuf Hajam Ph 2 (BDC) | 7 | 1.00 |
|  |  | *46* | R-Wall NLO Mohd Abdullah Baba & Ors | 4 | 1.00 |
|  |  | *47* | R-Wall NHO Gh Rasool Bhat | 3 | 1.00 |
|  |  | *44* | Link Road from Pry School Herpora to LO AB Rehman Shah at Ard Orchards near Geage | 2 | 2.00 |
|  |  | *45* | Drain from Masjid Sharief to public park | 6 | 2.00 |
|  |  | *46* | R-Wall around Public Park | 6 | 2.00 |
|  |  | *47* | Drain FHO Khurshid Ah Dhobi to Dilawar Ah Shah | 6 | 2.00 |
|  |  | *48* | Link Road from Masjid Sharief to main road | 6 | 2.00 |
|  |  | *49* | Drain from Ho Mohd Maqbool to Transformer | 6 | 2.00 |
|  |  | *50* | Drain FHO Peer Manzoor Ah & onwards | 7 | 2.00 |
|  |  | *51* | Lining Wall Graveyard Manznoo | 7 | 2.00 |
|  |  | *52* | R-Wall/Irr Ladh near Agricultural land of Haji Nazir Ah Hakeem | 7 | 2.00 |
|  |  | *53* | Dev of Janazgah cum Public Park near Govt Midlle School Manznoo | 7 | 2.00 |
|  |  | *54* | Drain from Masjid Sharief to Shop of Tawseef Ah Shah | 3 | 2.00 |
|  |  | JKRLM (UMEED) | *1* | Mohd Shafi Shah S/o Gh Hassan Shah R/o Bona Nambal |  |  |
|  |  | *2* | Khurshid Ah Shah S/o Mohd Hayat Shah R/o Herpora Nambal |  |  |
|  |  | *3* | Mohd Rafeeq Shah S/o Mohd Hayat Shah R/o Herpora Nambal |  |  |
|  |  | *4* | Manzoor Ah Shah S/o Mohd Maqbool Shah R/o Khahpora Nambal |  |  |
|  |  | *5* | Rouf Ah Shah S/o AB Rehman Shah R/o Ameerpora Nambal |  |  |
|  |  | *6* | Mohd Altaf Shah S/o Mohd Abdullah Shah R/o Herpora Nambal |  |  |
|  |  | *7* | Muzamil Reyaz S/o Reyaz Ahmad Shah R/o Herpora Nambal |  |  |
|  |  | *8* | Manzoor Ah Shah S/o Mohd Ramzan Shah R/o Herpora Nambal |  |  |
|  |  | *9* | Khurshid Ah Shah S/o Mohd Maqbool Shah R/o Khahpora Nambal |  |  |
|  |  | *10* | Bashir Ah Shah S/o Assadullah Shah R/o Khahpora Nambal |  |  |
|  |  | *11* | Towseef Ah Shah S/o Mohd Ramzan Shah R/o Gojipora Nambal |  |  |
|  |  | *12* | Tawseef Ah Bhat S/o Mohd Shaban Bhat R/o Khahpora Nambal |  |  |
|  |  | *13* | Burhan AH Bhat S/o Gh Hassan Bhat R/o Manznoo |  |  |
|  |  | *14* | Asif Hussain Bhat S/o Gh Mohd Bhat R/o Manznoo |  |  |
|  |  | *15* | Mohd Ismail Shah S/o Gh Mohd Shah R/o Khahpora |  |  |
|  |  | *16* | Mohd Amin Shah S/o Gh Mohd Shah r/o Khahpora |  |  |
|  |  | *17* | Suhail Ah Shah S/o Gh Rasool Shah R/o Gojipora |  |  |
|  |  | *18* | Javaid Ah Shah S/o Gh Hassan Shah R/o Herpora Amerpora |  |  |
|  |  | *19* | Rasik Ah Shah S/o Mohd Ayoub Shah R/o Nambal |  |  |
|  |  | *20* | Manzoor Ah Shah S/o GH Mohd Shah R/o khahpora |  |  |
|  |  | *21* | Mohd Abbas Shah S/o Ab Razak Shah R/o Amerpora |  |  |
|  |  | PMAY-G (10 beneficiaries to be identified) | *1* | Imtiyaz Ah Shah S/o Mohd Jabar Shah |  | 1.50 |
|  |  | *2* | Javaid Ah Shah S/o Mohd Maqbool Shah |  | 1.50 |
|  |  | *3* | Jan Mohd Kuchey S/o Ali Mohd Kuchey |  | 1.50 |
|  |  | *4* | Khushi Mohd Kuchey S/o Ali Mohd Kuchey |  | 1.50 |
|  |  | *5* | Mohd Rafeeq Shah S/o Mohd Hayat Shah |  | 1.50 |
|  |  | *6* | Altaf Ah Shah S/o Bashir Ah Shah |  | 1.50 |
|  |  | *7* | Farooq Ah Hakeem S/o Ab Aziz Hakeem |  | 1.50 |
|  |  | *8* | Mohd Shafi Khan S/o Ab Rehman Khan |  | 1.50 |
|  |  | *9* | Samy Jan W/o Lt Shabir Ah Hajam |  | 1.50 |
|  |  | *10* | Mehraj ud din Shah S/o Mohd Ismail Shah |  | 1.50 |
|  |  | HIMAYAT (DDU-GKY) (20 candidates to be identified per panchayat) | *1* | Arif Ahmad Shah S/o Manzoor Ahmad Shah |  |  |
|  |  | *2* | Owais Ashraf Shah S/o Mohd Ashraf Shah |  |  |
|  |  | *3* | Tawseef Ahmad Shah S/o Shareefud Din Shah |  |  |
|  |  | *4* | Rashmie Mushtaq D/o Mushtaq Ahmad Shah |  |  |
|  |  | *5* | Aabida Akhter W/o Musavir Ahmad Shah |  |  |
|  |  | *6* | Shabeena Jan D/o Ali Mohd Kuchey |  |  |
|  |  | *7* | Saima Akhter D/o Mohd Yousuf Shah |  |  |
|  |  | *8* | Rahie Mushtaq D/o Mushtaq Ahmad Shah |  |  |
|  |  | *9* | Shugufta Shereen D/o Mohd Abdullah Shah |  |  |
|  |  | *10* | Fancy Jan D/o Ghulam Nabi Khan |  |  |
|  |  | *11* | Razia Mushtaq D/o Mushtaq Ahmad Ganie |  |  |
|  |  | *12* | Shahid Hussain Shah S/o Mohd Hussain Shah |  |  |
|  |  | *13* | Rayees Ahmad Shah S/o Gh Mohd Shah |  |  |
|  |  | *14* | Taskeen Ahmad Vaid S/o Fayaz Ahmad Vaid |  |  |
|  |  | *15* | Yasir Hussain Shah S/o Mohd Hussain Shah |  |  |
|  |  | *16* | Adil Iqbal S/o Mohd Iqbal Shah |  |  |
|  |  | *17* | Owais Manzoor Wagey S/o Manzoor Ah Wagey |  |  |
|  |  | *18* | Akib Ahmad Shah S/o Ghulam Qadir Shah |  |  |
|  |  | *19* | Zakir Ahmad Bhat S/o Gh Hassan Bhat |  |  |
|  |  | *20* | Sabreena Mushtaq D/o Mushtaq Ahmad Ganie |  |  |
|  |  | Swachh Bharat Mission (Grameen) | *1* | Dilshada W/o Lt Gh Mohd Shah |  | 0.12 |
|  |  | *2* | Manzoor Ah Shah S/o Gh Mohd Shah |  | 0.12 |
|  |  | *3* | Farooq ahmad shah S/o Ab rashid |  | 0.12 |
|  |  | *4* | Ghulam rasool Shah S/o Jalalud din |  | 0.12 |
|  |  | *5* | MOHD YOUSUF BABA S/o Ab Gani Shah |  | 0.12 |
|  |  | *6* | MUZAFFAR AHMAD SHAH S/o Gh Hussain Shah |  | 0.12 |
|  |  | *8* | Nasir Ahmad shah S/o Gh Mohd Shah |  | 0.12 |
|  |  | *9* | Nazir Ah Shah S/o Ab Gani Shah |  | 0.12 |
|  |  | Sansad Adarsh Gram Yojana (SAGY) | *1* |  |  |  |
|  |  | *2* |  |  |  |
|  |  | *3* |  |  |  |
|  |  | **Department of Agriculture. Cooperation and Farmers Welfare (DAC&FW)** | Pradhan Mantri Kisan Samman Nidhi Yojana(PM-KISAN) |  | Rs 2000 in three equal instalments for eligible benficiaries | Whole Panchayat |  |
|  |  |  |  | Whole Panchayat |  |
|  |  |  |  | Whole Panchayat |  |
|  |  | Pradhan Mantri Kisan Maan Dhan Yojana(PM-KMY) |  | Pensionary benfit Scheme depends upon the age of farmer (Eligibility from 18 to 40 years age) | Whole Panchayat |  |
|  |  |  |  | Whole Panchayat |  |
|  |  |  |  | Whole Panchayat |  |
|  |  | Pradhan Mantri Annadata Aay Sanrakshan Abhiyan (PM-AASHA) |  | Procurement of Paddy | Whole Panchayat |  |
|  |  |  |  | Whole Panchayat |  |
|  |  |  |  | Whole Panchayat |  |
|  |  | Pradhan Mantri Fasal BimaYojana (PMFBY) | *1* | Fasal Bhima Yojana for Paddy @ 2% to the borne by farmer | Whole Panchayat |  |
|  |  | *2* | Fasal Bhima Yojana for Maize @ 2% to the borne by farmer | Whole Panchayat |  |
|  |  |  | Fasal Bhima Yojana for Oilseed @ 1.5% to the borne by farmer | Whole Panchayat |  |
|  |  | Pradhan Mantri Krishi Sinchayee Yojana (PMKSY) | *1* | Borewell on 50% subsidy max to rs 0.25 per unit (1 No.) | Whole Panchayat | 0.25 |
|  |  | *2* | Borewell on 50% subsidy max to rs 2.00 lacs per unit (1 No.) | Whole Panchayat | 2.00 |
|  |  | *3* | Irrigation Pump sets on 50% subsidy max to Rs 0.15 (2 No.) | Whole Panchayat | 0.30 |
|  |  | National Food Security Mission (NFSM) | *1* | Maize Sheller on 75% subsidy (2 no.) | Whole Panchayat | 0.60 |
|  |  | *2* | Paddy thresher on 75% subsidy (2No.) | Whole Panchayat | 0.48 |
|  |  | *3* | Power sprayer on 50% subsidy (2 No's) | Whole Panchayat | 0.48 |
|  |  | *4* | Seed storage godown on 50% subsidy (2 No's) | Whole Panchayat | 3.00 |
|  |  | Mission for Integrated Development of Horticulture (MIDH) | *1* | Polygreen house on 75% subsidy (3 No's) | Whole Panchayat | 0.54 |
|  |  | *2* | Vermicompost Unit on 50% subsidy (2 No's) | Whole Panchayat | 1.00 |
|  |  | *3* | Vermi beds on 100% subsidy (10 No's) | Whole Panchayat | 1.50 |
|  |  | Rashtriya Krishi Vikas Yojana | *1* | Power Weeder on 50% subsidy (3 No's) | Whole Panchayat | 0.30 |
|  |  | *2* | Brush Cutter on 50% subsidy (2 No's) | Whole Panchayat | 0.30 |
|  |  | *3* | Tool kit on 75% subsidy (10 No's) | Whole Panchayat | 0.30 |
|  |  | *4* | Tractors on 50% subsidy (02 No's) | Whole Panchayat | 4.00 |
|  |  | Paramparag at Krishi Vikas Yojana (PKVY) | *1* |  |  |  |
|  |  | *2* |  |  |  |
|  |  | *3* |  |  |  |
|  |  | Mission Organic Value Chain Development for North Eastern  Region (MOVCDNER) | *1* |  |  |  |
|  |  | *2* |  |  |  |
|  |  | *3* |  |  |  |
|  |  | **Department of Elementary  Education** | Samagra Shiksha | *1* | Dev. Of M/S Manznoo by way of filling/Walling/sanitary points/ grills for windows | 7 | 5.00 |
|  |  |  | *2* |  |  |  |
|  |  |  |  |  |  |  |
|  |  |  |  |  |  |  |
|  |  |  | *3* |  |  |  |
|  |  |  | National Program for Education of Girls at Elementary Education ( NPEGEL) | *1* |  |  |  |
|  |  |  | *2* |  |  |  |
|  |  |  | *3* |  |  |  |
|  |  |  | Mid-day Meal Scheme | *1* |  |  |  |
|  |  |  | *2* |  |  |  |
|  |  |  | *3* |  |  |  |
|  |  |  | National Means-cum-Merit Scholarship Scheme (NMMSS) | *1* |  |  |  |
|  |  |  | *2* |  |  |  |
|  |  |  | *3* |  |  |  |
|  |  |  | National Scheme of Incentive to Girls for Secondary  Education(NSIGSE) | *1* |  |  |  |
|  |  |  | *2* |  |  |  |
|  |  |  | *3* |  |  |  |
|  |  | **Deptt of social welfare** | Integrated Child Development Services (ICDS) | *1* | Storage bins for AW centres | Whole Panchayat | 0.50 |
|  |  |  | *2* | Matting for AW centres | Whole Panchayat | 1.00 |
|  |  |  | *3* | Bathroom | Whole Panchayat | 2.00 |
|  |  |  | National Social Assistance Programme (NSAP) | *1* |  |  |  |
|  |  |  | *2* |  |  |  |
|  |  |  | *3* |  |  |  |
|  |  |  | POSHAN Abhiyan | *1* | C/o Bathrooms for beneficiaries | Whole Panchayat | 5.00 |
|  |  |  | *2* |  |  |  |
|  |  |  | *3* |  |  |  |
|  |  | **Department of Health and  Family Welfare** | Ayushman Bharat - Health and Wellness Centres (AB-HWCs) | *1* |  |  |  |
|  |  |  | *2* |  |  |  |
|  |  |  | *3* |  |  |  |
|  |  |  | Janani Suraksha Yojana (JSY) | *1* |  |  |  |
|  |  |  | *2* |  |  |  |
|  |  |  | *3* |  |  |  |
|  |  |  | Janani Shishu Suraksha Karyakram (JSSK) | *1* |  |  |  |
|  |  |  | *2* |  |  |  |
|  |  |  | *3* |  |  |  |
|  |  |  | Universal Immunization Programme (UIP) | *1* |  |  |  |
|  |  |  | *2* |  |  |  |
|  |  |  | *3* |  |  |  |
|  |  |  | Home Based Care of Newborn and Young Children | *1* |  |  |  |
|  |  |  | *2* |  |  |  |
|  |  |  | *3* |  |  |  |
|  |  |  | (HBNC/HBYC) Rashtriya Bal Swasthya Karyakram (RBSK) | *1* |  |  |  |
|  |  |  | *2* |  |  |  |
|  |  |  | *3* |  |  |  |
|  |  |  | National Ambulance Service (NAS) | *1* |  |  |  |
|  |  |  | *2* |  |  |  |
|  |  |  | *3* |  |  |  |
|  |  |  | Disease Control Programs | *1* |  |  |  |
|  |  |  | *2* |  |  |  |
|  |  |  | *3* |  |  |  |
|  |  | **National Disaster  Management Authority (NDMA)** | National Cyclone Risk Mitigation Project | *1* |  |  |  |
|  |  |  | *2* |  |  |  |
|  |  |  | *3* |  |  |  |
|  |  | **Department of Drinking water  and Sanitation** | Jal Jeevan Mission | *1* |  |  |  |
|  |  |  | *2* |  |  |  |
|  |  |  | *3* |  |  |  |
|  |  | **Department of Animal  Husbandry and Dairying** | Rashtriya Gokul Mission | *1* | Introduction of indegenous breeds like Sahiwal, Gir for milk production |  |  |
|  |  |  | *2* | Availability of sexed semen at doorsteps |  |  |
|  |  |  | *3* |  |  |  |
|  |  |  | National Dairy Plan-II | *1* | Elite semen for increase in milk production |  |  |
|  |  |  | *2* |  |  |  |
|  |  |  | *3* |  |  |  |
|  |  |  | Dairy Processing and Infrastructure Development Fund | *1* | Milk ATM for village (400 litres capacity) |  | 6.00 |
|  |  |  | *2* |  |  |  |
|  |  |  | *3* |  |  |  |
|  |  |  | Supporting Dairy Cooperatives and Farmer Producer | *1* | Need of milk cooperative society to collect and market the milk |  |  |
|  |  |  | *2* |  |  |  |
|  |  |  | *3* |  |  |  |
|  |  |  | National Livestock Mission | *1* |  |  |  |
|  |  |  | *2* |  |  |  |
|  |  |  | *3* |  |  |  |
|  |  |  | Livestock Census and Integrated Sample Survey | *1* |  |  |  |
|  |  |  | *2* |  |  |  |
|  |  |  | *3* |  |  |  |
|  |  | **Food  Processing Industries** | Pradhan Pantri Kisan SamapdaYojana (PMKSY) | *1* |  |  |  |
|  |  |  | *2* |  |  |  |
|  |  |  | *3* |  |  |  |
|  |  | **Skill  Development and Entrepreneurship** | Pradhan Mantri Kaushal Vikas Yojana (PMKVY) | *1* |  |  |  |
|  |  |  | *2* |  |  |  |
|  |  |  | *3* |  |  |  |
|  |  |  | National Apprenticeship Promotion Scheme (NAPS) | *1* |  |  |  |
|  |  |  | *2* |  |  |  |
|  |  |  | *3* |  |  |  |
|  |  |  | Jan Shikshan Sansthan | *1* |  |  |  |
|  |  |  | *2* |  |  |  |
|  |  |  | *3* |  |  |  |
|  |  |  | Skills Acquisition and Knowledge Awareness for Livelihood  Promotion (SANKALP) | *1* |  |  |  |
|  |  |  | *2* |  |  |  |
|  |  |  | *3* |  |  |  |
|  |  |  | Mahatma Gandhi National Fellowship (MGNF) | *1* |  |  |  |
|  |  |  | *2* |  |  |  |
|  |  |  | *3* |  |  |  |
|  |  | **Tribal Affairs** | Inclusive and sustainable growth of tribal population | *1* |  |  |  |
|  |  |  | *2* |  |  |  |
|  |  |  | *3* |  |  |  |
|  |  | **Capex Plan** | UT Capex | *1* | 100 KVA creation for Ameerpora Bonpora/Herpora /Wani Mohalla/Ganie Mohalla/Kuchey Mohalla Ameerpora including instalation of poles and wires | Whole Panchayat | 30.00 |
|  |  |  | *2* | LT/HT network for Manznoo/Herpora | 2,3 | 15.00 |
|  |  |  | *3* | C/o Drain and laying pipes on BT Road at Ameerpora near Steel girder bridge | 1 | 2.00 |
|  |  |  |  | Zebra X-ing and link road infront of M/S Manznoo | 7 | 5.00 |
|  |  |  |  | Macadamisation of road from Sheikh Bridhe to Mohd Hussain Shah at Khahpora, Macadamisation of road at Manznoo, link road from Khakhad Mohalla to Herpora Graveyard , road from bidge to ziyarat Sharief, road from main road to dobi Masjid | Whole Panchayat | 45.00 |
|  |  |  | *1* | Flood Protection Bund near Peth Nambal seer Bridge | Whole Panchayat | 10.00 |
|  |  |  | District Capex | *2* | C/o Health and wellness Centre | Whole Panchayat | 15.00 |
|  |  |  | *3* | C/o Bathrooms (03 No's) and Flash point (01 No) for Masjid Sharief Gogipora | 6 | 5.00 |
|  |  |  | *4* | Fencing around Graveyard at Herpora | 3 | 8.00 |
|  |  |  | *5* | Fencing around Ziyarat Sharief bunpora | 1 | 5.00 |
|  |  |  | *6* | Dev of Play field at Manznoo | 7 | 7.30 |
|  |  |  | *7* | Dev od Graveyard at Khahpora | 6 | 3.00 |
|  |  |  | *8* | Dev of Graveyard at Manznoo | 7 | 3.00 |
|  |  | **PMGSY** | Road connectivity projects | *1* |  |  |  |
|  |  |  | *2* |  |  |  |
|  |  |  | *3* |  |  |  |

**DAY2ACTIVITIES**

**AGENDA5**

Ensuresaturationoffollowingschemesandgivestatus:

|  |  |  |  |
| --- | --- | --- | --- |
| **NAMEOFTHESCHEME** | **TOTALELIGIBLE BENEFICIARIESIN THE VILLAGE** | **TOTALBENEFICIARIESWHO AVAILEDTHEBENEFITSOFTHESCHEME** | **REASONSFOR PENDENCY** |
| GoldenHealthCardunder  AyushmanBharat | 3192 | 2908 | Adhar issue of minors |
| Jananisurakshayojana | 55 | 45 | Under process at antinatal |
| OLDAGEpension | 52 | 52 | Nil |
| Widowpension | 18 | 18 | Nil |
| Disabilitypension | 10 | 10 | Nil |
| Domicilecertificate | 3192 | 150 | Nil |
| Kisancreditcard | 181 | 60 | Because of land record digitization |
| PMkisansammannidhi | 106 | 106 | Nil |
| Landpassbook | 420 | 310 | Digitization u/p |
| Registrationofvillageven- dorsonGEMportal | 08 | 08 | Nil |
| Registrationofvillagecon- tractorsonjktendersportal | 08 | 08 | Nil |
| Registrationofvillagecon- tractorsonPWDportal | 01 | 01 | Nil |
| Incompletebuildings/pro- jects | -- | -- | -- |

**DAY2ACTIVITIES**

**AGENDA6**

**NASHAMUKTABHIYAN**

1. Whethergramsabharesolutionpassed: Yes

2. Detailsofactivities conducted: Pledge Ceremony/Awareness programme/Placards/banners

3. Whetherallactivities andGSresolutionuploadedonjkpanchayats.inportal: Yes

4. Howmanydrugaddictsinthevillage : None

5. WhetherreportedtotheDeputyCommissioner..

6. Howmanyregisteredforrehabilitationundergovernmentprogramme: None

**DAY2ACTIVITIES**

**AGENDA7**

**SOCIALAUDIT**

Conductsocialauditofatleast5workseachunderfollowingschemes:

|  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- |
| NAMEOFTHE SCHEME | DETAILSOFTHE WORKS | YEAROFWORK APPROVAL | AMOUNT APPROVED  FORTHEWORK | WHETHER  WORKEXECUTED SATISFACTORILY | GEO- TAGGED PHOTOS | ANY GRIEVANCE RECORDED RELATINGTOTHAT WORK |
| MGNREGA | R-wall near Ziyarat Sarief | 20-21 | 4.00 (lacs) | Yes | Yes | No |
| PMAY | Zaina | 20-21 | 1.50 (Lacs) | Yes | Yes | No |
| IHHL  UNDERSBM-G | Ab Rashid Magrey | 20-21 | 0.12 (Lacs) | Yes | Yes | No |
| CSCUNDER SBMG | -- | -- | -- | -- | -- | -- |
| AMRIT SAROVARS | -- | -- | -- | -- | -- | -- |

**DAY2ACTIVITIES**

**AGENDA8**

**MAHILASABHA**

Totalwomeninthevillageabovetheageof18 : 75

Totalattended :53

Proceedings: Women empowerment, Health and hygiene, Child Care

*(Plinsertpointerstobediscussedthere–referpalliproceedings)*

**DAY2ACTIVITIES**

**AGENDA9**

**BALSABHA**

Holda balsabhaandrecordproceedings: Held at Middle School Manznoo

Totalchildreninthevillageabovetheageof 06: 173

Totalattended: 107

Proceedings: Awareness regarding child labour, corporal punishment, drug menace, health and hygiene.

*(Plinsertpointerstobediscussedthere–referpalliproceedings)*

**DAY2ACTIVITIES**

**AGENDA10**

**INAUGURATIONS**

|  |  |  |  |
| --- | --- | --- | --- |
| **SR NO.** | **ASSETS/ACTIVITIES INAUGRATED** | **STATUSOFTHEASSET/AC- TIVITIES(NUMBER,OTHER DETAILS)** | **GEO-TAGGED PHOTOS** |
|  | VILLAGEHAATunderJKSRLM (SUN- DAYMARKET) | Handicraft, Embriodery (showcased their art) NRLM awareness | Yes |
|  | PMAYhousesifanyreadyforinaugra- tion | Under construction | Yes |
|  | Swachhgramprojects-segregation shedsetc | SBM, Compost and Soakage pits, Plastic free Panchayat, Distribution of dustbins. | Yes |
|  | Amritsarovars | Plan stands forwarded for approval |  |
|  | Sportskits | Participated in sports activity and distributed sports kit |  |
|  | Villageculturalevents | Kashmiri rouf performed by students |  |
|  | JJMassets/projects | Inspected the IHH water connections, Bore wells, water connection pipes (Har Ghar Nal se Jal) |  |
|  | Anyothertobeidentifiedatdistrict level | -- | -- |

**FOLLOWUPOF(B2V1,B2V2&B2V3):**

*(Prefilledexcelsheet tobetakenfromdistrictlevel/andalsotobedownloaded*

*from*[*www.jkpanchayat.in)*](http://www.jkpanchayat.in)

|  |  |  |  |
| --- | --- | --- | --- |
| S.NO. | Particulars | Actiontaken | Remarks# |
| I. Urgent Public Requirements/Demands-B2V1 Few demands fulfilled | | | |
|  | | | |
| II. Urgent Public Requirements/Demands-B2V2 | | | |
|  | | | |
| S.NO. | Particulars | Actiontaken | Remarks# |
| III. MajorProblems–B2V1 Some demands fulfilled | | | |
|  | | | |

|  |
| --- |
|  |
| IV. MajorProblems-B2V2 |
| Some demands full filled |
| V. MajorProblems-B2V3 |
| Some demands full filled |
| VI. MajorComplaints-B2V1 |
| Some demands full filled |
| VII. MajorComplaints-B2V2 |
| Some demands full filled |
| VIII. MajorComplaints-B2V3 |
| Some demands full filled |

**OVERALLPERCEPTIONOFFUCNTIONING OF GOVERNMENTDEPARTMENTS**

1. **BESTDEPARTMENT: RDD, R&B, ICDS, ICPS**

**2. LEASTRESPONSIVEDEPARTMENT: J&K Bank**

**GENERALASSESSMENTOFTHEVISTINGOFFICER**

|  |  |
| --- | --- |
| I | AnymajorcomplaintbroughttothenoticeoftheVisitingOfficer: Bifurcation of Ward No: 06 Gojipora into two separate wards |
| II | Major/urgentpublicdemandsthatwas/werereflectedearlierbuthavenotbeenaddressedsofar: C/o Govt building for Health and Wellness Centre.100KV creation for Amir pora ,Bunpora , Herpora , Wani Mohallah , Ganie Mohallah , Kuchay Mohallah. Including Poles and wires ,LT/HT Network f |
| III | For Manznoo/ Herpora , Zebara Crossing near GMS Manznoo ,Macadamisation of various roads in Amirpora and Manznoo  Overallassessmentofthevisitandsuggestions:  (Thevisitingofficertoensurethattheoverallassessmentisrecordedindetailsalongwithconcretesugges- tions) Inspections carried out of various govt institutions and demands forwarded to concerned authorities. Overall functioning of govt departments found satisfactory. |
| IV | OverallRatingofgovtfunctioningas givenbythePanchayat(Scaleof0to10): 8.5 |
| V | CertificatefromSarpanchthatthevisitingofficerhasstayedinthepanchayatfor2days: Certified that Visiting Officer nominated for Panchayat Halqa Bon Nambal Middle (B) Er. Fayaz Ahmad (AEE R&B Division Qazigund) has stayed in the concerned Pyt in B2V4 Programme from morning of 2nd November 2022 to evening of 3rd November 2022. |

Stayed in concerned Panchayat during B2V4 Programme from morning to 02Nov.2022 to Evening 03Nov -2022

**Signature of Sarpanch Signature of theVisitingOfficer**

**Name……………………… Name………………………**



**Department of Rural Development and Panchayati Raj**

**Government of Jammu &Kashmir**