4

15TH OCTto3RD NOV,2022

KEYFEATURES

•     DeputyCommissionerstoleadtheinitiative

•    RuraldevelopmentDepartmenttobethenodaldepartment

•	PlanningDevelopment&MonitoringdepartmentandITtobethesupport departments

ACTIONSANDTIMELINES

| ACTION | RESPONSIBILITY | LATESTBY | REMARKS |
| --- | --- | --- | --- |
| Janabhiyan | Alldepartments | Oct15-26th | Goingon |
| DeputationofSecttstaff/ HoDs | GAD | Oct14 | Done |
| DeploymentofStaffto Panchayatsandservingof ordersondeployedofficers | DCs | Oct25 | DCswilldeployseniorlevelstaff fromthedistricts.Strictactionto betakenagainstabstentions.No exemptionstobegiven |
| Trainingofdistricttrainors onB2V4 | RDD | Oct26 |  |
| Trainingofvisitingofficers | DCs | Oct27 |  |
| FieldVisitstobecompleted by | VisitingOfficers | Nov3 | DCstosuperviseandensurethat eachPanchayatisvisitedwithin theperiodspecified |
| DataofB2V4tobe uploadedby | VisitingOfficers | Nov10 | DCstosuperviseandensurethat dataofallPanchayatsisupload- edbythevisitingofficerwithin theperiodspecified |

INSTRUCTIONSFORTHEVISITINGOFFICER(DAYWISE)

| DATE | INSTRUCTIONS | ACTIONPOINTS |
| --- | --- | --- |
| Day0 | Meetingwithdeputy commissionerandhis/her team | a. TakeprintoutsoffilledbookletsofB2V1,B2V2andB2V3from www.jkpanchayat.in b.Alsotakeprintoutsofthesummarizedexcelsheetsofthe previousphasesfromwww.jkpanchayat.in c. CollectATRsonissuesraisedduringprevious3phasesfromthe officeofDeputyCommissioner(Planningdeptt) d.Takeprintsofblank 2bookletsofB2V4fromwww.jkpanchayat.ine.Takeplansfor2previousyearsandATRsfromtheplanningdeptt f. CompletetrainingsondifferentcomponentsofB2V4being organizedbyrespectiveDeputyCommissioners g.CollectListofnewworksstarted/ongoing/completedduringthe previousandcurrentFinancialyearunderthefollowingheads: • PRIgrants • DistrictPlan • UTplan • MGNREGA • Otherschemesofotherdepartments • Anyotherwork h. Plans/beneficiarylists: • MGNREGAdraftplandocumentfortheyear2022-23. • ListofAwaas+beneficiariesalongwithIHHL Convergence • Listofpensionbeneficiaries. • ListofSHGs • Listofagricultureschemebeneficiaries i. Listsofbeneficiariesfor: • Variouscertificates/benefitstobedistributedbythe visitingofficer. • Anyotheractivitiesidentifiedbydifferentdepartments |

| Day1 | Reachthevillage | 1. | Ensurethatallfrontlineworkersofdifferentdepttsarepresent. |
| --- | --- | --- | --- |
|  |  | 2. | Ensureexhibitionbydifferentdepts.aboutindividualbeneficiary schemes |
|  |  | 3. | InspectJKB/PSBcounters/outlets |
|  |  | 4. | Participate/ensureorganizationofsportsactivityinplayfield,talent hunt/culturalevent/youthactivity |
|  |  | 5. | GandhiKatha(suggesteddetailsuploadedonjkpanchayat.in) |
|  |  | 6. | Visitatleast2amritsarovarsandgetitsgeotaggedphotos |
|  |  | 7. | InspectKhidmat(CSC)CentresandcreateGenerateawarenesson 225schemesparticularlyG2CschemeslikeBEAMS,Janbhagidari, AapkiZaminAapkiNigrani,DigitalJ&K |
|  |  | 8. | Visitingofficershallalsoplanandconductpanchayatlevelconver- gencemeetingofalldepartments |
|  |  | 9. | CheckeffectivenessofCentrallysponsoredschemes |
|  |  | 10. | VisitandinspectallgovernmentestablishmentsincludingPHE, AWC,FPS,schools,etc |
|  |  | 11. | Attemptsaturationofdeliverableso JanAbhiyanandwherever deficienciesfound,leadadrivetoachievealldeliverables |
|  |  | 12. | Assesseffectivenessofsanitationcampaigninthepanchayat |
|  |  | 13. | Ensureselfemploymentactivitiesfor15youthperpanchayat |
|  |  | 14. | Identify20potentialcandidatesperpanchayatforHIMAYATtraining alongwiththetradeonwhichtheywanttraining |
|  |  | 15. | Whereverpossible,distributeemploymentlettersforpeopleselect- edundervariousgovernmentemployments |
|  |  | 16. | Intheevening,holdnormalmeetingwith seniorcitizens,govtem- ployeesincludingretiredemployees,exservicemen,youthclub,and any citizens ofthevillagewhoareenrolledincollege/university |
|  |  | 17. | OpendiscussiononNashaMuktAbhiyan |

Day2            Haveameetingwithall stakeholders-depttofficials andpanchayatmembers

1.       Discussionontheandassesstheprogressofdifferentschemesrelating tothelocalizedSDGsprioritizedforthatvillageaspertheresolution passedby thatGramPanchayaton21st April22,onNationalPanchayti RajDay.

2.	Sensitizevillage residentsaboutmyScheme”portal(myscheme.in) whichincludesinformationaboutalltheschemesbeingrunbyCen- tral/State/UTgovtacrossthecountry

3.	Hold meeting of theBiodiversityManagementCommitteestodeliber- ateonissuespertaining toconservation of biodiversityandsustaina- bleutilizationof biologicalresources.

4.       PrepareVillagedevelopmentplan,inconsultancywithGrampanchayat, discussitingramsabhaandgetitapproved.

5.       Ensure saturationofsoilhealthcardandgoldenhealthcardunderGold- enHealthCardunderAyushmanBharat,

6.       Ensuresaturation  of OldAge PensionScheme

7.       EnsureDomicileSaturation.

8.       EnsureKCCSaturation

9.       Ensure saturationoflandpassbooks

10.     Ensureregistrationofvillagevendorsneededforanyscheme,onGEM

portal

11.     Ensurepanchayatcontractors registration

12.     EncouragePanchayatmembers forimportanceofplantationdrivein

PanchayatunderHarGaonHariyali

13.     Ensure paintingondigitalJ&Kinpanchayatghars

14.     Ensure paintingonpanchayatactivitesandCSSinpanchayatghars

15.	Thevisiting officeshallchecknoof kindergarten andplayfields present inthepanchayat for kidsandstudents,iftheinfrastructure present inthesearegoodenough.

16.     Holdmeeting withpanchayatmembers todiscussaboutcorruption menaceandstepsrequiredtomakeJ&Kcorruptionfree

17.     Obtaina candidassessmentaboutperformanceofvariousdeptts in- cludingfairfeedbackaboutdiscrepanciesinfunctioning

18.	Check thestatusof NashaMuktAbhiyanandreporting of drugad- dictstoDeputyCommissioner.

19.     IdentifyTouristDestinations,Circuits,ThemeTreks,IdentifyHomestays, providesupportfortourismactivities throughVillageCooperative

20.     OrganizeTalentHuntatPanchayatLevel

21.     Conductsocialauditofatleast5worksunderfollowingschemes:

a.       MGNREGA

b.PMAY

c.        IHHLtoiletsandpayments d.CSCs

e.AMRITSAROVARS

22.     Holda mahilasabha anda balsabhaandrecordproceedingsinthefor- matgiven

23.     InauguratevillagehaatunderJKSRLM

24.     Checkifyouthclubsareformedinthepanchayatandwhatactivities theyareengagedin

25.     Organizea villagelevelculturaleventtoengagepanchayatmembers

26.     SensitizeGPaboutE-kitabkoshaninitiativeofJ&KGovtforempowering youthsthrough onlinedigitalliteracy

GENERALINSTRUCTIONS

1.	Thevisitingofficershallrefrainhimself/herselfgivingorofferinganycommitmentonbehalfofthe governmentandshalladoptanunbiasedattitudeinreportingissues.As faraspossible,his/her observation shouldbebasedona fairandanalytical viewemergingfromhis/herinteractioninthe village.

2.	Heisgoingtothevillageasplanningofficer,notforsanctioninganyworksorformakinganycom- mitments.

3.	Whilepreparingvillagedevelopmentplan,hehastoensurethat,demandsareprioritizedandre- flectedunderavailableschemes,wherevernecessarythelargerworksaretobereferredtoadminis- trativedepttunderCSS/UTplansunderintimationtoDCsandrestoftheworkstoDCsforreflecting itunderdistrict/CSS plans

4.    His workshallbehardcoreplanningandauditandisnota PRexercise.

5.	EveryDeputyCommissionerhastoensurethatatleastoneRDDofficial(ideallyPanchayatSecre- tary)ispresent  ineverypanchayatwithrelevantpanchayatrecords,toensureconductofallactivi- tiesasplanned.Panchayatwiseorderneedstobeissuedinadvance.

6.	Visitingofficershouldideallycarryhis/herlaptoptocompletethereportsatthepanchayatlevel itselfanduploadthefinalreport,duly signedbothbythesarpanchandbythevisitingofficeron www.jkpanchayat.inportal,beforetheyleavepanchayat.

7.	Focus ofvisitareyouth,skills,self-employment,nashamukt,bhrashtracharmukt,Rozgaryukt J&K, besidestocarryforwardtheactivities duringJanAbhiyanandsaturatethem.

8.    Inadditionattentionmaybegiventothefollowingareas a.     MakefulluseofCentrallySponsoredSchemes

b.Saturationofindividualbeneficiaryschemes c.     Self-employmentschemes

d.Banklinkedschemes-includingdepartmentalsubsidyschemes e.Empowermentandtransparencythrough digitalinitiatives

f.       Effectivenessofgrassrootsmachinery–

i.       Patwari,VLWpresent  andavailable

ii.      AvailablefundsutilizedinpublicinterestandasperGramSabharesolutions iii.   Fairness ingovernance

iv.    CSS/Individual beneficiaryschemesetc v.      BrashtacharMuktJ&K

vi.   BhaiMuktJ&K

vii.  NashaMuktJ&K

9.	ThePRImembers (Sarpanchs,Panchs,BDCChairperson)shallbeattheforefrontofallactivities and givendueimportanceandtheapproach shouldbetostrengthenthemandmakethemfeelem- powered.He/sheshallensurethattheBDCchairpersonandSarpanch/Panch arepresent  atthetime ofinaugurationandceremonies.

10.	Visitingofficershallnotleavethedistrictwithoutuploadingthereport,duly signedonthewww. jkpanchayat.inportal.EveryDeputyCommissionerhastoensurethat.

A)   DetailsofReportingOfficer:

Name:   Hazoor ahm,ed Bhatti

Designation:sr. Lecture

Department/placeof  posting:   Education/ Govt H.S.S Lassana

MobileNo:8492000890

EmailID:  hazoorahmedbhatti@gmail.com

HomeDistrict:   Poonch

Datesof  visit: 28-10-2022  to 29-10-2022

B)	LocationaldetailsofPanchayat:(tobepre-filled,informationtobetakenfromtheprevious phasesbooklets/summarizedexcelsheetuploadedonjkpanchayat.in/b2v4.php)(tobevali- datedbythevisitingofficerandmissingdetailstobefilled)

NameofthePanchayat:    ARIGAN

LocalGovernmentDirectory(LGD)codeof  thePanchayat:289230

Nameof  CDBlock:   Loran

NameofTehsil:   Mandi

Nameof    District:   Poonch

C)     PanchayatProfile:

No.ofrevenuevillagesinthePanchayat:df

No.ofhamletsinthePanchayat:  7

No.ofhouseholdsinthePanchayat: 550

Population(approx)of  thePanchayat:    1750

Part-II:

(TobefilledupbytheVisitingOfficerduringhis/hertwodayvisittothePanchayat.AllFieldshavetobe

FilledbytheVisitingOfficerbeforethebookletishanddovertotheDC

FrontlineOfficers/OfficialswhowereassignedtothePanchayatfortheprogramme:

| Department | Name | Designation |
| --- | --- | --- |
| Education | Ghulam Rasool | Teacher |
| PHE | Manzoor ahmed | Supervisor |
| PDD | Shokat Hussain | Need bose |
| PWD | Khadam Hussain | Do |
| Health | Mohd Aslam | Pharmas. PHC loran |
| Forest | Mohd sadiq | Forest gad |
| Social welfare | Farida Begum | A.W.W |
| Dy.S.S | Mohd Farooq | Rek teacher |
| Animal husbandry | Mohd Kabeer | a.H |
| JK Bank | Sharaz mohd | Head bach |
| Agriculture | Vishal Suden | AEA |
| FCS and CA food supply | Ranjeet Singh | Astt. Dmetic |
| Revenue | M. Anwer | NYC |

Horticulture                                         manweer Hussain                      NYC

Detailsofabsentemployeesvis-à-vislistfurnishedbytheDCoffice:

| Department | Name | Designation |
| --- | --- | --- |
| NIL |  |  |

DAY1-ACTIVITIES

AGENDA1:PANCHAYATASSETREGISTER

Infrastructure:

1.		PanchayatGharInfrastructure a.  Govtbuilding/private    Private Building

b.  New/needingrepairs      NEW

2.       Furniture(Y/N)                             Y

3.       Computer/printer(Y/N)              Y

4.       Internet(Y/N)                               N

5.       Telephone(Y/N)                          N

6.       Toilet(CSC/partofpanchayatghar)(Y/N)       N

7.       Water(Y/N)                      N

8.       Electricity(Y/N)               N

9.       Bankbranch(Y/N)             N

10.     CSC(Y/N)                          N

11.     Patwarkhana(Y/N)            N

12.     Villagehaat(Y/N)               N

13.     Playground(Y/N)               N

14.     School-                              Y

a.        Kindergarten(Y/N)        N

b.Primary(Y/N)                           Y

c.         Secondary(Y/N)                N

d. College (Y/N)                           N

e.University(Y/N)                        N

15.     AnganwadiCentre(Y/N)                Y

a.        (govt/private)                   Private

b.Totalchildrenenrolled

15.     AmritSarovars–details,location,condition           W.No. 3 Danna

16.     Governmentoffices-details,whetherfunctionalornot       No

17.     Rationshop(Y/N)                N

18.      Placesoftourismimportance–names,littledetailsonhistorical/culturalimportance   Nandi Choal

19.      Villageheritagesites/treks-names,littledetailson historical/culturalimportance    Dana Sultan Patwari

20.     VLWOffice (Y/N)                                       N

21.     PrimaryHealthcareCentre(Y/N),               N

22.     ListofIncompleteBuildings-names,yearofconstruction         PWD Dak bunglow 1983 M\S Arigam School Buil;ding 1980

23.     ListofUnderutilizedBuildings-names

DAY1-ACTIVITIES

AGENDA2:

DIFFERENTINSTITUTIONS/INFRASTRUCTUREPROJECTSTOBEVISITED

| AMRITSAROVARS | Visit,verify | COMMENTS |
| --- | --- | --- |
| KhidmatCentres | Create/Generateawarenesson225schemes particularlyG2CschemsAapkiZaminAapkiNigrani, Beams,Janbhagidari,DigitalJ&K | Nil |
| JKB/PSBcounters/outlets | a)Statusofcounter b)Numberofvisitors |  |
| Incompletebuildings/pro- jects | Verify whetheridentificationandredistribution done | N/A |
| PDS | Visit,evaluate,onlinestatus | nil |
| PHC | Visit-evaluate,statusofstaff,equipmentand quality | nil |
| Youthclubs | Meet,interact,seeksuggestions | M/S Arigam |
| SHG | Meet,identifyproblems,seeksuggestions | Nil |
| PMAY | Inspect,Inaugurate | 5 |
| Myschool,mypride progress;schools-water, toilets,staff | Visit,checkforwater,electricity,sanitation,meet studentsandstaff | M/S arigam |
| SwachhSBM | Evaluate | Toilet |
| Panchayatplayground, Sportskitsdistribution Villagegames | Ensure,verify.Participateinatleastonegamein theplayground | M/S arigam |
| HarGaonHariyali, Planta- tiondrive | Evaluatestatus,feedback | Yes |
| Villageculturalevent Dangal/Haat/Mela | Participatein;ensurethatitisheld | M/S arigam |
| Exhibitionofschemes | Ensurethateverydepartmentparticipatesand thatitcontinuesfortheentiredurationofB2V | Appellate |
| JalJeewanMission verifica- tion- WSS/JSD Electricitysupply | Verify |  |

DAY1-ACTIVITIES

AGENDA3:SATURATEJANBHIYAN

DELIVERABLESANDRECORDDEFICIENCIESIFANY(INSERTDELIVERABLESLISTHEREASPERGADFORMAT

DAY1-ACTIVITIES

AGENDA4:

SELFEMPLOYMENTACTIVITIES

EnsureSelf-employmentactivities foryouth,distributeemploymentlettersforpeopleselectedunder varioussocialschemes(15ISTHETARGETPERPANCHAYAT)

Numberofcasesindifferentcategoriessanctioned: Detailsofthebanksanctioningit:

Totalamountinvolved:

DAY1ACTIVITIES

AGENDA5

Intheevening,holdinformalmeetings  withseniorcitizens,govtemployees,retdemployees,youthclub andothercitizenswhoareenrolledoncollege/universityandhavediscussiononGandhiKatha,Nasha MuktAbhiyan,corruptionfreegovernance,doublingfarmersincomeandrecordtheproceedings

DAY2

- NoofIndividualCompostPitsconstructed   10

b.NoofIndividualSoakPitsconstructed          150

V.          No.ofBiodiversitymanagementcommitteemeetingsheld:

VI.         IsthenameofSarpanchdisplayedoncitizeninformationboardsofallRD&PRschemes:Yes/No      yes

VII.       AreSarpanchsbeinginvolvedinstart/inaugurationofactivities:Yes/No  No

VIII.      WhethersubjectshavebeenassignedbytheSarpanchtothePanchs:Yes/No      No

IX.        Whethergrievancesredressalboxisinstalled:Yes/No       Yes

X.         NoofgrievancesreceivedpertainingtoPanchayatlevel 8

XI.        NoofgrievancesdisposedofatPanchayatlevel:      10

XII.       WhethertheSarpanch/PanchayatSecretaryhavedigitalsignatures:Yes/No    YES

XIII.      WhetherallMGNREGA/14thFCpayments arebeingmadebySarpanchthrough DigitalSignature

Certificate(DSC):Yes/No      Yes

HUMAN RESOURCEAVAILABLEATTHEPANCHAYAT LEVEL:

| SRNO. | DEPARTMENTWISESTAFF | NUMBERS |  | NAMES |
| --- | --- | --- | --- | --- |
|  |  | SANCTIONED | ACTUAL | Zamood ahmed |
|  | Ruraldevelopmentdepartment: BDO JE GRS TA | 4 | 04 | Vikas Hansa Rayaz ahmed Imtaiz Ahmed |
|  | SCHOOLEDUCATION: TEACHER HEADMASTER ANYOTHER | 24 | 19 | Do |
|  | JAL JEEVAN: | 03 | 03 | Mohd Hanif Manzoor ahmed Mohd Latief |
|  | PDD: LINEMAN JE ANYOTHER |  | 02 | Mohd shokat Bashir Ahmed |
|  | FOOD&CIVILSUPPLIES | 01 | 01 | S Ahmed |
|  | AGRICULTURE&ANIMALHUS- BANDARY | B.Level | 01 | AEO sub-Division Vishal Sudden |
|  | SOCIALWELFARE | 7 | 07 | CDPO |
|  | HEALTH: ASHA ANM AYUSHDOCTOR ALLOPATHICDOCTOR | 01 01 01 01 | 04 | Mohd Aslem Naseem Akhter Nil Nil |
|  | ANYOTHERDEPARTMENT |  |  |  |

22

DAY2-ACTIVITIES

AGENDANO.1

DiscussionontheandassesstheprogressofdifferentschemesrelatingtothelocalizedSDGsprior-itizedforthatvillageaspertheresolutionpassedbythatGramPanchayaton21stApril22,onNational PanchayatiRajDay(Copyoftheresolutiontobetakenfromwww.jkpanchayat.inportalunderthelinkof GramSwarajMonth)

1.       SDGs AGREED FORTHATVILLAGE,TOBEIMPLEMENTED BYMARCH2024:

2.       STATUSOFWORKSUNDERTHEFOLLOWINGSCHEMES:

1      Cleanandgreenvillage

i.InitiativestakenbythePanchayatformanagingSolidandLiquidWaste    Yes

ii.     InitiativestakenbythePanchayatforusinggreensourcesoffuellikesolar,biogas

Nil

iii.  Hasmappingoflanduse,waterbodies,forest,slopes,wetlands,degradedforestwithintheGram

Panchayatbeendone?Yes/No.IfNo,reason,thereof

iv.    HastheClimateResiliencePlanbeendevelopedfortheGP?Yes/No                     No

v.     StepstakenbytheGramSabhaabouttheclimatechangemitigationfactorslikereducingenergy consumption,usageoffossilfuels,plastics,non-renewablebuildingmaterialsandalsotopromote measureslikeplantingoftrees,conservingforests,usageofgoodagriculturalpracticeslikedrip irrigation,waterconservationmeasuresandconservationofwetlands.

vi.  Whetherschoolshavestartedsegregatingwaste

vii. Whetherschoolshavetheirowncompost/soakagepitsforsolid/liquidwastemanagement                YES

2     Healthyvillage

i)    Aremeetings  relatedtoVillageHealthandSanitationCommitteebeingheldregularly?

ii)   DoalltheeligibleindividualsbeenprovidedtheGoldenCard?                       Yes

iii)  ArealltheChildrenbeingimmunizedaspertheSchedulerecommendedbyGovt.ofIndia?    Yes

iv)  ArealltheeligibleindividualsbeenvaccinatedagainstCOVID-19?                       Yes

v)   DoesGramPanchayatensurethatallpregnantwomenaregettingnecessaryprenatalcheckups?

vi)  WhetherallthedeliverieswereInstitutionalizedorconductedbytrainedMidwives?

3     Watersufficientvillage

i)    DoalltheIHHsintheGramPanchayathavewaterpipelineconnections?             No

ii)   WhetherGramPanchayathastakenstepsforgreywatermanagement.IfYespleasespecify	     NO

iii)  DoalltheIHHsintheGramPanchayathavetoilets?	    Yes

iv)  ArealltheIHHstoiletsfunctionalornot?    Yes

v)   DoalltheSchools/Anganwadicentershavea toiletfacilityornot?

vi)  Areallthetoiletsintheschools/Aaganwadifunctionalornot?    Yes

vii) WhetherGramPachachayatBhawanhasseparate toiletsforwomenornot?	    Yes

4      ChildFriendlyvillage

i)	Doallthechildrenundertheageof0-6yearsbeenenrolledintheAnganwadicentersforpre- schooling?Yes/NO    Yes

ii)    HowmanyBalSabha’swereorganizedintheGramPanchayat--------   02

iii)  WhethertheissuesraisedbyBalSabhaareaddressedduringtheGramSabha. Yes/NO       No

iv)	WhetherGramPanchayatistrackingthedatarelatedtodropoutchildrenandchildrenwithirregular attendance?Yes/NO.

v)   DoalltheschoolsundertheGramPanchayathaveseparate toiletsforgirlsandboys?Yes/No    Yes

5      Villagewithgoodgovernance

i)    IsCSClocatedintheGramPanchayatBhawanornot?              Not

ii)	IsthelistofbeneficiariesrelatedtotheSchemes/ProgramsdisplayedontheGrampanchayatwallor not?

iii)  DoestheGramPanchayathasitsbuildingornot?    No

iv)  IstheGramPanchayatofficefunctionalornot?	    Yes

v)   Aretheactivities approved undertheHalqaPanchayatDevelopmentPlandisplayedontheGram

Panchayatwallornot?

vi)  IsSocialAuditofearlierSchemes/Programscarriedoutornot?             Yes

6      Povertyfreeandenhancedlivelihoodvillage

- HasGramPanchayatdevelopedanycriteria fortheidentificationofthepoor?Yes/Noifyesspecify      Yes

- ii)   HavealltheeligiblehouseholdsregisteredinPDSornot?           YES

iii)	HasGramPanchayatprovidedspaceforSelf-helpGroupsinPanchyatGharforholdingmeetings  or not?

iv)  HavealltheeligiblehouseholdsbeenregisteredforPensionornot?        NO

v)   HasGramPanchayatfacilitatedYouthforSkillEnhancementCoursesandPlacement?    Yes

vi)  HasJobCardsbeendistributedtoalltheeligibleindividualsunderMGNREGA?	    Yes

vii) HasGramPanchayatfacilitatedSHGsforBankAccountLinkages?	    Yes

7     Sociallysecuredvillage

i)    WhetherGramPanchayatismaintainingdatarelatedtoDifferentlyAbledPeople?	    Yes

ii)   IsGramPanchayatOffice DisabledFriendlyornot?	    Yes

iii)	Areprovisionsfora separate BudgetundertheResourceEnvelopeforWomenandChildrenmadeor not?   No

iv)	DoalltheSchools intheGramPanchayathavefacilitiesforDifferentlyAbledChildrenliketoilets, barrier-freeaccess,etc.,ornot?              No

v)   Arealltheeligibleindividualsaregettingpensions,likeoldagepension,widowpension,etc?	NO

vi)  ArealltheeligiblehouseholdsgettingbenefitsfromIAYornot?	    Yes

8      EngenderedDevelopmentinVillage

i)    HowmanyMahilaSabha’swereorganizedintheGramPanchayat-------------------02

ii)	WhetherSHGsfederationshavebeenprovidedspaceformeetings  inthePanchayatBhawan(Yes/ No)

iii)  WhetherGPshavetakenstepsforincreasingwomen’sparticipationinGramSabha(Yes/No)	Yes

iv)  NumberofwomenbeneficiariesheadedhouseholdscoveredunderPDS

system………………………

v)   Numberofbeneficiaries(outoftotaleligiblepopulation)receivingsocialprotectionbenefitsunder

PradhanMantriMatritvaVandanaYojana………………….

9    Self-sufficientinfrastructureinthevillage

i.	WhetherGPhasa CommunityHallwithaccesstoelectricity,furniture,watersupply, toilet……………………….

ii.     WhethertheDisastermanagementplanisavailableattheGPLevel(Yes/No)	    No

iii.  Whetherchild-friendlyparkwithrequiredfacilitiesisavailableinGP(Yes/No)	    No

iv.    WhethertheGPhaseasyaccesstoGodownforstorage(Yes/No)	No

v.     Whetherstreetlightsareprovidedinpublicplacesforensuringsafety(Yes/No)          No

DAY2ACTIVITIES

AGENDANO.2

SensitizevillageresidentsaboutmyScheme”portal(myscheme.in)whichincludesinformationaboutall theschemesbeingrunbyCentral/State/UT govtacrossthecountry

(SchemeMaterialavailablefromhttps://jkpanchayat.in/b2v4.php)

DAY2ACTIVITIES

AGENDANO.3

HoldmeetingoftheBiodiversityManagementCommitteestodeliberateonissues pertainingtoconserva- tionofbiodiversityandsustainableutilizationofbiologicalresources.HeshouldcheckPeopleBiodiversity register(PBR)ofthatpanchayatandreviewifBiodiversityManagementCommittee constitutedforthat panchayatis holdingminimum4meetings inayearandmeeting onceinevery3months (RoleofBMC availableathttps://jkpanchayat.in/b2v4.php)

COMMITTEEMEMBERS PRESENT

BIODIVERSITYREGISTERPHOTOS

PAST 4MEETINGDETAILS-DATES,MINUTESPHOTOS

DAY2ACTIVITIES

AGENDA4

Visitingofficershallalsoplanandconductpanchayatlevelconvergencemeeting  ofalldepartmentsand prepareVillagedevelopmentplanforvillage,inconsultancywithGrampanchayat,discussitingram sabhaandgetitapproved.

(GPDPformatavailableonhttps://jkpanchayat.in/b2v4.php)

InadditionGPDPplanshallalsoinclude:

           Touristplaceswhichneedtobedeveloped       Nil;

           Specificproductwhichneedstobedeveloped     Nil

           Tourism-homestays	Nil

	20candidatesfortrainingunderHimayatschemealongwithtradeinwhich trainingistobegiven

DAY2ACTIVITIES

AGENDA5

Ensuresaturationoffollowingschemesandgivestatus:

| NAMEOFTHESCHEME | TOTALELIGIBLE BENEFICIARIESIN THE VILLAGE | TOTALBENEFICIARIESWHO AVAILEDTHEBENEFITSOFTHESCHEME | REASONSFOR PENDENCY |
| --- | --- | --- | --- |
| GoldenHealthCardunder AyushmanBharat | 2200 | 08 | Good Health |
| Jananisurakshayojana | 08 | 08 |  |
| OLDAGEpension | 130 | 130 |  |
| Widowpension | 40 | 40 |  |
| Disabilitypension | 01 | 01 |  |
| Domicilecertificate | 2200 | 2100 |  |
| Kisancreditcard | 150 | 150 |  |
| PMkisansammannidhi | 140 | 140 |  |

| Landpassbook | 350 | 20 |  |
| --- | --- | --- | --- |
| Registrationofvillageven- dorsonGEMportal | 05 | 05 |  |
| Registrationofvillagecon- tractorsonjktendersportal | 07 | 07 |  |
| Registrationofvillagecon- tractorsonPWDportal | 06 | 06 |  |
| Incompletebuildings/pro- jects | nil | nil |  |

DAY2ACTIVITIES

AGENDA6

NASHAMUKTABHIYAN

1.       Whethergramsabharesolutionpassed    Yes

2.       Detailsofactivities conducted	    Yes

3.       Whetherallactivities andGSresolutionuploadedonjkpanchayats.inportal	    Yes

4.       Howmanydrugaddictsinthevillage	    Yes

5.       WhetherreportedtotheDeputyCommissioner	    Yes

6.       Howmanyregisteredforrehabilitationundergovernmentprogramme	    Yes

DAY2ACTIVITIES

AGENDA7

SOCIALAUDIT

Conductsocialauditofatleast5workseachunderfollowingschemes:

| NAMEOFTHE SCHEME | DETAILSOFTHE WORKS | YEAROFWORK APPROVAL | AMOUNT APPROVED FORTHEWORK | WHETHER WORKEXECUTED SATISFACTORILY | GEO- TAGGED PHOTOS | ANY GRIEVANCE RECORDED RELATINGTOTHAT WORK |
| --- | --- | --- | --- | --- | --- | --- |
| MGNREGA | Sokage pits | 2200 | Yes | Yes | Yes | Yes |
| PMAY | 06 | 1.30 | Do | Do | Yes | Yes |
| IHHL UNDERSBM-G | 80 | 12000 | Do | Yes | Yes | Yes |
| CSCUNDER SBMG |  |  |  |  |  | Yes |
| AMRIT SAROVARS | 02 | 2022 |  |  | Yes | Yes |

DAY2ACTIVITIES

AGENDA8

MAHILASABHA

Totalwomeninthevillageabovetheageof18

Totalattended              180

Proceedings:	15

(Plinsertpointerstobediscussedthere–referpalliproceedings)

DAY2ACTIVITIES

AGENDA9

BALSABHA

Holda balsabhaandrecordproceedings

Totalchildreninthevillageabovetheageof….. Totalattended                         45

Proceedings:	45

(Plinsertpointerstobediscussedthere–referpalliproceedings)

DAY2ACTIVITIES

AGENDA10

INAUGURATIONS

| SR NO. | ASSETS/ACTIVITIES INAUGRATED | STATUSOFTHEASSET/AC- TIVITIES(NUMBER,OTHER DETAILS) | GEO-TAGGED PHOTOS |
| --- | --- | --- | --- |
|  | VILLAGEHAATunderJKSRLM (SUN- DAYMARKET) |  |  |
|  | PMAYhousesifanyreadyforinaugra- tion | 05 | Yes |
|  | Swachhgramprojects-segregation shedsetc |  |  |
|  | Amritsarovars | 1 completed at danna and other one is under construction | Yes |
|  | Sportskits | One sports kit issued to youth of pyt. | Yes |
|  | Villageculturalevents | Cultural program organized at M/S Arigam | Yes |
|  | JJMassets/projects | Sources are available but supply of pipeline yet to be not | Yes |
|  | Anyothertobeidentifiedatdistrict level | Establishment of Tourism revenue at Nandi chool danna gali kanyha sultan pathri | Yes |

FOLLOWUPOF(B2V1,B2V2&B2V3):

(Prefilledexcelsheet tobetakenfromdistrictlevel/andalsotobedownloaded

fromwww.jkpanchayat.in)

| S.NO. | Particulars | Actiontaken | Remarks# |
| --- | --- | --- | --- |
| - UrgentPublicRequirements/Demands-B2V1 Requirement of health facilities PHCF Nil Public transport is urgentwly |  |  |  |
| 2 | Public transport is urgently | Nil | Nil |
| 3 | Animal sheep center | Nil | Nil |
| 4 | Mobile connectivity | improved | Need to be improved |
| 5 | Education facilities are not | Nil | Nil |
| 6 | Road from zabri to kunjha | Nil | Nil |
| 7 | Playground danna | Nil | Nil |
| II. Urgent Public Requirements/Demands-B2V2 |  |  |  |
| 1 | Solar Home light | Nil | Nil |
| 2 | Medical aid center | Nil | Nil |
| 3 | Panchayat Ghar urgently | Nil | Nil |
| 4 | Education infrastructure | Nil | Nil |
| 5 | ICDS building. | Nil | Nil |
| 6 | Road from Bairan to kayha | Nil | Nil |
| 7 | Ambulance for panchayat | Nil | Nil |
| S.NO. | Particulars | Actiontaken | Remarks# |
| III. MajorProblems–B2V1 |  |  |  |
| 1 | Road from kunjha | Nil | Nil |
| 2 | Education facelities | Nil | Nil |
| 3 | Playground Danna | Nil | Nil |

Nil

| 4 | Animal Sheep center |  | Nil | Nil |
| --- | --- | --- | --- | --- |
| 5 | Mobile connectivity |  | improved | Need to be improved |
| Nil IVMajorProblems-B2V2 |  |  |  |  |  |  | Nil |
| 1 |  | Solar Home light | Nil | Nil |
| 2 |  | Medical aid center | Nil | Nil |
| 3 |  | Road from Bairan to kunjha | Nil | Nil |
| 4 |  | Ambulance for panchayat | Nil | Nil |
| 5 |  | Medical aid center | Nil | Nil |
| V. MajorProblems-B2V3 |  |  |  |  |
| 1 | Tourism establishment |  | Nil | Nil |
| 2 | Model village for panchayat |  | Nil | Nil |
| 3 | Eco tourism at nandi chool |  | Nil | Nil |
| 4 | Depo at arigam |  | Nil | Nil |
| 5 | Panchayat ghar |  | Nil | Nil |
| VI. MajorComplaints-B2V1 |  |  |  |  |
| 1 | MGNREGA delay payment |  | improved | Need to be improved |
| 2 | PMAY new survey |  | Nil | Nil |
| 3 | SBM baseline to be resume |  | Nil | Nil |
| VII. MajorComplaints-B2V2 |  |  |  |  |
| 1 | Urgent need of Panchayat ghar |  | Nil | Nil |
| 2 | Wrost condition of pyt ghar |  | Nil | Nil |
| 3 | Road from Bairan to kunjha |  | Nil | Nil |
| VIII. MajorComplaints-B2V3 |  |  |  |  |
| 1 | Water supply scheme |  | Nil | Nil |
| 2 | Road from Bairan to kunjha |  | Nil | Nil |
| 3 | m/S danna building |  | Nil | Nil |

DepartmentofRuralDevelompentandPanchayatiRaj

GovernmentofJammu &Kashmir