4

15TH OCTto3RD NOV,2022

KEYFEATURES

•     DeputyCommissionerstoleadtheinitiative

•    RuraldevelopmentDepartmenttobethenodaldepartment

•	PlanningDevelopment&MonitoringdepartmentandITtobethesupport departments

ACTIONSANDTIMELINES

| ACTION | RESPONSIBILITY | LATESTBY | REMARKS |
| --- | --- | --- | --- |
| Janabhiyan | Alldepartments | Oct15-26th | Goingon |
| DeputationofSecttstaff/ HoDs | GAD | Oct14 | Done |
| DeploymentofStaffto Panchayatsandservingof ordersondeployedofficers | DCs | Oct25 | DCswilldeployseniorlevelstaff fromthedistricts.Strictactionto betakenagainstabstentions.No exemptionstobegiven |
| Trainingofdistricttrainors onB2V4 | RDD | Oct26 |  |
| Trainingofvisitingofficers | DCs | Oct27 |  |
| FieldVisitstobecompleted by | VisitingOfficers | Nov3 | DCstosuperviseandensurethat eachPanchayatisvisitedwithin theperiodspecified |
| DataofB2V4tobe uploadedby | VisitingOfficers | Nov10 | DCstosuperviseandensurethat dataofallPanchayatsisupload- edbythevisitingofficerwithin theperiodspecified |

INSTRUCTIONSFORTHEVISITINGOFFICER(DAYWISE)

| DATE | INSTRUCTIONS | ACTIONPOINTS |
| --- | --- | --- |
| Day0 | Meetingwithdeputy commissionerandhis/her team | a. TakeprintoutsoffilledbookletsofB2V1,B2V2andB2V3from www.jkpanchayat.in b.Alsotakeprintoutsofthesummarizedexcelsheetsofthe previousphasesfromwww.jkpanchayat.in c. CollectATRsonissuesraisedduringprevious3phasesfromthe officeofDeputyCommissioner(Planningdeptt) d.Takeprintsofblank 2bookletsofB2V4fromwww.jkpanchayat.ine.Takeplansfor2previousyearsandATRsfromtheplanningdeptt f. CompletetrainingsondifferentcomponentsofB2V4being organizedbyrespectiveDeputyCommissioners g.CollectListofnewworksstarted/ongoing/completedduringthe previousandcurrentFinancialyearunderthefollowingheads: • PRIgrants • DistrictPlan • UTplan • MGNREGA • Otherschemesofotherdepartments • Anyotherwork h. Plans/beneficiarylists: • MGNREGAdraftplandocumentfortheyear2022-23. • ListofAwaas+beneficiariesalongwithIHHL Convergence • Listofpensionbeneficiaries. • ListofSHGs • Listofagricultureschemebeneficiaries i. Listsofbeneficiariesfor: • Variouscertificates/benefitstobedistributedbythe visitingofficer. • Anyotheractivitiesidentifiedbydifferentdepartments |

| Day1 | Reachthevillage | 1. | Ensurethatallfrontlineworkersofdifferentdepttsarepresent. |
| --- | --- | --- | --- |
|  |  | 2. | Ensureexhibitionbydifferentdepts.aboutindividualbeneficiary schemes |
|  |  | 3. | InspectJKB/PSBcounters/outlets |
|  |  | 4. | Participate/ensureorganizationofsportsactivityinplayfield,talent hunt/culturalevent/youthactivity |
|  |  | 5. | GandhiKatha(suggesteddetailsuploadedonjkpanchayat.in) |
|  |  | 6. | Visitatleast2amritsarovarsandgetitsgeotaggedphotos |
|  |  | 7. | InspectKhidmat(CSC)CentresandcreateGenerateawarenesson 225schemesparticularlyG2CschemeslikeBEAMS,Janbhagidari, AapkiZaminAapkiNigrani,DigitalJ&K |
|  |  | 8. | Visitingofficershallalsoplanandconductpanchayatlevelconver- gencemeetingofalldepartments |
|  |  | 9. | CheckeffectivenessofCentrallysponsoredschemes |
|  |  | 10. | VisitandinspectallgovernmentestablishmentsincludingPHE, AWC,FPS,schools,etc |
|  |  | 11. | Attemptsaturationofdeliverableso JanAbhiyanandwherever deficienciesfound,leadadrivetoachievealldeliverables |
|  |  | 12. | Assesseffectivenessofsanitationcampaigninthepanchayat |
|  |  | 13. | Ensureselfemploymentactivitiesfor15youthperpanchayat |
|  |  | 14. | Identify20potentialcandidatesperpanchayatforHIMAYATtraining alongwiththetradeonwhichtheywanttraining |
|  |  | 15. | Whereverpossible,distributeemploymentlettersforpeopleselect- edundervariousgovernmentemployments |
|  |  | 16. | Intheevening,holdnormalmeetingwithseniorcitizens,govtem- ployeesincludingretiredemployees,exservicemen,youthclub,andany citizens ofthevillagewhoareenrolledincollege/university |
|  |  | 17. | OpendiscussiononNashaMuktAbhiyan |

Day2            Haveameetingwithall stakeholders-depttofficialsandpanchayatmembers

1.       DiscussionontheandassesstheprogressofdifferentschemesrelatingtothelocalizedSDGsprioritizedforthatvillageaspertheresolutionpassedby thatGramPanchayaton21stApril22,onNationalPanchayti RajDay.

2.	SensitizevillageresidentsaboutmyScheme”portal(myscheme.in) whichincludesinformationaboutalltheschemesbeingrunbyCen- tral/State/UTgovtacrossthecountry

3.	Hold meeting of theBiodiversityManagementCommitteestodeliber- ateonissuespertainingtoconservationof biodiversityandsustaina- bleutilizationofbiologicalresources.

4.       PrepareVillagedevelopmentplan,inconsultancywithGrampanchayat, discussitingramsabhaandgetitapproved.

5.       EnsuresaturationofsoilhealthcardandgoldenhealthcardunderGold- enHealthCardunderAyushmanBharat,

6.       Ensuresaturation of OldAgePensionScheme

7.       EnsureDomicileSaturation.

8.       EnsureKCCSaturation

9.       Ensuresaturationoflandpassbooks

10.     Ensureregistrationofvillagevendorsneededforanyscheme,onGEM

portal

11.     Ensurepanchayatcontractorsregistration

12.     EncouragePanchayatmembersforimportanceofplantationdrivein

PanchayatunderHarGaonHariyali

13.     EnsurepaintingondigitalJ&Kinpanchayatghars

14.     EnsurepaintingonpanchayatactivitesandCSSinpanchayatghars

15.	Thevisitingofficeshallchecknoofkindergarten andplayfieldspresent inthepanchayatfor kidsandstudents,iftheinfrastructurepresent inthesearegoodenough.

16.     HoldmeetingwithpanchayatmemberstodiscussaboutcorruptionmenaceandstepsrequiredtomakeJ&Kcorruptionfree

17.     Obtainacandidassessmentaboutperformanceofvariousdepttsin- cludingfairfeedbackaboutdiscrepanciesinfunctioning

18.	Check thestatusofNashaMuktAbhiyanandreportingof drugad- dictstoDeputyCommissioner.

19.     IdentifyTouristDestinations,Circuits,ThemeTreks,IdentifyHomestays, providesupportfortourismactivitiesthroughVillageCooperative

20.     OrganizeTalentHuntatPanchayatLevel

21.     Conductsocialauditofatleast5worksunderfollowingschemes:

a.       MGNREGA

b.PMAY

c.        IHHLtoiletsandpaymentsd.CSCs

e.AMRITSAROVARS

22.     Holdamahilasabhaandabalsabhaandrecordproceedingsinthefor- matgiven

23.     InauguratevillagehaatunderJKSRLM

24.     Checkifyouthclubsareformedinthepanchayatandwhatactivitiestheyareengagedin

25.     Organizeavillagelevelculturaleventtoengagepanchayatmembers

26.     SensitizeGPaboutE-kitabkoshaninitiativeofJ&KGovtforempoweringyouthsthroughonlinedigitalliteracy

GENERALINSTRUCTIONS

1.	Thevisitingofficershallrefrainhimself/herselfgivingorofferinganycommitmentonbehalfofthe governmentandshalladoptanunbiasedattitudeinreportingissues.Asfaraspossible,his/her observation shouldbebasedonafairandanalyticalviewemergingfromhis/herinteractioninthevillage.

2.	Heisgoingtothevillageasplanningofficer,notforsanctioninganyworksorformakinganycom- mitments.

3.	Whilepreparingvillagedevelopmentplan,hehastoensurethat,demandsareprioritizedandre- flectedunderavailableschemes,wherevernecessarythelargerworksaretobereferredtoadminis- trativedepttunderCSS/UTplansunderintimationtoDCsandrestoftheworkstoDCsforreflecting itunderdistrict/CSS plans

4.    His workshallbehardcoreplanningandauditandisnotaPRexercise.

5.	EveryDeputyCommissionerhastoensurethatatleastoneRDDofficial(ideallyPanchayatSecre- tary)ispresent  ineverypanchayatwithrelevantpanchayatrecords,toensureconductofallactivi- tiesasplanned.Panchayatwiseorderneedstobeissuedinadvance.

6.	Visitingofficershouldideallycarryhis/herlaptoptocompletethereportsatthepanchayatlevel itselfanduploadthefinalreport,dulysignedbothbythesarpanchandbythevisitingofficeronwww.jkpanchayat.inportal,beforetheyleavepanchayat.

7.	Focus ofvisitareyouth,skills,self-employment,nashamukt,bhrashtracharmukt,Rozgaryukt J&K, besidestocarryforwardtheactivitiesduringJanAbhiyanandsaturatethem.

8.    Inadditionattentionmaybegiventothefollowingareasa.     MakefulluseofCentrallySponsoredSchemes

b.Saturationofindividualbeneficiaryschemesc.     Self-employmentschemes

d.Banklinkedschemes-includingdepartmentalsubsidyschemese.Empowermentandtransparencythroughdigitalinitiatives

f.       Effectivenessofgrassrootsmachinery–

i.       Patwari,VLWpresentandavailable

ii.      AvailablefundsutilizedinpublicinterestandasperGramSabharesolutions iii.   Fairness ingovernance

iv.    CSS/Individual beneficiaryschemesetcv.      BrashtacharMuktJ&K

vi.   BhaiMuktJ&K

vii.  NashaMuktJ&K

9.	ThePRImembers(Sarpanchs,Panchs,BDCChairperson)shallbeattheforefrontofallactivities and givendueimportanceandtheapproachshouldbetostrengthenthemandmakethemfeelem- powered.He/sheshallensurethattheBDCchairpersonandSarpanch/Pancharepresentatthetimeofinaugurationandceremonies.

10.	Visitingofficershallnotleavethedistrictwithoutuploadingthereport,duly signedonthewww. jkpanchayat.inportal.EveryDeputyCommissionerhastoensurethat.

A)   DetailsofReportingOfficer:

Name:             Nayaz Ahmed

Designation:     Horticulture development officer

Department/placeofposting:       Horticulture Lassana

MobileNo:        7006257611, 7298481435

EmailID:       naizgorsi70@gmail.com

HomeDistrict:  Poonch

Datesof  visit:     28/10/2022 & 29/10/2022

B)	LocationaldetailsofPanchayat:(tobepre-filled,informationtobetakenfromtheprevious phasesbooklets/summarizedexcelsheetuploadedonjkpanchayat.in/b2v4.php)(tobevali- datedbythevisitingofficerandmissingdetailstobefilled)

NameofthePanchayat:      Barachar

LocalGovernmentDirectory(LGD)codeofthePanchayat:       005

NameofCDBlock:      Loran

NameofTehsil:         Mandi

NameofDistrict:    Poonch

C)     PanchayatProfile:

No.ofrevenuevillagesinthePanchayat:     Barachar and Markote

No.ofhamletsinthePanchayat:    09

No.ofhouseholdsinthePanchayat:      607

Population(approx)of  thePanchayat:       3910

Part-II:

(TobefilledupbytheVisitingOfficerduringhis/hertwodayvisittothePanchayat.AllFieldshavetobe

filledbytheVisitingOfficerbeforethebookletishandedovertotheDC

FrontlineOfficers/OfficialswhowereassignedtothePanchayatfortheprogramme:

| Department | Name | Designation |
| --- | --- | --- |
| RDD | Karanjeetsingh | Pyt. Secretary |
| RDD | Shahnaz akhter | GRS |
| Education | Javaidahmediqbal | Teacher |
| PDD | Shahnaz ahmed | Lineman |
| PHE | Abdul hamid | Lineman |
| Horticulture | Mananu |  |
| Agriculture | Sunil Rana | JEAO |

Detailsofabsentemployeesvis-à-vislistfurnishedbytheDCoffice:

| Department | Name | Designation |
| --- | --- | --- |
| Social welfare |  |  |

DAY1-ACTIVITIES

AGENDA1:PANCHAYATASSETREGISTER

Infrastructure:

1.		PanchayatGharInfrastructur  e a.  Govtbuilding/private Govt

b.  New/needingrepairs:- Need repairs

2.       Furniture(Y/N)                 Y

3.       Computer/printer(Y/N)    Y

4.       Internet(Y/N)                N

5.       Telephone(Y/N)              N

6.       Toilet(CSC/partofpanchayatghar)(Y/N)     Y

7.       Water(Y/N)                    N

8.       Electricity(Y/N)                N

9.       Bankbranch(Y/N)             N

10.     CSC(Y/N)                       N

11.     Patwarkhana(Y/N)         Y

12.     Villagehaat(Y/N)N

13.     Playground(Y/N)            N

14.     School-

a.        Kindergarten(Y/N)        N

b.Primary(Y/N)                        Y

c.         Secondary(Y/N)            N

d. College (Y/N)                     N

e.University(Y/N)                   N

15.     AnganwadiCentre(Y/N)           Y

a.        (govt/private)                 Govt.

b.Totalchildrenenrolled           294

15.     AmritSarovars–details,location,condition       Nil

16.     Governmentoffices-details,whetherfunctionalornot   PHC Subcenter of rented building, 07 Govt school

17.     Rationshop(Y/N)           Y

18.      Placesoftourismimportance–names,littledetailsonhistorical/culturalimportance      Markote

19.      Villageheritagesites/treks-names,littledetailsonhistorical/culturalimportanceChakiwala

20.     VLWOffice(Y/N)                    Y

21.     PrimaryHealthcareCentre(Y/N),           N

22.     ListofIncompleteBuildings-names,yearofconstruction     GMS Barachar  and AWC Markote

23.     ListofUnderutilizedBuildings-names

Nill

DAY1-ACTIVITIES

AGENDA2:

DIFFERENTINSTITUTIONS/INFRASTRUCTUREPROJECTSTOBEVISITED

| AMRITSAROVARS | Visit,verify | COMMENTS |
| --- | --- | --- |
| KhidmatCentres | Create/Generateawarenesson225schemes particularlyG2CschemsAapkiZaminAapkiNigrani, Beams,Janbhagidari,DigitalJ&K | Need to create |
| JKB/PSBcounters/outlets | a)Statusofcounterb)Numberofvisitors | Nill |
| Incompletebuildings/pro- jects | Verify whetheridentificationandredistributiondone | NA |
| PDS | Visit,evaluate,onlinestatus | Nil |
| PHC | Visit-evaluate,statusofstaff,equipmentandquality | Satisfactory |
| Youthclubs | Meet,interact,seeksuggestions | There are 22 SHG and 180 members and are satisfactory |
| SHG | Meet,identifyproblems,seeksuggestions | 1 inaugurated 4 inspected |
| PMAY | Inspect,Inaugurate | 4 school inspected and done meeting with staff and |
| Myschool,myprideprogress;schools-water, toilets,staff | Visit,checkforwater,electricity,sanitation,meetstudentsandstaff |  |
| SwachhSBM | Evaluate | All are constructed |
| Panchayatplayground, SportskitsdistributionVillagegames | Ensure,verify.Participateinatleastonegameintheplayground | Nil but kits are distributed to school |
| HarGaonHariyali, Planta- tiondrive | Evaluatestatus,feedback | Few plants are planted |
| Villageculturalevent Dangal/Haat/Mela | Participatein;ensurethatitisheld | Organzed at GM Barachar |
| Exhibitionofschemes | EnsurethateverydepartmentparticipatesandthatitcontinuesfortheentiredurationofB2V | Satisfactory feedback |
| JalJeewanMissionverifica- tion- WSS/JSD Electricitysupply | Verify | WSS Barachar, Markote have been mentioned |

DAY1-ACTIVITIES

AGENDA3:SATURATEJANBHIYAN

DELIVERABLESANDRECORDDEFICIENCIESIFANY(INSERTDELIVERABLESLISTHEREASPERGADFORMAT

DAY1-ACTIVITIES

AGENDA4:

SELFEMPLOYMENTACTIVITIES

EnsureSelf-employmentactivitiesforyouth,distributeemploymentlettersforpeopleselectedundervarioussocialschemes(15ISTHETARGETPERPANCHAYAT)   Nil

Numberofcasesindifferentcategoriessanctioned   NA

Detailsofthebanksanctioningit:       NA

Totalamountinvolved:           NA

DAY1ACTIVITIES

AGENDA5

Intheevening,holdinformalmeetingswithseniorcitizens,govtemployees,retdemployees,youthclubandothercitizenswhoareenrolledoncollege/universityandhavediscussiononGandhiKatha,Nasha MuktAbhiyan,corruptionfreegovernance,doublingfarmersincomeandrecordtheproceedings

DAY2

a.       NoofIndividualCompostPitsconstructed         7

b.NoofIndividualSoakPitsconstructed        250

V.          No.ofBiodiversitymanagementcommitteemeetingsheld:      06 years

VI.         IsthenameofSarpanchdisplayedoncitizeninformationboardsofallRD&PRschemes:Yes/No        Yes

VII.       AreSarpanchsbeinginvolvedinstart/inaugurationofactivities:Yes/No                     Yes

VIII.      WhethersubjectshavebeenassignedbytheSarpanchtothePanchs:Yes/No             Yes

IX.        Whethergrievancesredressalboxisinstalled:Yes/No                      Yes

X.         NoofgrievancesreceivedpertainingtoPanchayatlevel:                Yes

XI.        NoofgrievancesdisposedofatPanchayatlevel:                                 01

XII.       WhethertheSarpanch/PanchayatSecretaryhavedigitalsignatures:Yes/No           Yes

XIII.      WhetherallMGNREGA/14thFCpayments arebeingmadebySarpanchthroughDigitalSignature

Certificate(DSC):Yes/No         Yes

HUMAN RESOURCEAVAILABLEATTHEPANCHAYAT LEVEL:

| SRNO. | DEPARTMENTWISESTAFF | NUMBERS |  | NAMES |
| --- | --- | --- | --- | --- |
|  |  | SANCTIONED | ACTUAL |  |
|  | Rural developmentdepartment: BDO JE GRS TA | 01 01 01 01 | 01 01 01 01 | Vikas hansa Shahnaz Akhter Imtiaz Ahmed |
|  | SCHOOLEDUCATION: TEACHER HEADMASTER ANYOTHER | 28 02 | 18 Nil 09 | List enclosed at additional page. ------ At honararium |
|  | JAL JEEVAN: supervisor Daily wager | 01 | 01 02 | Abdul Rashid Abdul hamid Dilshad Ahmed |
|  | PDD: LINEMAN JE ANYOTHER | 01 | 01 04 | Shahjan ahmed Mohd hanief, javed iqbal,jahanghir ahmed,mohd rafiq. [D/W] |
|  | FOOD&CIVILSUPPLIES | ----- | nil | ------- |
|  | AGRICULTURE&ANIMALHUS- BANDARY | 01 01 | 01 01 | Davinder Sharma Mohd Rashid |
|  | SOCIALWELFARE | Information nil | nil | nil |
|  | HEALTH: ASHA ANM AYUSHDOCTOR ALLOPATHICDOCTOR | 02 01 | 03 03 01 | Hamida begum,yasmeen akhter, Maryam bi. Tahzeem akhter,shagufta. Dr.darkshanda. |
|  | Sub center Markote ANYOTHERDEPARTMENT ICDS worker helper | 03 | 02 9 9 | Mohd iqbal, Richa Sharma. List enclosed for reference. |

DAY2-ACTIVITIES

AGENDANO.1

DiscussionontheandassesstheprogressofdifferentschemesrelatingtothelocalizedSDGsprior-itizedforthatvillageaspertheresolutionpassedbythatGramPanchayaton21stApril22,onNational PanchayatiRajDay(Copyoftheresolutiontobetakenfromwww.jkpanchayat.inportalunderthelinkof GramSwarajMonth)

1.       SDGs AGREED FORTHATVILLAGE,TOBEIMPLEMENTED BYMARCH2024:          Agreed.

2.       STATUSOFWORKSUNDERTHEFOLLOWINGSCHEMES:

1      Cleanandgreenvillage

i.InitiativestakenbythePanchayatformanagingSolidandLiquidWaste.                    Soakage pits etc.

ii.     InitiativestakenbythePanchayatforusinggreensourcesoffuellikesolar,biogas

Already proposed an amount of 8.00 lac. For solar light.

iii.  Hasmappingoflanduse,waterbodies,forest,slopes,wetlands,degradedforestwithintheGram

Panchayatbeendone?Yes/No.IfNo,reason,thereof

iv.    HastheClimateResiliencePlanbeendevelopedfortheGP?Yes/No                 Yes           likely to proposed.

v.     StepstakenbytheGramSabhaabouttheclimatechangemitigationfactorslikereducingenergy consumption,usageoffossilfuels,plastics,non-renewablebuildingmaterialsandalsotopromote measureslikeplantingoftrees,conservingforests,usageofgoodagriculturalpracticeslikedrip irrigation,waterconservationmeasuresandconservationofwetlands.

vi.  Whether school shave started segregatingwaste	            yes

vii. Whetherschoolshavetheirowncompost/soakagepitsforsolid/liquidwastemanagement	yes

2     Healthyvillage

i)    AremeetingsrelatedtoVillageHealthandSanitationCommitteebeingheldregularly?	yes

ii)   DoalltheeligibleindividualsbeenprovidedtheGoldenCard?	Left over 15%

iii)  ArealltheChildrenbeingimmunizedaspertheSchedulerecommendedbyGovt.ofIndia?	yes

iv)  ArealltheeligibleindividualsbeenvaccinatedagainstCOVID-19?	yes

v)   DoesGramPanchayatensurethatallpregnantwomenaregettingnecessaryprenatalcheckups?	yes

vi)  WhetherallthedeliverieswereInstitutionalizedorconductedbytrainedMidwives?	yes

3     Watersufficientvillage

i)    DoalltheIHHsintheGramPanchayathavewaterpipelineconnections?	50%

ii)   WhetherGramPanchayathastakenstepsforgreywatermanagement.IfYespleasespecify 	yes

iii)     DoalltheIHHsintheGramPanchayathavetoilets?                                                                              yes

iv)  ArealltheIHHstoiletsfunctionalornot?	yes

v)   DoalltheSchools/Anganwadicentershaveatoiletfacilityornot?	School yes.AWC ICDS nil

vi)  Areallthetoiletsintheschools/Aaganwadifunctionalornot?	As mentioned above.

vii) WhetherGramPachachayatBhawanhasseparatetoiletsforwomenornot?                                            yes

4      ChildFriendlyvillage

i)	Doallthechildrenundertheageof0-6yearsbeenenrolledintheAnganwadicentersforpre- schooling?Yes/NO        yes

ii)    HowmanyBalSabha’swereorganizedintheGramPanchayat-------------------	              01/per/month

iii)  WhethertheissuesraisedbyBalSabhaareaddressedduringtheGramSabha. Yes/NO	                yes

iv)	WhetherGramPanchayatistrackingthedatarelatedtodropoutchildrenandchildrenwithirregular attendance?Yes/NO.      yes

v)   DoalltheschoolsundertheGramPanchayathaveseparatetoiletsforgirlsandboys?Yes/No	yes

5      Villagewithgoodgovernance

i)    IsCSClocatedintheGramPanchayatBhawanornot?	nil

ii)	IsthelistofbeneficiariesrelatedtotheSchemes/ProgramsdisplayedontheGrampanchayatwallor not?    yes

iii)  DoestheGramPanchayathasitsbuildingornot?	yes

iv)  IstheGramPanchayatofficefunctionalornot?	yes

v)   Aretheactivities approved undertheHalqaPanchayatDevelopmentPlandisplayedontheGram	yes

Panchayatwallornot?

vi)  IsSocialAuditofearlierSchemes/Programscarriedoutornot?	yes

6      Povertyfreeandenhancedlivelihoodvillage

- HasGramPanchayatdevelopedanycriteriafortheidentificationofthepoor?Yes/Noifyesspecify                  yes

- HavealltheeligiblehouseholdsregisteredinPDSornot?                                                                        Information nil

iii)	HasGramPanchayatprovidedspaceforSelf-helpGroupsinPanchyatGharforholdingmeetings  or not?             yes

iv)  HavealltheeligiblehouseholdsbeenregisteredforPensionornot?	yes

v)   HasGramPanchayatfacilitatedYouthforSkillEnhancementCoursesandPlacement?	nil

vi)  HasJobCardsbeendistributedtoalltheeligibleindividualsunderMGNREGA?                                 Yes NHRM-140(SHG)

vii) HasGramPanchayatfacilitatedSHGsforBankAccountLinkages?

7     Sociallysecuredvillage

i)    WhetherGramPanchayatismaintainingdatarelatedtoDifferentlyAbledPeople?

ii)   IsGramPanchayatOfficeDisabledFriendlyornot?

iii)	Areprovisionsfora separate BudgetundertheResourceEnvelopeforWomenandChildrenmadeornot?

iv)	DoalltheSchools intheGramPanchayathavefacilitiesforDifferentlyAbledChildrenliketoilets, barrier-freeaccess,etc.,ornot?

v)   Arealltheeligibleindividualsaregettingpensions,likeoldagepension,widowpension,etc?

vi)  ArealltheeligiblehouseholdsgettingbenefitsfromIAYornot?

Para 7.  1 to 6 =information nil

8      EngenderedDevelopmentinVillage

i)    HowmanyMahilaSabha’swereorganizedintheGramPanchayat-------------------	                 09

ii)	WhetherSHGsfederationshavebeenprovidedspaceformeetingsinthePanchayatBhawan(Yes/ No)	yes

iii)  WhetherGPshavetakenstepsforincreasingwomen’sparticipationinGramSabha(Yes/No)                                        yes

iv)  NumberofwomenbeneficiariesheadedhouseholdscoveredunderPDS

system………………………	35

v)   Numberofbeneficiaries(outoftotaleligiblepopulation)receivingsocialprotectionbenefitsunder

PradhanMantriMatritvaVandanaYojana………………….	30

9    Self-sufficientinfrastructureinthevillage

i.	WhetherGPhasaCommunityHallwithaccesstoelectricity,furniture,watersupply, toilet……………………….                                                                                                        nil

ii.     WhethertheDisastermanagementplanisavailableattheGPLevel(Yes/No)                                         No

iii.  Whetherchild-friendlyparkwithrequiredfacilitiesisavailableinGP(Yes/No)                                     No

iv.    WhethertheGPhaseasyaccesstoGodownforstorage(Yes/no                                                        No

v.     Whetherstreetlightsareprovidedinpublicplacesforensuringsafety(Yes/no                         proposed

DAY2ACTIVITIES

AGENDANO.2

SensitizevillageresidentsaboutmyScheme”portal(myscheme.in)whichincludesinformationaboutall theschemesbeingrunbyCentral/State/UT govtacrossthecountry

(SchemeMaterialavailablefromhttps://jkpanchayat.in/b2v4.php)

DAY2ACTIVITIES

AGENDANO.3

HoldmeetingoftheBiodiversityManagementCommitteestodeliberateonissues pertainingtoconserva- tionofbiodiversityandsustainableutilizationofbiologicalresources.HeshouldcheckPeopleBiodiversity register(PBR)ofthatpanchayatandreviewifBiodiversityManagementCommittee constitutedforthatpanchayatis holdingminimum4meetings inayearandmeeting onceinevery3months (RoleofBMCavailableathttps://jkpanchayat.in/b2v4.php)

COMMITTEEMEMBERS PRESENT

BIODIVERSITYREGISTERPHOTOS

PAST 4MEETINGDETAILS-DATES,MINUTESPHOTOS

DAY2ACTIVITIES

AGENDA4

Visitingofficershallalsoplanandconductpanchayatlevelconvergencemeeting  ofalldepartmentsandprepareVillagedevelopmentplanforvillage,inconsultancywithGrampanchayat,discussitingram sabhaandgetitapproved.

(GPDPformatavailableonhttps://jkpanchayat.in/b2v4.php)

InadditionGPDPplanshallalsoinclude:

           Touristplaceswhichneedtobedeveloped                 chakiwala

           Specificproductwhichneedstobedeveloped            french been

           Tourism-homestays                                                 NA

	20candidatesfortrainingunderHimayatschemealongwithtradeinwhich trainingistobegiven not available

DAY2ACTIVITIES

AGENDA5

Ensure saturation of followingschemesandgivestatus:

| NAMEOFTHESCHEME | TOTALELIGIBLE BENEFICIARIESIN THE VILLAGE | TOTALBENEFICIARIESWHO AVAILEDTHEBENEFITSOFTHESCHEME | REASONSFOR PENDENCY |
| --- | --- | --- | --- |
| GoldenHealthCardunder AyushmanBharat | 2460 | 1810 | Finger print deficit |
| Jananisurakshayojana | 100 | 27 | Lack of a/ness |
| OLDAGEpension |  |  |  |
| Widowpension |  |  |  |
| Disabilitypension |  |  |  |
| Domicilecertificate | 960 | 200 | Benif.will not come |
| Kisancreditcard | 359 | 300 | Informationnil |
| PMkisansammannidhi | 359 | 330 | Do |

| Landpassbook | 749 | 10 | All are uploaded |
| --- | --- | --- | --- |
| Registrationofvillageven- dorsonGEMportal |  |  |  |
| Registrationofvillagecon- tractorsonjktendersportal |  |  |  |
| Registrationofvillagecon- tractorsonPWDportal | 03 | 02 | lack of A/ness |
| Incompletebuildings/pro- jects | nil | nil |  |

DAY2ACTIVITIES

AGENDA6

NASHAMUKTABHIYAN

1.       Whethergramsabharesolutionpassed                          yes

2.       Detailsofactivitiesconducted                              yes

3.       WhetherallactivitiesandGSresolutionuploadedonjkpanchayats.inportal               yes

4.       Howmanydrugaddictsinthevillage                                       nill

5.       WhetherreportedtotheDeputyCommissioner                               nill

6.       Howmanyregisteredforrehabilitationundergovernmentprogramme                   nill

DAY2ACTIVITIES

AGENDA7

SOCIALAUDIT

Conductsocialauditofatleast5workseachunderfollowingschemes:

| NAMEOFTHE SCHEME | DETAILSOFTHE WORKS | YEAROFWORK APPROVAL | AMOUNT APPROVED FORTHEWORK | WHETHER WORKEXECUTED SATISFACTORILY | GEO- TAGGED PHOTOS | ANY GRIEVANCE RECORDED RELATINGTOTHAT WORK |
| --- | --- | --- | --- | --- | --- | --- |
| MGNREGA | Drain | 2022-23 | .50 lac | yes | Yes | Nill |
| PMAY | Abdul salam | 2020-21 | 1.3 lac | Yes | Yes | Nill |
| IHHL UNDERSBM-G | Akhter hussain | 2018 | 1200 | Yes | Yes | Nill |
| CSCUNDER SBMG | CSC at pyt ghr barachar | 2017-18 | 2.00 | yes |  | Nill |
| AMRIT SAROVARS |  |  |  |  |  |  |

DAY2ACTIVITIES

AGENDA8

MAHILASABHA

Total women in the village above the age of 18        854 Nos

Totalattended                                                   40 nos

Proceedings:                                                               Recoeded

(Plinsertpointerstobediscussedthere–referpalliproceedings)

DAY2ACTIVITIES

AGENDA9

BALSABHA

Holdabalsabhaandrecordproceedings

Totalchildreninthevillageabovetheageof…1 year.. Totalattended               30

Proceedings:              recorded

(Plinsertpointerstobediscussedthere–referpalliproceedings)

DAY2ACTIVITIES

AGENDA10

INAUGURATIONS

| SR NO. | ASSETS/ACTIVITIES INAUGRATED | STATUSOFTHEASSET/AC- TIVITIES(NUMBER,OTHER DETAILS) | GEO-TAGGED PHOTOS |
| --- | --- | --- | --- |
|  | VILLAGEHAATunderJKSRLM(SUN- DAYMARKET) |  | Uploaded on JK pyt |
|  | PMAYhousesifanyreadyforinaugra- tion | 01 | PMAY-G side |
|  | Swachhgramprojects-segregation shedsetc | Nil | Nil |
|  | Amritsarovars | Nil | Nil |
|  | Sportskits | 01 | Maction soft |
|  | Villageculturalevents | 02 | Jk pyt |
|  | JJMassets/projects | Nil | Nil |
|  | Anyothertobeidentifiedatdistrictlevel | Inauguration one Road | Of JK. Pyt |

FOLLOWUPOF(B2V1,B2V2&B2V3):

(Prefilledexcelsheettobetakenfromdistrictlevel/andalsotobedownloaded

fromwww.jkpanchayat.in)

| S.NO. |  | Particulars | Actiontaken | Remarks# |
| --- | --- | --- | --- | --- |
| I. UrgentPublicRequirements/Demands-B2V1 |  |  |  |  |
| 1 | Road connectivity as there is no road in Panchayat |  | Sanctioned |  |
| 2 | Problem of water ongoing scheme |  | NIl |  |
| 3 | Opening of AWC in Markote |  | NIl |  |
| 4 | Opening of primary school at makote |  | v NIl |  |
| 5 | Animal Sheep center at GP |  | NIl |  |
| 6 |  |  |  |  |
| 7 |  |  |  |  |
| II. UrgentPublicRequirements/Demands-B2V2 |  |  |  |  |
| 1 | do as above in first all |  |  |  |
| 2 |  |  |  |  |
| 3 |  |  |  |  |
| 4 |  |  |  |  |
| 5 |  |  |  |  |
| 6 |  |  |  |  |
| 7 |  |  |  |  |
| S.NO. | Particulars |  | Actiontaken | Remarks# |
| III. MajorProblems–B2V1 |  |  |  |  |
| 1 |  |  |  |  |
| 2 |  |  |  |  |
| 3 |  |  |  |  |

| 4 |  |  |  |  |
| --- | --- | --- | --- | --- |
| 5 |  |  |  |  |
| IV. MajorProblems-B2V2 |  |  |  |  |
| 1 |  |  |  |  |
| 2 |  |  |  |  |
| 3 |  |  |  |  |
| 4 |  |  |  |  |
| 5 |  |  |  |  |
| V. MajorProblems-B2V3 |  |  |  |  |
| 1 | Playground for childrens |  |  |  |
| 2 | Opening of P/S at markote |  |  |  |
| 3 | Repair of existing schools |  |  |  |
| 4 | Opening of new AWC |  |  |  |
| 5 |  |  |  |  |
| VI. MajorComplaints-B2V1 |  |  |  |  |
| 1 |  |  |  |  |
| 2 |  |  |  |  |
| 3 |  |  |  |  |
| VII. MajorComplaints-B2V2 |  |  |  |  |
| 1 |  |  |  |  |
| 2 |  |  |  |  |
| 3 |  |  |  |  |
| VIII. MajorComplaints-B2V3 |  |  |  |  |
| 1 |  |  |  |  |
| 2 |  |  |  |  |
| 3 |  |  |  |  |

DepartmentofRuralDevelompentandPanchayatiRaj

GovernmentofJammu&Kashmir